## Meeting (hidden)
Production Schedule | Status | Order | Line | Total Sections | Remaining Section | Product Code | Missing Materials | Complete/Partial | Sum of Remaining value | Sum of Remaining Time
Grand Total

## Schedule
Assembly Line | Schedule Date | Order | Line | Status | Sales Category | Total Sections | Remaining Section | Product Code | Missing Materials | Issue Reason | Issue Resolved | Issue | Saw | BA | weld | lens | Sum of Remaining value | Sum of Remaining Time
1 |  | 59584 | 10 | Machine Shop Started | Regular | 7 | 7 | SCRPAT-OPR-90(1)-300-80-35-FL-61'11"-NL-W-UNV-DP-1+E(3)-D | Material | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 3945 | 57
|  |  | 12 | Machine Shop Started | Regular | 21 | 21 | SCRPAT-OPR-90(2)-300-80-35-FL-226'3/8"-NL-W-UNV-DP-1+E(2)-D | Material | Missing parts in BOM | TRUE |  | TRUE | TRUE | Ready |  | 14010 | 211
|  |  | 66 | Machine Shop Started | Regular | 5 | 5 | SCRPAT-OPR-90(1)-300-80-35-FL-34'9"-NL-W-UNV-DP-1+E(2)-D | Material | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 2325 | 36
|  |  | 67 | Machine Shop Started | Regular | 22 | 22 | SCRPAT-OPR-90(4)-300-80-35-FL-211'11 1/4-NL-W-UNV-DP-1+E(7)-D | Material | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 13395 | 330
|  | 59584 Total | [14 empty] | 33675 | 634
|  | 72049 | 3 | Packaging Finished | Regular | 8 | -4 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(28' 1 1/4")-550-80-35-SO-C(RAL5017)-UNV-DP-1-CT15(36)-B2(BSL10LST) | Material | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | -7360 | -100
|  |  | 4 | Packaging Finished | Regular | 4 | 0 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(19' 9 1/4")-550-80-35-SO-C(RAL5017)-UNV-DP-1-CT15(36) |  | Shortage | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 15 | Packaging Finished | Regular | 8 | -4 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(28' 1 1/4")-550-80-35-SO-C(RAL6017)-UNV-DP-1-CT15(36)-B2(BSL10LST) | Material | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | -7360 | -21
|  |  | 16 | Packaging Finished | Regular | 4 | 0 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(19' 9 1/4")-550-80-35-SO-C(RAL6017)-UNV-DP-1-CT15(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 72049 Total | [14 empty] | -14720 | -121
|  | 74294 | 4 | Machine Shop Finished | Regular | 32 | 32 | CCH-SL-700-90-TC1680-CP(26)-W-UNV-DMX-1-C |  | Shortage | FALSE | Shortage | TRUE | TRUE | Ready | Done | 13000 | 141.68
|  | 74294 Total | [14 empty] | 13000 | 141.68
|  | 75692 | 11 | Wiring Started | Regular | 5 | 5 | SP18435(2)-BMPRLED-OPRO(158°)-750-80-35-RG3-40'2 1/8"-C(BLK)-UNV-DP-1-DS-TS(2)-C(127° ANGLED END) |  | Shortage | FALSE | Shortage | TRUE | TRUE | Ready | Done | 3010 | 39.35
|  | 75692 Total | [14 empty] | 3010 | 39.35
|  | 76203 | 28 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | Wrong info. In SD | TRUE |  | FALSE | FALSE |  | Done | 1440 | 18
|  |  | 29 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-18'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  | Done | 1296 | 7
|  |  | 30 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  | Done | 432 | 7
|  |  | 31 | Machine Shop Started | Regular | 4 | 4 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  | Done | 2304 | 28
|  |  | 32 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  | Done | 864 | 14
|  | 76203 Total | [14 empty] | 6336 | 74
|  | 76884 | 1 | Wiring Started | NPI | 4 | 4 | NPI-N18008-SKPE-10004-SL60/40-CIR-AL# 12' 6.75"-1000-80-35-SO-W-UNV-D-1-CA(36) | Material+Cartridge | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 1840 | 0
|  | 76884 Total | [14 empty] | 1840 | 0
|  | 77249 | 1 | Machine Shop Finished | Mockup/Samples | 2 | 2 | SCML-8-BW-400-MLB(16)-300-GR-80-35-AP-UNV-DP-1-CA(36)-EN(1) |  | Others | FALSE | Others | TRUE | TRUE |  | Done | 1440 | 16
|  |  | 2 | Machine Shop Finished | Mockup/Samples | 7 | 7 | STSFF-SO(16-400)-80-35-AL(2)+AT(2)-MKL(10)-80-35-W-BLK-BLK-UNV-MD-1-SBS-C(REMOTE ENLIGHTED INTEGRAL SENSOR) |  | Missing info. In SD | FALSE | Missing info. In SD | TRUE | TRUE |  | Done | 1360 | 40
|  |  | 4 | Machine Shop Finished | Mockup/Samples | 4 | 4 | SCDIPAT-REC-90-500-300-80-35-BW-0.5M-6X8-NL-W-UNV-DP-1-CTS(12)-EN(1) |  | Wrong info. In SD | FALSE | Wrong info. In SD | TRUE | TRUE | Ready | Done | 2100 | 40.18
|  | 77249 Total | [14 empty] | 4900 | 96.18
|  | 79375 | 1 | Wiring Started | Mockup/Samples | 1 | 1 | SK-10003-ARC-AL 1' 11 9/16"-400-80-35-SO-W-UNV-DP-1-DS-C(CORD AND PLUG) |  | (blank) | FALSE |  | TRUE | TRUE |  | AfterWirin | 180 | 4.3
|  | 79375 Total | [14 empty] | 180 | 4.3
|  | 64752 | 8 | Wiring Started | Regular | 24 | 24 | BMRLED-500-80-35-ASO-16-W-UNV-O(DEXAL)-1-TB15 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 9600 | 162
|  |  | 10 | Wiring Started | Regular | 27 | 0 | BMRLED-500-80-35-FL-30-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 11 | Wiring Started | Regular | 15 | 0 | BMRLED-500-80-35-FL-36-W-UNV-O(DEXAL)-1-TG15 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 12 | Wiring Started | Regular | 4 | 0 | BMRLED-500-80-35-FL-46-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 13 | Wiring Started | Regular | 5 | 0 | BMRLED-500-80-35-FL-60-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 14 | Wiring Started | Regular | 116 | 116 | BMRLED-500-80-35-FL-6-W-UNV-O(DEXAL)-1-TG9 | Material | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 34800 | 754
|  |  | 15 | Wiring Started | Regular | 32 | 0 | BMRLED-500-80-35-FL-8-W-UNV-O(DEXAL)-1-TG15 |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 16 | Wiring Started | Regular | 1 | 0 | BMRLED-500-80-35-FL-10-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 17 | Wiring Started | Regular | 2 | 0 | BMRLED-500-80-35-FL-14-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 18 | Wiring Started | Regular | 2 | 0 | BMRLED-500-80-35-FL-16-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 19 | Wiring Started | Regular | 4 | 1 | BMRLED-500-80-35-FL-18-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 450 | 8.25
|  |  | 20 | Wiring Started | Regular | 18 | -1 | BMRLED-500-80-35-FL-20-W-UNV-O(DEXAL)-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -500 | -8.25
|  |  | 22 | Wiring Started | Regular | 1 | 0 | PRWLED-500-80-35-S-10-W-277-DP-1 |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 23 | Machine Shop Finished | Regular | 16 | 8 | PRWLED-500-80-35-S-16-W-277-DP-1 |  | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 2880 | 49.6
|  |  | 24 | Wiring Started | Regular | 4 | 0 | PRWLED-500-80-35-S-28-W-277-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 30 | Wiring Started | Regular | 26 | 7 | BBWDILED-640-400-80-35-SO-5-W-UNV-DP-1-D |  | Others | TRUE |  | TRUE | TRUE |  | Done | 2800 | 78.4
|  |  | 31 | Wiring Started | Regular | 2 | 0 | BMRLED-500-80-35-FL-6-W-UNV-O(DEXAL)-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 37 | Wiring Started | Regular | 12 | 6 | BMRLED-500-80-35-FL-4-W-UNV-O(DEXAL)-1-TG15 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1200 | 19.8
|  |  | 40 | Wiring Started | Regular | 10 | 10 | BMRLED-500-80-35-FL-6-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3000 | 67
|  | 64752 Total | [14 empty] | 54230 | 1130.8
|  | 77741 | 5 | Machine Shop Finished | Regular | 3 | 3 | BMWDLED-750-80-30-ASO-4'-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 975 | 12
|  |  | 6 | Machine Shop Finished | Regular | 2 | 2 | BMWDLED-750-80-30-ASO-5'-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 820 | 6.6
|  |  | 8 | Machine Shop Started | Regular | 1 | 1 | SCSPAT-OPR-90(2)-500-80-30-FL-12'-NL-W-UNV-BI-1-SC |  | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 1175 | 11.8
|  |  | 9 | Machine Shop Finished | Regular | 3 | 3 | SCSPAT-OPR-90(1)-500-80-30-FL-12'-NL-W-UNV-BI-1-SC |  | (blank) | FALSE |  | TRUE | TRUE | Ready | Done | 1075 | 16
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | SCRPAT-OPR-90(2)-500-80-30-FL-15' 1-3/4-NL-W-UNV-BI-1-DS |  | Wrong info. In SD | TRUE |  | TRUE | TRUE | Ready |  | 1500 | 15.8
|  |  | 11 | Machine Shop Finished | Regular | 1 | 1 | SCRPAT-OPR-90(2)-500-80-30-FL-11' 2-1/2-NL-W-UNV-BI-1-DS |  | (blank) | FALSE |  | TRUE | TRUE | Ready | Done | 1175 | 11.8
|  |  | 12 | Machine Shop Finished | Regular | 1 | 1 | SCRPAT-OPR-90(2)-500-80-30-FL-10' 9-1/2-NL-W-UNV-BI-1-DS |  | (blank) | FALSE |  | TRUE | TRUE | Ready | Done | 1175 | 11.8
|  |  | 13 | Machine Shop Started | Regular | 2 | 2 | SCRPAT-OPR-90(2)-500-80-30-FL-12'1-1/2-NL-W-UNV-BI-1-DS |  | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 1175 | 11.8
|  |  | 15 | Machine Shop Started | Regular | 1 | 1 | SCR-500-80-30-FL-4'2"-W-UNV-BI-1-DS |  | (blank) | FALSE |  | TRUE | FALSE | Ready |  | 325 | 24
|  |  | 17 | Machine Shop Finished | Regular | 3 | 3 | SCR-500-80-30-FL-30-W-UNV-BI-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1950 | 28.8
|  |  | 18 | Machine Shop Finished | Regular | 5 | 5 | SCS-500-80-30-FL-4'-W-UNV-BI-1-SC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1625 | 15.2
|  |  | 19 | Machine Shop Finished | Regular | 2 | 2 | SCS-500-80-30-FL-8'-W-UNV-BI-1-SC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1300 | 6
|  | 77741 Total | [14 empty] | 14270 | 171.6
|  | 74968 | 1 | Machine Shop Started | Regular | 4 | 4 | SKPE-18075-SL 60/40-ASO-AL(#23' 9 1/4")-1000-80-40-SO-C(RAL5012)-UNV-D-1-CA(36) | +Cartridge | Others | FALSE | Others | FALSE | FALSE |  | Done | 5400 | 60
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | SKPE-18075-SL 60/40-ASO-AL(#14' 10-1/4")-1000-80-40-SO-C(RAL6038)-UNV-D-1-CA(36) | +Cartridge | Others | TRUE |  | FALSE | FALSE |  | Done | 3375 | 40
|  |  | 3 | Machine Shop Started | Regular | 3 | 3 | SKPE-18075-SL 60/40-ASO-AL(# 16' 10-1/4")-1000-80-40-SO-C(RAL2007)-UNV-D-1-CA(36) | +Cartridge | Shortage | TRUE |  | FALSE | FALSE |  | Done | 3825 | 40
|  | 74968 Total | [14 empty] | 12600 | 140
|  | 78603 | 1 | Machine Shop Started | Regular | 2 | 2 | STD-SO-300-80-35-6'-C(RAL 1023)-UNV-MD-1-CA(36)-RC | Material+Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 1022.4 | 14.4
|  |  | 2 | Machine Shop Started | Regular | 2 | 2 | STD-SO-300-80-35-5'-C(RAL 5018)-UNV-MD-1-CA(36)-RC | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 873 | 14.4
|  | 78603 Total | [14 empty] | 1895.4 | 28.8
|  | 75697 | 1 | Machine Shop Finished | Regular | 7 | 7 | PRWLED-800-80-40-S-4-W-UNV-BI-1-OS(1) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 3767.8535 | 40.95
|  |  | 2 | Machine Shop Finished | Regular | 35 | 35 | PRWLED-800-80-40-S-4-W-UNV-BI-1-OS(1) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 18839.2673 | 204.75
|  |  | 3 | Machine Shop Finished | Regular | 26 | 26 | PRWLED-800-80-40-S-8-W-UNV-BI-1-OS(1) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 25909.7686 | 209.56
|  |  | 4 | Machine Shop Finished | Regular | 1 | 1 | PRWLED-800-80-40-S-12-W-UNV-BI-1-OS(1) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 1483.1105 | 9.81
|  | 75697 Total | [14 empty] | 49999.9999 | 465.07
|  | 76192 | 1 | Machine Shop Started | Regular | 2 | 2 | GPRLED-EX2W-750-80-35-RG2-7'-W-277-LT(L3D)-1-DF | +Cartridge | Others | FALSE | Others | TRUE | FALSE |  | Done | 1470 | 16
|  |  | 2 | Machine Shop Started | Regular | 2 | 2 | GPRLED-EX2W-750-80-35-RG2-9'-W-277-LT(L3D)-1-DF | +Cartridge | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 1890 | 20
|  |  | 3 | Machine Shop Started | Regular | 2 | 2 | GPRLED-EX2W-750-80-35-RG2-12'-W-277-LT(L3D)-1-DF | +Cartridge | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 2520 | 20
|  |  | 4 | Machine Shop Started | Regular | 4 | 4 | GPRLED-EX2W-750-80-35-RG2-13'-W-277-LT(L3D)-1-DF | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2730 | 28
|  |  | 5 | Machine Shop Started | Regular | 16 | 16 | GPRLED-EX2W-750-80-35-RG2-14'-W-277-LT(L3D)-1-DF | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 11760 | 112
|  |  | 6 | Machine Shop Started | Regular | 4 | 4 | GPRLED-EX2W-750-80-35-RG2-19'-W-277-LT(L3D)-1-DF | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3990 | 32
|  | 76192 Total | [14 empty] | 24360 | 228
|  | 77393 | 1 | Machine Shop Finished | Regular | 6 | 6 | STFC-NO-DSO(24' 0"-400)-80-35-AG(5)-BLK-UNV-MD-1-CA(96)-RC | +Cartridge | Others | FALSE | Others | TRUE | TRUE |  | Done | 1890 | 32
|  | 77393 Total | [14 empty] | 1890 | 32
|  | 75462 | 14 | Machine Shop Started | Regular | 24 | 24 | SP18276-SCRPAT-OPR-131°+49°+71°+109°+91°+89°+87°+101°-350-80-35-FL-339-EX-W-UNV-DP-6-DS-C(ANGLED ENDS) | Material+Cartridge | Others | FALSE | Others | FALSE | FALSE |  |  | 20305 | 622
|  | 75462 Total | [14 empty] | 20305 | 622
|  | 75745 | 13 | Wiring Started | Regular | 5 | 1 | SP18435(2)-BMPRLED-OPRI(119°)-750-80-35-RG3-36'6"-W-UNV-DP-1-TG9-TS(2)-C(140.6° ANGLED END) |  | Shortage | FALSE | Shortage | TRUE | TRUE | Ready | Done | 554 | 6.36
|  | 75745 Total | [14 empty] | 554 | 6.36
|  | 75746 | 5 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 432 | 7
|  |  | 6 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 576 | 7
|  |  | 7 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 720 | 9
|  |  | 8 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1440 | 4
|  |  | 22 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-9'8 1/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 675 | 9.28
|  |  | 24 | Machine Shop Started | Regular | 3 | 3 | BMPRLED-OPRI(1)-750-80-35-RG3-17'6"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | Material | (blank) | FALSE |  | FALSE | FALSE | ToDo |  | 1330 | 24
|  |  | 25 | Machine Shop Started | Regular | 3 | 3 | BMPRLED-OPRI(1)-750-80-35-RG3-19'6 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | Material | (blank) | FALSE |  | FALSE | FALSE | ToDo |  | 1450 | 24
|  |  | 26 | Machine Shop Started | Regular | 4 | 4 | BMPRLED-750-80-35-RG3-38'-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 2355 | 4
|  |  | 29 | Machine Shop Started | Regular | 3 | 3 | SP18276-SCR-350-80-35-FL-46'1"-W-UNV-DP-1-DS-C(32° & 85° ANGLED ENDS) | Material+Cartridge | Others | FALSE | Others | FALSE | FALSE |  |  | 2470 | 43.2
|  |  | 31 | Machine Shop Started | Regular | 3 | 3 | BMPRLED-OPRI(1)-750-80-35-RG3-19'6 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | Material | Missing info. In SD | TRUE |  | FALSE | FALSE | ToDo |  | 1360 | 24
|  |  | 34 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8'-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 576 | 7
|  | 75746 Total | [14 empty] | 13384 | 162.48
|  | 79048 | 1 | Machine Shop Started | Mockup/Samples | 1 | 1 | CLKLED-900-90-35-SO-4'-W-UNV-DP-1-AC-C(PLUG AND CORD ONLY) |  | (blank) | FALSE |  | TRUE | FALSE |  |  | 100 | 4.3
|  | 79048 Total | [14 empty] | 100 | 4.3
|  | 78694 | 1 | Machine Shop Finished | Regular | 20 | 20 | BBDILED-400-750-90-35-SO-16-W-UNV-DP-1-CA(132) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 21160 | 230
|  |  | 2 | Machine Shop Started | Regular | 8 | 8 | BBRLED-1000-90-35-1.5M-8-W-UNV-DP-1-TB9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 7384 | 37.6
|  |  | 3 | Machine Shop Finished | Regular | 20 | 20 | BBDILED-400-750-90-35-SO-16-W-UNV-DP-1-CA(132)-B1(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 23865.28 | 270
|  | 78694 Total | [14 empty] | 52409.28 | 537.6
|  | 75090 | 1 | Machine Shop Finished | Regular | 1 | 1 | TB-S-10-NL-T5HO-2-W-UNV-D(MARK7)-1-CA(36) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1350 | 10
|  |  | 2 | Machine Shop Finished | Regular | 4 | 4 | ZESQDI-SL 50/50-1200-80-35-SO-15-AP-UNV-MD-1-CA(36) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4350 | 37.4
|  |  | 3 | Machine Shop Started | Regular | 12 | 12 | SKPE-10005-SL 60/40-CIR-AL(7'10 1/4")-1000-80-35-SO-W-277-D-1-CTS(36) | Material+Cartridge | Others | FALSE | Others | TRUE | FALSE |  | Done | 6600 | 54
|  |  | 4 | Machine Shop Finished | Regular | 4 | 4 | ZESQDI-SL 50/50-1200-80-35-SO-20-AP-UNV-MD-1-CA(36) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 5800 | 45.6
|  | 75090 Total | [14 empty] | 18100 | 147
|  | 78798 | 1 | Machine Shop Started | Regular | 8 | 8 | CLKLED-500-80-30-SO-4'-W-120-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3040 | 36
|  |  | 2 | Machine Shop Started | Regular | 28 | 28 | CLKLED-500-80-30-SO-4'-W-120-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 10640 | 126
|  | 78798 Total | [14 empty] | 13680 | 162
|  | 77432 | 1 | Machine Shop Started | Regular | 20 | 20 | BRLED-400-80-35-FL-4-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 5920 | 78
|  |  | 2 | Machine Shop Started | Regular | 16 | 16 | BRLED-400-80-35-FL-6-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 7072 | 116.8
|  |  | 3 | Machine Shop Started | Regular | 42 | 42 | BDLED-400-80-35-SO-24'6"-W-UNV-DP-1-CA(60) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 24766 | 343
|  |  | 4 | Machine Shop Started | Regular | 8 | 8 | BRLED-750-80-35-FL-6' 0"-DMLED(2)-C(RAL#7004)-UNV-DP-2-D | Material+Cartridge | Shortage | FALSE | Shortage | TRUE | TRUE |  |  | 5296 | 78.4
|  |  | 5 | Machine Shop Started | Regular | 6 | 6 | BRLED-1000-80-35-FL-6' 0"-DMLED(2)-C(RAL#7004)-UNV-DP-2-D |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 3972 | 58.8
|  |  | 6 | Machine Shop Started | Regular | 4 | 4 | BRLED-750-80-35-FL-8-C(RAL#7004)-UNV-DP-1-D |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 2360 | 25.6
|  |  | 7 | Machine Shop Started | Regular | 26 | 26 | SLWLED-SL 75/25-800-80-35-VL-8' 0"-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 26000 | 187.2
|  | 77432 Total | [14 empty] | 75386 | 887.8
|  | 74964 | 1 | Scheduled/Released | Regular | 6 | 6 | GPRLED-FC2W-500-90-35-RG2-35'5"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 10733.34 | 62
|  |  | 2 | Scheduled/Released | Regular | 26 | 26 | GPRLED-EX2W-500-90-35-RG2-16-W-120-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 31893.16 | 145.6
|  |  | 3 | Scheduled/Released | Regular | 12 | 12 | GPRLED-FC2W-500-90-35-RG2-34'8"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 21466.68 | 124
|  |  | 4 | Scheduled/Released | Regular | 8 | 8 | GPRLED-FC2W-500-90-35-RG2-36'7"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 11346.66 | 75.4
|  |  | 5 | Scheduled/Released | Regular | 8 | 8 | GPRLED-FC2W-500-90-35-RG2-37'1"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 11346.66 | 75.4
|  |  | 6 | Scheduled/Released | Regular | 3 | 3 | GPRLED-FC2W-500-90-35-RG2-35'4"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 5366.67 | 31
|  |  | 7 | Scheduled/Released | Regular | 15 | 15 | GPRLED-FC2W-500-90-35-RG2-33'2"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 25300 | 155
|  |  | 8 | Scheduled/Released | Regular | 21 | 21 | GPRLED-FC2W-500-90-35-RG2-33'7"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 36493.31 | 217
|  |  | 9 | Scheduled/Released | Regular | 3 | 3 | GPRLED-FC2W-500-90-35-RG2-35'6"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 5520 | 31
|  |  | 10 | Scheduled/Released | Regular | 8 | 8 | GPRLED-FC2W-500-90-35-RG2-36'9"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 10746.66 | 75.4
|  |  | 11 | Scheduled/Released | Regular | 6 | 6 | GPRLED-FC2W-500-90-35-RG2-34'6"-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 10733.34 | 62
|  |  | 12 | Scheduled/Released | Regular | 2 | 2 | GPRLED-EX2W-500-90-35-RG2-12'-W-120-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 3680 | 14.4
|  |  | 13 | Scheduled/Released | Regular | 3 | 3 | GPRLED-FC2W-500-90-35-RG2-27'-W-120-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 4293.33 | 27
|  |  | 14 | Scheduled/Released | Regular | 3 | 3 | GPRLED-FC2W-500-90-35-RG2-27'10"-W-120-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 4293.33 | 19
|  |  | 15 | Scheduled/Released | Regular | 3 | 3 | GPRLED-FC2W-500-90-35-RG2-34'-W-120-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 5213.33 | 23
|  |  | 16 | Scheduled/Released | Regular | 3 | 3 | GPRLED-FC2W-500-90-35-RG2-27'9"-W-120-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 4293.33 | 19
|  |  | 17 | Machine Shop Started | Regular | 18 | 18 | CLKLED-750-90-35-SO-12-W-120-DP-1-ST | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 13680 | 76.5
|  |  | 18 | Machine Shop Started | Regular | 110 | 110 | CLKLED-750-90-35-SO-16-W-120-DP-1-ST | Material | Shortage | FALSE | Shortage | TRUE | FALSE |  |  | 108216.35 | 924
|  |  | 19 | Machine Shop Started | Regular | 5 | 5 | SP18407-ARCLED-SL 23/77-800-80-35-SO-8-W-120-DP-1-CTS(36) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 4426.65 | 43.5
|  |  | 20 | Machine Shop Started | Regular | 3 | 3 | SP18407-ARCLED-SL 23/77-800-80-35-SO-4-W-120-DP-1-CTS(36) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1327.98 | 15
|  |  | 21 | Machine Shop Started | Regular | 1 | 1 | SP18407-ARCWLED-SL 23/77-800-80-35-SO-8-W-120-DP-1 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 885.33 | 8.7
|  |  | 22 | Machine Shop Started | Regular | 3 | 3 | SP18407-ARCWLED-SL 23/77-800-80-35-SO-18-W-120-DP-1 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1992 | 20.8
|  |  | 23 | Scheduled/Released | Regular | 3 | 3 | GPRLED-EXNW-500-90-35-RG2-27' 11 1/2"-W-120-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 4293.33 | 19
|  | 74964 Total | [14 empty] | 337541.44 | 2263.7
|  | 77765 | 1 | Machine Shop Started | Regular | 16 | 16 | SCRPAT-OPI-90(1)-300-80-30-FL-9'0"-NL-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 6965.04 | 72
|  |  | 2 | Machine Shop Started | Regular | 5 | 5 | SCRPAT-OPI-90(2)-500-80-30-FL-26'4"-NL-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 2743.1 | 30
|  |  | 5 | Machine Shop Started | Regular | 4 | 4 | SCD-300-80-30-FL-6'10"-BLK-UNV-DP-1-CTS(48) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2003.64 | 28
|  |  | 22 | Machine Shop Started | Regular | 5 | 5 | SCRPAT-OPI-90(2)-500-80-30-FL-26'4"-NL-W-UNV-DP-1-DS | +Cartridge | Missing info. In SD | TRUE |  | TRUE | TRUE | Ready |  | 2743.1 | 30
|  | 77765 Total | [14 empty] | 14454.88 | 160
|  | 78448 | 1 | Machine Shop Started | Regular | 2 | 2 | SCR-300-80-30-FL-1'3"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 254 | 10
|  |  | 2 | Machine Shop Started | Regular | 1 | 1 | SCR-300-80-30-FL-10'2"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 632 | 10.2
|  |  | 3 | Machine Shop Started | Regular | 1 | 1 | SCR-300-80-30-FL-6'10"-W-UNV-DP-1-DS-B1(BSL310LP) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 632 | 11.9
|  |  | 4 | Machine Shop Started | Regular | 2 | 2 | SCD-300-80-30-FL-10'7 3/4"-BLK-UNV-DP-1-CA(48)-C(BLK CANOPIES AND CORD) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1506 | 18
|  |  | 5 | Machine Shop Started | Regular | 4 | 4 | SCD-300-80-30-FL-16'8 1/2"-BLK-UNV-DP-1-CA(48)-C(BLK CANOPIES AND CORD) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2328 | 32
|  |  | 6 | Machine Shop Started | Regular | 1 | 1 | SCD-300-80-30-FL-10'7 3/4"-BLK-UNV-DP-1-CA(48)-B1(BSL310LP)-C(BLK CANOPIES AND CORD) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 943 | 13
|  |  | 7 | Machine Shop Started | Regular | 4 | 4 | SCD-300-80-30-FL-16'8 1/2"-BLK-UNV-DP-1-CA(48)-B1(BSL310LP)-C(BLK CANOPIES AND CORD) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2706 | 40
|  |  | 8 | Machine Shop Started | Regular | 8 | 8 | SCRPAT-REC-90(4)-300-80-30-FL-55'4"-NL-W-UNV-DP-1-DS-C(RECT 13' 6" X 14' 2") | +Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 3927 | 50
|  |  | 9 | Machine Shop Started | Regular | 8 | 8 | SCRPAT-REC-90(4)-300-80-30-FL-48'0"-NL-W-UNV-DP-1-DS-C(RECT 12' 3" X 10' 8") | +Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 3453 | 45
|  |  | 10 | Machine Shop Started | Regular | 1 | 1 | SCRV-300-80-30-FL-1'0"-W-UNV-DP-1-DS-C(DRIVER TO BE REMOTE, NO FLANGE ON ONE END) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 137 | 5
|  |  | 11 | Machine Shop Started | Regular | 2 | 2 | SCRV-300-80-30-FL-2'0"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 254 | 10
|  |  | 12 | Machine Shop Started | Regular | 4 | 4 | SCRV-300-80-30-FL-3'0"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 760 | 20
|  |  | 13 | Machine Shop Started | Regular | 2 | 2 | SCRV-300-80-30-FL-5'0"-W-UNV-DP-1-Ds-C(NO FLANGE ON ONE END) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 632 | 14
|  |  | 14 | Machine Shop Started | Regular | 22 | 22 | ZESQDI-SL 25/75-1050-80-30-MSO-8'-BLK-UNV-MD-1-CA(48) | Material | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 17600 | 275
|  |  | 15 | Machine Shop Started | Regular | 18 | 18 | ZESQDI-SL 25/75-1050-80-30-MSO-8'-BLK-UNV-MD-1-CA(48)-B1(BSL310LP) |  | Missing parts in BOM | TRUE |  | TRUE | FALSE |  | Done | 17820 | 297
|  |  | 16 | Machine Shop Started | Regular | 8 | 8 | SCRPAT-REC-90(4)-300-80-30-FL-53'10 6/8"-NL-W-UNV-DP-1-DS-C(RECT 15' 4" 3/8"X 11' 7") | +Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 3750 | 49
|  |  | 17 | Machine Shop Started | Regular | 1 | 1 | SCRV-300-80-30-FL-3'0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 240 | 5
|  |  | 18 | Machine Shop Started | Regular | 3 | 3 | SCRV-300-80-30-FL-2'0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 630 | 15
|  |  | 19 | Machine Shop Started | Regular | 1 | 1 | SCR-300-80-30-FL-10'2"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 770 | 9
|  |  | 20 | Machine Shop Started | Regular | 1 | 1 | SCR-300-80-30-FL-1'3"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 180 | 5
|  | 78448 Total | [14 empty] | 59154 | 934.1
| Total | [15 empty] | 812534.9999 | 8952.12
1 Total | [16 empty] | 812534.9999 | 8952.12
4 |  | 75398 | 1 | Wiring Started | Regular | 3 | 3 | SP000-B2SQILED-1100-80-TW2750-SL-4-BLK-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) |  | Missing parts in BOM | TRUE |  | TRUE | TRUE |  | Done | 1470 | 26.46
|  |  | 2 | Wiring Started | Regular | 129 | 14 | SP000-B2SQILED-1100-80-TW2750-SLA-26-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) |  | Others | FALSE | Others | TRUE | TRUE |  | Done | 16986.6667 | 159.6
|  |  | 3 | Wiring Started | Regular | 1 | 0 | SP000-B2SQILED-1100-80-TW2750-SLA-4' 6 1/2"-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) |  | Others | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 4 | Packaging Finished | Regular | 4 | 4 | SP000-CCH-SL-1100-80-TW2750-CL(2)-W-277-O(ELDOLED)-1-C-C(NIO EZ-CCT. NLIGHT) |  | Mechanical issue | TRUE |  | #N/A | #N/A | #N/A | #N/A | 1080 | 40
|  |  | 5 | Packaging Finished | Regular | 16 | 16 | SP000-CCH-SL-1100-80-TW2750-CL(8)-W-277-O(ELDOLED)-1-C-C(ZIO EZ-CCT. NLIGHT) |  | Mechanical issue | TRUE |  | #N/A | #N/A | #N/A | #N/A | 12480 | 115.2
|  | 75398 Total | [14 empty] | 32016.6667 | 341.26
|  | 77249 | 3 | Machine Shop Finished | Mockup/Samples | 1 | 1 | ED2WD-1000-80-35-UB-8-W-W-UNV-DP-1-FL-C(REMOTE DRIVER AND ENLIGHTED INTEGRAL SENSOR) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 680 | 10.26
|  |  | 10 | Machine Shop Started | Mockup/Samples | 1 | 1 | ED2-1000-80-35-UB-6-W-W-UNV-MD-1-90D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 510 | 10.26
|  |  | 11 | Machine Shop Finished | Mockup/Samples | 1 | 1 | ED2-1000-80-35-UB-6-W-W-UNV-MD-1-45D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 510 | 10.26
|  |  | 15 | Machine Shop Finished | Mockup/Samples | 1 | 1 | ED2-1000-80-35-UB-4-W-W-UNV-MD-1-45D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 340 | 7.45
|  | 77249 Total | [14 empty] | 2040 | 38.23
|  | 78875 | 1 | Scheduled/Released | Mockup/Samples | 8 | 8 | STFC-SLI(4-350)-DSO(4-400)-90-30-AL(4)-W-UNV-MD-1-CA(36)-RC | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1520 | 43
|  | 78875 Total | [14 empty] | 1520 | 43
|  | 70634 | 1 | Machine Shop Finished | Regular | 20 | 20 | SP18083-CCH-SL-1100-80-2740-CP(110)-W-120-O(DMX)-2-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 12320 | 280.77
|  |  | 2 | Machine Shop Finished | Regular | 28 | 28 | SP18083-CCH-SL-1100-80-2740-CP(116)-W-120-O(DMX)-2-C |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 12992 | 374.74
|  |  | 3 | Machine Shop Finished | Regular | 21 | 21 | SP18083-CCH-SL-1100-80-2740-CP(110)-W-120-O(DMX)-2-C |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 12320 | 280.77
|  |  | 4 | Machine Shop Finished | Regular | 28 | 28 | SP18083-CCH-SL-1100-80-2740-CP(116)-W-120-O(DMX)-3-C |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  | Done | 12992 | 471.77
|  | 70634 Total | [14 empty] | 50624 | 1408.05
|  | 78511 | 1 | Machine Shop Finished | Regular | 16 | 16 | CCL-SL-300-80-35-CL(184')-W-277-DP-2-AC |  | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 15640 | 147
|  |  | 2 | Machine Shop Finished | Regular | 4 | 4 | CCL-SL-300-80-35-CL(45')-W-277-DP-1-AC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3825 | 37.8
|  | 78511 Total | [14 empty] | 19465 | 184.8
|  | 77375 | 1 | Machine Shop Started | Regular | 4 | 4 | BMPRLED-750-90-35-RG2-15'0"-W-UNV-DP-1-TB9-TS(1) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 2910.44 | 26.8
|  |  | 2 | Machine Shop Started | Regular | 4 | 4 | BMPRLED-750-90-35-RG2-21'0"-W-UNV-DP-1-TB9-TS(1) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 4074.6 | 37.6
|  |  | 3 | Machine Shop Started | Regular | 2 | 2 | BMPRLED-750-90-35-RG2-23'0"-W-UNV-DP-1-TB9-TS(1) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 2231.31 | 18.8
|  |  | 5 | Machine Shop Started | Regular | 2 | 2 | BMPRLED-750-90-35-RG2-7' 5"-W-UNV-DP-1-TB9-TS(1)-B1(BSL10LST) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 1643.52 | 22
|  |  | 6 | Machine Shop Started | Regular | 8 | 8 | B2SQILED-1000-90-35-SL-95'0"-W-UNV-DP-1-CA(36) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 9500 | 72
|  |  | 7 | Machine Shop Started | Regular | 9 | 9 | BDLED-750-90-35-SO-105'0"-BLK-UNV-DP-1-CA(36) | Material+Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 8988.02 | 88
|  |  | 8 | Machine Shop Started | Regular | 8 | 8 | TB2WDILED-1100-1000-80-35-SLA-SO-3'5"-W-UNV-DP-1-B1(BSL10LST)-OS(1) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 6756.64 | 104
|  | 77375 Total | [14 empty] | 36104.53 | 369.2
|  | 78889 | 1 | Machine Shop Finished | Regular | 4 | 4 | CCH-SL-1100-80-35-CL(17' 4")-W-UNV-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2880 | 33.2
|  |  | 2 | Machine Shop Finished | Regular | 2 | 0 | CCH-SL-1100-80-35-CL(8' 6")-W-UNV-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 3 | Machine Shop Finished | Regular | 2 | 1 | CCH-SL-1100-80-35-CL(17')-W-UNV-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 680 | 8.3
|  |  | 4 | Machine Shop Finished | Regular | 2 | 2 | CCH-SL-1100-80-35-CL(16')-W-UNV-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1280 | 14
|  | 78889 Total | [14 empty] | 4840 | 55.5
|  | 76028 | 32 | Machine Shop Started | Regular | 10 | 10 | CCH-SL-1100-80-35-CL(56)-W-UNV-DP-1-C |  | (blank) | FALSE |  | FALSE | FALSE |  |  | 6944 | 89.6
|  |  | 44 | Scheduled/Released | Regular | 9 | 9 | CCH-SL-1100-80-35-CL(80)-W-UNV-DP-1-C |  | (blank) | FALSE |  | FALSE | FALSE |  |  | 4960 | 63.5
|  | 76028 Total | [14 empty] | 11904 | 153.1
|  | 76191 | 1 | Machine Shop Started | Regular | 5 | 5 | ZESLED-SL 0/100-600-80-35-MSO-8-W-UNV-MD-1-S |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 3240 | 56.65
|  | 76191 Total | [14 empty] | 3240 | 56.65
|  | 79418 | 1 | Machine Shop Started | Mockup/Samples | 1 | 1 | ZELED-SL 65/35-700-80-35-MSO-W-4-W-UNV-MD-1-CT15(36) |  | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 100 | 7
|  |  | 2 | Machine Shop Started | Mockup/Samples | 1 | 1 | ZELED-SL 65/35-700-80-35-MAL-W-4-W-UNV-MD-1-CT15(36) |  | (blank) | FALSE |  | FALSE | FALSE |  |  | 100 | 7
|  |  | 3 | Machine Shop Started | Mockup/Samples | 1 | 1 | ZESQD-SL 0/100-750-90-35-SO-4-W-UNV-MD-1-CT15(36)-SE |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 100 | 5.6
|  |  | 4 | Machine Shop Started | Mockup/Samples | 1 | 1 | ZESQD-SL 0/100-750-80-35-MAL-W-4-BLK-UNV-MD-1-CT15(36) |  | Shortage | FALSE | Shortage | #N/A | #N/A | #N/A | #N/A | 100 | 5.6
|  | 79418 Total | [14 empty] | 400 | 25.2
|  | 78593 | 1 | Wiring Started | Regular | 3 | 3 | SL2HLED-2XSL-1000-750-80-40-SM-4-AP-UNV-DP-2-CA(36) |  | PM wrong/missing info | TRUE |  | TRUE | TRUE |  | Done | 1680 | 18.3
|  |  | 2 | Wiring Started | Regular | 2 | 2 | SL2HLED-2XSL-1000-750-80-40-SM-4-AP-UNV-DP-2-CA(36)-B1(BSL10LST) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1480 | 20
|  |  | 3 | Wiring Started | Regular | 2 | 2 | SCS-750-80-40-0.5P-6-AP-UNV-DP-1-S |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 816 | 12.4
|  |  | 4 | Wiring Started | Regular | 8 | 8 | SCDPAT-SQ-90(4)-750-80-40-0.5M-20-NL-AP-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE | Ready | Done | 7040 | 116
|  | 78593 Total | [14 empty] | 11016 | 166.7
|  | 77207 | 1 | Machine Shop Finished | Regular | 36 | 36 | TB2DILED-1000-400-80-30-SL-SO-16'-W-277-DP-2-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 27540 | 405
|  |  | 2 | Machine Shop Finished | Regular | 12 | 12 | TB2DILED-1000-400-80-30-SL-SO-30'-W-277-DP-2-CA(36) |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  | Done | 10880 | 161.6
|  |  | 3 | Machine Shop Finished | Regular | 3 | 3 | B2SQDLED-1000-80-30-SO-2-W-277-DP-1-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 390 | 12.6
|  |  | 4 | Machine Shop Finished | Regular | 5 | 5 | B2SQDLED-1000-80-30-SO-4-W-277-DP-1-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1300 | 21
|  |  | 5 | Machine Shop Finished | Regular | 3 | 3 | B2SQDLED-1000-80-30-SO-6-W-277-DP-1-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1170 | 20.7
|  |  | 6 | Machine Shop Finished | Regular | 4 | 4 | B2SQDLED-1000-80-30-SO-8-W-277-DP-1-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2080 | 27.6
|  |  | 7 | Machine Shop Finished | Regular | 1 | 1 | B2SQDLED-1000-80-30-SO-8-W-277-DP-1+E(1)-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 550 | 8.2
|  |  | 8 | Machine Shop Finished | Regular | 1 | 1 | BRLED-1000-80-30-FL-3-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 195 | 4
|  |  | 9 | Machine Shop Finished | Regular | 9 | 9 | BRLED-1000-80-30-FL-4-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2340 | 36
|  |  | 10 | Machine Shop Finished | Regular | 5 | 5 | BRLED-1000-80-30-FL-6-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1950 | 37.5
|  |  | 11 | Machine Shop Finished | Regular | 2 | 2 | BRLED-1000-80-30-FL-6-W-277-DP-1+E(1)-DS-FW(6) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 840 | 15.6
|  |  | 12 | Machine Shop Finished | Regular | 6 | 6 | BRLED-1000-80-30-FL-8-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3120 | 45
|  |  | 13 | Machine Shop Finished | Regular | 1 | 1 | BRLED-1000-80-30-FL-8-W-277-DP-1+E(1)-DS-FW(6) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 550 | 7.8
|  |  | 14 | Machine Shop Started | Regular | 7 | 7 | BMRLED-1000-80-30-FL-6-W-277-DP-1-TG9-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2730 | 44.1
|  |  | 15 | Machine Shop Started | Regular | 3 | 3 | BMRLED-1000-80-30-FL-8-W-277-DP-1-TG9-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1560 | 18.9
|  |  | 16 | Machine Shop Started | Regular | 8 | 8 | BMRLEDPAT-REC-90(4)-1000-80-30-SO-FL-42'-EX-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 3730 | 52
|  |  | 17 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-1000-80-30-RG3-4' 8"-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 303.52 | 7.2
|  |  | 18 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-1000-80-30-RG3-7' 4"-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 476.96 | 7.2
|  |  | 19 | Machine Shop Started | Regular | 2 | 2 | BMPRLED-1000-80-30-RG3-14'-W-277-DP-1-DS-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 910.56 | 10.2
|  |  | 20 | Machine Shop Started | Regular | 2 | 2 | BMPRLED-1000-80-30-RG3-19' 9"-W-277-DP-1-DS-FW(6) |  | Others | TRUE |  | TRUE | FALSE |  | Done | 1300.8 | 18
|  | 77207 Total | [14 empty] | 63916.84 | 960.2
|  | 79121 | 1 | Scheduled/Released | Replacement | 10 | 9 | STSLF-ML-600-80-30-8'-BLK-277-MD-1-SB9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 3960 | 65.7
|  | 79121 Total | [14 empty] | 3960 | 65.7
|  | 77607 | 1 | Machine Shop Finished | Regular | 2 | 2 | B2SQDLED-750-90-35-SO-19-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1862 | 16
|  |  | 2 | Machine Shop Finished | Regular | 2 | 2 | B2SQDLED-750-90-35-SO-21-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2058 | 18.4
|  |  | 3 | Machine Shop Finished | Regular | 3 | 3 | B2SQDLED-750-90-35-SO-35-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3430 | 27.4
|  |  | 4 | Machine Shop Finished | Regular | 12 | 12 | B2SQDLED-750-90-35-SO-38-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 11172 | 94.8
|  |  | 5 | Machine Shop Started | Regular | 15 | 15 | BRLEDPAT-OPR-90(1)-1000-90-35-SO-FL-41-NL-W-120-DP-1-DS-C(L-SHAPE PATTERN, 15'H X 26'W) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 11400 | 138
|  |  | 6 | Machine Shop Finished | Regular | 36 | 36 | B2SQDLED-1000-90-35-SO-4-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 14112 | 151.2
|  | 77607 Total | [14 empty] | 44034 | 445.8
|  | 76817 | 1 | Given to Shipping | Regular | 1 | 0 | SCS-300-80-35-0.5M-4-AP-UNV-DP-1-S |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 2 | Given to Shipping | Regular | 4 | 1 | SCS-300-80-35-0.5M-14-AP-UNV-DP-1-S-B1(BSL310LP) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 478 | 8.1
|  |  | 3 | Given to Shipping | Regular | 4 | 0 | SCS-300-80-35-0.5M-22-AP-UNV-DP-1-S-B2(BSL310LP) |  | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 4 | Given to Shipping | Regular | 1 | 0 | SCS-300-80-35-0.5M-6-AP-UNV-DP-1-S-B1(BSL310LP) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 5 | Given to Shipping | Regular | 2 | 0 | SCS-300-80-35-0.5M-6-AP-UNV-DP-1-S |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 6 | Given to Shipping | Regular | 2 | 0 | SCS-300-80-35-0.5M-8-AP-UNV-DP-1-S-B1(BSL310LP) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 7 | Given to Shipping | Regular | 24 | -1 | SCS-400-80-35-0.5M-16-AP-UNV-DP-1-S-B1(BSL310LP) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -534.5 | -8.15
|  |  | 8 | Given to Shipping | Regular | 8 | 1 | SCS-400-80-35-0.5M-16-AP-UNV-DP-1-S-B2(BSL310LP) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 615.5 | 10
|  |  | 9 | Given to Shipping | Regular | 8 | -1 | SCDI-500-300-80-35-SO-FL-8-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -576 | -9.9
|  |  | 10 | Given to Shipping | Regular | 2 | 0 | SCDI-500-300-80-35-SO-FL-8-W-UNV-DP-2-CA(180)-B1(BSL310LP)-C(15FT POWER CORD & CABLES) |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 11 | Given to Shipping | Regular | 4 | 0 | SCDI-500-300-80-35-SO-FL-18-W-UNV-DP-2-CA(180)-B1(BSL310LP)-C(15FT POWER CORD & CABLES) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 12 | Given to Shipping | Regular | 4 | 0 | SCDI-500-300-80-35-SO-FL-18-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 13 | Given to Shipping | Regular | 2 | 0 | SCDI-500-300-80-35-SO-FL-14-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 14 | Given to Shipping | Regular | 1 | 0 | SCR-300-80-35-FL-8-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 76817 Total | [14 empty] | -17 | 0.05
|  | 78778 | 1 | Machine Shop Finished | Regular | 4 | 4 | CCWH-SL-700-90-35-CL(45'8")-W-UNV-DP-1-AC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3818 | 37.8
|  |  | 2 | Machine Shop Finished | Regular | 3 | 3 | CCWH-SL-700-90-35-CL(31'8")-W-UNV-DP-1-AC | Material | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 2656 | 26
|  | 78778 Total | [14 empty] | 6474 | 63.8
|  | 77868 | 1 | Machine Shop Started | Regular | 22 | 22 | SP16308(2)-CCWH-SL-1100-80-27-CP(197' 2")-C(NATATORIUM)-120-DP-2-C | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 18900 | 210
|  |  | 2 | Machine Shop Started | Regular | 13 | 13 | SP16308(2)-CCH-SL-1100-80-27-CP(103' 7")-C(NATATORIUM)-120-DP-1-C | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 9734 | 98
|  | 77868 Total | [14 empty] | 28634 | 308
|  | 78820 | 2 | Machine Shop Finished | Regular | 14 | 14 | TB2DILED-600-500-90-35-SO-SO-4'-W-UNV-LT(LDE5)-1-CT15(60) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 8680 | 98
|  |  | 3 | Machine Shop Finished | Regular | 24 | 24 | TB2DILED-600-500-90-35-SO-SO-8'-W-UNV-LT(LDE5)-1-CT15(60) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 29736 | 256.8
|  |  | 4 | Machine Shop Finished | Regular | 24 | 24 | TB2DILED-600-500-90-35-SO-SO-4'-W-UNV-LT(LDE5)-1-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 14880 | 168
|  |  | 5 | Machine Shop Finished | Regular | 18 | 18 | TB2DILED-600-500-90-35-SO-SO-8'-W-UNV-LT(LDE5)-1-CA(96) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 22302 | 192.6
|  | 78820 Total | [14 empty] | 75598 | 715.4
|  | 79311 | 1 | Machine Shop Started | Replacement | 1 | 1 | CCH-SL-1100-80-35-CL(26")-W-UNV-DP-1-C-C(23 7/16" LENGTH TO ADD TO EXISTING) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 150 | 4.3
|  |  | 2 | Machine Shop Started | Replacement | 1 | 1 | CCH-SL-1100-80-35-CL(48")-W-UNV-DP-1-C-C(46 3/4" LENGTH TO ADD TO EXISTING) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 300 | 4.3
|  | 79311 Total | [14 empty] | 450 | 8.6
|  | 77945 | 1 | Machine Shop Finished | Regular | 3 | 3 | SP000-B2SQILED-1100-80-TW2750-SL-6-BLK-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | +Cartridge | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 2370 | 23.67
|  |  | 2 | Machine Shop Finished | Regular | 21 | 21 | SP000-B2SQILED-1100-80-TW2750-SLA-32-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | +Cartridge | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 33670 | 187.67
|  |  | 3 | Machine Shop Finished | Regular | 2 | 2 | SP000-B2SQILED-1100-80-TW2750-SLA-18-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | +Cartridge | Shortage | TRUE |  | TRUE | TRUE |  | Done | 3150 | 17.45
|  | 77945 Total | [14 empty] | 39190 | 228.79
|  | 77947 | 1 | Machine Shop Finished | Regular | 3 | 3 | SP000-B2SQILED-1100-80-TW2750-SLA-34-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | +Cartridge | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 5520 | 29.09
|  |  | 2 | Machine Shop Finished | Regular | 8 | 8 | SP000-B2SQILED-1100-80-TW2750-SLA-24-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | +Cartridge | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 16960 | 78.96
|  |  | 15 | Machine Shop Finished | Regular | 4 | 4 | SP000-B2SQILED-1100-80-TW2750-SLA-37' 5"-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) |  | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 6010 | 33.71
|  | 77947 Total | [14 empty] | 28490 | 141.76
|  | 77615 | 1 | Machine Shop Finished | Regular | 5 | 5 | TB2DILED-600-500-80-35-SO-SO-12-W-277-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4800 | 70
|  |  | 2 | Machine Shop Finished | Regular | 16 | 16 | TB2DILED-600-500-80-35-SO-SO-16-W-277-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 10240 | 160
|  |  | 3 | Machine Shop Finished | Regular | 12 | 12 | TB2DILED-600-500-80-35-SO-SO-20-W-277-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 9600 | 144
|  |  | 4 | Machine Shop Started | Regular | 94 | 94 | CLKLED-500-80-35-SO-6-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 39480 | 846
|  |  | 5 | Machine Shop Started | Regular | 25 | 25 | BBRLED-500-80-35-FL-4-W-277-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 6000 | 75
|  |  | 6 | Machine Shop Started | Regular | 7 | 7 | BBRLED-500-80-35-FL-8-W-277-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3360 | 35
|  |  | 7 | Machine Shop Started | Regular | 10 | 10 | BBRLED-500-80-35-FL-12-W-277-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 7200 | 70
|  |  | 8 | Machine Shop Started | Regular | 6 | 6 | BBRLED-500-80-35-FL-16-W-277-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2880 | 30
|  |  | 9 | Machine Shop Started | Regular | 10 | 10 | BBRLED-500-80-35-FL-20-W-277-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 6000 | 60
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | BBRLED-500-80-35-FL-24-W-277-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1440 | 14
|  |  | 11 | Machine Shop Finished | Regular | 17 | 17 | PWWLED-800-90-35-S-4-W-277-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4335 | 68
|  |  | 12 | Machine Shop Finished | Regular | 8 | 8 | PWWLED-800-90-35-S-4-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2040 | 32
|  |  | 13 | Machine Shop Started | Regular | 12 | 12 | WBRLED-500-80-35-S-6-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 6000 | 84
|  | 77615 Total | [14 empty] | 103375 | 1688
|  | 79034 | 1 | Machine Shop Finished | Replacement | 4 | 4 | ZESQDI-SL 25/75-1050-80-35-MSO-44-BLK-UNV-MD-1-CA(96)-B2(BSL10LST) | Material | Shortage | TRUE |  | TRUE | TRUE |  | Done | 3568 | 74
|  | 79034 Total | [14 empty] | 3568 | 74
|  | 78220 | 1 | Machine Shop Started | Regular | 8 | 8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 5440 | 80
|  |  | 2 | Machine Shop Started | Regular | 2 | 2 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1190 | 20
|  |  | 3 | Machine Shop Started | Regular | 32 | 32 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 16320 | 219.2
|  |  | 4 | Machine Shop Started | Regular | 2 | 2 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-10-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 850 | 13.7
|  |  | 5 | Machine Shop Started | Regular | 3 | 3 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2040 | 30.3
|  |  | 6 | Machine Shop Started | Regular | 4 | 4 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-6-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2040 | 40.4
|  |  | 7 | Machine Shop Started | Regular | 4 | 4 | WWR-SL-750-80-30-13-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1950 | 33
|  |  | 8 | Machine Shop Started | Regular | 2 | 2 | WWR-SL-750-80-30-10-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 750 | 9.8
|  |  | 9 | Machine Shop Started | Regular | 1 | 1 | WWR-SL-750-80-30-6-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 450 | 7.8
|  |  | 10 | Machine Shop Started | Regular | 10 | 10 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1500 | 48
|  |  | 11 | Machine Shop Started | Regular | 4 | 4 | BBPRLED-300-80-30-FL-26' 6"-W-UNV-DP-1+E(2)-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1714 | 18.3
|  |  | 12 | Machine Shop Started | Regular | 12 | 12 | BBPRLED-300-80-30-FL-92' 11"-W-UNV-DP-2+E(6)-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 5806 | 61
|  |  | 13 | Machine Shop Started | Regular | 5 | 5 | BBPRLED-300-80-30-FL-39' 5"-W-UNV-DP-1+E(3)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2520 | 26.2
|  |  | 14 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-19' 5"-W-UNV-DP-1+E(1)-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1218 | 12.5
|  |  | 15 | Machine Shop Started | Regular | 4 | 4 | BBPRLED-300-80-30-FL-26' 5"-W-UNV-DP-1+E(2)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1714 | 18.3
|  | 78220 Total | [14 empty] | 45502 | 638.5
|  | 78221 | 1 | Machine Shop Started | Regular | 6 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-22-W-UNV-DP-1-CT9(36") | Material+Cartridge | PM wrong/missing info | TRUE |  | FALSE | FALSE |  |  | 3740 | 55
|  |  | 2 | Machine Shop Started | Regular | 12 | 12 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | Material+Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 7140 | 120.6
|  |  | 3 | Machine Shop Started | Regular | 6 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 3060 | 41.1
|  |  | 4 | Machine Shop Started | Regular | 2 | 2 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1360 | 20.2
|  |  | 5 | Machine Shop Started | Regular | 15 | 15 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2250 | 45
|  |  | 6 | Machine Shop Started | Regular | 4 | 4 | WWR-SL-750-80-30-10-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1500 | 14
|  |  | 7 | Machine Shop Started | Regular | 1 | 1 | WWR-SL-750-80-30-6-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 450 | 5.2
|  |  | 8 | Machine Shop Started | Regular | 13 | 13 | BBPRLED-300-80-30-FL-97'-W-UNV-DP-2+E(7)-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 6054 | 64.2
|  |  | 9 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-18' 8"-W-UNV-DP-1+E(2)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1218 | 12.8
|  |  | 10 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-23' 8"-W-UNV-DP-1+E(2)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1528 | 14.8
|  |  | 11 | Machine Shop Started | Regular | 10 | 10 | BBPRLED-300-80-30-FL-76' 2"-W-UNV-DP-2+E(5)-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 4752 | 48.7
|  |  | 12 | Machine Shop Started | Regular | 4 | 4 | BBPRLED-300-80-30-FL-18' 9"-W-UNV-DP-1+E(2)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1218 | 12.8
|  |  | 13 | Machine Shop Started | Regular | 2 | 2 | BBPRLED-300-80-30-FL-11' 5"-W-UNV-DP-1+E(1)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 722 | 6.9
|  |  | 14 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-17' 11"-W-UNV-DP-1+E(2)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 784 | 12.8
|  |  | 15 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-18' 3"-W-UNV-DP-1+E(2)-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1156 | 12.8
|  |  | 16 | Machine Shop Started | Regular | 11 | 11 | BBPRLED-300-80-30-FL-75' 9"-W-UNV-DP-2+E(5)-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 4752 | 48.7
|  | 78221 Total | [14 empty] | 41684 | 535.6
|  | 78226 | 1 | Machine Shop Finished | Regular | 8 | 8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 5440 | 80.4
|  |  | 2 | Machine Shop Started | Regular | 28 | 28 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | +Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  | Done | 16660 | 281.4
|  |  | 3 | Machine Shop Finished | Regular | 10 | 10 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 10200 | 137
|  |  | 4 | Machine Shop Started | Regular | 45 | 45 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | +Cartridge | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 6750 | 135
|  |  | 5 | Machine Shop Started | Regular | 4 | 4 | BBPRLED-300-80-30-FL-28' 6"-W-UNV-DP-1+E(3)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1776 | 20.6
|  |  | 6 | Machine Shop Started | Regular | 12 | 12 | BBPRLED-300-80-30-FL-90' 6"-W-UNV-DP-2+E(6)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 5682 | 59
|  |  | 7 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-18' 11"-W-UNV-DP-1+E(2)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1094 | 11.4
|  |  | 8 | Machine Shop Started | Regular | 10 | 10 | BBPRLED-300-80-30-FL-73' 5"-W-UNV-DP-2+E(6)-TG9 | +Cartridge | Others | TRUE |  | TRUE | FALSE |  | Done | 4566 | 49.5
|  |  | 9 | Machine Shop Started | Regular | 4 | 4 | BBPRLED-300-80-30-FL-28'-W-UNV-DP-1+E(3)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1776 | 18.8
|  | 78226 Total | [14 empty] | 53944 | 793.1
|  | 77922 | 1 | Machine Shop Started | Regular | 1 | 1 | TB4DILED-640-400-80-35-SL-SO-8'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1291.81 | 10
|  |  | 2 | Machine Shop Started | Regular | 5 | 5 | TB4DILED-640-400-80-35-SL-SO-12'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 9617.95 | 65
|  |  | 3 | Machine Shop Started | Regular | 20 | 20 | TB4DILED-640-400-80-35-SL-SO-18'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 28712.7 | 260
|  |  | 4 | Machine Shop Started | Regular | 8 | 8 | TB4DILED-640-400-80-35-SL-SO-20'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 12748.68 | 104
|  |  | 5 | Machine Shop Started | Regular | 16 | 16 | TB4DILED-640-400-80-35-SL-SO-22'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 28024.48 | 224
|  |  | 6 | Machine Shop Started | Regular | 6 | 6 | TB4DILED-640-400-80-35-SL-SO-24'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 11456.88 | 87
|  |  | 7 | Machine Shop Started | Regular | 9 | 9 | TB4DILED-640-400-80-35-SL-SO-28'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 13352.25 | 108
|  |  | 8 | Machine Shop Started | Regular | 22 | 22 | TB2WDILED-1100-1000-80-35-SO-SO-4'-W-UNV-DP-1 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 11484 | 154
|  |  | 9 | Machine Shop Started | Regular | 2 | 2 | CCH-SL-900-80-35-CL(23)-W-UNV-DP-1-C | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 2668.21 | 18
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | TB4DILED-640-400-80-35-SL-SO-10'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 4478.96 | 26
|  |  | 11 | Machine Shop Started | Regular | 8 | 8 | TB4DILED-640-400-80-35-SL-SO-16'-W-UNV-DP-2-CA(120) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 11485.12 | 88
|  | 77922 Total | [14 empty] | 135321.04 | 1144
|  | 76823 | 1 | Machine Shop Finished | Regular | 13 | 13 | ZERLED-TR-400-80-35-4-W-UNV-DP-1-TG9 |  | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 4784 | 65.13
|  |  | 3 | Machine Shop Finished | Regular | 20 | 20 | ZERLED-TR-400-80-35-8-W-UNV-DP-1-TG9 |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 14720 | 163.8
|  |  | 4 | Machine Shop Finished | Regular | 9 | 9 | ZERLED-TR-400-80-35-12-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 9936 | 103.68
|  |  | 5 | Machine Shop Finished | Regular | 2 | 2 | ZERLED-TR-400-80-35-16-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1472 | 16.3
|  |  | 6 | Machine Shop Finished | Regular | 4 | 4 | ZERLED-TR-400-80-35-20-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3680 | 39.64
|  | 76823 Total | [14 empty] | 34592 | 388.55
|  | 75103 | 3 | Machine Shop Finished | Regular | 6 | 6 | TWRWLED-SL 90/10-1000-80-35-SO-4-W-120-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2880 | 30
|  |  | 4 | Machine Shop Finished | Regular | 5 | 5 | TWRWLED-SL 90/10-1000-80-35-SO-6-W-120-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3600 | 40
|  |  | 5 | Machine Shop Finished | Regular | 12 | 12 | TWRWLED-SL 90/10-1000-80-35-SO-8-W-120-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 11520 | 96
|  |  | 6 | Machine Shop Finished | Regular | 7 | 7 | TWRLED-SL 90/10-1250-80-35-SO-4-W-120-DP-1-CTS(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3360 | 35
|  |  | 7 | Machine Shop Finished | Regular | 3 | 3 | TWRLED-SL 90/10-1250-80-35-SO-6-W-120-DP-1-CTS(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2160 | 24
|  |  | 10 | Machine Shop Finished | Regular | 1 | 1 | TWRWLED-SL 90/10-1000-80-35-SO-4-W-120-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 480 | 5
|  |  | 11 | Machine Shop Finished | Regular | 4 | 4 | TWRWLED-SL 90/10-1000-80-35-SO-6-W-120-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2880 | 32
|  |  | 12 | Machine Shop Finished | Regular | 1 | 1 | TWRWLED-SL 90/10-1000-80-35-SO-8-W-120-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 960 | 8
|  |  | 13 | Machine Shop Finished | Regular | 1 | 1 | TWRLED-SL 90/10-1250-80-35-SO-4-W-120-DP-1-CTS(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 480 | 10
|  |  | 14 | Machine Shop Finished | Regular | 1 | 1 | TWRLED-SL 90/10-1250-80-35-SO-6-W-120-DP-1-CTS(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 720 | 8
|  |  | 15 | Machine Shop Finished | Regular | 1 | 1 | TWRLED-SL 90/10-1250-80-35-SO-8-W-120-DP-1-CTS(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 960 | 8
|  | 75103 Total | [14 empty] | 30000 | 296
|  | 78170 | 1 | Machine Shop Started | Regular | 10 | 10 | SCRPAT-REC-90(4)-500-80-30-2M-58'-EX-W-UNV-DP-1-TB9-B4(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 5000 | 4.3
|  |  | 2 | Machine Shop Started | Regular | 5 | 5 | SCRPAT-OPR-90(2)-300-80-30-2P-29'-EX-W-UNV-DP-1-TB9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 2540 | 30
|  | 78170 Total | [14 empty] | 7540 | 34.3
| Total | [15 empty] | 919426.0767 | 11371.84
| 2018-12-28 | 75467 | 6 | Wiring Started | NPI | 6 | 6 | NPI-N18003-GPDLED-1000-80-TW2750-RG2-14-W-O(DALIDT6)-1-CA(72)-LBC | Material+Cartridge | Others | FALSE | Others | TRUE | TRUE |  | Done | 3600 | 0
|  | 75467 Total | [14 empty] | 3600 | 0
| 12/28/2018 Total | [15 empty] | 3600 | 0
4 Total | [16 empty] | 923026.0767 | 11371.84
7 |  | 70411 | 37 | Wiring Started | Regular | 281 | 228 | SCRM-3'-(3)-1000-90-TW2750-D55-BLK-C(HS512W1186)-UNV-O(DALIDT6)-1-TB15-LBC-C(PENDANT HANGERS 120" WITH CORD) |  | Others | TRUE |  | TRUE | TRUE |  | Done | 58140 | 1140
|  | 70411 Total | [14 empty] | 58140 | 1140
|  | 75475 | 5 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 720 | 9
|  |  | 6 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 576 | 7
|  |  | 7 | Machine Shop Started | Regular | 4 | 4 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2304 | 28
|  |  | 8 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-4'-C(PS541A1391)-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 288 | 4
|  |  | 9 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 720 | 9
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS-C(1 LONG SIDE D) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1440 | 16
|  |  | 27 | Machine Shop Started | Regular | 3 | 3 | SP18276-SCR-350-80-35-FL-46'2"-W-UNV-DP-1-DS-C(ANGLED ENDS) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2470 | 44
|  |  | 28 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 864 | 14
|  | 75475 Total | [14 empty] | 9382 | 131
|  | 75693 | 4 | Machine Shop Finished | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Material+Cartridge | Others | FALSE | Others | TRUE | FALSE |  |  | 1152 | 14
|  |  | 5 | Machine Shop Finished | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1440 | 18
|  |  | 6 | Machine Shop Finished | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-12'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 864 | 9
|  |  | 7 | Machine Shop Finished | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 432 | 7
|  |  | 8 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-C(PS541A1391)-UNV-DP-1-DS | Material+Cartridge | Shortage | FALSE | Shortage | TRUE | FALSE |  |  | 432 | 7
|  |  | 12 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-OPRI(79°)-750-80-35-RG3-22'11 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(102° ANGLED END) | Material | Wrong info. In SD | TRUE |  | TRUE | FALSE |  |  | 1930 | 20.16
|  |  | 13 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-OPRI(79°)-750-80-35-RG3-19'10 5/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(102° ANGLED END) | Material | Wrong info. In SD | TRUE |  | TRUE | FALSE |  |  | 1750 | 18.88
|  |  | 14 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-OPRI(102°)-750-80-35-RG3-17'1 5/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(79°ANGLED END) | Material | Wrong info. In SD | TRUE |  | TRUE | FALSE |  |  | 1570 | 16.27
|  |  | 17 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-OPRI(1)-750-80-35-RG3-18'8 1/2"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(74° ANGLED END) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1590 | 19.03
|  |  | 18 | Machine Shop Started | Regular | 2 | 2 | SP18435(2)-BMPRLED-750-80-35-RG3-10'3 3/16"-W-UNV-DP-1-TG9-TS(1)-C(74° & 107° ANGLED END) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1135 | 9.28
|  |  | 19 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-9'10 1/6"-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 675 | 9.28
|  |  | 20 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-10'4 1/8"-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 735 | 9.28
|  |  | 21 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-10'4 1/8"-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 735 | 9.28
|  |  | 22 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-OPRI(107°)-750-80-35-RG3-21'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(72.5°ANGLED END) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1870 | 22.11
|  |  | 23 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-9'7 3/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 675 | 9.28
|  |  | 24 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-9'5 1/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | Missing parts in BOM | TRUE |  | TRUE | FALSE |  |  | 675 | 9.28
|  |  | 25 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-9'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 675 | 9.28
|  |  | 26 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-9'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 675 | 9.28
|  |  | 27 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-8'10"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 615 | 6.7
|  |  | 28 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-8'4 7/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 615 | 6.7
|  |  | 29 | Machine Shop Started | Regular | 2 | 2 | SP18435(2)-BMPRLED-750-80-35-RG3-22'6 5/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1)-C(98° & 82° ANGLED END) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1855 | 18.78
|  |  | 30 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-750-80-35-RG3-24'11 1/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1)-C(98° & 75° ANGLED END) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1975 | 22.95
|  |  | 31 | Machine Shop Started | Regular | 3 | 3 | SP18435(2)-BMPRLED-750-80-35-RG3-34'7 1/2"-W-UNV-DP-1-TG9-TS(1)-C(64° & 105° ANGLED END) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 2575 | 28.28
|  |  | 32 | Machine Shop Started | Regular | 8 | 8 | SP18435(2)-BMPRLED-OPRI(113°)+OPRO(113°+67°)-750-80-35-RG3-48'6" 3/8"-W-UNV-DP-1-TG9-TS(4)-C(79°&67°ANGLED END) | Material | Missing info. In SD | TRUE |  | TRUE | FALSE |  |  | 4240 | 57
|  |  | 33 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-7'10 3/8"-W-UNV-DP-1-DS-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 555 | 7.67
|  |  | 36 | Machine Shop Started | Regular | 3 | 3 | SP18276-SCR-350-80-35-FL-45'5"-W-UNV-DP-1-DS-C(85°&46° ANGLED ENDS) | Material+Cartridge | Others | FALSE | Others | TRUE | FALSE |  |  | 2470 | 43.2
|  |  | 40 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-10'-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 675 | 9.28
|  |  | 41 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-8'-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 555 | 6.7
|  |  | 42 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-7'8"-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 555 | 6.7
|  |  | 43 | Machine Shop Started | Regular | 2 | 2 | BMPRLED-750-80-35-RG3-17'8"-W-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1155 | 16.2
|  |  | 44 | Machine Shop Finished | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-C(ROCKFON723)-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 432 | 7
|  |  | 45 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-750-80-35-RG3-12'2"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 795 | 9.28
|  | 75693 Total | [14 empty] | 38077 | 472.13
|  | 78927 | 4 | Machine Shop Finished | Regular | 1 | 1 | SP000-SCDI-500-300-80-TW2765-SO-FL-4'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36") | +Cartridge | Others | TRUE |  | TRUE | TRUE |  | Done | 698.04 | 7.6
|  |  | 5 | Machine Shop Finished | Regular | 8 | 8 | SP000-SCDI-500-300-80-TW2765-SO-FL-16'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 10822.08 | 94.4
|  |  | 6 | Machine Shop Finished | Regular | 8 | 8 | SP000-SCDI-500-300-80-TW2765-SO-FL-16'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36")-B1(BSL310LP) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 11652.76 | 109.6
|  | 78927 Total | [14 empty] | 23172.88 | 211.6
|  | 73251 | 28 | Machine Shop Started | Regular | 7 | 7 | BMRLED-750-90-35-FL-83'7 1/8"-W-UNV-DP-1+E(6)-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 4152 | 67.5
|  |  | 29 | Machine Shop Started | Regular | 1 | 1 | BMRLED-750-90-35-FL-97"-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 400 | 8.7
|  |  | 30 | Machine Shop Started | Regular | 3 | 3 | BMRLED-750-90-35-FL-2-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 300 | 10.5
|  |  | 31 | Machine Shop Started | Regular | 1 | 1 | BMRLED-750-90-35-FL-57 1/2"-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 240 | 6.1
|  |  | 32 | Machine Shop Started | Regular | 4 | 4 | BMPRLED-OPRO(1)-750-90-35-FL-32'3 7/8"-W-UNV-DP-1+E(1)-DF |  | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 1594 | 29.5
|  |  | 33 | Machine Shop Started | Regular | 4 | 4 | BMPRLED-OPRO(1)-750-90-35-FL-42'1/4"-W-UNV-DP-1+E(4)-DF |  | (blank) | FALSE |  | FALSE | FALSE |  |  | 2104 | 57
|  |  | 36 | Machine Shop Started | Regular | 3 | 3 | BMRLEDPAT-OPI-90-750-80-35-SO-13'5 5/8"-EX-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 950 | 15
|  |  | 37 | Machine Shop Started | Regular | 4 | 4 | BMRLEDPAT-OPI-90-750-80-35-SO-31'1"-EX-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1800 | 26
|  |  | 41 | Machine Shop Started | Regular | 1 | 1 | BMRLED-750-90-35-FL-96 3/4"-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 400 | 6.1
|  |  | 42 | Machine Shop Started | Regular | 1 | 1 | BMRLED-750-90-35-FL-57 3/4"-W-UNV-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 240 | 6.1
|  |  | 43 | Machine Shop Started | Regular | 3 | 3 | BMPRLED-750-90-35-FL-28'7 1/4"-W-UNV-DP-1-DF |  | (blank) | FALSE |  | FALSE | FALSE |  |  | 1392 | 24.9
|  | 73251 Total | [14 empty] | 13572 | 257.4
|  | 78614 | 1 | Machine Shop Started | Regular | 24 | 24 | WBDIWLED-500-500-80-35-SO-SO-2-BLK-UNV-DP-1-BF | Material+Cartridge | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 9120 | 158.4
|  | 78614 Total | [14 empty] | 9120 | 158.4
|  | 78720 | 1 | Machine Shop Started | Replacement | 8 | 8 | SCPLED-OPRI(4)-300-80-35-FL-52-W-UNV-DP-1-ST-C(10'X6'X10' PRE MITTERED CORNER) | +Cartridge | Missing info. In SD | TRUE |  | FALSE | FALSE |  |  | 5540 | 57
|  | 78720 Total | [14 empty] | 5540 | 57
|  | 76762 | 4 | Machine Shop Started | Regular | 16 | 16 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-48-EX-W-UNV-DP-1+E(2)-DS |  | (blank) | FALSE |  | TRUE | FALSE | Ready |  | 4280 | 88
|  |  | 5 | Machine Shop Started | Regular | 16 | 16 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-48-EX-W-UNV-DP-1+E(2)-DS |  | (blank) | FALSE |  | TRUE | FALSE | Ready |  | 4280 | 88
|  |  | 6 | Machine Shop Started | Regular | 9 | 9 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-28-EX-W-UNV-DP-1+E(1)-DS |  | (blank) | FALSE |  | TRUE | FALSE | Ready |  | 2380 | 46
|  |  | 7 | Machine Shop Started | Regular | 10 | 10 | SP18415(1)-BMRLEDPAT-REC-90-1200-80-35-SO-FL-12'X20'-EX-W-UNV-DP-1-ST |  | Wrong info. In SD | TRUE |  | TRUE | FALSE | Ready |  | 4640 | 67
|  |  | 8 | Machine Shop Started | Regular | 10 | 10 | BMRLEDPAT-REC-90-400-80-35-SO-FL-9'X25'-EX-W-UNV-DP-1-DS |  | Wrong part in BOM | TRUE |  | TRUE | FALSE | Ready |  | 4880 | 63
|  | 76762 Total | [14 empty] | 20460 | 352
|  | 78535 | 1 | Machine Shop Started | Regular | 3 | 3 | BMRLED-500-80-30-ASO-4'-W-277-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1004.4 | 9
|  |  | 2 | Machine Shop Started | Regular | 4 | 4 | BMRLED-500-80-30-ASO-2'-W-277-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1173.6 | 12
|  |  | 3 | Machine Shop Started | Regular | 12 | 12 | BMRLED-500-80-30-FL-2'-W-277-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 3801.6 | 38.4
|  |  | 4 | Machine Shop Started | Regular | 3 | 3 | SP19011-BMRLEDPAT-OPR-90(1)-500-80-30-ASO-FL-10'-NL-W-UNV-DP-1-DF | Material+Cartridge | Wrong info. In SD | TRUE |  | FALSE | FALSE | ToDo |  | 1080 | 15
|  | 78535 Total | [14 empty] | 7059.6 | 74.4
|  | 72221 | 1 | Machine Shop Finished | Regular | 13 | 13 | BDLED-1000-80-35-SO-4-W-UNV-DP-1-CTS(36) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3952 | 62.4
|  |  | 2 | Machine Shop Started | Regular | 14 | 14 | BDLED-1000-80-35-SO-6-W-UNV-DP-1-CTS(36) | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 6370 | 105
|  |  | 3 | Machine Shop Finished | Regular | 12 | 12 | BDLED-1000-80-35-SO-8-W-UNV-DP-1-CTS(36) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 7278 | 90
|  |  | 4 | Machine Shop Finished | Regular | 13 | 13 | BSLED-750-80-35-SO-8-W-UNV-DP-1-SC | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 7670 | 91
|  | 72221 Total | [14 empty] | 25270 | 348.4
|  | 78150 | 1 | Machine Shop Finished | Regular | 3 | 3 | STSLF-SO-400-80-35-8'-AP-UNV-MD-1-SC | +Cartridge | Others | TRUE |  | TRUE | TRUE |  | Done | 2148 | 24
|  |  | 2 | Machine Shop Finished | Regular | 1 | 1 | STSLF-SO-400-80-35-12'-AP-UNV-MD-1-SC | +Cartridge | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 1040 | 11
|  |  | 3 | Machine Shop Finished | Regular | 1 | 1 | STSLF-SO-400-B(3')-80-35-9'-AP-UNV-MD-1-SC-AC(4)-R-D35-AP | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1134 | 25.8
|  | 78150 Total | [14 empty] | 4322 | 60.8
|  | 72101 | 1 | Machine Shop Started | Regular | 228 | 228 | STFD-DSO(12'-400)-80-40-AH(6)-W-UNV-MD-1-CA(120)-RC | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 47500 | 1216
|  | 72101 Total | [14 empty] | 47500 | 1216
|  | 76592 | 1 | Machine Shop Started | Regular | 8 | 8 | BMRLEDPAT-REC-90-1000-90-35-SO-RG-40-NL-W-277-DP-1-DS-FW(6) |  | Wrong part in BOM | TRUE |  | FALSE | FALSE | Ready |  | 4210 | 50
|  |  | 2 | Machine Shop Started | Regular | 8 | 8 | BMRLEDPAT-ASO-87+93+93+87-1000-90-35-SO-RG-35'-NL-W-277-DP-1-DS-FW(6) |  | Wrong part in BOM | TRUE |  | FALSE | FALSE | Ready |  | 4027 | 40
|  |  | 19 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-OPRI(1)-750-90-35-RG2-5' 1"X5'5 1/2"-W-277-DP-1-DS-TS(1)-FW(6) |  | (blank) | FALSE |  | FALSE | FALSE | Ready |  | 1160 | 8.9
|  |  | 22 | Machine Shop Started | Regular | 5 | 5 | BBPRLED-OPRI(2)-750-90-35-RG2-5' 2"X11'11 1/2"X8' 4"-W-277-DP-1-DS-TS(1)-FW(6) |  | Wrong part in BOM | TRUE |  | FALSE | FALSE | Ready |  | 3480 | 31
|  | 76592 Total | [14 empty] | 12877 | 129.9
|  | 78328 | 1 | Machine Shop Started | Regular | 7 | 7 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 12012 | 114.1
|  |  | 2 | Machine Shop Started | Regular | 7 | 7 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-2-CA(48)-B2(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 14812 | 196
|  |  | 3 | Machine Shop Started | Regular | 10 | 10 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-2-CA(48)-B2(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 19160 | 210
|  |  | 4 | Machine Shop Started | Regular | 4 | 4 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 6864 | 64
|  |  | 5 | Machine Shop Started | Regular | 2 | 2 | BBLED2-SL-500-750-80-35-SO-8-W-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2288 | 23.6
|  |  | 6 | Machine Shop Started | Regular | 1 | 1 | BRLED-750-80-35-FL-12-W-UNV-DP-1-DS-B2(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1260 | 18.1
|  |  | 7 | Machine Shop Started | Regular | 4 | 4 | BRLED-750-80-35-FL-12-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 3600 | 41.2
|  |  | 8 | Machine Shop Started | Regular | 5 | 5 | BRLED-750-80-35-FL-6-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 2250 | 36.5
|  |  | 9 | Machine Shop Started | Regular | 2 | 2 | BRLED-750-80-35-FL-6-W-UNV-DP-1-DS-B1(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1260 | 22.4
|  |  | 10 | Machine Shop Started | Regular | 5 | 5 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 8580 | 81.5
|  |  | 11 | Machine Shop Started | Regular | 4 | 4 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-2-CA(48)-B2(BSL10LST) | Material+Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 8464 | 112
|  |  | 12 | Machine Shop Started | Regular | 4 | 4 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 6288 | 56
|  |  | 13 | Machine Shop Started | Regular | 14 | 14 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 22288 | 210
|  |  | 14 | Machine Shop Started | Regular | 6 | 6 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48)-B3(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 11172 | 126
|  |  | 15 | Machine Shop Started | Regular | 16 | 16 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48)-B2(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 28352 | 304
|  |  | 16 | Machine Shop Started | Regular | 2 | 2 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-3-CA(48) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 3230.71 | 32
|  |  | 17 | Machine Shop Started | Regular | 4 | 4 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-3-CA(48)-B2(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 7168 | 80
|  |  | 18 | Machine Shop Started | Regular | 6 | 6 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-2-CA(48)-B2(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 13206 | 126
|  | 78328 Total | [14 empty] | 172254.71 | 1853.4
|  | 77938 | 1 | Machine Shop Started | Regular | 4 | 4 | SP18489(1)-STFDI-SLI-500-DSO-400-16'-90-30-AL(4')-AP-120-DP-2-CA(36")-SC |  | Missing parts in BOM | TRUE |  | TRUE | TRUE |  | Done | 1692 | 40
|  | 77938 Total | [14 empty] | 1692 | 40
|  | 77908 | 1 | Given to Shipping | Regular | 2 | 1 | SCDI-300-500-80-35-SO-2M-12'0"-AP-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 780 | 20
|  |  | 2 | Given to Shipping | Regular | 4 | 0 | SCDI-300-500-80-35-SO-2M-20'0"-AP-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 3 | Given to Shipping | Regular | 2 | 0 | SCDI-300-500-80-35-SO-2M-24'0"-AP-UNV-DP-1-CA(36) |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 4 | Given to Shipping | Regular | 6 | 0 | SCDI-300-500-80-35-SO-2M-28'0"-AP-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 0 | 0
|  |  | 5 | Given to Shipping | Regular | 6 | 0 | SCDI-300-500-80-35-SO-2M-32'0"-AP-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 6 | Given to Shipping | Regular | 5 | 0 | SCR-500-80-35-0.5P-4'0"-W-UNV-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 7 | Given to Shipping | Regular | 4 | 0 | SCR-500-80-35-0.5P-4'0"-W-UNV-DP-1-TB9-B1(BSL10LST) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 9 | Given to Shipping | Regular | 12 | 4 | TWRWLED-SL 90/10-1250-80-35-SO-8'0"-W-UNV-DP-1-B1(BSL10LST) |  | PM wrong/missing info | TRUE |  | TRUE | TRUE |  | Done | 3760 | 56
|  |  | 10 | Given to Shipping | Regular | 3 | 0 | SCDI-300-500-80-35-SO-2M-32'0"-AP-UNV-DP-1-CA(36)-B3(BSL10LST) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 77908 Total | [14 empty] | 4540 | 76
|  | 78538 | 4 | Machine Shop Started | Regular | 24 | 24 | BBS-S-8'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  |  | 11280 | 96
|  |  | 5 | Machine Shop Started | Regular | 12 | 12 | BBS-S-6'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  |  | 4680 | 48
|  |  | 6 | Machine Shop Started | Regular | 20 | 20 | BBS-S-16'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  |  | 7900 | 40
|  | 78538 Total | [14 empty] | 23860 | 184
|  | 73829 | 1 | Wiring Started | Regular | 24 | -5 | CUBLED-SL 75/25-1000-90-35-PL-36-W-UNV-DP-1-CT9(120) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -5574.2633 | -85.5
|  |  | 2 | Wiring Started | Regular | 27 | 22 | CUBLED-SL 75/25-1000-90-35-PL-28-W-UNV-DP-1-CT9(120) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 18968.5027 | 304.3333
|  |  | 3 | Wiring Started | Regular | 2 | 2 | CUBLED-SL 75/25-1000-90-35-PL-24-W-UNV-DP-1-CT9(120) |  | Others | FALSE | Others | TRUE | TRUE |  | Done | 3694.54 | 34.5
|  |  | 4 | Wiring Started | Regular | 4 | 4 | SCR-500-90-35-FL-16-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2697.756 | 23
|  |  | 5 | Wiring Started | Regular | 3 | 3 | B6RLED-500-90-35-FL-36-W-UNV-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2340 | 27.7
|  |  | 6 | Wiring Started | Regular | 1 | 1 | BBRLED-1000-90-35-FL-8-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 941.283 | 4.7
|  |  | 7 | Wiring Started | Regular | 1 | 1 | BMRLED-1000-90-35-FL-12-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1411.926 | 8.7
|  |  | 8 | Wiring Started | Regular | 1 | 1 | TBDILED-650-400-90-35-SO-10-W-UNV-DP-1-CT9(36) |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 1991.17 | 12.8
|  | 73829 Total | [14 empty] | 26470.9143 | 330.2333
|  | 75462 | 4 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1440 | 20
|  |  | 5 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-11'8"-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 764 | 10
|  |  | 6 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1152 | 14
|  |  | 7 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 432 | 7
|  |  | 8 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-DS | Material+Cartridge | Wrong info. In SD | TRUE |  | FALSE | FALSE |  |  | 720 | 10
|  |  | 9 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-18'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1296 | 16
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-14'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1008 | 14
|  |  | 11 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-4'-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 288 | 4
|  |  | 15 | Machine Shop Started | Regular | 3 | 3 | SP18276-SCR-350-80-35-FL-46'5"-W-UNV-DP-1-DS-C(ANGLED ENDS) | Material+Cartridge | Others | FALSE | Others | FALSE | FALSE |  |  | 2515 | 44
|  | 75462 Total | [14 empty] | 9615 | 139
|  | 75745 | 5 | Machine Shop Started | Regular | 4 | 4 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 2304 | 28
|  |  | 6 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-16'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1152 | 13
|  |  | 7 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8'-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | Wrong part in BOM | TRUE |  | TRUE | TRUE |  |  | 576 | 7
|  |  | 8 | Machine Shop Started | Regular | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 720 | 9
|  |  | 9 | Machine Shop Started | Regular | 2 | 2 | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS-C(1 LONG SIDE D) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1440 | 16
|  |  | 21 | Machine Shop Started | Regular | 3 | 3 | SP18276-SCR-350-80-35-FL-46'5"-W-UNV-DP-1-DS-C(133° & 85° ANGLED ENDS) | Material+Cartridge | Others | FALSE | Others | TRUE | TRUE |  |  | 2515 | 43.22
|  | 75745 Total | [14 empty] | 8707 | 116.22
|  | 78664 | 1 | Machine Shop Started | Regular | 8 | 8 | STD-SO-400-80-30-12'-W-UNV-MD-1-CT9(36)-RC | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 3849.4 | 36
|  |  | 2 | Machine Shop Started | Regular | 9 | 9 | STD-SO-400-80-30-15'-W-UNV-MD-1-CT9(36)-RC | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 3585.3 | 40.5
|  |  | 3 | Machine Shop Started | Regular | 16 | 16 | STD-SO-400-80-30-25'-W-UNV-MD-1-CT9(36)-RC | Material+Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 8105.4 | 90
|  | 78664 Total | [14 empty] | 15540.1 | 166.5
|  | 75811 | 1 | Wiring Started | Regular | 12 | 12 | STD-SO-300-80-35-20-AP-UNV-MD-1-CA(36)-RC |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 6400 | 63.2
|  |  | 2 | Wiring Started | Regular | 9 | 9 | STD-SO-300-80-35-20-AP-UNV-MD-1+E(1)-CA(36)-RC |  | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 4950 | 51
|  |  | 3 | Wiring Started | Regular | 3 | 3 | STD-SO-300-80-35-20-AP-UNV-MD-1+E(2)-CA(36)-RC |  | Others | FALSE | Others | TRUE | TRUE |  | Done | 1650 | 18.3
|  | 75811 Total | [14 empty] | 13000 | 132.5
|  | 77142 | 1 | Machine Shop Started | Regular | 1 | 1 | ZELED-SL 50/50-1050-80-35-MSO-8-W-UNV-MD-2-CT15(48) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 776 | 13.5
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | STSLF-SO-300-80-30-6-BLK-120-MD-1-SG15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1740 | 21.9
|  | 77142 Total | [14 empty] | 2516 | 35.4
|  | 78607 | 1 | Machine Shop Started | Regular | 22 | 22 | STFC-NO-DSO(4'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 4510 | 121
|  |  | 2 | Machine Shop Started | Regular | 18 | 18 | STFC-NO-DSO(10'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 7110 | 135
|  |  | 3 | Machine Shop Started | Regular | 6 | 6 | STFC-NO-DSO(6'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1620 | 33
|  |  | 4 | Machine Shop Started | Regular | 6 | 6 | STFC-NO-DSO(8'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1950 | 36
|  | 78607 Total | [14 empty] | 15190 | 325
|  | 78225 | 1 | Machine Shop Finished | Regular | 6 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-22-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3740 | 55
|  |  | 2 | Machine Shop Finished | Regular | 30 | 30 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 20400 | 300
|  |  | 3 | Machine Shop Finished | Regular | 10 | 10 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 5950 | 100
|  |  | 4 | Machine Shop Finished | Regular | 6 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4080 | 60.6
|  |  | 5 | Machine Shop Finished | Regular | 1 | 1 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-6-W-UNV-DP-1-CT9(36") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 510 | 10.1
|  |  | 6 | Machine Shop Finished | Regular | 24 | 24 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4320 | 69.6
|  |  | 7 | Machine Shop Finished | Regular | 4 | 4 | WWR-SL-750-80-30-13-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1950 | 33
|  |  | 8 | Machine Shop Finished | Regular | 2 | 2 | WWR-SL-750-80-30-14-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1050 | 16.5
|  |  | 9 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-18' 9"-W-UNV-DP-1+E(3)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1218 | 13.3
|  |  | 10 | Machine Shop Started | Regular | 13 | 13 | BBPRLED-300-80-30-FL-97' 3"-W-UNV-DP-2+E(7)-TG9 | +Cartridge | Wrong info. In SD | TRUE |  | TRUE | FALSE |  | Done | 6054 | 64.8
|  |  | 11 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-18' 10"-W-UNV-DP-1+E(1)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1218 | 12.5
|  |  | 12 | Machine Shop Started | Regular | 3 | 3 | BBPRLED-300-80-30-FL-18' 6"-W-UNV-DP-1+E(2)-DF | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1156 | 12.9
|  |  | 13 | Machine Shop Started | Regular | 5 | 5 | BBPRLED-300-80-30-FL-38' 1"-W-UNV-DP-1+E(2)-DF | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2396 | 25.7
|  |  | 14 | Machine Shop Started | Regular | 7 | 7 | BBPRLED-300-80-30-FL-55' 9"-W-UNV-DP-2+E(4)-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3512 | 36
|  | 78225 Total | [14 empty] | 57554 | 810
|  | 78165 | 1 | Machine Shop Started | Regular | 9 | 9 | BRLEDPAT-OPI-90(4)-400-80-35-SO-FL-34-NL-W-UNV-DP-1-DB | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 7778 | 43
|  |  | 2 | Machine Shop Started | Regular | 9 | 9 | BRLEDPAT-OPI-90(4)-400-80-35-SO-FL-32-NL-W-UNV-DP-1-DB | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 7445 | 43
|  |  | 7 | Machine Shop Started | Regular | 2 | 2 | B6RLED-750-80-35-2M-8-W-UNV-DP-1-TB9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1476 | 11.8
|  | 78165 Total | [14 empty] | 16699 | 97.8
|  | 77440 | 1 | Given to Shipping | Regular | 12 | 0 | STFC-I(6-175)-DSO(12-400)-80-35-AH(6)-W-UNV-MD-1-CA(36)-RC |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 77440 Total | [14 empty] | 0 | 0
|  | 78423 | 8 | Machine Shop Finished | Regular | 3 | 3 | SP19018(1)-SCR-1000-80-35-FL-5' 4"-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1712.963 | 16.5
|  |  | 9 | Machine Shop Finished | Regular | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-5' 4"-W-UNV-DP-1-TG9-B1(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1570.2161 | 18.6
|  |  | 10 | Machine Shop Finished | Regular | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-6' 3"-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1296.6178 | 11
|  |  | 11 | Machine Shop Finished | Regular | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-6' 3"-W-UNV-DP-1-TG9-B1(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1724.8586 | 18.6
|  |  | 12 | Machine Shop Finished | Regular | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-5' 6"-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 1141.9753 | 11
|  |  | 13 | Machine Shop Finished | Regular | 1 | 1 | SP19018(1)-SCD-1000-80-35-FL-6' 3"-W-UNV-DP-1-SA(18) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 606.6744 | 5.5
|  |  | 14 | Machine Shop Finished | Regular | 1 | 1 | SP19018(1)-SCD-1000-80-35-FL-6' 3"-W-UNV-DP-1-SA(18)-B1(BSL10LST) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 820.7948 | 9.3
|  | 78423 Total | [14 empty] | 8874.1 | 90.5
|  | 76823 | 7 | Wiring Started | Regular | 24 | 0 | STFD-DSO(16-400)-80-35-AL(3)-AP-120-MD-1-CA(72)-RC |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 0 | 0
|  |  | 8 | Wiring Started | Regular | 15 | 0 | STFD-DSO(20-400)-80-35-AL(4)-AP-120-MD-1-CA(72)-RC |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 0 | 0
|  |  | 9 | Wiring Started | Regular | 2 | 0 | STD-SO-400-80-35-16-AP-120-MD-1-CA(72)-RC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 10 | Wiring Started | Regular | 3 | 0 | STD-SO-400-80-35-20-AP-120-MD-1-CA(72)-RC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 11 | Wiring Started | Regular | 81 | -9 | STFD-DSO(36-400)-80-35-AH(4)+AY(2)-AP-120-MD-1-CA(72)-RC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -3050 | -49
|  |  | 12 | Wiring Started | Regular | 24 | 9 | STFD-DSO(12-400)-80-35-AH(6)-AP-120-MD-1-CA(72)-RC |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1845 | 49.5
|  |  | 13 | Machine Shop Finished | Regular | 10 | 10 | ZESQDI-SL-50/50-800-80-35-SO-12-AP-UNV-MD-1-CA(72) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 11040 | 120
|  | 76823 Total | [14 empty] | 9835 | 120.5
|  | 77180 | 1 | Machine Shop Started | Regular | 6 | 6 | SCR-300-80-35-FL-4'-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 1440 | 18.36
|  |  | 2 | Machine Shop Started | Regular | 6 | 6 | SCR-300-80-35-FL-8'-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 2880 | 32.7
|  |  | 3 | Machine Shop Started | Regular | 2 | 2 | SCR-300-80-35-FL-8'-W-UNV-DP-1-DF-B1(BSL310LP) | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 960 | 18.52
|  |  | 4 | Machine Shop Started | Regular | 8 | 8 | SCR-300-80-35-FL-16'-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 3840 | 46.2
|  |  | 5 | Machine Shop Started | Regular | 12 | 12 | SCR-300-80-35-FL-28'-W-UNV-DP-1-DF-B2(BSL310LP) | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 6720 | 110.04
|  |  | 6 | Machine Shop Started | Regular | 4 | 4 | SCR-300-80-35-FL-4'-C(BLK)-UNV-DP-1-DF | Material | Shortage | FALSE | Shortage | TRUE | TRUE |  |  | 960 | 12.24
|  |  | 7 | Machine Shop Started | Regular | 5 | 5 | SCR-300-80-35-FL-8'-C(BLK)-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 2400 | 27.25
|  |  | 8 | Machine Shop Started | Regular | 5 | 5 | SCR-300-80-35-FL-8'-C(BLK)-UNV-DP-1-DF-B1(BSL310LP) | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 2400 | 46.3
|  |  | 9 | Machine Shop Started | Regular | 9 | 9 | SCR-300-80-40-FL-4'-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 2160 | 27.54
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | SCR-300-80-40-FL-4'-W-UNV-DP-1-DF-B1(BSL310LP) | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 480 | 13.76
|  |  | 11 | Machine Shop Started | Regular | 3 | 3 | SCR-300-80-40-FL-8'-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 1440 | 16.35
|  |  | 12 | Machine Shop Started | Regular | 3 | 3 | SCR-300-80-40-FL-8'-W-UNV-DP-1-DF-B1(BSL310LP) | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 1440 | 27.78
|  | 77180 Total | [14 empty] | 27120 | 397.04
|  | 78506 | 1 | Machine Shop Started | Regular | 6 | 6 | STLDI-I-500-DSO-400-8'-80-35-W-UNV-DP-1-CTS(60)-RC |  | (blank) | FALSE |  | FALSE | FALSE |  |  | 5400 | 48
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | STLDI-I-500-DSO-400-4'-80-35-W-UNV-DP-1-CTS(36)-RC |  | Missing parts in BOM | TRUE |  | FALSE | FALSE |  |  | 1440 | 15
|  |  | 3 | Machine Shop Started | Regular | 8 | 8 | STFC-NO-DSO(8-400)-80-35-AL(4)-W-UNV-MD-1-CA(76)-RC-C(SWIVEL GRIP LOCK) | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2480 | 38
|  |  | 4 | Machine Shop Started | Regular | 4 | 4 | STFC-NO-DSO(16-400)-80-35-AL(4)-W-UNV-MD-1-CA(70)-RC-C(SWIVEL GRIP LOCK) | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 760 | 19
|  | 78506 Total | [14 empty] | 10080 | 120
|  | 77939 | 3 | Machine Shop Finished | Regular | 6 | 6 | STSFR-SO(32-200)-80-35-AL(4)+AI(2)-W-UNV-MD-1-SB15 | +Cartridge | Others | FALSE | Others | TRUE | FALSE |  | Done | 3680 | 31.3
|  |  | 4 | Machine Shop Finished | Regular | 6 | 6 | STSFR-SO(36-200)-80-35-AL(4)+AI(2)-W-UNV-MD-1-SB15 | +Cartridge | Shortage | TRUE |  | TRUE | FALSE |  | Done | 4140 | 35.4
|  | 77939 Total | [14 empty] | 7820 | 66.7
|  | 76468 | 1 | Order UnShipped | Regular | 29 | 1 | PWWLED-800-80-35-S-2-W-UNV-DP-1-F | Material | Shortage | TRUE |  | #N/A | #N/A | #N/A | #N/A | 216 | 4.1
|  |  | 2 | Order UnShipped | Regular | 2 | 0 | PWWLED-800-80-35-S-4-W-UNV-DP-1-F | Material | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 3 | Order UnShipped | Regular | 65 | -13 | B6RLED-500-80-35-FL-4-W-UNV-DP-1-TB15-C(F) | Material | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | -3458 | -45.5
|  |  | 4 | Order UnShipped | Regular | 1 | 0 | PWWLED-800-80-35-S-2-W-UNV-DP-1-F | Material | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 5 | Order UnShipped | Regular | 1 | 0 | PWWLED-800-80-35-S-4-W-UNV-DP-1-F | Material | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 6 | Order UnShipped | Regular | 1 | 0 | B6RLED-500-80-35-FL-4-W-UNV-DP-1-TB15-C(F) | Material | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  | 76468 Total | [14 empty] | -3242 | -41.4
| Total | [15 empty] | 702618.3043 | 9668.4233
7 Total | [16 empty] | 702618.3043 | 9668.4233
10 |  | 75966 | 8 | Machine Shop Started | Regular | 520 | 462 | SKVLED-14-2400-80-40-2XVL-RE-W-277-DP-1-TB15-C(NLIGHT POWER PACK - NPP16-D) | Material | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 115500 | 1617
|  | 75966 Total | [14 empty] | 115500 | 1617
|  | 77926 | 1 | Scheduled/Released | Regular | 72 | 72 | SKFLED-22-2400-80-35-4SF-W-UNV-DP-1-TG9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 18000 | 161.28
|  | 77926 Total | [14 empty] | 18000 | 161.28
|  | 78927 | 1 | Wiring Started | Regular | 37 | 37 | DIALED-22-2500-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-C(ELDOLED DUALDRIVER) | Material | Others | TRUE |  | FALSE | TRUE |  | Done | 13660.4 | 103.6
|  |  | 2 | Machine Shop Started | Regular | 17 | 17 | DIALED-22-2500-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-B1(BSL310LP)-C(ELDOLED DUALDRIVER) | Material | (blank) | FALSE |  | FALSE | TRUE |  | Done | 9937.52 | 107.1
|  |  | 3 | Machine Shop Started | Regular | 22 | 8 | DIALED-24-3100-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-C(ELDOLED DUALDRIVER) | Material | (blank) | FALSE |  | FALSE | TRUE |  | Done | 3968.8 | 26.4
|  | 78927 Total | [14 empty] | 27566.72 | 237.1
|  | 78559 | 1 | Machine Shop Started | Regular | 39 | 39 | DIALED-22-2500-80-35-VL-W-277-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 9555 | 113.1
|  |  | 2 | Machine Shop Started | Regular | 80 | 80 | DIALED-22-4400-80-35-VL-W-277-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 19600 | 232
|  |  | 3 | Machine Shop Started | Regular | 11 | 11 | DIALED-24-7000-80-35-VL-W-UNV-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 3850 | 38.5
|  |  | 4 | Machine Shop Finished | Regular | 5 | 5 | MBSLED-600-80-35-S-4'-W-UNV-DP-1-S | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1500 | 19.5
|  |  | 5 | Machine Shop Started | Regular | 22 | 22 | AULED-22-2500-80-35-SO-W-277-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 4510 | 55
|  |  | 6 | Machine Shop Started | Regular | 33 | 33 | DIALED-22-2500-80-35-VL-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 15510 | 211.2
|  |  | 7 | Machine Shop Started | Regular | 10 | 10 | DIALED-22-4400-80-35-VL-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 4700 | 64
|  |  | 8 | Machine Shop Finished | Regular | 1 | 1 | MBSLED-600-80-35-S-4'-W-UNV-DP-1-S-B1(BSL310LP) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 525 | 7.8
|  |  | 9 | Machine Shop Started | Regular | 1 | 1 | AULED-22-2500-80-35-SO-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 430 | 6
|  |  | 10 | Machine Shop Finished | Regular | 2 | 2 | MBLED-500-80-35-S-4'-W-UNV-DP-1-CA(36) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 600 | 8.3
|  | 78559 Total | [14 empty] | 60780 | 755.4
|  | 79342 | 1 | Scheduled/Released | Regular | 1 | 1 | AULED-24-3100-80-30-SO-W-277-DP-1-TB15-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 265 | 3
|  | 79342 Total | [14 empty] | 265 | 3
|  | 79240 | 1 | Machine Shop Started | Regular | 6 | 6 | DIALED-22-3000-90-35-VL-W-120-DP-1-ST | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 1650 | 16.8
|  |  | 2 | Machine Shop Started | Regular | 1 | 1 | DIALED-22-3000-90-35-VL-W-120-DP-1-ST-B1(BSL310LP) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 520 | 6.3
|  | 79240 Total | [14 empty] | 2170 | 23.1
|  | 78933 | 1 | Machine Shop Started | Regular | 20 | 20 | DIALED-22-4000-80-35-VL-W-UNV-DP-1-TG9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 4500 | 56
|  | 78933 Total | [14 empty] | 4500 | 56
|  | 78812 | 1 | Packaging Finished | Regular | 1 | 0 | DIALED-24-3100-90-30-VL-W-120-DP-1-ST-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  | Done | 0 | 0
|  |  | 2 | Packaging Finished | Regular | 3 | 0 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  | Done | 0 | 0
|  |  | 3 | Packaging Finished | Regular | 1 | 0 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST-FW(6) | Material | (blank) | FALSE |  | FALSE | FALSE |  | Done | 0 | 0
|  | 78812 Total | [14 empty] | 0 | 0
|  | 79170 | 1 | Order UnShipped | Replacement | 0 | 0 | RECESSED DRYWALL MOUNTING KITS- POWERED 3 WIRES - DAY-DIA-DUO-PLANO-WAVE - 1X1 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | #DIV/0! | #DIV/0!
|  | 79170 Total | [14 empty] | #DIV/0! | #DIV/0!
|  | 79370 | 1 | Machine Shop Started | Regular | 29 | 29 | DIALED-22-2500-80-30-VL-W-UNV-DP-1-TB15 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 5639.05 | 81.2
|  | 79370 Total | [14 empty] | 5639.05 | 81.2
|  | 77908 | 8 | Packaging Finished | Regular | 12 | 4 | SKSLED-22-3200-80-35-GL-FL-UNV-DP-1-TB15 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1140 | 12
|  | 77908 Total | [14 empty] | 1140 | 12
|  | 79043 | 1 | Packaging Finished | Regular | 10 | 0 | DIALED-22-3600-80-35-VL-W-277-LT(LDE1)-1-TG9-AR | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 79043 Total | [14 empty] | 0 | 0
|  | 78820 | 1 | Machine Shop Started | Regular | 7 | 7 | DIALED-22-2500-90-35-VL-W-277-LT(LDE5)-1-TB15-FW(6') | Material | Shortage | FALSE | Shortage | FALSE | TRUE |  | Done | 1988 | 20.3
|  | 78820 Total | [14 empty] | 1988 | 20.3
|  | 79085 | 1 | Given to Shipping | Replacement | 88 | -12 | BBRLED-1000-90-40-FL-2-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -2400 | -30
|  | 79085 Total | [14 empty] | -2400 | -30
|  | 79220 | 1 | Machine Shop Started | Regular | 21 | 21 | POLED-22-3000-80-35-VL-W-120-DP-1-ST | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 6177.9984 | 54.6
|  | 79220 Total | [14 empty] | 6177.9984 | 54.6
|  | 78806 | 1 | Machine Shop Finished | Regular | 2 | 2 | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 640 | 10
|  |  | 2 | Machine Shop Finished | Regular | 5 | 5 | SCR-500-80-35-FL-8'-W-UNV-DP-1-MFTB9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2600 | 27.5
|  |  | 3 | Machine Shop Finished | Regular | 4 | 4 | SCD-500-80-35-FL-6'-BLK-UNV-DP-1-CA(36") |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1840 | 28
|  | 78806 Total | [14 empty] | 5080 | 65.5
|  | 79110 | 1 | Machine Shop Started | Regular | 3 | 3 | POLED-22-4400-90-35-VL-W-UNV-DP-1-ST | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 540 | 5.2
|  | 79110 Total | [14 empty] | 540 | 5.2
|  | 78165 | 3 | Machine Shop Started | Regular | 11 | 11 | SKFLED-22-3200-80-35-FL-W-120-DP-1-TB9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 4345 | 25.3
|  |  | 4 | Machine Shop Started | Regular | 5 | 5 | SKFLED-22-3200-80-35-1SF-W-120-DP-1-TB9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 1975 | 11.5
|  |  | 5 | Machine Shop Started | Regular | 7 | 7 | SKFLED-22-3200-80-35-2SF-W-120-DP-1-TB9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 2765 | 16.1
|  |  | 6 | Machine Shop Started | Regular | 7 | 7 | SKFLED-22-3200-80-35-3SF-W-120-DP-1-TB9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 2765 | 16.1
|  | 78165 Total | [14 empty] | 11850 | 69
|  | 79005 | 1 | Packaging Finished | Regular | 3 | 0 | AULED-24-3100-80-30-SO-W-UNV-DP-1-TB9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 0 | 0
|  | 79005 Total | [14 empty] | 0 | 0
|  | 74695 | 1 | Machine Shop Started | Regular | 28 | 28 | DIALED-22-2500-80-35-VL-W-UNV-DP-1-TB9 | Material | (blank) | FALSE |  | FALSE | TRUE |  | Done | 4060 | 78.4
|  |  | 2 | Machine Shop Started | Regular | 14 | 14 | DIALED-11-1600-80-35-VL-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | FALSE | TRUE |  | Done | 2030 | 30.8
|  |  | 3 | Machine Shop Started | Regular | 8 | 8 | DIALED-11-1600-80-35-VL-W-UNV-DP-E(1)-DF-B1 | Material | (blank) | FALSE |  | FALSE | TRUE |  | Done | 2912 | 48
|  |  | 4 | Machine Shop Started | Regular | 3 | 3 | DIALED-14-4000-80-30-VL-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | FALSE | TRUE |  | Done | 537 | 9.3
|  |  | 5 | Machine Shop Finished | Regular | 3 | 3 | BMDLED-750-80-35-SO-4'-BLK-UNV-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 615 | 14.4
|  | 74695 Total | [14 empty] | 10154 | 180.9
|  | 79411 | 1 | Machine Shop Started | Regular | 37 | 37 | DAYFLED-22-3000-80-35-SO-W-UNV-DP-1-TB15 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 6105 | 85.1
|  | 79411 Total | [14 empty] | 6105 | 85.1
|  | 78861 | 1 | Wiring Started | Regular | 8 | 0 | DIALED-22-4000-90-30-VL-W-120-DP-1-TB9 | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 0 | 0
|  |  | 2 | Wiring Started | Regular | 5 | 3 | DIALED-22-3000-90-30-VL-W-120-BI-1-TB9 | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 504 | 8.4
|  | 78861 Total | [14 empty] | 504 | 8.4
|  | 79431 | 1 | Scheduled/Released | Quick Ship+ | 75 | 75 | AULED-22-4400-80-35-SO-W-277-DP-1-TG9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 14794.5 | 180
|  | 79431 Total | [14 empty] | 14794.5 | 180
|  | 78796 | 1 | Machine Shop Started | Regular | 6 | 6 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 1770 | 18
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9-B1(BSL310LP) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 1620 | 9
|  |  | 3 | Machine Shop Started | Regular | 5 | 5 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-SM | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 1850 | 15
|  | 78796 Total | [14 empty] | 5240 | 42
|  | 78731 | 1 | Packaging Finished | Regular | 12 | 0 | DIALED-14-2400-80-35-VL-W-277-DP-1-TG9 | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 0 | 0
|  | 78731 Total | [14 empty] | 0 | 0
|  | 77765 | 4 | Machine Shop Started | Regular | 1 | 1 | AULED-22-3000-80-30-SO-W-UNV-DP-1-TB9-B1(BSL310LP) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 381.65 | 6
|  | 77765 Total | [14 empty] | 381.65 | 6
|  | 78624 | 4 | Scheduled/Released | Regular | 25 | 25 | SKFLED-22-2000-80-30-2SF-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 8625 | 669
|  | 78624 Total | [14 empty] | 8625 | 669
| Total | [15 empty] | #DIV/0! | #DIV/0!
10 Total | [16 empty] | #DIV/0! | #DIV/0!
12 |  | 75859 | 91 | Scheduled/Released | Regular | 2 | 2 | BMRLED-600-80-35-ASO-4-W-UNV-DP-1-DS-FW(6) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 322 | 8
|  | 75859 Total | [14 empty] | 322 | 8
|  | 79198 | 1 | Given to Shipping | Regular | 12 | 0 | SCR-500-80-30-FL-14'-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 79198 Total | [14 empty] | 0 | 0
|  | 78306 | 1 | Machine Shop Started | NPI | 1 | 1 | SCILAC-AC(2)-D24-D-500-80-30-BW-6'0"-C(BRIGHT COPPER)-120-DP-2-CA(36) | Material | Shortage | FALSE | Shortage | FALSE | FALSE |  | Done | 500 | 8
|  | 78306 Total | [14 empty] | 500 | 8
|  | 78982 | 1 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  | Done | 1020 | 9.4
|  | 78982 Total | [14 empty] | 1020 | 9.4
|  | 78986 | 1 | Machine Shop Finished | Regular | 4 | 4 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG15 |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 2040 | 18.4
|  | 78986 Total | [14 empty] | 2040 | 18.4
|  | 79106 | 1 | Packaging Finished | Regular | 3 | 0 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG9 | Material | Others | FALSE | Others | TRUE | TRUE |  |  | 0 | 0
|  |  | 2 | Packaging Finished | Regular | 3 | 0 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-D | Material | Others | FALSE | Others | TRUE | TRUE |  |  | 0 | 0
|  | 79106 Total | [14 empty] | 0 | 0
|  | 78822 | 1 | Machine Shop Finished | Regular | 2 | 2 | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST-B1(BSL310LP) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 960 | 15
|  |  | 2 | Machine Shop Finished | Regular | 1 | 1 | BMRLED-750-80-30-ASO-6'-W-UNV-DP-1-ST |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 480 | 5.9
|  |  | 3 | Machine Shop Finished | Regular | 3 | 3 | CCL-SL-500-80-30-CL(10')-W-UNV-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2400 | 28.5
|  |  | 4 | Machine Shop Finished | Regular | 1 | 1 | CCL-SL-500-80-30-CL(7')-W-UNV-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 560 | 7
|  | 78822 Total | [14 empty] | 4400 | 56.4
|  | 78651 | 1 | Machine Shop Finished | Regular | 1 | 1 | SLWLED-SL 75/25-1000-80-35-RE-6-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 670.6 | 6.8
|  |  | 2 | Machine Shop Finished | Regular | 8 | 8 | SLWLED-SL 75/25-1000-80-35-RE-8-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 7153.2 | 54.4
|  |  | 3 | Machine Shop Finished | Regular | 1 | 1 | SLWLED-SL 75/25-1000-80-35-RE-12-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1341.2 | 9
|  | 78651 Total | [14 empty] | 9165 | 70.2
|  | 78590 | 1 | Machine Shop Started | Regular | 9 | 9 | STSLF-SO-400-80-35-12'-BLK-UNV-MD-1-SG9 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 7884 | 63
|  | 78590 Total | [14 empty] | 7884 | 63
|  | 76704 | 1 | Machine Shop Started | Regular | 2 | 2 | BRLED-400-80-35-FL-12' 6"-W-277-DP-1-DS | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 780 | 16
|  | 76704 Total | [14 empty] | 780 | 16
|  | 67875 | 1 | Machine Shop Started | Regular | 14 | 14 | CCL-SL-300-80-30-CP(83' 6")-W-UNV-DP-1-AC | Material | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 5850 | 82
|  | 67875 Total | [14 empty] | 5850 | 82
|  | 79098 | 1 | Machine Shop Started | Regular | 2 | 2 | WBRLED-500-90-30-S-4'-AP-UNV-DP-1-D | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 934 | 7
|  | 79098 Total | [14 empty] | 934 | 7
|  | 79285 | 1 | Machine Shop Started | Regular | 1 | 1 | BRLED-500-80-30-FL-11-W-120-DP-1-DF | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 880 | 9
|  | 79285 Total | [14 empty] | 880 | 9
|  | 78710 | 1 | Machine Shop Started | Regular | 2 | 2 | SCDI-300-300-80-40-SO-0.5M-2X6-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 3080 | 68
|  |  | 2 | Machine Shop Finished | Regular | 3 | 3 | SCDI-300-300-80-40-SO-0.5M-6'-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1854 | 30.6
|  |  | 3 | Machine Shop Started | Regular | 1 | 1 | SCDI-300-300-80-40-SO-0.5M-4X4-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE | Ready |  | 1600 | 30.2
|  | 78710 Total | [14 empty] | 6534 | 128.8
|  | 75738 | 1 | Given to Shipping | Regular | 9 | 0 | BMRLED-500-80-35-ASO-4-W-120-DP-1-D |  | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 2 | Given to Shipping | Regular | 9 | 0 | BMRLED-500-80-35-ASO-2-W-120-DP-1-D |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 75738 Total | [14 empty] | 0 | 0
|  | 78812 | 4 | Wiring Started | Regular | 2 | -3 | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -1500 | -16.2
|  |  | 5 | Wiring Started | Regular | 9 | 9 | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36) |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 4500 | 48.6
|  |  | 6 | Wiring Started | Regular | 5 | 5 | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36)-B1(BSL310LP) |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 3500 | 46.5
|  |  | 7 | Wiring Started | Regular | 10 | 10 | LTLED-SL 80/20-800-90-30-SO-8'-W-120-DP-1-CA(36)-DS(1) |  | Others | TRUE |  | TRUE | TRUE |  | Done | 10000 | 136
|  | 78812 Total | [14 empty] | 16500 | 214.9
|  | 78936 | 1 | Wiring Started | Regular | 3 | 3 | BBRLED-600-80-35-FL-8'-W-UNV-DP-1-TG9-FW(6) |  | Mechanical issue | TRUE |  | TRUE | FALSE |  | Done | 2040 | 14.4
|  | 78936 Total | [14 empty] | 2040 | 14.4
|  | 78789 | 1 | Machine Shop Finished | Regular | 1 | 1 | WWR-SL-400-80-35-10'-W-UNV-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 830 | 9
|  | 78789 Total | [14 empty] | 830 | 9
|  | 79135 | 1 | Machine Shop Started | Regular | 2 | 2 | WBRVLED-500-80-35-SO-5'-AP-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1488 | 15.2
|  | 79135 Total | [14 empty] | 1488 | 15.2
|  | 79024 | 1 | Order UnShipped | Regular | 1 | 0 | B6RLED-1000-90-40-FL-5-W-UNV-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 79024 Total | [14 empty] | 0 | 0
|  | 79164 | 1 | Machine Shop Started | Regular | 1 | 1 | BRLED-750-80-40-FL-8'-W-UNV-DP-1+NL(1)-TB15 | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 612 | 6.5
|  | 79164 Total | [14 empty] | 612 | 6.5
|  | 78637 | 1 | Packaging Finished | Regular | 1 | 0 | CUBLED-SL 75/25-1000-80-35-SO-8'-AP-UNV-DP-1-CA(36) |  | Others | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 2 | Packaging Finished | Regular | 3 | 1 | CUBWLED-SL 75/25-1000-80-35-SO-4'-AP-UNV-DP-1 |  | Others | FALSE | Others | TRUE | FALSE |  | Done | 342 | 5.2
|  | 78637 Total | [14 empty] | 342 | 5.2
|  | 76076 | 1 | Machine Shop Finished | Regular | 4 | 4 | BRVLED-500-90-27-SO-6'-W-277-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3700 | 25.2
|  |  | 2 | Machine Shop Finished | Regular | 1 | 1 | BRVLED-500-90-27-SO-4'-W-277-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 688 | 3.3
|  |  | 3 | Machine Shop Finished | Regular | 2 | 2 | BRVLED-500-90-27-SO-5'-W-277-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1540 | 12.6
|  |  | 4 | Machine Shop Finished | Regular | 3 | 3 | BRVLED-500-90-27-SO-8'-W-277-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3660 | 18.9
|  | 76076 Total | [14 empty] | 9588 | 60
|  | 79502 | 1 | Machine Shop Started | Replacement | 1 | 1 | BMRLED-575-80-30-FL-2-W-UNV-DP-1-ST-C(FILLER) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 160 | 3.2
|  |  | 2 | Machine Shop Started | Replacement | 1 | 1 | BMRLED-575-80-30-FL-2-W-UNV-DP-1-ST-C(FILLER) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 160 | 3.2
|  | 79502 Total | [14 empty] | 320 | 6.4
|  | 78545 | 1 | Machine Shop Started | Regular | 6 | 6 | SCDLAC-AC(2)-D36-HX-D-500-80-30-FL-4'-BLK-UNV-DP-1-CT9(60") | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2640 | 28.638
|  | 78545 Total | [14 empty] | 2640 | 28.638
|  | 76983 | 1 | Machine Shop Finished | Regular | 2 | 2 | WWS-SL-1000-90-35-16'-AP-UNV-DP-1-SC | Material+Cartridge | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 1658 | 11.2
|  | 76983 Total | [14 empty] | 1658 | 11.2
|  | 78706 | 1 | Machine Shop Finished | Regular | 7 | 7 | SCS-300-80-35-FL-8'-BLK-UNV-DP-1-SB9 |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 7000 | 43.4
|  |  | 2 | Machine Shop Finished | Regular | 10 | 10 | SCDI-300-300-80-35-SO-FL-8-BLK-UNV-DP-1-SA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 10000 | 102
|  | 78706 Total | [14 empty] | 17000 | 145.4
|  | 78949 | 1 | Machine Shop Started | Regular | 1 | 1 | BBDLED-400-80-30-SO-12'-W-UNV-DP-1-CTS(36) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 900 | 11.4
|  | 78949 Total | [14 empty] | 900 | 11.4
|  | 79189 | 1 | Machine Shop Started | Replacement | 1 | 1 | BBRLED-400-80-30-RG-4'7"-W-120-DP-1-D-B1(BSL310LP) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 555 | 8.6
|  | 79189 Total | [14 empty] | 555 | 8.6
|  | 79201 | 1 | Scheduled/Released | Regular | 4 | 4 | CU-S-24-T8-3-W-0-0-UNV-E-1-CT9(36) | Material | (blank) | FALSE |  | FALSE | FALSE |  |  | 2352.94 | 61
|  | 79201 Total | [14 empty] | 2352.94 | 61
|  | 76939 | 2 | Machine Shop Started | Regular | 2 | 2 | BRLED-400-80-35-FL-12-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1512 | 18
|  |  | 3 | Machine Shop Started | Regular | 4 | 4 | BRLED-400-80-35-FL-16-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2016 | 26.6
|  |  | 4 | Machine Shop Started | Regular | 6 | 6 | BRLED-400-80-35-FL-34-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4284 | 57.4
|  | 76939 Total | [14 empty] | 7812 | 102
|  | 78931 | 1 | Packaging Finished | Regular | 2 | 2 | BBDLED-1000-90-35-SO-4'-W-UNV-DP-1-CA(96)-C(BLACK CANOPIES & CORD) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 704 | 10.8
|  | 78931 Total | [14 empty] | 704 | 10.8
|  | 79076 | 1 | Machine Shop Finished | Replacement | 1 | 1 | BBWDILED-640-400-80-40SO-4-W-120-BI-1-OS(1 LOS-CDT)-C(SENSOR FOR INDIRECT ONLY) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 448 | 9
|  | 79076 Total | [14 empty] | 448 | 9
|  | 78711 | 1 | Machine Shop Finished | Regular | 1 | 1 | BBWDILED-400-750-90-35-SO-2'-W-277-DP-1+GTD(1) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 353 | 11.2
|  | 78711 Total | [14 empty] | 353 | 11.2
|  | 78290 | 1 | Machine Shop Finished | Regular | 2 | 2 | ZELED-SL 65/35-1100-80-35-MSO-W-12-AP-UNV-MD-1-CA(18") |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2542 | 36
|  | 78290 Total | [14 empty] | 2542 | 36
|  | 79186 | 1 | Machine Shop Started | Replacement | 1 | 1 | SP000-BBDILED-300-750-80-35-SO-28-BLK-UNV-DP-1-CA(36)-C(SECTION #3 ONLY TO JOIN TO EXISTING) | +Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  | Done | 840 | 38.8
|  | 79186 Total | [14 empty] | 840 | 38.8
|  | 70875 | 1 | Scheduled/Released | Regular | 12 | 12 | STFD-DSO(12)-300-90-35-AY(1)-AP-UNV-MD-1-CA(36)-RC | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 5942.16 | 68
|  | 70875 Total | [14 empty] | 5942.16 | 68
|  | 79320 | 1 | Packaging Finished | Regular | 4 | 0 | BDLED-700-80-30-SO-32'-W-UNV-DP-1-CA(36) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 79320 Total | [14 empty] | 0 | 0
|  | 79014 | 1 | Machine Shop Started | Regular | 2 | 2 | BILED-640-90-30-C-4'-W-UNV-DP-1-CA(48") | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 640 | 9.6
|  | 79014 Total | [14 empty] | 640 | 9.6
|  | 78050 | 1 | Machine Shop Finished | Regular | 10 | 10 | ARSLED-600-80-30-S-4'-AP-120-DP-1-SC | +Cartridge | Wrong part in BOM | TRUE |  | TRUE | TRUE |  | Done | 4731.5 | 38
|  | 78050 Total | [14 empty] | 4731.5 | 38
|  | 79322 | 1 | Machine Shop Started | Replacement | 1 | 1 | GPRLED-FC2W-1200-90-27-RG2-24 3/4"-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 0 | 3
|  | 79322 Total | [14 empty] | 0 | 3
|  | 78727 | 1 | Machine Shop Started | Regular | 6 | 6 | BBPRLED-400-80-30-RG2-30'-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 5760 | 39.1
|  | 78727 Total | [14 empty] | 5760 | 39.1
|  | 78401 | 1 | Machine Shop Finished | Regular | 2 | 2 | BBDLED-750-80-35-SO-24-W-UNV-DP-1-CA(120) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2118 | 22.7
|  |  | 2 | Machine Shop Started | Regular | 1 | 1 | BBDLED-750-80-35-SO-8-W-UNV-DP-1-CA(120) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 706 | 8.7
|  | 78401 Total | [14 empty] | 2824 | 31.4
|  | 78854 | 1 | Machine Shop Finished | Regular | 2 | 2 | BMRLED-500-80-35-FL-4'-W-UNV-DP-1-D | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 720 | 6.28
|  | 78854 Total | [14 empty] | 720 | 6.28
|  | 77187 | 1 | Machine Shop Started | Regular | 4 | 4 | SCDIPAT-REC-90(4)-500-400-80-30-SO-FL-40'-NL-AP-UNV-DP-2-CA(36) |  | Missing info. In SD | TRUE |  | TRUE | FALSE |  |  | 2890 | 50
|  |  | 2 | Machine Shop Started | Regular | 1 | 1 | SCDIPAT-REC-90(4)-500-400-80-30-SO-FL-20'-NL-AP-UNV-DP-2-CA(36) |  | Missing info. In SD | TRUE |  | TRUE | FALSE |  |  | 1700 | 30
|  | 77187 Total | [14 empty] | 4590 | 80
|  | 72844 | 1 | Given to Shipping | Regular | 8 | 0 | BBRLED-750-80-27-FL-6-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 72844 Total | [14 empty] | 0 | 0
|  | 76093 | 2 | Machine Shop Finished | Regular | 5 | 5 | WWR-SL-400-90-40-L-4-W-UNV-DP-1-DS | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2364 | 24
|  | 76093 Total | [14 empty] | 2364 | 24
|  | 79010 | 1 | Machine Shop Started | Regular | 1 | 1 | ARSLED-500-80-35-S-4'-AP-277-DP-1-SC | Material | Others | TRUE |  | #N/A | #N/A | #N/A | #N/A | 380 | 3.8
|  | 79010 Total | [14 empty] | 380 | 3.8
|  | 78616 | 1 | Machine Shop Started | Regular | 2 | 2 | BBDLED-750-80-40-SO-8-BLK-UNV-DP-1-CA(36") |  | Shortage | FALSE | Shortage | FALSE | FALSE |  | Done | 1440 | 18
|  | 78616 Total | [14 empty] | 1440 | 18
|  | 78703 | 1 | Machine Shop Started | Regular | 1 | 1 | SCWDI-750-500-80-35-SO-FL-4'-W-UNV-DP-1-B1(BSL10LST) | Material+Cartridge | Missing parts in BOM | TRUE |  | TRUE | FALSE |  |  | 660 | 10.5
|  | 78703 Total | [14 empty] | 660 | 10.5
|  | 78699 | 1 | Machine Shop Started | Regular | 3 | 3 | BMDLED-1000-80-35-SO-26'-BLK-UNV-DP-1-CA(72") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 2030.1429 | 24
|  |  | 2 | Machine Shop Started | Regular | 2 | 2 | BMDLED-1000-80-35-SO-24'-BLK-UNV-DP-1-CA(72") | +Cartridge | Others | TRUE |  | TRUE | TRUE |  |  | 1880.1428 | 39
|  |  | 3 | Machine Shop Started | Regular | 4 | 4 | BMDLED-1000-80-35-SO-16'-BLK-UNV-DP-1-CA(72") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 2560.2857 | 29.2
|  |  | 4 | Machine Shop Started | Regular | 1 | 1 | BMDLED-1000-80-35-SO-8'-BLK-UNV-DP-1-CA(72") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 680.1428 | 7.5
|  |  | 5 | Machine Shop Started | Regular | 1 | 1 | BMDLED-1000-80-35-SO-9'-BLK-UNV-DP-1-CA(72") | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 755.1428 | 9.8
|  |  | 6 | Machine Shop Started | Regular | 2 | 2 | BMDLED-1000-80-35-SO-20'-BLK-UNV-DP-1-CA(72") | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1575.1429 | 17
|  | 78699 Total | [14 empty] | 9481 | 126.5
|  | 79347 | 1 | Machine Shop Started | Replacement | 1 | 1 | B2SQDLED-750-80-30-SO-110 1/2"-W-UNV-DP-1-CT9(72)-C( ADD TO EXISITING) | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 0 | 9.2
|  | 79347 Total | [14 empty] | 0 | 9.2
|  | 78943 | 1 | Machine Shop Started | Regular | 3 | 3 | SCDI-750-500-80-30-SO-FL-8'-BLK-UNV-DP-1-CA(36) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2472 | 30.6
|  | 78943 Total | [14 empty] | 2472 | 30.6
|  | 75954 | 27 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-375-80-30-RG3-150 3/4"-W-UNV-DP-1-DS-TS(2)-CP |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1006 | 23
|  |  | 28 | Machine Shop Started | Regular | 4 | 4 | BMPRLED-375-80-30-RG3-23'-W-UNV-DP-1-DS-TS(2)-CP |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3368 | 64.4
|  |  | 29 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-375-80-30-RG3-134"-W-UNV-DP-1-DS-TS(2)-CP |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 800 | 16.3
|  |  | 41 | Machine Shop Started | Regular | 1 | 1 | BMPRLED-375-80-30-RG3-144"-W-UNV-DP-1-DS-TS(2)-CP |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 936 | 16.3
|  |  | 42 | Machine Shop Started | Regular | 2 | 2 | BMPRLED-375-80-30-RG3-168"-W-UNV-DP-1-DS-TS(2)-CP |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 775 | 23
|  | 75954 Total | [14 empty] | 6885 | 143
|  | 78926 | 1 | Machine Shop Started | Regular | 1 | 1 | BBPRLED-400-80-35-RG2-148 3/4"-W-UNV-DP-1-TG9-FW(6)-C(LENGTH IS BETWEEN TBARS) | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 1283 | 10.3
|  | 78926 Total | [14 empty] | 1283 | 10.3
|  | 77910 | 1 | Machine Shop Started | Regular | 8 | 8 | BMRLED-500-80-35-FL-16'-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4412 | 51.2
|  |  | 2 | Machine Shop Started | Regular | 4 | 4 | BMRLED-500-80-35-FL-16'-W-UNV-DP-1+E(1)-TB15 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2286 | 26.4
|  | 77910 Total | [14 empty] | 6698 | 77.6
|  | 79157 | 1 | Machine Shop Started | Regular | 2 | 2 | SP000-BMRLED-100-90-30-ASO-6'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 960 | 11.8
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | SP000-BMRLED-100-90-30-ASO-8'-W-UNV-DP-1-TG9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1920 | 17.7
|  |  | 3 | Machine Shop Started | Regular | 2 | 2 | SP000-BMRLED-100-90-30-ASO-8'-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1280 | 11.6
|  | 79157 Total | [14 empty] | 4160 | 41.1
|  | 78517 | 1 | Machine Shop Finished | Regular | 1 | 1 | CCWL-SL-300-90-35-CL(8)-W-UNV-DP-1-C | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 664 | 7.2
|  |  | 2 | Machine Shop Finished | Regular | 2 | 2 | WWR-SL-400-80-35-3-W-UNV-DP-1-D-FW(6) | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 708 | 6.2
|  | 78517 Total | [14 empty] | 1372 | 13.4
|  | 78964 | 1 | Machine Shop Finished | Replacement | 2 | 2 | CCH-SL-700-80-40-CL(22)-W-277-DP-1-C-F-C (SEE PDF ATTACHED JOINING TO EXISTING FIXTURE ON SITE) | Material | (blank) | FALSE |  | TRUE | TRUE |  |  | 910 | 38.6
|  | 78964 Total | [14 empty] | 910 | 38.6
|  | 78667 | 1 | Machine Shop Finished | Regular | 2 | 2 | BMRLED-500-80-30-1.25M-16'-W-277-DP-1-TG9 | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1400 | 13
|  | 78667 Total | [14 empty] | 1400 | 13
|  | 75392 | 1 | Machine Shop Finished | Regular | 6 | 6 | CCWH-SL-1100-80-27-CP(30')-W-120-DP-1-C |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2945 | 34
|  | 75392 Total | [14 empty] | 2945 | 34
|  | 78645 | 1 | Packaging Finished | Regular | 1 | 0 | TB2DILED-750-500-80-40-SO-L-6-W-UNV-LT(LDE1)-1-CA(48)-C(DFCSJ-OEM-RF & DFC-OEM-DBI) |  | Mechanical issue | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 2 | Packaging Finished | Regular | 1 | 0 | TB2DILED-750-500-80-40-SO-L-6-W-UNV-LT(LDE1)-2-CA(48)-C(DFCSJ-OEM-RF & DFC-OEM-DBI) |  | Electrical issue | TRUE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 78645 Total | [14 empty] | 0 | 0
|  | 78661 | 1 | Wiring Started | Regular | 1 | 1 | WWR-SL-750-80-40-8-W-UNV-LT(LDE1)-1-TG9-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | Material | Mechanical issue | FALSE | Mechanical issue | TRUE | FALSE |  | Done | 805 | 7
|  |  | 2 | Wiring Started | Regular | 2 | 2 | BBRLED-750-80-40-FL-4-W-UNV-LT(LDE1)-1-TG9-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 830 | 10
|  | 78661 Total | [14 empty] | 1635 | 17
|  | 78047 | 1 | Machine Shop Finished | Regular | 9 | 9 | BBDILED-640-400-80-35-SO-4'-W-UNV-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4320 | 67.5
|  |  | 2 | Machine Shop Finished | Regular | 1 | 1 | BBDILED-640-400-80-35-SO-8'-W-UNV-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 960 | 11.8
|  |  | 3 | Machine Shop Finished | Regular | 1 | 1 | ARWLED-600-80-35-S-2'-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 240 | 3.8
|  |  | 4 | Machine Shop Finished | Regular | 3 | 3 | BBRLED-400-80-35-1.5M-4'-W-UNV-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1050 | 7.5
|  |  | 5 | Machine Shop Finished | Regular | 2 | 2 | BBRLED-400-80-35-1.5M-4'-W-UNV-DP-1-TB9-B1(BSL310LP) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1060 | 12.8
|  | 78047 Total | [14 empty] | 7630 | 103.4
|  | 78272 | 1 | Machine Shop Finished | Regular | 6 | 6 | TEK6LED-R-580-90-35-S-4-W-120-D-1-TG9-FW(6) |  | Shortage | TRUE |  | TRUE | FALSE |  | Done | 3480 | 19.2
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | TEK6LED-R-580-90-35-S-4-W-120-D-1-TG9-B1(BSL310LP)-FW(6) |  | Shortage | TRUE |  | TRUE | FALSE |  | Done | 2475 | 33
|  | 78272 Total | [14 empty] | 5955 | 52.2
|  | 78110 | 1 | Machine Shop Started | Regular | 9 | 9 | BMDLED-1000-90-35-SO-8'-W-UNV-DP-1-CA(60) |  | Wrong info. In SD | TRUE |  | TRUE | TRUE |  |  | 5139 | 74.5
|  |  | 2 | Machine Shop Started | Regular | 10 | 10 | BMDLED-1000-90-35-SO-8'-W-UNV-DP-2-CA(60) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 6170 | 118.4
|  |  | 3 | Machine Shop Started | Regular | 1 | 1 | BMRLED-1000-90-35-RG-8'-W-UNV-DP-1-TG9-CP | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 605 | 9.7
|  | 78110 Total | [14 empty] | 11914 | 202.6
|  | 79133 | 1 | Machine Shop Finished | Replacement | 1 | 1 | SCWD-300-80-35-FL-5' 6"-AP-UNV-DP-1 |  | Wrong info. In SD | TRUE |  | TRUE | FALSE |  |  | 520 | 6.2
|  | 79133 Total | [14 empty] | 520 | 6.2
|  | 77060 | 2 | Machine Shop Started | Regular | 12 | 12 | B3RLED-SL-750-80-30-FL-4-W-UNV-DP-1-TG15 | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4080 | 36
|  | 77060 Total | [14 empty] | 4080 | 36
|  | 78663 | 1 | Machine Shop Started | Regular | 3 | 3 | SCDI-500-500-80-35-SO-0.5M-8-AP-UNV-DP-1-CA(36)-B1(BSL10LST) | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2818.65 | 30.6
|  | 78663 Total | [14 empty] | 2818.65 | 30.6
|  | 78388 | 1 | Machine Shop Finished | Regular | 4 | 4 | STSLR-SO-400-80-35-6-AP-UNV-MD-1-SB9 | Material+Cartridge | Others | FALSE | Others | TRUE | TRUE |  | Done | 1800 | 22
|  | 78388 Total | [14 empty] | 1800 | 22
|  | 79049 | 1 | Machine Shop Started | Regular | 1 | 1 | BILED-640-90-40-C-8'-W-277-DP-1-CT15(48") | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 560 | 7.6
|  |  | 2 | Machine Shop Started | Regular | 5 | 5 | BILED-640-90-40-C-5'-W-277-DP-1-CT15(48") | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1750 | 38
|  | 79049 Total | [14 empty] | 2310 | 45.6
|  | 79307 | 5 | Machine Shop Started | Replacement | 1 | 1 | SCS-400-80-35-FL-K(L4X4)-W-UNV-DP-1-S | +Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 775 | 0
|  | 79307 Total | [14 empty] | 775 | 0
|  | 79264 | 1 | Machine Shop Finished | Regular | 2 | 2 | BBWDLED-400-80-40-SO-4-W-UNV-DP-1 | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 560 | 8.86
|  | 79264 Total | [14 empty] | 560 | 8.86
|  | 78759 | 1 | Machine Shop Finished | Regular | 6 | 6 | BRLED-300-90-35-FL-10'-W-UNV-DP-1-TB15 | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 6000 | 54
|  |  | 2 | Machine Shop Finished | Regular | 4 | 4 | BRLED-300-90-35-FL-8'-W-UNV-DP-1-TB15 | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3200 | 25.6
|  | 78759 Total | [14 empty] | 9200 | 79.6
|  | 79234 | 1 | Machine Shop Started | Regular | 1 | 1 | BMRLED-700-80-40-FL-12'-W-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  | Done | 650 | 8.7
|  | 79234 Total | [14 empty] | 650 | 8.7
|  | 78469 | 1 | Machine Shop Started | Regular | 2 | 2 | BMRLED-750-90-30-FL-7'4"-W-120-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1280 | 12.2
|  |  | 2 | Machine Shop Started | Regular | 1 | 1 | BMRLED-750-90-30-FL-8'-W-120-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 640 | 6.1
|  | 78469 Total | [14 empty] | 1920 | 18.3
|  | 77378 | 1 | Machine Shop Started | Regular | 10 | 10 | BMWILEDPAT-REC-90(4)-750-90-30-C-58' 1/2"-NL-W-UNV-DP-1 | Material | Mechanical issue | FALSE | Mechanical issue | TRUE | FALSE | ToDo |  | 5000 | 60
|  | 77378 Total | [14 empty] | 5000 | 60
|  | 78707 | 1 | Machine Shop Started | Regular | 1 | 1 | SCD-500-80-35-FL-K(4X4)-W-UNV-DP-1-CT9(48) |  | (blank) | FALSE |  | TRUE | FALSE |  |  | 883 | 22.3
|  | 78707 Total | [14 empty] | 883 | 22.3
|  | 78640 | 1 | Machine Shop Started | Regular | 1 | 1 | BRLED-536-90-40-FL-4-W-277-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 347 | 3.26
|  |  | 3 | Machine Shop Started | Regular | 3 | 3 | BRLED-536-90-40-FL-32'-W-277-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2774 | 26
|  | 78640 Total | [14 empty] | 3121 | 29.26
|  | 78171 | 1 | Machine Shop Finished | Regular | 7 | 7 | WWR-SL-500-90-40-4'0"-W-UNV-DP-1-TB15 | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2912 | 20.3
|  | 78171 Total | [14 empty] | 2912 | 20.3
|  | 78106 | 1 | Scheduled/Released | Regular | 3 | 3 | BBRLED-500-80-35-FL-4'-W-UNV-DP-1-ST | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1110 | 7.5
|  |  | 2 | Scheduled/Released | Regular | 2 | 2 | BBPRLED-500-80-35-RG4-6' 9"-W-UNV-DP-1-ST-TS(1) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1540 | 10.8
|  |  | 3 | Scheduled/Released | Regular | 2 | 2 | BBPRLED-500-80-35-RG4-10' 10"-W-UNV-DP-1-ST-TS(1) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2338 | 14.4
|  |  | 4 | Scheduled/Released | Regular | 3 | 3 | BBPRLED-OPRI(1)-500-80-35-FL-16'-W-UNV-DP-1-DS-TS(1)-C( 9FT 8.6IN X 6FT) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1950 | 21
|  | 78106 Total | [14 empty] | 6938 | 53.7
|  | 78715 | 1 | Machine Shop Finished | Regular | 2 | 2 | ZESQDI-SL 75/25-900-80-35-MAL-16-W-UNV-MD-1-CA(36) | Material | Shortage | FALSE | Shortage | TRUE | TRUE |  | Done | 1728 | 30.3
|  | 78715 Total | [14 empty] | 1728 | 30.3
|  | 78521 | 1 | Wiring Started | Regular | 1 | 1 | WWR-SL-1000-80-30-2-W-UNV-DP-1-DF |  | Mechanical issue | FALSE | Mechanical issue | TRUE | TRUE |  | Done | 240 | 2.9
|  | 78521 Total | [14 empty] | 240 | 2.9
|  | 78442 | 1 | Machine Shop Finished | Regular | 2 | 2 | TB2WDILED-750-750-90-35-SLA-SO-6'-AP-UNV-DP-1 | Material | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 1344 | 20
|  | 78442 Total | [14 empty] | 1344 | 20
|  | 76528 | 1 | Machine Shop Finished | Mockup/Samples | 1 | 1 | SCML-6-BW-700-MLB(6)-1000-BLK-80-35-BLK-UNV-DP-2-CA(36)-C(CORD, PLUG & DIMMER) |  | Others | FALSE | Others | TRUE | TRUE |  | Done | 1060 | 8.6
|  | 76528 Total | [14 empty] | 1060 | 8.6
|  | 79035 | 1 | Machine Shop Started | Replacement | 2 | 2 | SCRPAT-ASO-90-300-80-35-0.5M-10'-EX-W-120-DP-1-MFTB9 | Material+Cartridge | Others | FALSE | Others | FALSE | FALSE |  |  | 630 | 11
|  | 79035 Total | [14 empty] | 630 | 11
|  | 78994 | 1 | Machine Shop Started | Regular | 2 | 2 | SCDI-300-400-80-35-SO-FL-6-W-UNV-DP-1-CT15(72) |  | Wrong part in BOM | TRUE |  | TRUE | TRUE |  |  | 1200 | 19.4
|  |  | 2 | Machine Shop Started | Regular | 1 | 1 | SCDI-300-400-80-35-SO-FL-8-W-UNV-DP-1-CA(72)-C(4.5 CANOPIES) |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 800 | 9.7
|  | 78994 Total | [14 empty] | 2000 | 29.1
|  | 78988 | 1 | Machine Shop Started | Regular | 17 | 17 | BBR-S-FL-8'-NL-T5-2-W-UNV-ERS-1-TB9 | Material | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 10217 | 96.9
|  |  | 2 | Machine Shop Started | Regular | 7 | 7 | BBR-S-FL-4-NL-T5-2-W-UNV-ERS-1-TB9 | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2296 | 21
|  | 78988 Total | [14 empty] | 12513 | 117.9
|  | 78968 | 1 | Machine Shop Finished | Regular | 4 | 4 | BDLED-750-80-30-SO-4'-AP-120-DP-1-CT9(96") | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1312 | 19.2
|  | 78968 Total | [14 empty] | 1312 | 19.2
|  | 78686 | 1 | Packaging Finished | Regular | 1 | 1 | SCD-300-90-35-FL-8-W-120-DP-1-CA(36)-C(4.5 CANOPIES) |  | Others | FALSE | Others | #N/A | #N/A | #N/A | #N/A | 600 | 7
|  |  | 2 | Packaging Finished | Regular | 1 | 1 | SCD-300-90-35-FL-8-W-120-DP-1-CT9(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 600 | 7
|  | 78686 Total | [14 empty] | 1200 | 14
|  | 78515 | 1 | Given to Shipping | Regular | 5 | 0 | BSLED-400-80-30-SO-6-AP-120-DP-1-S |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 78515 Total | [14 empty] | 0 | 0
|  | 79116 | 1 | Machine Shop Started | Regular | 4 | 4 | B6R-S-FL-4-NL4-T8-2-W-120-E-1-TG9 |  | (blank) | FALSE |  | TRUE | FALSE |  |  | 1093.96 | 11.2
|  | 79116 Total | [14 empty] | 1093.96 | 11.2
|  | 79284 | 1 | Packaging Finished | Mockup/Samples | 1 | 1 | B2SQWILED-1100-80-35-SLA-2-W-UNV-DP-1-C(AXIS CORD PLUG DIMMER) | Material+Cartridge | Others | TRUE |  | TRUE | TRUE |  | Done | 240 | 5.1
|  | 79284 Total | [14 empty] | 240 | 5.1
|  | 79011 | 2 | Wiring Started | Replacement | 1 | 1 | SKPLED-22-3200-80-35-0.5-W-UNV-DP-2-TB9 | Material | Others | FALSE | Others | TRUE | TRUE |  | Done | 195 | 2
|  |  | 3 | Wiring Started | Replacement | 1 | 1 | SKPLED-22-3200-80-35-0.5-W-UNV-DP-2-TB15 | Material | Others | FALSE | Others | TRUE | TRUE |  | Done | 195 | 2
|  | 79011 Total | [14 empty] | 390 | 4
|  | 79017 | 1 | Machine Shop Finished | Regular | 1 | 1 | SCR-400-80-35-FL-8' 11"-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 765 | 7.5
|  | 79017 Total | [14 empty] | 765 | 7.5
|  | 78525 | 1 | Machine Shop Started | Regular | 1 | 1 | SCDI-300-500-80-35-SO-FL-K(2X6)-BLK-UNV-DP-1-CA(48")-C(SWIVEL MOUNTING) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1700 | 34
|  | 78525 Total | [14 empty] | 1700 | 34
|  | 77211 | 1 | Machine Shop Finished | Regular | 12 | 12 | BBWDILED-640-400-80-40-SO-8-W-UNV-DP-1-D |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 11520 | 121
|  |  | 2 | Machine Shop Finished | Regular | 8 | 8 | BBWDILED-640-400-80-40-SO-4-W-UNV-DP-1-D |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3840 | 56
|  | 77211 Total | [14 empty] | 15360 | 177
|  | 78930 | 1 | Machine Shop Started | Replacement | 3 | 3 | BMSLEDPAT-OPR-90-600-80-35-SO-16'5 3/4"-EX-W-UNV-DP-1-S | Material+Cartridge | PM wrong/missing info | TRUE |  | FALSE | FALSE | ToDo |  | 1050 | 5.2
|  | 78930 Total | [14 empty] | 1050 | 5.2
|  | 79125 | 1 | Machine Shop Started | Regular | 2 | 2 | WBRLED-500-80-40-S-5'-AP-UNV-DP-1-DF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2200 | 12.2
|  | 79125 Total | [14 empty] | 2200 | 12.2
|  | 79168 | 1 | Machine Shop Started | Regular | 6 | 6 | B6RLED-400-80-35-RG-4'-W-120-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 2280 | 19.2
|  | 79168 Total | [14 empty] | 2280 | 19.2
|  | 78971 | 1 | Machine Shop Finished | Mockup/Samples | 1 | 1 | BMWDLED-500-80-35-SO-4'-AP-UNV-DP-1-C(CORD & PLUG) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 300 | 4.2
|  | 78971 Total | [14 empty] | 300 | 4.2
|  | 78866 | 1 | Machine Shop Finished | Regular | 1 | 1 | BBPRLED-700-80-35-RG4-4'-W-UNV-DP-1-TB9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 356 | 2.5
|  |  | 2 | Machine Shop Finished | Regular | 1 | 1 | BBPRLED-700-80-35-RG4-8'-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 712 | 8.3
|  | 78866 Total | [14 empty] | 1068 | 10.8
|  | 79019 | 1 | Machine Shop Started | Replacement | 1 | 1 | SCR-500-90-40-FL-TR60X4-W-277-DP-1-MFTG9 |  | (blank) | FALSE |  | TRUE | FALSE |  |  | 930 | 15
|  | 79019 Total | [14 empty] | 930 | 15
|  | 78864 | 1 | Machine Shop Finished | Replacement | 1 | 1 | ZESQDI-SL 25/75-1050-80-35-SO-8-AP-UNV-MD-1-CA(96") |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 280 | 9.4
|  |  | 2 | Machine Shop Finished | Replacement | 1 | 1 | ZESQDI-SL 25/75-1050-80-35-SO-4-AP-UNV-MD-1-CA(120") |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 145 | 5.6
|  | 78864 Total | [14 empty] | 425 | 15
|  | 77608 | 1 | Wiring Started | Regular | 3 | 3 | SCML-6-SO-300-SO-500-MLA(6)-500-W-80-35-W-UNV-DP-1-CA(36) | Material | Others | TRUE |  | TRUE | TRUE |  | Done | 1890 | 21
|  | 77608 Total | [14 empty] | 1890 | 21
|  | 78588 | 1 | Scheduled/Released | Regular | 4 | 4 | SCIPAT-REC-90(4)-500-80-30-SO-26-NL-C(RAL6022)-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2820 | 18.5
|  |  | 2 | Scheduled/Released | Regular | 4 | 4 | SCIPAT-REC-90(4)-500-80-30-SO-26-NL-C(RAL6022)-UNV-DP-1-CA(48) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 2820 | 18.5
|  | 78588 Total | [14 empty] | 5640 | 37
| Total | [15 empty] | 305472.21 | 3598.838
12 Total | [16 empty] | 305472.21 | 3598.838
15 |  | 67150 | 41 | Machine Shop Finished | Regular | 20 | 20 | B6RLED-400-80-30-FL-15-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 8350 | 130
|  |  | 42 | Machine Shop Finished | Regular | 2 | 2 | B6RLED-400-80-30-FL-15-W-120-DP-E(1)-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 835 | 13.4
|  |  | 43 | Machine Shop Finished | Regular | 5 | 5 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2800 | 44
|  |  | 44 | Machine Shop Finished | Regular | 8 | 8 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3340 | 52
|  |  | 45 | Machine Shop Finished | Regular | 4 | 4 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1140 | 25.2
|  |  | 46 | Machine Shop Finished | Regular | 3 | 3 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1680 | 26.4
|  |  | 47 | Machine Shop Finished | Regular | 8 | 8 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3340 | 52
|  |  | 48 | Machine Shop Finished | Regular | 5 | 5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1425 | 31.5
|  |  | 49 | Machine Shop Finished | Regular | 12 | 12 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 6720 | 105.6
|  |  | 50 | Machine Shop Finished | Regular | 10 | 10 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4175 | 65
|  |  | 51 | Machine Shop Finished | Regular | 5 | 5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1425 | 31.5
|  |  | 52 | Machine Shop Finished | Regular | 14 | 14 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 7840 | 123.2
|  |  | 53 | Machine Shop Finished | Regular | 18 | 18 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 7515 | 117
|  |  | 55 | Machine Shop Finished | Regular | 1 | 1 | B6RLED-750-80-30-FL-4-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 230 | 3.3
|  |  | 56 | Machine Shop Finished | Regular | 3 | 3 | B6RLED-750-80-30-FL-5-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 855 | 18.9
|  |  | 57 | Machine Shop Finished | Regular | 10 | 10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 5600 | 88
|  |  | 58 | Machine Shop Finished | Regular | 2 | 2 | BRLED-500-80-30-FL-13-W-120-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 715 | 13.3
|  |  | 59 | Machine Shop Finished | Regular | 12 | 12 | BRLED-500-80-30-FL-18-W-120-DP-1-D | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 5940 | 97.2
|  |  | 60 | Machine Shop Finished | Regular | 2 | 2 | BRLED-500-80-30-FL-17-W-120-DP-E(1)-D | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 935 | 16.5
|  |  | 61 | Machine Shop Finished | Regular | 12 | 12 | BRLED-500-80-30-FL-18-W-120-DP-E(1)-D | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 5940 | 99
|  | 67150 Total | [14 empty] | 70800 | 1153
|  | 78650 | 1 | Given to Shipping | Regular | 3 | 3 | BBDLED-1000-80-35-SO-8'-W-UNV-DP-1-CT15(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2040 | 27
|  |  | 2 | Given to Shipping | Regular | 12 | 12 | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4080 | 36
|  | 78650 Total | [14 empty] | 6120 | 63
|  | 77560 | 1 | Machine Shop Finished | Regular | 12 | 12 | WBWLED-750-80-40-S-8' 0"-BLK-UNV-DP-1 |  | Others | TRUE |  | TRUE | TRUE |  | Done | 11388.6 | 86.88
|  | 77560 Total | [14 empty] | 11388.6 | 86.88
|  | 78529 | 1 | Machine Shop Finished | Regular | 1 | 1 | BBRLED-1000-80-35-FL-12'-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 972 | 7
|  |  | 2 | Machine Shop Finished | Regular | 2 | 2 | BBRLED-1000-80-35-FL-20'-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1620 | 12
|  |  | 3 | Machine Shop Finished | Regular | 25 | 25 | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 8550 | 75
|  |  | 4 | Machine Shop Finished | Regular | 1 | 1 | BBRLED-1000-80-35-FL-8'-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 648 | 5
|  | 78529 Total | [14 empty] | 11790 | 99
|  | 78491 | 1 | Machine Shop Finished | Regular | 21 | 21 | BDLED-1000-90-30-SO-4'-AP-UNV-DP-1-CA(72) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 5880 | 100.8
|  | 78491 Total | [14 empty] | 5880 | 100.8
|  | 74124 | 1 | Given to Shipping | Regular | 215 | 215 | BBRLED-1000-80-35-FL-4-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 42140 | 645
|  |  | 2 | Given to Shipping | Regular | 2 | 2 | BBRLED-1000-80-35-FL-8-W-UNV-DP-1-TG9 |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 784 | 10
|  |  | 3 | Given to Shipping | Regular | 11 | 11 | BBRLED-1000-80-35-FL-4-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2156 | 33
|  |  | 4 | Given to Shipping | Regular | 1 | 1 | BBRLED-1000-80-35-FL-8-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 392 | 5
|  |  | 5 | Given to Shipping | Regular | 2 | 2 | BBRLED-1000-80-35-FL-16-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 784 | 10
|  |  | 6 | Given to Shipping | Regular | 2 | 2 | BDLED-750-80-35-SO-20-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 980 | 18
|  |  | 7 | Given to Shipping | Regular | 2 | 2 | BDLED-750-80-35-SO-23-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1127 | 20
|  |  | 8 | Given to Shipping | Regular | 3 | 3 | BDLED-750-80-35-SO-26-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1274 | 25
|  |  | 9 | Given to Shipping | Regular | 3 | 3 | BDLED-750-80-35-SO-29-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1421 | 27
|  |  | 10 | Given to Shipping | Regular | 3 | 3 | BDLED-750-80-35-SO-32-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1568 | 28
|  |  | 11 | Given to Shipping | Regular | 3 | 3 | BDLED-750-80-35-SO-35-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1751 | 30
|  |  | 12 | Given to Shipping | Regular | 4 | 4 | BDLED-750-80-35-SO-38-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1862 | 35
|  |  | 13 | Given to Shipping | Regular | 4 | 4 | BDLED-750-80-35-SO-41-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2009 | 37
|  |  | 14 | Given to Shipping | Regular | 4 | 4 | BDLED-750-80-35-SO-44-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2156 | 37
|  |  | 15 | Given to Shipping | Regular | 4 | 4 | BDLED-750-80-35-SO-48-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2352 | 40
|  |  | 16 | Given to Shipping | Regular | 5 | 5 | BDLED-750-80-35-SO-51-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2499 | 45
|  |  | 17 | Given to Shipping | Regular | 5 | 5 | BDLED-750-80-35-SO-54-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2646 | 47
|  |  | 18 | Given to Shipping | Regular | 5 | 5 | BDLED-750-80-35-SO-57-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2793 | 50
|  |  | 19 | Given to Shipping | Regular | 5 | 5 | BDLED-750-80-35-SO-60-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 2940 | 50
|  |  | 20 | Given to Shipping | Regular | 6 | 6 | BDLED-750-80-35-SO-64-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 3136 | 54
|  |  | 21 | Given to Shipping | Regular | 10 | 10 | BBDILED-640-400-80-35-SO-4-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 3000 | 80
|  |  | 22 | Given to Shipping | Regular | 4 | 4 | BBDILED-640-400-80-35-SO-8-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2400 | 48
|  |  | 23 | Given to Shipping | Regular | 20 | 20 | BBDILED-640-400-80-35-SO-16-W-UNV-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 12000 | 230
|  |  | 24 | Given to Shipping | Regular | 16 | 16 | BBDILED-640-400-80-35-SO-24-W-UNV-DP-2-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 14400 | 272
|  |  | 25 | Given to Shipping | Regular | 4 | 4 | BBRLED-750-80-35-FL-4-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 784 | 12
|  |  | 26 | Given to Shipping | Regular | 3 | 3 | BBRLED-750-80-35-FL-8-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1176 | 15
|  |  | 27 | Given to Shipping | Regular | 8 | 8 | BBRLED-750-80-35-FL-12-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 4704 | 56
|  |  | 28 | Given to Shipping | Regular | 16 | 16 | BBRLED-750-80-35-FL-20-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 7840 | 96
|  | 74124 Total | [14 empty] | 123074 | 2055
|  | 78534 | 1 | Machine Shop Started | Regular | 70 | 70 | BBRLED-950-80-35-FL-4'-W-UNV-DP-1-TG15-CP | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 19320 | 336
|  |  | 2 | Machine Shop Started | Regular | 19 | 19 | BBRLED-950-80-35-FL-2'-W-UNV-DP-1-TG15-CP | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  |  | 3173 | 91.2
|  | 78534 Total | [14 empty] | 22493 | 427.2
|  | 78643 | 5 | Machine Shop Finished | Regular | 7 | 7 | TB2DILED-400-1000-80-35-SL-SO-8'-W-UNV-DP-1-CA(72) | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 5652.85 | 71.4
|  | 78643 Total | [14 empty] | 5652.85 | 71.4
|  | 78744 | 1 | Machine Shop Finished | Regular | 18 | 18 | SCD-500-90-40-FL-4'-W-UNV-DP-1-CA(72) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4320 | 82.8
|  | 78744 Total | [14 empty] | 4320 | 82.8
|  | 77175 | 17 | Machine Shop Finished | Regular | 45 | 45 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Others | TRUE |  | TRUE | TRUE |  | Done | 13500 | 130.5
|  |  | 18 | Machine Shop Finished | Regular | 12 | 12 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | Others | TRUE |  | TRUE | TRUE |  | Done | 5400 | 58.8
|  |  | 23 | Machine Shop Finished | Regular | 3 | 3 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2700 | 25.5
|  |  | 24 | Machine Shop Finished | Regular | 18 | 18 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4950 | 72
|  |  | 26 | Machine Shop Finished | Regular | 8 | 8 | SCS-750-80-35-0.5P-16-BLK-UNV-DP-1-SC-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4220 | 50.4
|  |  | 27 | Machine Shop Finished | Regular | 49 | 49 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Others | TRUE |  | TRUE | TRUE |  | Done | 14700 | 142.1
|  |  | 28 | Machine Shop Finished | Regular | 18 | 18 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 8100 | 88.2
|  |  | 33 | Machine Shop Finished | Regular | 18 | 18 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 4950 | 72
|  |  | 145 | Machine Shop Finished | Regular | 2 | 2 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1800 | 17
|  | 77175 Total | [14 empty] | 60320 | 656.5
|  | 78825 | 1 | Machine Shop Finished | Regular | 20 | 20 | WBSLED-500-80-35-S-4'-W-UNV-DP-1-SC-C(END FEED) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 8800 | 92
|  |  | 2 | Machine Shop Finished | Regular | 10 | 10 | WBSLED-500-80-35-S-4'-W-UNV-DP-E(1)-SC-C(End Feed) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4800 | 59
|  | 78825 Total | [14 empty] | 13600 | 151
| Total | [15 empty] | 335438.45 | 4946.58
15 Total | [16 empty] | 335438.45 | 4946.58
18 |  | 75728 | 1 | Machine Shop Finished | Regular | 4 | 4 | SCR-500-80-30-FL-4-W-120-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1120 | 12.4
|  |  | 2 | Machine Shop Finished | Regular | 1 | 1 | SCR-500-80-30-FL-8-W-120-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 560 | 5.5
|  |  | 3 | Machine Shop Finished | Regular | 1 | 1 | SCR-300-80-30-FL-8-W-120-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 560 | 5.5
|  |  | 4 | Machine Shop Finished | Regular | 3 | 3 | SCR-500-80-30-FL-36-W-120-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2520 | 24.2
|  |  | 5 | Machine Shop Finished | Regular | 4 | 4 | SCR-500-80-30-FL-16-W-120-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2240 | 23.1
|  |  | 9 | Machine Shop Started | Regular | 16 | 16 | SCRPAT-OPR-90(2)-300-80-30-FL-159'-EX-W-120-DP-1-TG9 | +Cartridge | (blank) | FALSE |  | TRUE | FALSE | ToDo |  | 10990 | 120
|  | 75728 Total | [14 empty] | 17990 | 190.7
|  | 77808 | 1 | Order UnShipped | Regular | 15 | -3 | PWSLED-1000-90-35-S-4-W-120-DP-1-SB15 |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | -1140 | -13.68
|  |  | 2 | Order UnShipped | Regular | 3 | 3 | PWSLED-1000-90-35-S-4-W-120-DP-1-S | Material+Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1140 | 11.4
|  | 77808 Total | [14 empty] | 0 | -2.28
|  | 77630 | 1 | Machine Shop Started | Regular | 3 | 3 | SCR-300-80-35-FL-TR45X2-W-UNV-DP-1-MFTB15 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 750 | 36.9
|  |  | 2 | Machine Shop Started | Regular | 3 | 3 | ARLED-500-80-35-S-4-AP-UNV-DP-1-CTS(210) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1275 | 11.7
|  |  | 3 | Machine Shop Started | Regular | 3 | 3 | ARLED-500-80-35-S-4-AP-UNV-DP-1-CA(210) | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 1275 | 11.7
|  | 77630 Total | [14 empty] | 3300 | 60.3
|  | 78569 | 1 | Machine Shop Finished | Regular | 31 | 31 | WBRLED-500-80-30-S-5-C(RAL 7030)-UNV-DP-1-D | Material | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 12927 | 189.1
|  | 78569 Total | [14 empty] | 12927 | 189.1
|  | 79124 | 1 | Machine Shop Started | Mockup/Samples | 2 | 2 | CLKLED-750-80-30-SO-12'-W-277-DP-1-TG9-FW(6) | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 200 | 8.6
|  | 79124 Total | [14 empty] | 200 | 8.6
|  | 73887 | 1 | Packaging Finished | Regular | 7 | 0 | BMSLED-1000-80-35-SO-4-BLK-UNV-DP-1-SC |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 3 | Packaging Finished | Regular | 34 | 0 | BMRLED-1000-80-35-FL-4-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 4 | Packaging Finished | Regular | 1 | 0 | BMRLED-1000-80-35-FL-8-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 5 | Packaging Finished | Regular | 2 | 0 | BMRLED-1000-80-35-FL-16-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 6 | Packaging Finished | Regular | 1 | 0 | BMRLED-1000-80-35-FL-12-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 7 | Packaging Finished | Regular | 30 | 0 | BMRLED-1000-80-35-1.25M-4-W-UNV-DP-1-TB15 |  | Others | FALSE | Others | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 8 | Packaging Finished | Regular | 1 | 0 | BMRLED-1000-80-35-1.25M-12-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 9 | Packaging Finished | Regular | 2 | 0 | BMRLED-1000-80-35-1.25M-16-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 10 | Packaging Finished | Regular | 4 | 0 | BMRLED-1000-80-35-1.25M-20-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 11 | Packaging Finished | Regular | 4 | 0 | BMRLED-1000-80-35-FL-6-W-UNV-DP-1-TB15 |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 12 | Packaging Finished | Regular | 8 | 0 | BMDLED-400-80-35-SO-4-AP-UNV-DP-1-CTS(144) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 13 | Packaging Finished | Regular | 4 | 0 | BMDLED-400-80-35-SO-8-AP-UNV-DP-1-CTS(144) |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 15 | Machine Shop Finished | Regular | 14 | 14 | STFD-DSO(16-400)-80-35-AH(6)-BLK-UNV-MD-1-CA(36)-RC | +Cartridge | Others | TRUE |  | TRUE | TRUE |  | Done | 2664 | 74
|  |  | 16 | Packaging Finished | Regular | 12 | 0 | BMRLED-1000-80-35-FL-4-BLK-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 18 | Packaging Finished | Regular | 3 | 1 | BMRLED-1000-80-35-FL-8-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 468 | 6.1
|  |  | 19 | Packaging Finished | Regular | 4 | 0 | BMRLED-1000-80-35-FL-8-BLK-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 20 | Packaging Finished | Regular | 3 | 2 | BMRLED-1000-80-35-FL-12-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 1404 | 17.4
|  |  | 21 | Packaging Finished | Regular | 7 | 0 | BMRLED-1000-80-35-1.25M-4-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 23 | Packaging Finished | Regular | 2 | 0 | BMRLED-1000-80-35-FL-6-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 24 | Packaging Finished | Regular | 3 | 0 | BMRLED-1000-80-35-FL-6-BLK-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  |  | 26 | Packaging Finished | Regular | 3 | 0 | BMRLED-1000-80-35-FL-8-W-UNV-DP-1-DF |  | (blank) | FALSE |  | #N/A | #N/A | #N/A | #N/A | 0 | 0
|  | 73887 Total | [14 empty] | 4536 | 97.5
|  | 72906 | 2 | Machine Shop Finished | Regular | 1 | 1 | BRLED-1000-90-35-FL-4-W-120-DP-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 288 | 3.86
|  |  | 3 | Machine Shop Finished | Regular | 2 | 2 | BRLED-1000-90-35-FL-10-W-120-DP-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1440 | 20.58
|  |  | 4 | Machine Shop Finished | Regular | 1 | 1 | BRLED-1000-90-35-FL-6-W-120-DP-1-DS |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 432 | 7.3
|  |  | 5 | Machine Shop Finished | Regular | 10 | 10 | B2SQDLED-1000-90-35-SO-50-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 8500 | 81.32
|  |  | 6 | Machine Shop Finished | Regular | 2 | 2 | B2SQDLED-1000-90-35-SO-22-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1870 | 18.34
|  |  | 7 | Machine Shop Finished | Regular | 2 | 2 | B2SQDLED-1000-90-35-SO-21-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1785 | 18.34
|  |  | 8 | Machine Shop Finished | Regular | 2 | 2 | B2SQDLED-1000-90-35-SO-20-AP-120-DP-1-CA(36) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1700 | 16.07
|  | 72906 Total | [14 empty] | 16015 | 165.81
|  | 78279 | 1 | Machine Shop Started | Regular | 2 | 2 | BBDILED-400-400-80-30-SO-8-BLK-UNV-DP-1-CA(48) | Material+Cartridge | Shortage | FALSE | Shortage | FALSE | FALSE |  |  | 1280 | 23.6
|  |  | 2 | Machine Shop Started | Regular | 30 | 30 | BMRLED-650-80-30-FL-4-W-UNV-DP-1-TB9 | Material+Cartridge | (blank) | FALSE |  | FALSE | FALSE |  |  | 7200 | 96
|  | 78279 Total | [14 empty] | 8480 | 119.6
|  | 78729 | 1 | Machine Shop Finished | Regular | 58 | 58 | WBRLED-750-80-35-S-2'-W-UNV-DP-1-DF |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 18560 | 203
|  | 78729 Total | [14 empty] | 18560 | 203
|  | 77011 | 1 | Given to Shipping | Regular | 13 | 13 | SP16169(2)-WBRLED-750-30-S-12'-W-UNV-DP-1-DS-TF |  | On Hold | FALSE | On Hold | TRUE | TRUE |  | Done | 14352 | 77.48
|  | 77011 Total | [14 empty] | 14352 | 77.48
|  | 77356 | 1 | Machine Shop Finished | Regular | 95 | 95 | BBDLED-750-80-35-SO-2' 0"-W-UNV-DP-1-SA(120) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 18430 | 513
|  |  | 2 | Machine Shop Finished | Regular | 89 | 89 | BBDLED-750-80-35-SO-4' 0"-W-UNV-DP-1-SA(120) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 19224 | 480.6
|  |  | 3 | Machine Shop Finished | Regular | 5 | 5 | BBDLED-750-80-35-ASO-2' 0"-W-UNV-DP-1-SA(120) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 920 | 26.5
|  |  | 4 | Machine Shop Started | Regular | 3 | 3 | BBDILED-400-640-80-35-SO-8' 0"-W-UNV-DP-2-CT15(36) | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2040 | 39.6
|  |  | 5 | Machine Shop Started | Regular | 15 | 15 | WBRLED-750-80-35-S-4' 0"-AP-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | FALSE |  | Done | 5145 | 81
|  |  | 6 | Machine Shop Started | Regular | 8 | 8 | BBRLED-400-80-35-FL-4' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1728 | 40
|  |  | 7 | Machine Shop Started | Regular | 10 | 10 | BBRLED-400-80-35-FL-5' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2700 | 83
|  |  | 8 | Machine Shop Started | Regular | 3 | 3 | BBRLED-400-80-35-FL-6' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 969 | 24.9
|  |  | 9 | Machine Shop Started | Regular | 10 | 10 | BBRLED-400-80-35-FL-7' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3780 | 83
|  |  | 10 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-8' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 864 | 16.6
|  |  | 11 | Machine Shop Started | Regular | 1 | 1 | BBRLED-400-80-35-FL-9' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 486 | 10.5
|  |  | 12 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-10' 0"-W-UNV-DP-1-TB15 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1080 | 13
|  |  | 13 | Machine Shop Started | Regular | 7 | 7 | BBRLED-400-80-35-FL-11' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4158 | 72.8
|  |  | 14 | Machine Shop Started | Regular | 1 | 1 | BBRLED-400-80-35-FL-12' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 648 | 10.4
|  |  | 15 | Machine Shop Started | Regular | 4 | 4 | BBRLED-400-80-35-FL-13' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1404 | 34.4
|  |  | 16 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-14' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 756 | 17.2
|  |  | 17 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-13' 0"-W-UNV-DP-1-TB15 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 702 | 9.9
|  |  | 18 | Machine Shop Started | Regular | 16 | 16 | BBRLED-400-80-35-FL-15' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 6480 | 137.6
|  |  | 19 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-15' 0"-W-UNV-DP-1-TB15 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 810 | 9.9
|  |  | 20 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-24' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1296 | 21.7
|  |  | 21 | Machine Shop Started | Regular | 3 | 3 | BBRLED-400-80-35-FL-28' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1712 | 28.5
|  |  | 22 | Machine Shop Started | Regular | 3 | 3 | BBRLED-400-80-35-FL-33' 0"-W-UNV-DP-1-TB15 | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1782 | 21.2
|  |  | 23 | Machine Shop Started | Regular | 5 | 5 | BBRLED-400-80-35-FL-52' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2808 | 51
|  |  | 25 | Machine Shop Started | Regular | 2 | 2 | BBRLED-400-80-35-FL-10' 0"-W-UNV-DP-1-DS | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1080 | 20.8
|  | 77356 Total | [14 empty] | 81002 | 1847.1
|  | 78680 | 1 | Machine Shop Started | Regular | 9 | 9 | TWRWLED-SL 90/10-750-80-40-SO-4'-W-UNV-DP-1 |  | (blank) | FALSE |  | TRUE | TRUE |  |  | 3060 | 38.7
|  | 78680 Total | [14 empty] | 3060 | 38.7
|  | 77175 | 19 | Machine Shop Finished | Regular | 4 | 4 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2560 | 21.2
|  |  | 20 | Machine Shop Finished | Regular | 2 | 2 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 640 | 5.8
|  |  | 21 | Machine Shop Started | Regular | 3 | 3 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1616 | 87
|  |  | 22 | Machine Shop Started | Regular | 4 | 4 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1712 | 98
|  |  | 25 | Machine Shop Finished | Regular | 8 | 8 | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4040 | 58.4
|  |  | 29 | Machine Shop Finished | Regular | 5 | 5 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3200 | 26.5
|  |  | 30 | Machine Shop Finished | Regular | 3 | 3 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 960 | 8.7
|  |  | 31 | Machine Shop Started | Regular | 3 | 3 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 1616 | 87
|  |  | 32 | Machine Shop Started | Regular | 2 | 2 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC | Material | (blank) | FALSE |  | TRUE | FALSE |  |  | 856 | 49
|  |  | 34 | Machine Shop Finished | Regular | 4 | 4 | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC | Material | Others | TRUE |  | TRUE | TRUE |  | Done | 2020 | 29.2
|  |  | 143 | Machine Shop Finished | Regular | 8 | 8 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 2560 | 24
|  |  | 144 | Machine Shop Finished | Regular | 10 | 10 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 | Material | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3200 | 30
|  | 77175 Total | [14 empty] | 24980 | 524.8
|  | 75212 | 30 | Given to Shipping | Regular | 14 | 0 | BMRLED-1000-80-30-ASO-4'-W-UNV-DP-1-D |  | Shortage | FALSE | Shortage | TRUE | FALSE |  | Done | 0 | 0
|  |  | 38 | Machine Shop Started | Regular | 8 | 8 | BMRLED-1000-80-30-ASO-24'-W-UNV-DP-1+E(1)-TB15 |  | (blank) | FALSE |  | TRUE | FALSE |  |  | 4800 | 71.32
|  | 75212 Total | [14 empty] | 4800 | 71.32
|  | 77693 | 1 | Wiring Started | Regular | 13 | 3 | SCD-500-80-40-FL-4'0"-BLK-UNV-DP-1-CA(12) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 897.87 | 13.5
|  |  | 2 | Wiring Started | Regular | 3 | 3 | SCD-500-80-40-FL-6'0"-BLK-UNV-DP-1-CA(12) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1336.05 | 21
|  |  | 3 | Wiring Started | Regular | 6 | 6 | SCD-500-80-40-FL-8'0"-BLK-UNV-DP-1-CA(12) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 3591.42 | 42
|  |  | 4 | Wiring Started | Regular | 8 | 0 | ARLED-800-80-35-S-4'0"-BLK-UNV-DP-1-CA(48) | +Cartridge | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 5 | Wiring Started | Regular | 7 | 0 | SCDI-500-300-80-40-SO-0.5M-4'0"-BLK-UNV-DP-1-CA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 6 | Wiring Started | Regular | 2 | 2 | SCDI-500-300-80-40-SO-0.5M-6'0"-BLK-UNV-DP-1-CA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1257.02 | 19.8
|  |  | 7 | Wiring Started | Regular | 5 | 5 | SCDI-500-300-80-40-SO-0.5M-8'0"-BLK-UNV-DP-1-CA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 4190.05 | 49.5
|  |  | 8 | Wiring Started | Regular | 30 | 15 | SCDI-500-300-80-40-SO-FL-4'0"-BLK-UNV-DP-1-CA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 6092.7 | 100.5
|  |  | 9 | Wiring Started | Regular | 20 | 20 | SCDI-500-300-80-40-SO-FL-6'0"-BLK-UNV-DP-1-CA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 12185.4 | 198
|  |  | 10 | Wiring Started | Regular | 12 | 12 | SCDI-500-300-80-40-SO-FL-8'0"-BLK-UNV-DP-1-CA(48) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 9748.2 | 118.8
|  |  | 11 | Wiring Started | Regular | 5 | 5 | SCD-500-80-40-FL-4'0"-BLK-UNV-DP-1-CA(12) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 1496.45 | 22.5
|  | 77693 Total | [14 empty] | 40795.16 | 585.6
|  | 78098 | 1 | Machine Shop Started | Regular | 12 | 12 | TB3DILED-700-700-80-35-SL-SO-8-BLK-UNV-DP-1-CT9(36) |  | PM wrong/missing info | TRUE |  | TRUE | FALSE |  | Done | 8040 | 111.6
|  |  | 2 | Machine Shop Started | Regular | 4 | 4 | TB3DILED-700-700-80-35-SL-SO-12-BLK-UNV-DP-1-CT9(36) |  | PM wrong/missing info | TRUE |  | TRUE | FALSE |  | Done | 3840 | 52
|  |  | 3 | Machine Shop Started | Regular | 2 | 2 | TB3DILED-700-700-80-35-SL-SO-12-BLK-UNV-DP-1+E(1)-CT9(36) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 2120 | 28
|  |  | 4 | Machine Shop Started | Regular | 6 | 6 | TB3DILED-700-700-80-35-SL-SO-16-BLK-UNV-DP-1-CT9(36) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 3600 | 54.9
|  |  | 5 | Machine Shop Started | Regular | 1 | 1 | TB3DILED-700-700-80-35-SL-SO-16-BLK-UNV-DP-1+E(1)-CT9(36) |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1300 | 20
|  |  | 6 | Machine Shop Finished | Regular | 1 | 1 | BBPRLED-700-80-35-RG4-3-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 270 | 5
|  |  | 7 | Machine Shop Finished | Regular | 1 | 1 | BBPRLED-700-80-35-RG4-5-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 375 | 8.3
|  |  | 8 | Machine Shop Finished | Regular | 2 | 2 | BBPRLED-700-80-35-RG4-6-W-UNV-DP-1-TB9 |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 900 | 9.2
|  |  | 9 | Machine Shop Finished | Regular | 3 | 3 | BBPRLED-700-80-35-RG4-6-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 1350 | 24.6
|  |  | 10 | Machine Shop Finished | Regular | 1 | 1 | BBPRLED-700-80-35-RG4-8-W-UNV-DP-1-DS |  | (blank) | FALSE |  | TRUE | FALSE |  | Done | 600 | 8.2
|  | 78098 Total | [14 empty] | 22395 | 321.8
|  | 78386 | 1 | Given to Shipping | Regular | 3 | 0 | BDLED-1000-90-40-SO-5-W-UNV-DP-1-CA(56)-C(OVERALL LENGTH) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 2 | Given to Shipping | Regular | 3 | 0 | BDLED-1000-90-40-SO-6-W-UNV-DP-1-CA(56)-C(OVERALL LENGTH) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  |  | 3 | Given to Shipping | Regular | 13 | 0 | BDLED-1000-90-40-SO-4-W-UNV-DP-1-CA(56) |  | (blank) | FALSE |  | TRUE | TRUE |  | Done | 0 | 0
|  | 78386 Total | [14 empty] | 0 | 0
|  | 76021 | 1 | Machine Shop Started | Regular | 10 | 10 | WBRLED-500-80-40-S-2-W-UNV-DP-1-DF-EF | Material+Cartridge | (blank) | FALSE |  | TRUE | FALSE |  |  | 3420 | 36
|  | 76021 Total | [14 empty] | 3420 | 36
| Total | [15 empty] | 276812.16 | 4535.13
18 Total | [16 empty] | 276812.16 | 4535.13
Grand Total | [16 empty] | #DIV/0! | #DIV/0!

## Production Meeting
order-line | Assembly Line | Scheduled Ship Date | Orig Sched Date | Status | Sales Category | Rework | Order | Sched Date Priority | Issue Reason | Issue Resolved | Contains Tag | Line | Rel | Open Qty | Total Sections | Product Code | Final Assembly | Open Value | Open Discount Value | Comment | Sales Rep Code | PM | Operations Meeting Comments | Production Comment | Fixture Type | Pick Status | MachineShop Delivered | Wiring Delivered | Production Issue | NT | Material Check | Missing Materials | Schedule Date | Status2 | Production Schedule | Unit Price | Unit Time | Section Completed | Remaining Section | Remaining value | Remaining Time | Issue | Rep. Count | Year | Month | Date | Order Count | Complete/Partial | Saw | BA | weld | lens
78927-1 | 10 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78927 | High Priority | Others | TRUE | waiting for wires | 1 | 1 | 37 | 37 | DIALED-22-2500-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-C(ELDOLED DUALDRIVER) | 103.6 | 13660.4 | 0 |  | Smart Li | Zahra Vatani |  |  | LA | Picked - Complete |  |  | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 369.2 | 2.8 | 0 | 37 | 13660.4 | 103.6 |  | 1 | 2019 | 2 | 6 | 3 | Partial | FALSE | TRUE |  | Done
78927-2 | 10 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 78927 | High Priority |  | FALSE |  | 2 | 1 | 17 | 17 | DIALED-22-2500-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-B1(BSL310LP)-C(ELDOLED DUALDRIVER) | 107.1 | 9937.52 | 0 |  | Smart Li | Zahra Vatani |  |  | LAE | Picked - Complete |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 584.56 | 6.3 | 0 | 17 | 9937.52 | 107.1 |  | 1 | 2019 | 2 | 6 | 3 | Partial | FALSE | TRUE |  | Done
78927-3 | 10 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 78927 | High Priority |  | FALSE |  | 3 | 1 | 22 | 22 | DIALED-24-3100-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-C(ELDOLED DUALDRIVER) | 72.6 | 10914.2 | 0 |  | Smart Li | Zahra Vatani |  |  | LB | Picked - Complete |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 496.1 | 3.3 | 14 | 8 | 3968.8 | 26.4 |  | 0 | 2019 | 2 | 6 | 3 | Partial | FALSE | TRUE |  | Done
78927-4 | 7 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78927 | High Priority | Others | TRUE | need snapping reflectors in lines 4,5,6 | 4 | 1 | 1 | 1 | SP000-SCDI-500-300-80-TW2765-SO-FL-4'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36") | 7.6 | 698.04 | 0 |  | Smart Li | Zahra Vatani |  |  | LC-4' |  |  | 2019-01-31 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 698.04 | 7.6 | 0 | 1 | 698.04 | 7.6 |  | 1 | 2019 | 2 | 6 | 3 | Partial | TRUE | TRUE |  | Done
78927-5 | 7 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78927 | High Priority |  | FALSE |  | 5 | 1 | 4 | 8 | SP000-SCDI-500-300-80-TW2765-SO-FL-16'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36") | 94.4 | 10822.08 | 0 |  | Smart Li | Zahra Vatani |  |  | LC-16' |  |  | 2019-01-31 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1352.76 | 11.8 | 0 | 8 | 10822.08 | 94.4 |  | 0 | 2019 | 2 | 6 | 3 | Partial | TRUE | TRUE |  | Done
78927-6 | 7 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78927 | High Priority |  | FALSE |  | 6 | 1 | 4 | 8 | SP000-SCDI-500-300-80-TW2765-SO-FL-16'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36")-B1(BSL310LP) | 109.6 | 11652.76 | 0 |  | Smart Li | Zahra Vatani |  |  | LCE-16' |  |  | 2019-01-31 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1456.595 | 13.7 | 0 | 8 | 11652.76 | 109.6 |  | 0 | 2019 | 2 | 6 | 3 | Partial | TRUE | TRUE |  | Done
79198-1 | 12 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 79198 | High Priority |  | FALSE |  | 1 | 1 | 6 | 12 | SCR-500-80-30-FL-14'-W-UNV-DP-1-DF | 69 | 5880 | 0 |  | Internat | Joe Brier |  |  | F1-14' | Picked - Complete |  | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 490 | 5.75 | 12 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
79375-1 | 1 | 2019-02-01 | 2019-02-01 | Wiring Started | Mockup/Samples | FALSE | 79375 | High Priority |  | FALSE |  | 1 | 1 | 1 | 1 | SK-10003-ARC-AL 1' 11 9/16"-400-80-35-SO-W-UNV-DP-1-DS-C(CORD AND PLUG) | 4.3 | 180 | 180 | SAMPLE FOR HOWARD | HOUSE | Stan Buyansky |  |  | A | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 180 | 4.3 | 0 | 1 | 180 | 4.3 |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | AfterWirin
77249-1 | 1 | 2019-01-18 |  | Machine Shop Finished | Mockup/Samples | FALSE | 77249 | High Priority | Others | FALSE | SUB ASSEMBLY | 1 | 1 | 2 | 2 | SCML-8-BW-400-MLB(16)-300-GR-80-35-AP-UNV-DP-1-CA(36)-EN(1) | 16 | 1440 | 1440 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel | Sukwhinder to advise. Edited on 1/18/2019 ::: MS: 01/22 Edited on 1/22/2019 - other lines scheduled on 1/24 Edited on 1/22/2019 :: kaushik to advise Edited on 1/29/2019 ::: Elizabeth to follow up with Bilal Edited on 2/5/2019 |  | PRIVATE OFFICE - NEIL | Picked - Complete |  | 2019-01-24 | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 720 | 8 | 0 | 2 | 1440 | 16 | Others | 1 | 2019 | 1 | 18 | 1 | Complete | TRUE | TRUE |  | Done
77249-2 | 1 | 2019-01-10 |  | Machine Shop Finished | Mockup/Samples | FALSE | 77249 | High Priority | Missing info. In SD | FALSE | SUB ASSEMBLY/NPI HEAT SINK | 2 | 1 | 1 | 7 | STSFF-SO(16-400)-80-35-AL(2)+AT(2)-MKL(10)-80-35-W-BLK-BLK-UNV-MD-1-SBS-C(REMOTE ENLIGHTED INTEGRAL SENSOR) | 40 | 1360 | 1360 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel | MS: 01/23 - Ready: Kaushik to advise Edited on 1/22/2019 ::: Kaushik to advise Edited on 1/23/2019 ::: Elizabeth to follow Edited on 1/28/2019:: Kaushik to advise Edited on 1/29/2019 ::: Ready : Jan 31st ok per Kaushik Edited on 1/30/2019::: Elizabeth to follow up with Bilal Edited on 2/5/2019 |  | MEETING ROOM 4 | Picked - Complete | 2019-01-23 |  | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 194.2857 | 5.7143 | 0 | 7 | 1360 | 40 | Missing info. In SD | 0 | 2019 | 1 | 10 | 0 | Complete | TRUE | TRUE |  | Done
77249-3 | 4 | 2019-01-24 |  | Machine Shop Finished | Mockup/Samples | FALSE | 77249 | High Priority |  | FALSE |  | 3 | 1 | 1 | 1 | ED2WD-1000-80-35-UB-8-W-W-UNV-DP-1-FL-C(REMOTE DRIVER AND ENLIGHTED INTEGRAL SENSOR) | 10.26 | 680 | 680 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel |  |  | MEETING ROOM 3 |  |  |  | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 680 | 10.26 | 0 | 1 | 680 | 10.26 |  | 0 | 2019 | 1 | 24 | 1 | Complete | TRUE | TRUE |  | Done
77249-4 | 1 | 2019-01-18 |  | Machine Shop Finished | Mockup/Samples | FALSE | 77249 | High Priority | Wrong info. In SD | FALSE | LED TAPE | 4 | 1 | 1 | 4 | SCDIPAT-REC-90-500-300-80-35-BW-0.5M-6X8-NL-W-UNV-DP-1-CTS(12)-EN(1) | 40.18 | 2100 | 2100 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel | MS: 01/24 - Ship: Kaushik to advise Edited on 1/24/2019 ::: Elizabeth to follow Edited on 1/28/2019 :: Kaushik to advise Edited on 1/29/2019 ::: Ready: Jan 31st ok per Kaushik Edited on 1/30/2019 Ready for Feb 4th. Edited on 1/31/2019::: Elizabeth to follow up with Bilal Edited on 2/5/2019 |  | HR OFFICE | Picked - Complete | 2019-01-11 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 525 | 10.045 | 0 | 4 | 2100 | 40.18 | Wrong info. In SD | 0 | 2019 | 1 | 18 | 1 | Complete | TRUE | TRUE | Ready | Done
77249-10 | 4 | 2019-01-24 |  | Machine Shop Started | Mockup/Samples | FALSE | 77249 | High Priority | Mechanical issue | FALSE | ENG. APPROVAL ???? | 10 | 1 | 1 | 1 | ED2-1000-80-35-UB-6-W-W-UNV-MD-1-90D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) | 10.26 | 510 | 510 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel | Added new parts for line: 10 only - Bom Update??? Edited on 2/5/2019 |  | MICHAEL R |  |  |  | FALSE | TRUE | NO |  |  | Machine Shop Started |  | 510 | 10.26 | 0 | 1 | 510 | 10.26 | Mechanical issue | 1 | 2019 | 1 | 24 | 1 | Complete | TRUE | TRUE |  | Done
77249-11 | 4 | 2019-01-24 |  | Machine Shop Finished | Mockup/Samples | FALSE | 77249 | High Priority |  | FALSE |  | 11 | 1 | 1 | 1 | ED2-1000-80-35-UB-6-W-W-UNV-MD-1-45D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) | 10.26 | 510 | 510 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel |  |  | LAZER |  |  |  | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 510 | 10.26 | 0 | 1 | 510 | 10.26 |  | 0 | 2019 | 1 | 24 | 1 | Complete | TRUE | TRUE |  | Done
77249-15 | 4 | 2019-01-24 |  | Machine Shop Finished | Mockup/Samples | FALSE | 77249 | High Priority |  | FALSE |  | 15 | 1 | 1 | 1 | ED2-1000-80-35-UB-4-W-W-UNV-MD-1-45D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) | 7.45 | 340 | 340 | For Axis Lines 1-2-4-7-9-12 must be ready by 1/10. Contractor waiting to install. | HOUSE | Jatin Patel |  |  | HR CORRIDOR |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 340 | 7.45 | 0 | 1 | 340 | 7.45 |  | 0 | 2019 | 1 | 24 | 1 | Complete | TRUE | TRUE |  | Done
78306-1 | 12 | 2019-02-06 | 2019-02-01 | Machine Shop Started | NPI | FALSE | 78306 | Regular | Shortage | FALSE | Extrusion/Brackets | 1 | 1 | 1 | 1 | SCILAC-AC(2)-D24-D-500-80-30-BW-6'0"-C(BRIGHT COPPER)-120-DP-2-CA(36) | 8 | 500 | 500 |  | HOUSE | Sacha Lempka |  |  | COPPER-6' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 500 | 8 | 0 | 1 | 500 | 8 | Shortage | 1 | 2019 | 2 | 6 | 1 | Complete | FALSE | FALSE |  | Done
75467-6 | 4 | 2018-11-29 | 2018-11-09 | Wiring Started | NPI | FALSE | 75467 | Regular | Others | FALSE | Ind. Eng. to check | 6 | 1 | 3 | 6 | NPI-N18003-GPDLED-1000-80-TW2750-RG2-14-W-O(DALIDT6)-1-CA(72)-LBC | 0 | 3600 | 3600 | HARVARD NPI - MUST DO ON TIME!!! RE-SCHEDULED TO NOV 29th (from 11/09) - PER FAIZ | HOUSE | Stan Buyansky | Carlos to advise Faiz Edited on 1/21/2019 ::: Kaushik to follow Edited on 1/22/2019 |  | L-04-14' |  |  |  | FALSE | FALSE | NO |  | 2018-12-28 | Wiring Issue |  | 600 | 20 | 0 | 6 | 3600 | 120 |  | 1 | 2018 | 11 | 29 | 1 | Complete | TRUE | TRUE |  | Done
76884-1 | 1 | 2019-02-06 | 2018-12-18 | Wiring Started | NPI | FALSE | 76884 | Regular | Mechanical issue | FALSE | Light guide- NPI | 1 | 1 | 2 | 4 | NPI-N18008-SKPE-10004-SL60/40-CIR-AL# 12' 6.75"-1000-80-35-SO-W-UNV-D-1-CA(36) | 0 | 1840 | 1840 |  | HOUSE | Stan Buyansky |  |  | A |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Wiring Issue |  | 460 | 0 | 0 | 4 | 1840 | 0 | Mechanical issue | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
78982-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78982 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG15 | 9.4 | 1020 | 0 |  | LS Phill | Gaurav Jain |  |  | AL7-6' |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 510 | 4.7 | 0 | 2 | 1020 | 9.4 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE |  | Done
78986-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78986 | Regular |  | FALSE |  | 1 | 1 | 4 | 4 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG15 | 18.4 | 2040 | 0 |  | LS Phill | Gaurav Jain |  |  | AL7-6' | Picked - Complete | 2019-01-29 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 510 | 4.6 | 0 | 4 | 2040 | 18.4 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE
79106-1 | 12 | 2019-02-07 | 2019-02-07 | Packaging Finished | Regular | FALSE | 79106 | Priority | Others | FALSE |  | 1 | 1 | 3 | 3 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG9 | 14.1 | 1710 | 0 | NEEDS ON SITE FOR FEB 13TH SHIPPING TO: 10 W. Manor Way Robbinsville NJ 08691 United States | LS Phill | Gaurav Jain |  |  | LT-09-6' G | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 570 | 4.7 | 3 | 0 | 0 | 0 | Others | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
79106-2 | 12 | 2019-02-07 | 2019-02-07 | Packaging Finished | Regular | FALSE | 79106 | Priority | Others | FALSE |  | 2 | 1 | 3 | 3 | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-D | 14.1 | 1710 | 0 | NEEDS ON SITE FOR FEB 13TH SHIPPING TO: 10 W. Manor Way Robbinsville NJ 08691 United States | LS Phill | Gaurav Jain |  |  | LT-09-6' F | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 570 | 4.7 | 3 | 0 | 0 | 0 | Others | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
78822-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78822 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST-B1(BSL310LP) | 15 | 960 | 0 |  | TLS | Jessica Kennedy |  |  | L7-4' | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 480 | 7.5 | 0 | 2 | 960 | 15 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78822-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78822 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | BMRLED-750-80-30-ASO-6'-W-UNV-DP-1-ST | 5.9 | 480 | 0 |  | TLS | Jessica Kennedy |  |  | L2-6' | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 480 | 5.9 | 0 | 1 | 480 | 5.9 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78822-3 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78822 | Regular |  | FALSE |  | 3 | 1 | 3 | 3 | CCL-SL-500-80-30-CL(10')-W-UNV-DP-1-C | 28.5 | 2400 | 0 |  | TLS | Jessica Kennedy |  |  | L5-10' | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 800 | 9.5 | 0 | 3 | 2400 | 28.5 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78822-4 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78822 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | CCL-SL-500-80-30-CL(7')-W-UNV-DP-1-C | 7 | 560 | 0 |  | TLS | Jessica Kennedy |  |  | L5-7' | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 560 | 7 | 0 | 1 | 560 | 7 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78650-1 | 15 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 78650 | High Priority |  | FALSE |  | 1 | 1 | 3 | 3 | BBDLED-1000-80-35-SO-8'-W-UNV-DP-1-CT15(36) | 27 | 2040 | 0 | MUST SHIP 2/4 | westernl | Sacha Lempka | Ship: Feb 5th Edited on 2/5/2019 |  | A-8' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 680 | 9 | 0 | 3 | 2040 | 27 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
78650-2 | 15 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 78650 | High Priority |  | FALSE |  | 2 | 1 | 12 | 12 | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-TB15 | 36 | 4080 | 0 | MUST SHIP 2/4 | westernl | Sacha Lempka |  |  | A-4' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 340 | 3 | 0 | 12 | 4080 | 36 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | FALSE |  | Done
78651-1 | 12 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78651 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | SLWLED-SL 75/25-1000-80-35-RE-6-W-UNV-DP-1 | 6.8 | 670.6 | 0 |  | westernl | Sacha Lempka | Ship: Feb 6th Edited on 2/5/2019 |  | LW2-6 | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 670.6 | 6.8 | 0 | 1 | 670.6 | 6.8 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78651-2 | 12 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78651 | Regular |  | FALSE |  | 2 | 1 | 8 | 8 | SLWLED-SL 75/25-1000-80-35-RE-8-W-UNV-DP-1 | 54.4 | 7153.2 | 0 |  | westernl | Sacha Lempka |  |  | LW2-8 | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 894.15 | 6.8 | 0 | 8 | 7153.2 | 54.4 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78651-3 | 12 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78651 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | SLWLED-SL 75/25-1000-80-35-RE-12-W-UNV-DP-1 | 9 | 1341.2 | 0 |  | westernl | Sacha Lempka |  |  | LW2-12 | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 1341.2 | 9 | 0 | 1 | 1341.2 | 9 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78590-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78590 | Regular |  | FALSE |  | 1 | 1 | 9 | 9 | STSLF-SO-400-80-35-12'-BLK-UNV-MD-1-SG9 | 63 | 7884 | 0 |  | TLS | Jessica Kennedy |  |  | D-12' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 876 | 7 | 0 | 9 | 7884 | 63 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78875-1 | 4 | 2019-02-11 | 2019-02-11 | Scheduled/Released | Mockup/Samples | FALSE | 78875 | High Priority |  | FALSE |  | 1 | 1 | 2 | 8 | STFC-SLI(4-350)-DSO(4-400)-90-30-AL(4)-W-UNV-MD-1-CA(36)-RC | 43 | 1520 | 0 | MOCK UP / SAMPLE ORDER SHIP BY FEB. 8TH IF POSSIBLE | CHARRON | Sacha Lempka |  |  | A | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Scheduled/Released |  | 190 | 5.375 | 0 | 8 | 1520 | 43 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78559-1 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 1 | 1 | 39 | 39 | DIALED-22-2500-80-35-VL-W-277-DP-1-TG9-FW(6) | 113.1 | 9555 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F01A |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 245 | 2.9 | 0 | 39 | 9555 | 113.1 |  | 1 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-2 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 2 | 1 | 80 | 80 | DIALED-22-4400-80-35-VL-W-277-DP-1-TG9-FW(6) | 232 | 19600 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F01B |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 245 | 2.9 | 0 | 80 | 19600 | 232 |  | 0 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-3 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 3 | 1 | 11 | 11 | DIALED-24-7000-80-35-VL-W-UNV-DP-1-TG9-FW(6) | 38.5 | 3850 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F02 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 350 | 3.5 | 0 | 11 | 3850 | 38.5 |  | 0 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-4 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 78559 | Regular |  | FALSE |  | 4 | 1 | 5 | 5 | MBSLED-600-80-35-S-4'-W-UNV-DP-1-S | 19.5 | 1500 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F03-4' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 300 | 3.9 | 0 | 5 | 1500 | 19.5 |  | 1 | 2019 | 2 | 13 | 2 | Partial | TRUE | TRUE |  | Done
78559-5 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 5 | 1 | 22 | 22 | AULED-22-2500-80-35-SO-W-277-DP-1-TG9-FW(6) | 55 | 4510 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F04 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 205 | 2.5 | 0 | 22 | 4510 | 55 |  | 0 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-6 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 6 | 1 | 33 | 33 | DIALED-22-2500-80-35-VL-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) | 211.2 | 15510 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F1A/EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 470 | 6.4 | 0 | 33 | 15510 | 211.2 |  | 0 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-7 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 7 | 1 | 10 | 10 | DIALED-22-4400-80-35-VL-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) | 64 | 4700 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F1B/EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 470 | 6.4 | 0 | 10 | 4700 | 64 |  | 0 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-8 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 78559 | Regular |  | FALSE |  | 8 | 1 | 1 | 1 | MBSLED-600-80-35-S-4'-W-UNV-DP-1-S-B1(BSL310LP) | 7.8 | 525 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F03-4' EM |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 525 | 7.8 | 0 | 1 | 525 | 7.8 |  | 0 | 2019 | 2 | 13 | 2 | Partial | TRUE | TRUE |  | Done
78559-9 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78559 | Regular |  | FALSE |  | 9 | 1 | 1 | 1 | AULED-22-2500-80-35-SO-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) | 6 | 430 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F04/EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 430 | 6 | 0 | 1 | 430 | 6 |  | 0 | 2019 | 2 | 13 | 2 | Partial | FALSE | FALSE
78559-10 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 78559 | Regular |  | FALSE |  | 10 | 1 | 2 | 2 | MBLED-500-80-35-S-4'-W-UNV-DP-1-CA(36) | 8.3 | 600 | 0 | MUST SHIP BY FEB 14 | Internat | Rohan Srivastava |  |  | F05-4' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 300 | 4.15 | 0 | 2 | 600 | 8.3 |  | 0 | 2019 | 2 | 13 | 2 | Partial | TRUE | TRUE |  | Done
79342-1 | 10 | 2019-02-07 | 2019-02-07 | Scheduled/Released | Regular | FALSE | 79342 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | AULED-24-3100-80-30-SO-W-277-DP-1-TB15-FW(6) | 3 | 265 | 0 |  | Internat | Joe Brier |  |  | LF06 |  |  |  | FALSE | FALSE | NO | Material |  | Scheduled/Released |  | 265 | 3 | 0 | 1 | 265 | 3 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
76704-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 76704 | High Priority |  | FALSE |  | 1 | 1 | 1 | 2 | BRLED-400-80-35-FL-12' 6"-W-277-DP-1-DS | 16 | 780 | 0 | MUST SHIP ASAP, HIGH PRIORITY | Internat | Rohan Srivastava |  |  | F24-12' 6" |  | 2019-02-04 | 2019-02-05 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 390 | 8 | 0 | 2 | 780 | 16 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
73251-28 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 28 | 1 | 1 | 7 | BMRLED-750-90-35-FL-83'7 1/8"-W-UNV-DP-1+E(6)-DF | 67.5 | 4152 | 0 |  | Internat | Gagandeep Singh |  |  | F1-83'7-1/8" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 593.1429 | 9.6429 | 0 | 7 | 4152 | 67.5 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-29 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 29 | 1 | 1 | 1 | BMRLED-750-90-35-FL-97"-W-UNV-DP-1-DF | 8.7 | 400 | 0 |  | Internat | Gagandeep Singh |  |  | F1A-97" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 400 | 8.7 | 0 | 1 | 400 | 8.7 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-30 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 30 | 1 | 3 | 3 | BMRLED-750-90-35-FL-2-W-UNV-DP-1-DF | 10.5 | 300 | 0 |  | Internat | Gagandeep Singh |  |  | F1B-2' - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 100 | 3.5 | 0 | 3 | 300 | 10.5 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-31 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 31 | 1 | 1 | 1 | BMRLED-750-90-35-FL-57 1/2"-W-UNV-DP-1-DF | 6.1 | 240 | 0 |  | Internat | Gagandeep Singh |  |  | F1C-57-1/2" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 240 | 6.1 | 0 | 1 | 240 | 6.1 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-32 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority | Shortage | FALSE | Extrusion 12' | 32 | 1 | 1 | 4 | BMPRLED-OPRO(1)-750-90-35-FL-32'3 7/8"-W-UNV-DP-1+E(1)-DF | 29.5 | 1594 | 0 |  | Internat | Gagandeep Singh |  |  | F1W-20'3-7/8"X12' - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 398.5 | 7.375 | 0 | 4 | 1594 | 29.5 | Shortage | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-33 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 33 | 1 | 1 | 4 | BMPRLED-OPRO(1)-750-90-35-FL-42'1/4"-W-UNV-DP-1+E(4)-DF | 57 | 2104 | 0 |  | Internat | Gagandeep Singh |  |  | F1W-21'7 3/4"X20'4-1/2" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 526 | 14.25 | 0 | 4 | 2104 | 57 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-36 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 36 | 1 | 1 | 3 | BMRLEDPAT-OPI-90-750-80-35-SO-13'5 5/8"-EX-W-UNV-DP-1-DF | 15 | 950 | 0 |  | Internat | Gagandeep Singh |  |  | F7-5'3-1/4"X8'2-3/8" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 316.6667 | 5 | 0 | 3 | 950 | 15 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-37 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 37 | 1 | 1 | 4 | BMRLEDPAT-OPI-90-750-80-35-SO-31'1"-EX-W-UNV-DP-1-DF | 26 | 1800 | 0 |  | Internat | Gagandeep Singh |  |  | F7-9'11-5/8"X22'-3/8" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 450 | 6.5 | 0 | 4 | 1800 | 26 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-41 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 41 | 1 | 1 | 1 | BMRLED-750-90-35-FL-96 3/4"-W-UNV-DP-1-DF | 6.1 | 400 | 0 |  | Internat | Gagandeep Singh |  |  | F1A-96-3/4" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 400 | 6.1 | 0 | 1 | 400 | 6.1 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-42 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 42 | 1 | 1 | 1 | BMRLED-750-90-35-FL-57 3/4"-W-UNV-DP-1-DF | 6.1 | 240 | 0 |  | Internat | Gagandeep Singh |  |  | F1C-57-3/4" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 240 | 6.1 | 0 | 1 | 240 | 6.1 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
73251-43 | 7 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 73251 | High Priority |  | FALSE |  | 43 | 1 | 1 | 3 | BMPRLED-750-90-35-FL-28'7 1/4"-W-UNV-DP-1-DF | 24.9 | 1392 | 0 |  | Internat | Gagandeep Singh |  |  | F1W-28'7-1/4" - 22ND FL | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 464 | 8.3 | 0 | 3 | 1392 | 24.9 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
67150-41 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 41 | 1 | 10 | 20 | B6RLED-400-80-30-FL-15-W-120-DP-1-ST-FW(6) | 130 | 8350 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02D-15'-BASEMNT FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 417.5 | 6.5 | 0 | 20 | 8350 | 130 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-42 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 42 | 1 | 1 | 2 | B6RLED-400-80-30-FL-15-W-120-DP-E(1)-ST-FW(6) | 13.4 | 835 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02D-15'EM-BASEMNT FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 417.5 | 6.7 | 0 | 2 | 835 | 13.4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-43 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 43 | 1 | 5 | 5 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | 44 | 2800 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-10'-1ST FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 8.8 | 0 | 5 | 2800 | 44 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-44 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 44 | 1 | 4 | 8 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | 52 | 3340 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-15'-1ST FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 417.5 | 6.5 | 0 | 8 | 3340 | 52 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-45 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 45 | 1 | 4 | 4 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) | 25.2 | 1140 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02C-5'-1ST FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 285 | 6.3 | 0 | 4 | 1140 | 25.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-46 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 46 | 1 | 3 | 3 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | 26.4 | 1680 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-10'-2ND FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 8.8 | 0 | 3 | 1680 | 26.4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-47 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 47 | 1 | 4 | 8 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | 52 | 3340 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-15'-2ND FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 417.5 | 6.5 | 0 | 8 | 3340 | 52 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-48 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 48 | 1 | 5 | 5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) | 31.5 | 1425 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02C-5'-2ND FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 285 | 6.3 | 0 | 5 | 1425 | 31.5 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-49 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 49 | 1 | 12 | 12 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | 105.6 | 6720 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-10'-3RD FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 8.8 | 0 | 12 | 6720 | 105.6 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-50 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 50 | 1 | 5 | 10 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | 65 | 4175 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-15'-3RD FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 417.5 | 6.5 | 0 | 10 | 4175 | 65 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-51 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 51 | 1 | 5 | 5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) | 31.5 | 1425 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02C-5'-3RD FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 285 | 6.3 | 0 | 5 | 1425 | 31.5 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-52 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 52 | 1 | 14 | 14 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | 123.2 | 7840 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-10'-4TH FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 8.8 | 0 | 14 | 7840 | 123.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-53 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 53 | 1 | 9 | 18 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) | 117 | 7515 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-15'-4TH FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 417.5 | 6.5 | 0 | 18 | 7515 | 117 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-55 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 55 | 1 | 1 | 1 | B6RLED-750-80-30-FL-4-W-120-DP-1-ST-FW(6) | 3.3 | 230 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-4'-5TH FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 230 | 3.3 | 0 | 1 | 230 | 3.3 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-56 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 56 | 1 | 3 | 3 | B6RLED-750-80-30-FL-5-W-120-DP-1-ST-FW(6) | 18.9 | 855 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-5'-5TH FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 285 | 6.3 | 0 | 3 | 855 | 18.9 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-57 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 57 | 1 | 10 | 10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) | 88 | 5600 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-02B-10'-5TH FL |  | 2019-01-31 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 8.8 | 0 | 10 | 5600 | 88 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE |  | Done
67150-58 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 58 | 1 | 1 | 2 | BRLED-500-80-30-FL-13-W-120-DP-1-D | 13.3 | 715 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-63D-13'-BASEMNT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 357.5 | 6.65 | 0 | 2 | 715 | 13.3 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-59 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 59 | 1 | 6 | 12 | BRLED-500-80-30-FL-18-W-120-DP-1-D | 97.2 | 5940 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-63D-18'-BASEMNT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 495 | 8.1 | 0 | 12 | 5940 | 97.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-60 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 60 | 1 | 1 | 2 | BRLED-500-80-30-FL-17-W-120-DP-E(1)-D | 16.5 | 935 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-63D-17'EM-BASEMNT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 467.5 | 8.25 | 0 | 2 | 935 | 16.5 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
67150-61 | 15 | 2019-02-11 |  | Machine Shop Finished | Regular | FALSE | 67150 | Regular |  | FALSE |  | 61 | 1 | 6 | 12 | BRLED-500-80-30-FL-18-W-120-DP-E(1)-D | 99 | 5940 | 0 | do not ship before 1/4/2019 | Internat | Gagandeep Singh |  |  | LT-63D-18'EM-BASEMNT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 495 | 8.25 | 0 | 12 | 5940 | 99 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
70634-1 | 4 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 70634 | High Priority |  | FALSE | Sections | 1 | 1 | 1 | 20 | SP18083-CCH-SL-1100-80-2740-CP(110)-W-120-O(DMX)-2-C | 280.77 | 12320 | 0 | Ship complete | Internat | Gagandeep Singh | Elizabeth to follow up with Bilal. Edited on 2/1/2019 |  | LF05-110' INSIDE | Picked - Complete |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 616 | 14.0385 | 0 | 20 | 12320 | 280.77 |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
70634-2 | 4 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 70634 | High Priority | Wrong part in BOM | TRUE | Eng. to Approved END Plates | 2 | 1 | 1 | 28 | SP18083-CCH-SL-1100-80-2740-CP(116)-W-120-O(DMX)-2-C | 374.74 | 12992 | 0 | Ship complete | Internat | Gagandeep Singh | Ship: Feb 6th Edited on 2/5/2019 |  | LF05-116' INSIDE | Picked - Complete |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 464 | 13.3836 | 0 | 28 | 12992 | 374.74 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
70634-3 | 4 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 70634 | High Priority | Wrong part in BOM | TRUE | Eng. to Approved END Plates | 3 | 1 | 1 | 21 | SP18083-CCH-SL-1100-80-2740-CP(110)-W-120-O(DMX)-2-C | 280.77 | 12320 | 0 | Ship complete | Internat | Gagandeep Singh |  |  | LF05-110' OUTSIDE | Picked - Complete |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 586.6667 | 13.37 | 0 | 21 | 12320 | 280.77 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
70634-4 | 4 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 70634 | High Priority | Wrong info. In SD | TRUE | WRONG QTY OF ITEM NO.10 | 4 | 1 | 1 | 28 | SP18083-CCH-SL-1100-80-2740-CP(116)-W-120-O(DMX)-3-C | 471.77 | 12992 | 0 | Ship complete | Internat | Gagandeep Singh |  |  | LF05-116' OUTSIDE | Picked - Complete |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 464 | 16.8489 | 0 | 28 | 12992 | 471.77 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78614-1 | 7 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78614 | High Priority | Shortage | FALSE | EXTRUSION?? | 1 | 1 | 24 | 24 | WBDIWLED-500-500-80-35-SO-SO-2-BLK-UNV-DP-1-BF | 158.4 | 9120 | 0 | MUST SHIP NO LATER THAN FEB 8TH - NO BUFFER | LS Phill | Jessica Kennedy |  |  | W2 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 380 | 6.6 | 0 | 24 | 9120 | 158.4 | Shortage | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
67875-1 | 12 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 67875 | Regular |  | FALSE |  | 1 | 1 | 1 | 14 | CCL-SL-300-80-30-CP(83' 6")-W-UNV-DP-1-AC | 82 | 5850 | 0 |  | HOUSE | Gagandeep Singh |  |  | LF15-8'5"X33'4" |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 417.8571 | 5.8571 | 0 | 14 | 5850 | 82 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE | Ready
64752-8 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 8 | 1 | 12 | 24 | BMRLED-500-80-35-ASO-16-W-UNV-O(DEXAL)-1-TB15 | 162 | 9600 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | B-16' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 400 | 6.75 | 0 | 24 | 9600 | 162 |  | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-10 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 10 | 1 | 9 | 27 | BMRLED-500-80-35-FL-30-W-UNV-O(DEXAL)-1-TG9 | 238.5 | 13500 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C10-30' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 500 | 8.8333 | 27 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-11 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 11 | 1 | 5 | 15 | BMRLED-500-80-35-FL-36-W-UNV-O(DEXAL)-1-TG15 | 145.5 | 9000 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C11-36' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 600 | 9.7 | 15 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-12 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 12 | 1 | 1 | 4 | BMRLED-500-80-35-FL-46-W-UNV-O(DEXAL)-1-TG9 | 39.2 | 2300 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C13-46' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 575 | 9.8 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-13 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 13 | 1 | 1 | 5 | BMRLED-500-80-35-FL-60-W-UNV-O(DEXAL)-1-TG9 | 49.3 | 3000 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C14-60' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 600 | 9.86 | 5 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-14 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular | Shortage | FALSE | Driver DR18771 | 14 | 1 | 116 | 116 | BMRLED-500-80-35-FL-6-W-UNV-O(DEXAL)-1-TG9 | 754 | 34800 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh | ETA: 2/7 - If we ship partial it would be Feb 6th - Joshua to advise or ship complete Edited on 2/5/2019 |  | C2-6'-TG9 |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 300 | 6.5 | 0 | 116 | 34800 | 754 | Shortage | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-15 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular | Wrong info. In SD | TRUE | Quantity | 15 | 1 | 32 | 32 | BMRLED-500-80-35-FL-8-W-UNV-O(DEXAL)-1-TG15 | 204.8 | 12800 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C3-8'-TG15 |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 400 | 6.4 | 32 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-16 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 16 | 1 | 1 | 1 | BMRLED-500-80-35-FL-10-W-UNV-O(DEXAL)-1-TG9 | 9 | 500 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C4-10' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 500 | 9 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-17 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 17 | 1 | 1 | 2 | BMRLED-500-80-35-FL-14-W-UNV-O(DEXAL)-1-TG9 | 13.7 | 700 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C6-14' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 350 | 6.85 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-18 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 18 | 1 | 1 | 2 | BMRLED-500-80-35-FL-16-W-UNV-O(DEXAL)-1-TG9 | 13.7 | 800 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C7-16' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 400 | 6.85 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-19 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 19 | 1 | 2 | 4 | BMRLED-500-80-35-FL-18-W-UNV-O(DEXAL)-1-TG9 | 33 | 1800 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C8-18' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 450 | 8.25 | 3 | 1 | 450 | 8.25 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-20 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 20 | 1 | 9 | 18 | BMRLED-500-80-35-FL-20-W-UNV-O(DEXAL)-1-TG9 | 148.5 | 9000 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C9-20' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 500 | 8.25 | 19 | -1 | -500 | -8.25 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-22 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular | Wrong part in BOM | TRUE | Driver | 22 | 1 | 1 | 1 | PRWLED-500-80-35-S-10-W-277-DP-1 | 8.2 | 450 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | D-10' |  | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 450 | 8.2 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-23 | 1 | 2019-02-05 |  | Machine Shop Finished | Regular | FALSE | 64752 | Regular | Shortage | FALSE | Extrusion | 23 | 1 | 8 | 16 | PRWLED-500-80-35-S-16-W-277-DP-1 | 99.2 | 5760 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | D1-16' |  | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 360 | 6.2 | 8 | 8 | 2880 | 49.6 | Shortage | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-24 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 24 | 1 | 1 | 4 | PRWLED-500-80-35-S-28-W-277-DP-1 | 20.5 | 1260 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | D2-28' |  | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 315 | 5.125 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-30 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular | Others | TRUE | MISSING DUST COVER | 30 | 1 | 26 | 26 | BBWDILED-640-400-80-35-SO-5-W-UNV-DP-1-D | 291.2 | 10400 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | TT-5' |  | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 400 | 11.2 | 19 | 7 | 2800 | 78.4 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-31 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 31 | 1 | 2 | 2 | BMRLED-500-80-35-FL-6-W-UNV-O(DEXAL)-1-DF | 13 | 600 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C2-6'-DF |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 300 | 6.5 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-37 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 37 | 1 | 12 | 12 | BMRLED-500-80-35-FL-4-W-UNV-O(DEXAL)-1-TG15 | 39.6 | 2400 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C1-4' |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 200 | 3.3 | 6 | 6 | 1200 | 19.8 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
64752-40 | 1 | 2019-02-05 |  | Wiring Started | Regular | FALSE | 64752 | Regular |  | FALSE |  | 40 | 1 | 10 | 10 | BMRLED-500-80-35-FL-6-W-UNV-DP-1-TG9 | 67 | 3000 | 0 | **LINE 4 MOUNTING KITS TO BE SHIPPED AHEAD OF TIME** | HOUSE | Gagandeep Singh |  |  | C2-DP |  | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 300 | 6.7 | 0 | 10 | 3000 | 67 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
78720-1 | 7 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 78720 | High Priority | Missing info. In SD | TRUE | Missing Bottom View | 1 | 1 | 1 | 8 | SCPLED-OPRI(4)-300-80-35-FL-52-W-UNV-DP-1-ST-C(10'X6'X10' PRE MITTERED CORNER) | 57 | 5540 | 0 |  | Internat | Robert Lipura |  |  | F2-40'X6' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 692.5 | 7.125 | 0 | 8 | 5540 | 57 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
78511-1 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78511 | Regular | Shortage | FALSE | Extrusion | 1 | 1 | 1 | 16 | CCL-SL-300-80-35-CL(184')-W-277-DP-2-AC | 147 | 15640 | 0 |  | HIGH | Rohan Srivastava |  |  | LC-184' |  |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 977.5 | 9.1875 | 0 | 16 | 15640 | 147 | Shortage | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
78511-2 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78511 | Regular |  | FALSE |  | 2 | 1 | 1 | 4 | CCL-SL-300-80-35-CL(45')-W-277-DP-1-AC | 37.8 | 3825 | 0 |  | HIGH | Rohan Srivastava |  |  | LC-45' |  |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 956.25 | 9.45 | 0 | 4 | 3825 | 37.8 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
76762-4 | 7 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 76762 | High Priority |  | FALSE |  | 4 | 1 | 1 | 16 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-48-EX-W-UNV-DP-1+E(2)-DS | 88 | 4280 | 0 | MUST SHIP BY 1/28 | Internat | Rohan Srivastava |  |  | F2-48'/1 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 267.5 | 5.5 | 0 | 16 | 4280 | 88 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | Ready
76762-5 | 7 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 76762 | High Priority |  | FALSE |  | 5 | 1 | 1 | 16 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-48-EX-W-UNV-DP-1+E(2)-DS | 88 | 4280 | 0 | MUST SHIP BY 1/28 | Internat | Rohan Srivastava |  |  | F2-48'/2 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 267.5 | 5.5 | 0 | 16 | 4280 | 88 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | Ready
76762-6 | 7 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 76762 | High Priority |  | FALSE |  | 6 | 1 | 1 | 9 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-28-EX-W-UNV-DP-1+E(1)-DS | 46 | 2380 | 0 | MUST SHIP BY 1/28 | Internat | Rohan Srivastava |  |  | F2-28' |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 264.4444 | 5.1111 | 0 | 9 | 2380 | 46 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | Ready
76762-7 | 7 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 76762 | High Priority | Wrong info. In SD | TRUE | Wiring Diagram | 7 | 1 | 1 | 10 | SP18415(1)-BMRLEDPAT-REC-90-1200-80-35-SO-FL-12'X20'-EX-W-UNV-DP-1-ST | 67 | 4640 | 0 | MUST SHIP BY 1/28 | Internat | Rohan Srivastava |  |  | F3-64' REC |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 464 | 6.7 | 0 | 10 | 4640 | 67 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | Ready
76762-8 | 7 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 76762 | High Priority | Wrong part in BOM | TRUE | Drivers | 8 | 1 | 1 | 10 | BMRLEDPAT-REC-90-400-80-35-SO-FL-9'X25'-EX-W-UNV-DP-1-DS | 63 | 4880 | 0 | MUST SHIP BY 1/28 | Internat | Rohan Srivastava |  |  | F3A-68' REC |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 488 | 6.3 | 0 | 10 | 4880 | 63 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | Ready
75728-1 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 75728 | High Priority |  | FALSE |  | 1 | 1 | 4 | 4 | SCR-500-80-30-FL-4-W-120-DP-1-TG9 | 12.4 | 1120 | 0 | MUST SHIP 2/8/19 | HiTec QC | Sacha Lempka |  |  | A-4 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 280 | 3.1 | 0 | 4 | 1120 | 12.4 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
75728-2 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 75728 | High Priority |  | FALSE |  | 2 | 1 | 1 | 1 | SCR-500-80-30-FL-8-W-120-DP-1-TG9 | 5.5 | 560 | 0 | MUST SHIP 2/8/19 | HiTec QC | Sacha Lempka |  |  | A-8 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 5.5 | 0 | 1 | 560 | 5.5 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
75728-3 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 75728 | High Priority |  | FALSE |  | 3 | 1 | 1 | 1 | SCR-300-80-30-FL-8-W-120-DP-1-TG9 | 5.5 | 560 | 0 | MUST SHIP 2/8/19 | HiTec QC | Sacha Lempka |  |  | AA-8 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 5.5 | 0 | 1 | 560 | 5.5 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
75728-4 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 75728 | High Priority |  | FALSE |  | 4 | 1 | 1 | 3 | SCR-500-80-30-FL-36-W-120-DP-1-TG9 | 24.2 | 2520 | 0 | MUST SHIP 2/8/19 | HiTec QC | Sacha Lempka |  |  | A-36 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 840 | 8.0667 | 0 | 3 | 2520 | 24.2 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
75728-5 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 75728 | High Priority |  | FALSE |  | 5 | 1 | 2 | 4 | SCR-500-80-30-FL-16-W-120-DP-1-TG9 | 23.1 | 2240 | 0 | MUST SHIP 2/8/19 | HiTec QC | Sacha Lempka |  |  | A-16 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 560 | 5.775 | 0 | 4 | 2240 | 23.1 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
75728-9 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 75728 | High Priority |  | FALSE |  | 9 | 1 | 1 | 16 | SCRPAT-OPR-90(2)-300-80-30-FL-159'-EX-W-120-DP-1-TG9 | 120 | 10990 | 0 | MUST SHIP 2/8/19 | HiTec QC | Sacha Lempka |  |  | AA-98X51X10 | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 686.875 | 7.5 | 0 | 16 | 10990 | 120 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE | ToDo
77808-1 | 18 | 2019-02-04 | 2019-02-04 | Order UnShipped | Regular | FALSE | 77808 | Regular |  | FALSE |  | 1 | 1 | 15 | 15 | PWSLED-1000-90-35-S-4-W-120-DP-1-SB15 | 68.4 | 5700 | 0 |  | HiTec QC | Sacha Lempka |  |  | L6-L6A | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Order UnShipped |  | 380 | 4.56 | 18 | -3 | -1140 | -13.68 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
77808-2 | 18 | 2019-02-04 | 2019-02-04 | Order UnShipped | Regular | FALSE | 77808 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | PWSLED-1000-90-35-S-4-W-120-DP-1-S | 11.4 | 1140 | 0 |  | HiTec QC | Sacha Lempka |  |  | L6-S | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Order UnShipped |  | 380 | 3.8 | 0 | 3 | 1140 | 11.4 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
77741-5 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 5 | 1 | 3 | 3 | BMWDLED-750-80-30-ASO-4'-W-UNV-DP-1 | 12 | 975 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | W5-4' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 325 | 4 | 0 | 3 | 975 | 12 |  | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77741-6 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 6 | 1 | 2 | 2 | BMWDLED-750-80-30-ASO-5'-W-UNV-DP-1 | 6.6 | 820 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | W5-5' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 410 | 3.3 | 0 | 2 | 820 | 6.6 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77741-8 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Started | Regular | FALSE | 77741 | Regular |  | FALSE |  | 8 | 1 | 1 | 1 | SCSPAT-OPR-90(2)-500-80-30-FL-12'-NL-W-UNV-BI-1-SC | 11.8 | 1175 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk | MS: Feb 4th - Kaushik to advise??? Edited on 2/5/2019 |  | G1-4.5-4'X4'X4' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1175 | 11.8 | 0 | 1 | 1175 | 11.8 |  | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE | Ready
77741-9 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 9 | 1 | 1 | 3 | SCSPAT-OPR-90(1)-500-80-30-FL-12'-NL-W-UNV-BI-1-SC | 16 | 1075 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk | Partial : Joshua to advise?? Edited on 2/5/2019 |  | G1-L-6'X6' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 358.3333 | 5.3333 | 0 | 3 | 1075 | 16 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE | Ready | Done
77741-10 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Started | Regular | FALSE | 77741 | Regular | Wrong info. In SD | TRUE | LED Tape Length | 10 | 1 | 1 | 2 | SCRPAT-OPR-90(2)-500-80-30-FL-15' 1-3/4-NL-W-UNV-BI-1-DS | 15.8 | 1500 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G2-1.66 | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 750 | 7.9 | 0 | 2 | 1500 | 15.8 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE | Ready
77741-11 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 11 | 1 | 1 | 1 | SCRPAT-OPR-90(2)-500-80-30-FL-11' 2-1/2-NL-W-UNV-BI-1-DS | 11.8 | 1175 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G2-2.33 | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1175 | 11.8 | 0 | 1 | 1175 | 11.8 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE | Ready | Done
77741-12 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 12 | 1 | 1 | 1 | SCRPAT-OPR-90(2)-500-80-30-FL-10' 9-1/2-NL-W-UNV-BI-1-DS | 11.8 | 1175 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G2-2.66 | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1175 | 11.8 | 0 | 1 | 1175 | 11.8 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE | Ready | Done
77741-13 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Started | Regular | FALSE | 77741 | Regular |  | FALSE |  | 13 | 1 | 1 | 2 | SCRPAT-OPR-90(2)-500-80-30-FL-12'1-1/2-NL-W-UNV-BI-1-DS | 11.8 | 1175 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G2-3.33 | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 587.5 | 5.9 | 0 | 2 | 1175 | 11.8 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE | Ready
77741-15 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Started | Regular | FALSE | 77741 | Regular |  | FALSE |  | 15 | 1 | 1 | 1 | SCR-500-80-30-FL-4'2"-W-UNV-BI-1-DS | 24 | 325 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G2-5' | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 325 | 24 | 0 | 1 | 325 | 24 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | FALSE | Ready
77741-17 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 17 | 1 | 1 | 3 | SCR-500-80-30-FL-30-W-UNV-BI-1-DS | 28.8 | 1950 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G2-30' |  | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 650 | 9.6 | 0 | 3 | 1950 | 28.8 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77741-18 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 18 | 1 | 5 | 5 | SCS-500-80-30-FL-4'-W-UNV-BI-1-SC | 15.2 | 1625 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G1-4' |  | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 325 | 3.04 | 0 | 5 | 1625 | 15.2 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77741-19 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 77741 | Regular |  | FALSE |  | 19 | 1 | 2 | 2 | SCS-500-80-30-FL-8'-W-UNV-BI-1-SC | 6 | 1300 | 0 | LINES 5 6 7 HAS TO BE DELIVERED ONSITE BY FEB 11TH ( | Enterpri | Jessica Pasternyk |  |  | G1-8' |  | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 650 | 3 | 0 | 2 | 1300 | 6 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
79098-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 79098 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | WBRLED-500-90-30-S-4'-AP-UNV-DP-1-D | 7 | 934 | 0 |  | Enterpri | Jessica Pasternyk |  |  | A-4' |  |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 467 | 3.5 | 0 | 2 | 934 | 7 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
79285-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 79285 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BRLED-500-80-30-FL-11-W-120-DP-1-DF | 9 | 880 | 0 |  | LtgUnlim | Rajithan Sivapatharajahon |  |  | LC-11' |  | 2019-02-04 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 880 | 9 | 0 | 1 | 880 | 9 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
79240-1 | 10 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 79240 | Regular |  | FALSE |  | 1 | 1 | 6 | 6 | DIALED-22-3000-90-35-VL-W-120-DP-1-ST | 16.8 | 1650 | 0 |  | Internat | Rohan Srivastava |  |  | A2 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 275 | 2.8 | 0 | 6 | 1650 | 16.8 |  | 1 | 2019 | 2 | 6 | 1 | Complete | FALSE | FALSE
79240-2 | 10 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 79240 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | DIALED-22-3000-90-35-VL-W-120-DP-1-ST-B1(BSL310LP) | 6.3 | 520 | 0 |  | Internat | Rohan Srivastava |  |  | A2EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 520 | 6.3 | 0 | 1 | 520 | 6.3 |  | 0 | 2019 | 2 | 6 | 1 | Complete | FALSE | FALSE
78710-1 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 78710 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | SCDI-300-300-80-40-SO-0.5M-2X6-W-UNV-DP-1-CA(36) | 68 | 3080 | 0 |  | MAC'S II | George Bacalla |  |  | A-2X6 | Picked - Complete | 2019-01-27 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1540 | 34 | 0 | 2 | 3080 | 68 |  | 1 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE | Ready
78710-2 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78710 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | SCDI-300-300-80-40-SO-0.5M-6'-W-UNV-DP-1-CA(36) | 30.6 | 1854 | 0 |  | MAC'S II | George Bacalla |  |  | A1-6' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 618 | 10.2 | 0 | 3 | 1854 | 30.6 |  | 1 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
78710-3 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 78710 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | SCDI-300-300-80-40-SO-0.5M-4X4-W-UNV-DP-1-CA(36) | 30.2 | 1600 | 0 |  | MAC'S II | George Bacalla |  |  | B-4X4 | Picked - Complete | 2019-01-27 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1600 | 30.2 | 0 | 1 | 1600 | 30.2 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE | Ready
75738-1 | 12 | 2019-02-04 | 2018-12-03 | Given to Shipping | Regular | FALSE | 75738 | Regular | Mechanical issue | TRUE | Quantity | 1 | 2 | 9 | 9 | BMRLED-500-80-35-ASO-4-W-120-DP-1-D | 27 | 2851.2 | 0 |  | MAC'S II | George Bacalla | Ms: 2/1 - Kaushik to advise. Edited on 2/1/2019 |  | LI04-4' |  | 2019-01-27 | 2019-02-03 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 316.8 | 3 | 9 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
75738-2 | 12 | 2019-02-04 | 2018-12-03 | Given to Shipping | Regular | FALSE | 75738 | Regular | Wrong info. In SD | TRUE | Quantity | 2 | 2 | 9 | 9 | BMRLED-500-80-35-ASO-2-W-120-DP-1-D | 27 | 2673 | 0 |  | MAC'S II | George Bacalla |  |  | LI05-2' |  | 2019-01-27 | 2019-02-03 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 297 | 3 | 9 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
78933-1 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78933 | Regular |  | FALSE |  | 1 | 1 | 20 | 20 | DIALED-22-4000-80-35-VL-W-UNV-DP-1-TG9 | 56 | 4500 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | 2X2 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 225 | 2.8 | 0 | 20 | 4500 | 56 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
59584-10 | 1 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 59584 | High Priority |  | FALSE |  | 10 | 1 | 1 | 7 | SCRPAT-OPR-90(1)-300-80-35-FL-61'11"-NL-W-UNV-DP-1+E(3)-D | 57 | 3945 | 0 |  | Internat | Gagandeep Singh |  |  | F4-16'2"X45'9"'-L SHAPE | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 563.5714 | 8.1429 | 0 | 7 | 3945 | 57 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE | Ready
59584-12 | 1 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 59584 | High Priority | Missing parts in BOM | TRUE | Driver | 12 | 1 | 1 | 21 | SCRPAT-OPR-90(2)-300-80-35-FL-226'3/8"-NL-W-UNV-DP-1+E(2)-D | 211 | 14010 | 0 |  | Internat | Gagandeep Singh |  |  | F4-12'10"X67'4-5/8"X145'9 3/4" | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 667.1429 | 10.0476 | 0 | 21 | 14010 | 211 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE | Ready
59584-66 | 1 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 59584 | High Priority |  | FALSE |  | 66 | 1 | 1 | 5 | SCRPAT-OPR-90(1)-300-80-35-FL-34'9"-NL-W-UNV-DP-1+E(2)-D | 36 | 2325 | 0 |  | Internat | Gagandeep Singh |  |  | F4-16'2"X18'7"-L SHAPE | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 465 | 7.2 | 0 | 5 | 2325 | 36 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE | Ready
59584-67 | 1 | 2019-02-06 |  | Machine Shop Started | Regular | FALSE | 59584 | High Priority |  | FALSE |  | 67 | 1 | 1 | 22 | SCRPAT-OPR-90(4)-300-80-35-FL-211'11 1/4-NL-W-UNV-DP-1+E(7)-D | 330 | 13395 | 0 |  | Internat | Gagandeep Singh |  |  | F4-57'6-3/4"X31'4"X29'1"X65'2"X28'9-1/2 | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 608.8636 | 15 | 0 | 22 | 13395 | 330 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE | Ready
78812-1 | 10 | 2019-02-06 | 2019-02-06 | Packaging Finished | Regular | FALSE | 78812 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | DIALED-24-3100-90-30-VL-W-120-DP-1-ST-FW(6) | 3.5 | 355 | 0 |  | Internat | Rohan Srivastava |  |  | A-2X4 |  |  | 2019-02-01 | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 355 | 3.5 | 1 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 6 | 2 | Partial | FALSE | FALSE |  | Done
78812-2 | 10 | 2019-02-06 | 2019-02-06 | Packaging Finished | Regular | FALSE | 78812 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST-FW(6) | 8.7 | 765 | 0 |  | Internat | Rohan Srivastava |  |  | A2-2X2 |  |  | 2019-02-01 | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 255 | 2.9 | 3 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 6 | 2 | Partial | FALSE | FALSE |  | Done
78812-3 | 10 | 2019-02-06 | 2019-02-06 | Packaging Finished | Regular | FALSE | 78812 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST-FW(6) | 2.9 | 255 | 0 |  | Internat | Rohan Srivastava |  |  | A3-2X2 |  |  | 2019-02-01 | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 255 | 2.9 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 6 | 2 | Partial | FALSE | FALSE |  | Done
78812-4 | 12 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78812 | Regular |  | FALSE |  | 4 | 1 | 2 | 2 | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36) | 10.8 | 1000 | 0 |  | Internat | Rohan Srivastava |  |  | B1-4' | Picked - Complete | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 500 | 5.4 | 5 | -3 | -1500 | -16.2 |  | 1 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
78812-5 | 12 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78812 | Regular | Mechanical issue | FALSE |  | 5 | 1 | 9 | 9 | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36) | 48.6 | 4500 | 0 |  | Internat | Rohan Srivastava |  |  | B2-4' | Picked - Complete | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 500 | 5.4 | 0 | 9 | 4500 | 48.6 | Mechanical issue | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
78812-6 | 12 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78812 | Regular | Mechanical issue | FALSE |  | 6 | 1 | 5 | 5 | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36)-B1(BSL310LP) | 46.5 | 3500 | 0 |  | Internat | Rohan Srivastava |  |  | B2-4' EM | Picked - Complete | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 700 | 9.3 | 0 | 5 | 3500 | 46.5 | Mechanical issue | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
78812-7 | 12 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78812 | Regular | Others | TRUE | Mising Sensor Cover | 7 | 1 | 10 | 10 | LTLED-SL 80/20-800-90-30-SO-8'-W-120-DP-1-CA(36)-DS(1) | 136 | 10000 | 0 |  | Internat | Rohan Srivastava |  |  | B4-8' | Picked - Complete | 2019-02-03 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 1000 | 13.6 | 0 | 10 | 10000 | 136 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
78936-1 | 12 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 78936 | Regular | Mechanical issue | TRUE | FIXTURE NOT DELIVER | 1 | 1 | 3 | 3 | BBRLED-600-80-35-FL-8'-W-UNV-DP-1-TG9-FW(6) | 14.4 | 2040 | 0 |  | Internat | Rohan Srivastava |  |  | F1-8' |  | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 680 | 4.8 | 0 | 3 | 2040 | 14.4 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | FALSE |  | Done
74968-1 | 1 | 2019-01-29 | 2019-01-29 | Machine Shop Started | Regular | FALSE | 74968 | High Priority | Others | FALSE | Sub Assembly parts | 1 | 1 | 1 | 4 | SKPE-18075-SL 60/40-ASO-AL(#23' 9 1/4")-1000-80-40-SO-C(RAL5012)-UNV-D-1-CA(36) | 60 | 5400 | 0 | NO LATER THAN FEB 5TH | HIGH | Rohan Srivastava | MS:01/29 Edited on 1/28/2019 |  | A-23 '9-1/4" | Picked - Complete | 2019-01-17 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 1350 | 15 | 0 | 4 | 5400 | 60 | Others | 1 | 2019 | 1 | 29 | 1 | Complete | FALSE | FALSE |  | Done
74968-2 | 1 | 2019-01-29 | 2019-01-29 | Machine Shop Started | Regular | FALSE | 74968 | High Priority | Others | TRUE | Sub Assembly parts | 2 | 1 | 1 | 3 | SKPE-18075-SL 60/40-ASO-AL(#14' 10-1/4")-1000-80-40-SO-C(RAL6038)-UNV-D-1-CA(36) | 40 | 3375 | 0 | NO LATER THAN FEB 5TH | HIGH | Rohan Srivastava | MS: 01/30 - Ship: ? Edited on 1/29/2019 |  | B-14' 10-1/4" | Picked - Complete | 2019-01-17 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 1125 | 13.3333 | 0 | 3 | 3375 | 40 |  | 0 | 2019 | 1 | 29 | 1 | Complete | FALSE | FALSE |  | Done
74968-3 | 1 | 2019-01-29 | 2019-01-29 | Machine Shop Started | Regular | FALSE | 74968 | High Priority | Shortage | TRUE | PATTERN INFORMATION | 3 | 1 | 1 | 3 | SKPE-18075-SL 60/40-ASO-AL(# 16' 10-1/4")-1000-80-40-SO-C(RAL2007)-UNV-D-1-CA(36) | 40 | 3825 | 0 | NO LATER THAN FEB 5TH | HIGH | Rohan Srivastava | Sukhwinder to follow Edited on 1/30/2019 Ms:Feb 1st - Kaushik to advise. Edited on 1/31/2019 :::: Machine Shop Started - Sukhwinder to advise??? Edited on 2/5/2019 |  | C-16' 10-1/4"` | Picked - Complete | 2019-01-17 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 1275 | 13.3333 | 0 | 3 | 3825 | 40 |  | 0 | 2019 | 1 | 29 | 1 | Complete | FALSE | FALSE |  | Done
77375-1 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular |  | FALSE |  | 1 | 1 | 2 | 4 | BMPRLED-750-90-35-RG2-15'0"-W-UNV-DP-1-TB9-TS(1) | 26.8 | 2910.44 | 0 |  | IllumBos | Philip Halsey |  |  | L04-15' |  | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 727.61 | 6.7 | 0 | 4 | 2910.44 | 26.8 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77375-2 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular |  | FALSE |  | 2 | 1 | 2 | 4 | BMPRLED-750-90-35-RG2-21'0"-W-UNV-DP-1-TB9-TS(1) | 37.6 | 4074.6 | 0 |  | IllumBos | Philip Halsey |  |  | L04-21' |  | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 1018.65 | 9.4 | 0 | 4 | 4074.6 | 37.6 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77375-3 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular |  | FALSE |  | 3 | 1 | 1 | 2 | BMPRLED-750-90-35-RG2-23'0"-W-UNV-DP-1-TB9-TS(1) | 18.8 | 2231.31 | 0 |  | IllumBos | Philip Halsey |  |  | L04-23' |  | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 1115.655 | 9.4 | 0 | 2 | 2231.31 | 18.8 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77375-5 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular |  | FALSE |  | 5 | 1 | 2 | 2 | BMPRLED-750-90-35-RG2-7' 5"-W-UNV-DP-1-TB9-TS(1)-B1(BSL10LST) | 22 | 1643.52 | 0 |  | IllumBos | Philip Halsey |  |  | L04E 7.5' |  | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 821.76 | 11 | 0 | 2 | 1643.52 | 22 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77375-6 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular |  | FALSE |  | 6 | 1 | 1 | 8 | B2SQILED-1000-90-35-SL-95'0"-W-UNV-DP-1-CA(36) | 72 | 9500 | 0 |  | IllumBos | Philip Halsey |  |  | L07 |  | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1187.5 | 9 | 0 | 8 | 9500 | 72 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77375-7 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular | Shortage | FALSE |  | 7 | 1 | 1 | 9 | BDLED-750-90-35-SO-105'0"-BLK-UNV-DP-1-CA(36) | 88 | 8988.02 | 0 |  | IllumBos | Philip Halsey |  |  | L08 |  | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 998.6689 | 9.7778 | 0 | 9 | 8988.02 | 88 | Shortage | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77375-8 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77375 | Regular |  | FALSE |  | 8 | 1 | 8 | 8 | TB2WDILED-1100-1000-80-35-SLA-SO-3'5"-W-UNV-DP-1-B1(BSL10LST)-OS(1) | 104 | 6756.64 | 0 |  | IllumBos | Philip Halsey |  |  | L09E-3.5 |  | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 844.58 | 13 | 0 | 8 | 6756.64 | 104 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78789-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78789 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | WWR-SL-400-80-35-10'-W-UNV-DP-1-TG9 | 9 | 830 | 0 |  | IllumBos | Philip Halsey |  |  | L3-10' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 830 | 9 | 0 | 1 | 830 | 9 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
79135-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 79135 | High Priority |  | FALSE |  | 1 | 1 | 2 | 2 | WBRVLED-500-80-35-SO-5'-AP-UNV-DP-1-DS | 15.2 | 1488 | 0 | no buffer, must ship by 2/13 | IllumBos | Philip Halsey |  |  | VERT-5' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 744 | 7.6 | 0 | 2 | 1488 | 15.2 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77560-1 | 15 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77560 | Regular | Others | TRUE | STORES-Picked Wrong Part | 1 | 1 | 12 | 12 | WBWLED-750-80-40-S-8' 0"-BLK-UNV-DP-1 | 86.88 | 11388.6 | 0 | *DO NOT SHIP BEFORE FEBRUARY 6 2019* | RichardM | George Bacalla |  |  | W2-8'-0" |  |  | 2019-02-03 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 949.05 | 7.24 | 0 | 12 | 11388.6 | 86.88 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
79024-1 | 12 | 2019-02-05 | 2019-02-05 | Order UnShipped | Regular | FALSE | 79024 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | B6RLED-1000-90-40-FL-5-W-UNV-DP-1-TB9 | 298.851 | 396 | 0 |  | RichardM | George Bacalla |  |  | L8-5' | Picked - Complete | 2019-02-03 | 2019-01-30 | FALSE | FALSE | NO |  |  | Order UnShipped |  | 396 | 298.851 | 1 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
79164-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 79164 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BRLED-750-80-40-FL-8'-W-UNV-DP-1+NL(1)-TB15 | 6.5 | 612 | 0 |  | RichardM | George Bacalla |  |  | L39A-8' |  | 2019-02-04 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 612 | 6.5 | 0 | 1 | 612 | 6.5 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78603-1 | 1 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78603 | Regular | Shortage | FALSE | Extrusion | 1 | 1 | 2 | 2 | STD-SO-300-80-35-6'-C(RAL 1023)-UNV-MD-1-CA(36)-RC | 14.4 | 1022.4 | 0 |  | RichardM | George Bacalla |  |  | D-6' | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 511.2 | 7.2 | 0 | 2 | 1022.4 | 14.4 | Shortage | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78603-2 | 1 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78603 | Regular |  | FALSE |  | 2 | 1 | 2 | 2 | STD-SO-300-80-35-5'-C(RAL 5018)-UNV-MD-1-CA(36)-RC | 14.4 | 873 | 0 |  | RichardM | George Bacalla |  |  | E-5' | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 436.5 | 7.2 | 0 | 2 | 873 | 14.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78637-1 | 12 | 2019-02-05 | 2019-02-05 | Packaging Finished | Regular | FALSE | 78637 | Regular | Others | TRUE | Covers | 1 | 1 | 1 | 1 | CUBLED-SL 75/25-1000-80-35-SO-8'-AP-UNV-DP-1-CA(36) | 11.7 | 669.6 | 0 |  | RichardM | George Bacalla | Kaushik to advise?? Edited on 2/5/2019 |  | J-8' | Picked - Complete |  | 2019-01-30 | FALSE | FALSE | NO |  |  | Packaging Finished |  | 669.6 | 11.7 | 1 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78637-2 | 12 | 2019-02-05 | 2019-02-05 | Packaging Finished | Regular | FALSE | 78637 | Regular | Others | FALSE | End Cap | 2 | 1 | 3 | 3 | CUBWLED-SL 75/25-1000-80-35-SO-4'-AP-UNV-DP-1 | 15.6 | 1026 | 0 |  | RichardM | George Bacalla |  |  | K-4' | Picked - Complete |  | 2019-01-30 | FALSE | FALSE | NO |  |  | Packaging Finished |  | 342 | 5.2 | 2 | 1 | 342 | 5.2 | Others | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | FALSE |  | Done
77630-1 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 77630 | High Priority |  | FALSE |  | 1 | 1 | 3 | 3 | SCR-300-80-35-FL-TR45X2-W-UNV-DP-1-MFTB15 | 36.9 | 750 | 0 |  | RichardM | George Bacalla |  |  | L09 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 250 | 12.3 | 0 | 3 | 750 | 36.9 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
77630-2 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 77630 | High Priority |  | FALSE |  | 2 | 1 | 3 | 3 | ARLED-500-80-35-S-4-AP-UNV-DP-1-CTS(210) | 11.7 | 1275 | 0 |  | RichardM | George Bacalla |  |  | L08 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 425 | 3.9 | 0 | 3 | 1275 | 11.7 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
77630-3 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 77630 | High Priority |  | FALSE |  | 3 | 1 | 3 | 3 | ARLED-500-80-35-S-4-AP-UNV-DP-1-CA(210) | 11.7 | 1275 | 0 |  | RichardM | George Bacalla |  |  | L08-DRY | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 425 | 3.9 | 0 | 3 | 1275 | 11.7 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
78529-1 | 15 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78529 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BBRLED-1000-80-35-FL-12'-W-UNV-DP-1-DF | 7 | 972 | 0 |  | RichardM | George Bacalla |  |  | 1-12' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 972 | 7 | 0 | 1 | 972 | 7 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78529-2 | 15 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78529 | Regular |  | FALSE |  | 2 | 1 | 1 | 2 | BBRLED-1000-80-35-FL-20'-W-UNV-DP-1-DF | 12 | 1620 | 0 |  | RichardM | George Bacalla |  |  | 1-20' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 810 | 6 | 0 | 2 | 1620 | 12 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78529-3 | 15 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78529 | Regular |  | FALSE |  | 3 | 1 | 25 | 25 | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-DF | 75 | 8550 | 0 |  | RichardM | George Bacalla |  |  | 1-4' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 342 | 3 | 0 | 25 | 8550 | 75 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78529-4 | 15 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78529 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | BBRLED-1000-80-35-FL-8'-W-UNV-DP-1-DF | 5 | 648 | 0 |  | RichardM | George Bacalla |  |  | 1-8' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 648 | 5 | 0 | 1 | 648 | 5 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78535-1 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78535 | Regular |  | FALSE |  | 1 | 1 | 3 | 3 | BMRLED-500-80-30-ASO-4'-W-277-DP-1-DF | 9 | 1004.4 | 0 |  | RichardM | George Bacalla |  |  | LI04-4' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 334.8 | 3 | 0 | 3 | 1004.4 | 9 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78535-2 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78535 | Regular |  | FALSE |  | 2 | 1 | 4 | 4 | BMRLED-500-80-30-ASO-2'-W-277-DP-1-TG9 | 12 | 1173.6 | 0 |  | RichardM | George Bacalla |  |  | LI05-2' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 293.4 | 3 | 0 | 4 | 1173.6 | 12 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78535-3 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78535 | Regular |  | FALSE |  | 3 | 1 | 12 | 12 | BMRLED-500-80-30-FL-2'-W-277-DP-1-TG9 | 38.4 | 3801.6 | 0 |  | RichardM | George Bacalla |  |  | LI05D-2' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 316.8 | 3.2 | 0 | 12 | 3801.6 | 38.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78535-4 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78535 | Regular | Wrong info. In SD | TRUE | LIGHT DIRECTION IS | 4 | 1 | 1 | 3 | SP19011-BMRLEDPAT-OPR-90(1)-500-80-30-ASO-FL-10'-NL-W-UNV-DP-1-DF | 15 | 1080 | 0 |  | RichardM | George Bacalla |  |  | LI05/LI04-L-10' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 360 | 5 | 0 | 3 | 1080 | 15 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE | ToDo
76076-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 76076 | Regular |  | FALSE |  | 1 | 1 | 4 | 4 | BRVLED-500-90-27-SO-6'-W-277-DP-1-D | 25.2 | 3700 | 0 |  | LS Phill | Gaurav Jain |  |  | L13-6' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 925 | 6.3 | 0 | 4 | 3700 | 25.2 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
76076-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 76076 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | BRVLED-500-90-27-SO-4'-W-277-DP-1-D | 3.3 | 688 | 0 |  | LS Phill | Gaurav Jain |  |  | L14-4' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 688 | 3.3 | 0 | 1 | 688 | 3.3 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
76076-3 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 76076 | Regular |  | FALSE |  | 3 | 1 | 2 | 2 | BRVLED-500-90-27-SO-5'-W-277-DP-1-D | 12.6 | 1540 | 0 |  | LS Phill | Gaurav Jain |  |  | L15-5' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 770 | 6.3 | 0 | 2 | 1540 | 12.6 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
76076-4 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 76076 | Regular |  | FALSE |  | 4 | 1 | 3 | 3 | BRVLED-500-90-27-SO-8'-W-277-DP-1-D | 18.9 | 3660 | 0 |  | LS Phill | Gaurav Jain |  |  | L16-8' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1220 | 6.3 | 0 | 3 | 3660 | 18.9 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
79502-1 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Replacement | FALSE | 79502 | High Priority |  | FALSE |  | 1 | 1 | 1 | 1 | BMRLED-575-80-30-FL-2-W-UNV-DP-1-ST-C(FILLER) | 3.2 | 160 | 0 | ROCKEFELLER - NEW TO WEEK - URGENT!!! FEDEX PRIORITY | Internat | Robert Lipura |  |  | 146/145-4.50(27 SW BMR) |  | 2019-02-05 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 160 | 3.2 | 0 | 1 | 160 | 3.2 |  | 1 | 2019 | 2 | 6 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
79502-2 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Replacement | FALSE | 79502 | High Priority |  | FALSE |  | 2 | 1 | 1 | 1 | BMRLED-575-80-30-FL-2-W-UNV-DP-1-ST-C(FILLER) | 3.2 | 160 | 0 | ROCKEFELLER - NEW TO WEEK - URGENT!!! FEDEX PRIORITY | Internat | Robert Lipura |  |  | 146/145-4.50(26 NW BMR) |  | 2019-02-05 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 160 | 3.2 | 0 | 1 | 160 | 3.2 |  | 0 | 2019 | 2 | 6 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
79170-1 | 10 | 2019-02-01 | 2019-02-01 | Order UnShipped | Replacement | FALSE | 79170 | Regular |  | FALSE |  | 1 | 1 | 80 | 0 | RECESSED DRYWALL MOUNTING KITS- POWERED 3 WIRES - DAY-DIA-DUO-PLANO-WAVE - 1X1 | 0 | 1968 | 0 | PLEASE PRODUCE DRYWALL KIT ONLY 1X1 | IllumBos | Daljit Singh | Ship:2/4 Edited on 2/1/2019 | [5 empty] | FALSE | FALSE | NO | Material+Cartridge |  | Order UnShipped |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE
78545-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78545 | Regular |  | FALSE |  | 1 | 1 | 6 | 6 | SCDLAC-AC(2)-D36-HX-D-500-80-30-FL-4'-BLK-UNV-DP-1-CT9(60") | 28.638 | 2640 | 0 |  | Smart Li | Zahra Vatani |  |  | A-4' | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 440 | 4.773 | 0 | 6 | 2640 | 28.638 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
72221-1 | 7 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 72221 | Regular |  | FALSE |  | 1 | 1 | 13 | 13 | BDLED-1000-80-35-SO-4-W-UNV-DP-1-CTS(36) | 62.4 | 3952 | 0 |  | Enterpri | Jessica Pasternyk |  |  | L13 |  |  | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 304 | 4.8 | 0 | 13 | 3952 | 62.4 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
72221-2 | 7 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 72221 | Regular |  | FALSE |  | 2 | 1 | 14 | 14 | BDLED-1000-80-35-SO-6-W-UNV-DP-1-CTS(36) | 105 | 6370 | 0 |  | Enterpri | Jessica Pasternyk |  |  | L13-6' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 455 | 7.5 | 0 | 14 | 6370 | 105 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
72221-3 | 7 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 72221 | Regular |  | FALSE |  | 3 | 1 | 12 | 12 | BDLED-1000-80-35-SO-8-W-UNV-DP-1-CTS(36) | 90 | 7278 | 0 |  | Enterpri | Jessica Pasternyk |  |  | L13-8 |  |  | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 606.5 | 7.5 | 0 | 12 | 7278 | 90 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
72221-4 | 7 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 72221 | Regular |  | FALSE |  | 4 | 1 | 13 | 13 | BSLED-750-80-35-SO-8-W-UNV-DP-1-SC | 91 | 7670 | 0 |  | Enterpri | Jessica Pasternyk |  |  | L14 |  |  | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 590 | 7 | 0 | 13 | 7670 | 91 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
78491-1 | 15 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78491 | Regular |  | FALSE |  | 1 | 1 | 21 | 21 | BDLED-1000-90-30-SO-4'-AP-UNV-DP-1-CA(72) | 100.8 | 5880 | 0 |  | Vanguard | Philip Halsey |  |  | PENDANT-4' |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 280 | 4.8 | 0 | 21 | 5880 | 100.8 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
76983-1 | 12 | 2019-01-31 | 2019-01-31 | Machine Shop Finished | Regular | FALSE | 76983 | Regular | Shortage | FALSE | SUB ASSEMLY/EXTRUSION | 1 | 1 | 1 | 2 | WWS-SL-1000-90-35-16'-AP-UNV-DP-1-SC | 11.2 | 1658 | 0 |  | CAL | Stan Buyansky | Extrusion eta: 2/1 - Ms:2/1 Edited on 1/31/2019 - Ms:2/3 - Kaushik to advise. Edited on 2/1/2019 ::: Elizabeth to follow Edited on 2/5/2019 |  | A |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 829 | 5.6 | 0 | 2 | 1658 | 11.2 | Shortage | 1 | 2019 | 1 | 31 | 1 | Complete | TRUE | TRUE |  | Done
78889-1 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78889 | Regular |  | FALSE |  | 1 | 1 | 2 | 4 | CCH-SL-1100-80-35-CL(17' 4")-W-UNV-DP-1-C | 33.2 | 2880 | 0 |  | IllumBos | Philip Halsey |  |  | C1-17' 4" |  |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 720 | 8.3 | 0 | 4 | 2880 | 33.2 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78889-2 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78889 | Regular |  | FALSE |  | 2 | 1 | 2 | 2 | CCH-SL-1100-80-35-CL(8' 6")-W-UNV-DP-1-C | 18.8 | 1440 | 0 |  | IllumBos | Philip Halsey |  |  | C1 8' 6" |  |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 720 | 9.4 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78889-3 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78889 | Regular |  | FALSE |  | 3 | 1 | 1 | 2 | CCH-SL-1100-80-35-CL(17')-W-UNV-DP-1-C | 16.6 | 1360 | 0 |  | IllumBos | Philip Halsey |  |  | C1 17' |  |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 680 | 8.3 | 1 | 1 | 680 | 8.3 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78889-4 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78889 | Regular |  | FALSE |  | 4 | 1 | 1 | 2 | CCH-SL-1100-80-35-CL(16')-W-UNV-DP-1-C | 14 | 1280 | 0 |  | IllumBos | Philip Halsey |  |  | C1 16' |  |  |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 640 | 7 | 0 | 2 | 1280 | 14 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78706-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78706 | Regular | Mechanical issue | FALSE |  | 1 | 1 | 7 | 7 | SCS-300-80-35-FL-8'-BLK-UNV-DP-1-SB9 | 43.4 | 7000 | 0 |  | Internat | Rohan Srivastava |  |  | D-8' | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1000 | 6.2 | 0 | 7 | 7000 | 43.4 | Mechanical issue | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78706-2 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78706 | Regular |  | FALSE |  | 2 | 1 | 10 | 10 | SCDI-300-300-80-35-SO-FL-8-BLK-UNV-DP-1-SA(48) | 102 | 10000 | 0 |  | Internat | Rohan Srivastava |  |  | F-8' | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1000 | 10.2 | 0 | 10 | 10000 | 102 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78949-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78949 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BBDLED-400-80-30-SO-12'-W-UNV-DP-1-CTS(36) | 11.4 | 900 | 0 |  | AES | Christina Torok |  |  | 13 LOBBY | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 900 | 11.4 | 0 | 1 | 900 | 11.4 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
79189-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 79189 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BBRLED-400-80-30-RG-4'7"-W-120-DP-1-D-B1(BSL310LP) | 8.6 | 555 | 555 | FIXTURE WAS PRODUCED WITH THE WRONG DIMENSION. | Ltg Spec | Anil Surendra Sanchara |  |  | 12E 604 HALL @ 55" | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 555 | 8.6 | 0 | 1 | 555 | 8.6 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
79201-1 | 12 | 2019-02-13 | 2019-02-13 | Scheduled/Released | Regular | FALSE | 79201 | Regular |  | FALSE |  | 1 | 1 | 2 | 4 | CU-S-24-T8-3-W-0-0-UNV-E-1-CT9(36) | 61 | 2352.94 | 0 |  | Vanguard | Philip Halsey |  |  | L1-24' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Scheduled/Released |  | 588.235 | 15.25 | 0 | 4 | 2352.94 | 61 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
76939-2 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 76939 | High Priority |  | FALSE |  | 2 | 1 | 2 | 2 | BRLED-400-80-35-FL-12-W-UNV-DP-1-DF | 18 | 1512 | 0 |  | Concordi | George Bacalla |  |  | F23 12' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 756 | 9 | 0 | 2 | 1512 | 18 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
76939-3 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 76939 | High Priority |  | FALSE |  | 3 | 1 | 2 | 4 | BRLED-400-80-35-FL-16-W-UNV-DP-1-DF | 26.6 | 2016 | 0 |  | Concordi | George Bacalla |  |  | F23 16' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 504 | 6.65 | 0 | 4 | 2016 | 26.6 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
76939-4 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 76939 | High Priority |  | FALSE |  | 4 | 1 | 2 | 6 | BRLED-400-80-35-FL-34-W-UNV-DP-1-DF | 57.4 | 4284 | 0 |  | Concordi | George Bacalla |  |  | F23 34' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 714 | 9.5667 | 0 | 6 | 4284 | 57.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78931-1 | 12 | 2019-02-05 | 2019-02-05 | Packaging Finished | Regular | FALSE | 78931 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BBDLED-1000-90-35-SO-4'-W-UNV-DP-1-CA(96)-C(BLACK CANOPIES & CORD) | 10.8 | 704 | 0 |  | CAL | Stan Buyansky |  |  | A | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE |  |  |  | Packaging Finished |  | 352 | 5.4 | 0 | 2 | 704 | 10.8 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
76028-32 | 4 | 2019-02-08 | 2019-01-21 | Machine Shop Started | Regular | FALSE | 76028 | High Priority |  | FALSE |  | 32 | 1 | 2 | 10 | CCH-SL-1100-80-35-CL(56)-W-UNV-DP-1-C | 89.6 | 6944 | 0 |  | ERW Ltg | George Bacalla |  |  | L02-56' |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 694.4 | 8.96 | 0 | 10 | 6944 | 89.6 |  | 1 | 2019 | 2 | 8 | 2 | Partial | FALSE | FALSE
76028-44 | 4 | 2019-02-08 | 2019-01-21 | Scheduled/Released | Regular | FALSE | 76028 | High Priority |  | FALSE |  | 44 | 1 | 1 | 9 | CCH-SL-1100-80-35-CL(80)-W-UNV-DP-1-C | 63.5 | 4960 | 0 |  | ERW Ltg | George Bacalla |  |  | L02-80' |  |  |  | FALSE | FALSE | NO |  |  | Scheduled/Released |  | 551.1111 | 7.0556 | 0 | 9 | 4960 | 63.5 |  | 1 | 2019 | 2 | 8 | 2 | Partial | FALSE | FALSE
76191-1 | 4 | 2019-01-17 | 2019-01-17 | Machine Shop Started | Regular | FALSE | 76191 | Regular | Mechanical issue | FALSE | Machining | 1 | 1 | 5 | 5 | ZESLED-SL 0/100-600-80-35-MSO-8-W-UNV-MD-1-S | 56.65 | 3240 | 0 |  | PSGI | Sacha Lempka | Ship: Jan 18th Edited on 1/17/2019 - Ship:1 /21 Edited on 1/18/2019 ::: Will Ship: Jan 22nd Edited on 1/22/2019 ::: Ship: Jan 23rd Edited on 1/22/2019::: End Caps (Misplaced) - ETA: Jay/Erin to advise Edited on 1/24/2019 - End cap Received - SHIP: Jan 29th Edited on 1/28/2019::: Will Ship: Jan 30th Edited on 1/29/2019 ::: Ship: Jan 31st Edited on 1/30/2019 - Elizabeth following up. Edited on 2/1/2019:::: Elizabeth to follow Edited on 2/5/2019 |  | P2 | Picked - Complete | 2019-01-13 | 2019-01-17 | FALSE | FALSE | OK |  |  | Machine Shop Started |  | 648 | 11.33 | 0 | 5 | 3240 | 56.65 | Mechanical issue | 1 | 2019 | 1 | 17 | 1 | Complete | TRUE | TRUE |  | Done
79076-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Replacement | FALSE | 79076 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BBWDILED-640-400-80-40SO-4-W-120-BI-1-OS(1 LOS-CDT)-C(SENSOR FOR INDIRECT ONLY) | 9 | 448 | 448 |  | KSA Ltg | Anil Surendra Sanchara |  |  | L11 - REPLACE | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 448 | 9 | 0 | 1 | 448 | 9 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78711-1 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78711 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BBWDILED-400-750-90-35-SO-2'-W-277-DP-1+GTD(1) | 11.2 | 353 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3 | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 353 | 11.2 | 0 | 1 | 353 | 11.2 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
78150-1 | 7 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 78150 | Regular | Others | TRUE | sub assembly parts | 1 | 1 | 3 | 3 | STSLF-SO-400-80-35-8'-AP-UNV-MD-1-SC | 24 | 2148 | 0 |  | Enterpri | Jessica Pasternyk | Ship: Kaushik to advise Edited on 2/5/2019 |  | L1-8' |  | 2019-01-27 | 2019-02-05 | FALSE | TRUE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 716 | 8 | 0 | 3 | 2148 | 24 |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78150-2 | 7 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 78150 | Regular | Shortage | FALSE | Extrusion | 2 | 1 | 1 | 1 | STSLF-SO-400-80-35-12'-AP-UNV-MD-1-SC | 11 | 1040 | 0 |  | Enterpri | Jessica Pasternyk |  |  | L2-12' |  | 2019-01-27 | 2019-02-05 | FALSE | TRUE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1040 | 11 | 0 | 1 | 1040 | 11 | Shortage | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78150-3 | 7 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 78150 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | STSLF-SO-400-B(3')-80-35-9'-AP-UNV-MD-1-SC-AC(4)-R-D35-AP | 25.8 | 1134 | 0 |  | Enterpri | Jessica Pasternyk |  |  | L3-9' |  | 2019-01-27 | 2019-02-05 | FALSE | TRUE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1134 | 25.8 | 0 | 1 | 1134 | 25.8 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78290-1 | 12 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 78290 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | ZELED-SL 65/35-1100-80-35-MSO-W-12-AP-UNV-MD-1-CA(18") | 36 | 2542 | 0 |  | Enterpri | Jessica Pasternyk | Ms:2/1 - Kaushik to advise. Edited on 2/1/2019 ::: Ship: Feb 5th Edited on 2/5/2019 |  | JL1 |  |  | 2019-01-29 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 1271 | 18 | 0 | 2 | 2542 | 36 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
75697-1 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 75697 | Regular |  | FALSE |  | 1 | 1 | 7 | 7 | PRWLED-800-80-40-S-4-W-UNV-BI-1-OS(1) | 40.95 | 3767.8535 | 0 |  | LS Phill | Gaurav Jain | Ship: Feb 6th Edited on 2/5/2019 |  | F5-4' |  |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 538.2648 | 5.85 | 0 | 7 | 3767.8535 | 40.95 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE
75697-2 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 75697 | Regular |  | FALSE |  | 2 | 1 | 35 | 35 | PRWLED-800-80-40-S-4-W-UNV-BI-1-OS(1) | 204.75 | 18839.2673 | 0 |  | LS Phill | Gaurav Jain |  |  | F5-4' E |  |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 538.2648 | 5.85 | 0 | 35 | 18839.2673 | 204.75 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE
75697-3 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 75697 | Regular |  | FALSE |  | 3 | 1 | 26 | 26 | PRWLED-800-80-40-S-8-W-UNV-BI-1-OS(1) | 209.56 | 25909.7686 | 0 |  | LS Phill | Gaurav Jain |  |  | F5-8' E |  |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 996.5296 | 8.06 | 0 | 26 | 25909.7686 | 209.56 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE
75697-4 | 1 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 75697 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | PRWLED-800-80-40-S-12-W-UNV-BI-1-OS(1) | 9.81 | 1483.1105 | 0 |  | LS Phill | Gaurav Jain |  |  | F5-12' E |  |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1483.1105 | 9.81 | 0 | 1 | 1483.1105 | 9.81 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE
78569-1 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78569 | High Priority | Shortage | FALSE | Extrusion | 1 | 1 | 31 | 31 | WBRLED-500-80-30-S-5-C(RAL 7030)-UNV-DP-1-D | 189.1 | 12927 | 0 |  | Performa | Stan Buyansky |  |  | SD-5 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 417 | 6.1 | 0 | 31 | 12927 | 189.1 | Shortage | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
79186-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Replacement | FALSE | 79186 | Regular | Shortage | FALSE |  | 1 | 1 | 1 | 1 | SP000-BBDILED-300-750-80-35-SO-28-BLK-UNV-DP-1-CA(36)-C(SECTION #3 ONLY TO JOIN TO EXISTING) | 38.8 | 840 | 840 |  | Performa | Tajinder Singh |  |  | LP3-28 | Picked - Complete | 2019-01-30 | 2019-02-05 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 840 | 38.8 | 0 | 1 | 840 | 38.8 | Shortage | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE |  | Done
70875-1 | 12 | 2019-02-11 | 2019-02-11 | Scheduled/Released | Regular | FALSE | 70875 | Regular |  | FALSE |  | 1 | 1 | 4 | 12 | STFD-DSO(12)-300-90-35-AY(1)-AP-UNV-MD-1-CA(36)-RC | 68 | 5942.16 | 0 |  | Performa | Stan Buyansky |  |  | H15 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 495.18 | 5.6667 | 0 | 12 | 5942.16 | 68 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
79418-1 | 4 | 2019-02-05 |  | Machine Shop Started | Mockup/Samples | FALSE | 79418 | High Priority | Shortage | FALSE |  | 1 | 1 | 1 | 1 | ZELED-SL 65/35-700-80-35-MSO-W-4-W-UNV-MD-1-CT15(36) | 7 | 100 | 100 | Howard’s tours in the lab - need for Thursday Feb 7th latest | HOUSE | Joe Brier | MS: Feb 5th Edited on 2/5/2019 |  | ZEN-A | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 100 | 7 | 0 | 1 | 100 | 7 | Shortage | 1 | 2019 | 2 | 5 | 1 | Complete | FALSE | FALSE
79418-2 | 4 | 2019-02-05 |  | Machine Shop Started | Mockup/Samples | FALSE | 79418 | High Priority |  | FALSE |  | 2 | 1 | 1 | 1 | ZELED-SL 65/35-700-80-35-MAL-W-4-W-UNV-MD-1-CT15(36) | 7 | 100 | 100 | Howard’s tours in the lab - need for Thursday Feb 7th latest | HOUSE | Joe Brier |  |  | ZEN-B | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 100 | 7 | 0 | 1 | 100 | 7 |  | 0 | 2019 | 2 | 5 | 1 | Complete | FALSE | FALSE
79418-3 | 4 | 2019-02-05 |  | Machine Shop Started | Mockup/Samples | FALSE | 79418 | High Priority |  | FALSE |  | 3 | 1 | 1 | 1 | ZESQD-SL 0/100-750-90-35-SO-4-W-UNV-MD-1-CT15(36)-SE | 5.6 | 100 | 100 | Howard’s tours in the lab - need for Thursday Feb 7th latest | HOUSE | Joe Brier |  |  | ZESQ-A | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 100 | 5.6 | 0 | 1 | 100 | 5.6 |  | 0 | 2019 | 2 | 5 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
79418-4 | 4 | 2019-02-05 |  | Machine Shop Started | Mockup/Samples | FALSE | 79418 | High Priority | Shortage | FALSE |  | 4 | 1 | 1 | 1 | ZESQD-SL 0/100-750-80-35-MAL-W-4-BLK-UNV-MD-1-CT15(36) | 5.6 | 100 | 100 | Howard’s tours in the lab - need for Thursday Feb 7th latest | HOUSE | Joe Brier |  |  | ZESQ-B | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 100 | 5.6 | 0 | 1 | 100 | 5.6 | Shortage | 0 | 2019 | 2 | 5 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
79124-1 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Mockup/Samples | FALSE | 79124 | Regular |  | FALSE |  | 1 | 1 | 1 | 2 | CLKLED-750-80-30-SO-12'-W-277-DP-1-TG9-FW(6) | 8.6 | 200 | 200 | Call Joe/Gagan when ready. | HOUSE | Joe Brier |  |  | A1-SAMPLE |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 100 | 4.3 | 0 | 2 | 200 | 8.6 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
79320-1 | 12 | 2019-02-04 | 2019-02-04 | Packaging Finished | Regular | FALSE | 79320 | High Priority |  | FALSE |  | 1 | 1 | 1 | 4 | BDLED-700-80-30-SO-32'-W-UNV-DP-1-CA(36) | 27.2 | 2080 | 2080 | MUST SHIP 2/4 | HOUSE | Rohan Srivastava |  |  | B2-32' | Picked - Complete |  | 2019-01-30 | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 520 | 6.8 | 4 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
73887-1 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 1 | 1 | 7 | 7 | BMSLED-1000-80-35-SO-4-BLK-UNV-DP-1-SC | 29.4 | 1638 | 0 |  | Visual | Christina Torok | Ship: Feb 6th Edited on 2/5/2019 |  | B-4 |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 234 | 4.2 | 7 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-3 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 3 | 1 | 34 | 34 | BMRLED-1000-80-35-FL-4-W-UNV-DP-1-TB15 | 105.4 | 7956 | 0 |  | Visual | Christina Torok |  |  | B3-4-GRID |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 234 | 3.1 | 34 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-4 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | BMRLED-1000-80-35-FL-8-W-UNV-DP-1-TB15 | 6.1 | 468 | 0 |  | Visual | Christina Torok |  |  | B3-8-GRID |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 468 | 6.1 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-5 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 5 | 1 | 1 | 2 | BMRLED-1000-80-35-FL-16-W-UNV-DP-1-DF | 12.8 | 936 | 0 |  | Visual | Christina Torok |  |  | B3-16-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 468 | 6.4 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-6 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | BMRLED-1000-80-35-FL-12-W-UNV-DP-1-TB15 | 8.7 | 702 | 0 |  | Visual | Christina Torok |  |  | B3-12-GRID |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 702 | 8.7 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-7 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular | Others | FALSE | Wrong Size Flange | 7 | 1 | 30 | 30 | BMRLED-1000-80-35-1.25M-4-W-UNV-DP-1-TB15 | 93 | 7500 | 0 |  | Visual | Christina Torok |  |  | B4-4-GRID |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 250 | 3.1 | 30 | 0 | 0 | 0 | Others | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-8 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 8 | 1 | 1 | 1 | BMRLED-1000-80-35-1.25M-12-W-UNV-DP-1-DF | 8.7 | 750 | 0 |  | Visual | Christina Torok |  |  | B4-12-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 750 | 8.7 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-9 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 9 | 1 | 1 | 2 | BMRLED-1000-80-35-1.25M-16-W-UNV-DP-1-DF | 12.8 | 998 | 0 |  | Visual | Christina Torok |  |  | B4-16-GRID |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 499 | 6.4 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-10 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 10 | 1 | 2 | 4 | BMRLED-1000-80-35-1.25M-20-W-UNV-DP-1-DF | 31.2 | 2500 | 0 |  | Visual | Christina Torok |  |  | B4-20-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 625 | 7.8 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-11 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 11 | 1 | 4 | 4 | BMRLED-1000-80-35-FL-6-W-UNV-DP-1-TB15 | 24.4 | 1372 | 0 |  | Visual | Christina Torok |  |  | B5-6-GRID |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 343 | 6.1 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-12 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 12 | 1 | 8 | 8 | BMDLED-400-80-35-SO-4-AP-UNV-DP-1-CTS(144) | 38.4 | 2200 | 0 |  | Visual | Christina Torok |  |  | B8-4 |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 275 | 4.8 | 8 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-13 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 13 | 1 | 4 | 4 | BMDLED-400-80-35-SO-8-AP-UNV-DP-1-CTS(144) | 29.6 | 2032 | 0 |  | Visual | Christina Torok |  |  | B8-8 |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 508 | 7.4 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-15 | 18 | 2019-02-05 |  | Machine Shop Finished | Regular | FALSE | 73887 | Regular | Others | TRUE | sub assembly | 15 | 1 | 2 | 14 | STFD-DSO(16-400)-80-35-AH(6)-BLK-UNV-MD-1-CA(36)-RC | 74 | 2664 | 0 |  | Visual | Christina Torok |  |  | Q4 |  | 2019-01-28 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 190.2857 | 5.2857 | 0 | 14 | 2664 | 74 |  | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
73887-16 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 16 | 1 | 12 | 12 | BMRLED-1000-80-35-FL-4-BLK-UNV-DP-1-DF | 37.2 | 2808 | 0 |  | Visual | Christina Torok |  |  | B3-4- INT METAL |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 234 | 3.1 | 12 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-18 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 18 | 1 | 3 | 3 | BMRLED-1000-80-35-FL-8-W-UNV-DP-1-DF | 18.3 | 1404 | 0 |  | Visual | Christina Torok |  |  | B3-8-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 468 | 6.1 | 2 | 1 | 468 | 6.1 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-19 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 19 | 1 | 4 | 4 | BMRLED-1000-80-35-FL-8-BLK-UNV-DP-1-DF | 24.4 | 1872 | 0 |  | Visual | Christina Torok |  |  | B3 8 INT METAL |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 468 | 6.1 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-20 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 20 | 1 | 3 | 3 | BMRLED-1000-80-35-FL-12-W-UNV-DP-1-DF | 26.1 | 2106 | 0 |  | Visual | Christina Torok |  |  | B3-12-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 702 | 8.7 | 1 | 2 | 1404 | 17.4 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-21 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 21 | 1 | 7 | 7 | BMRLED-1000-80-35-1.25M-4-W-UNV-DP-1-DF | 21.7 | 1764 | 0 |  | Visual | Christina Torok |  |  | B4-4-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 252 | 3.1 | 7 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-23 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 23 | 1 | 2 | 2 | BMRLED-1000-80-35-FL-6-W-UNV-DP-1-DF | 12.2 | 702 | 0 |  | Visual | Christina Torok |  |  | B5-6-GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 351 | 6.1 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-24 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 24 | 1 | 3 | 3 | BMRLED-1000-80-35-FL-6-BLK-UNV-DP-1-DF | 18.3 | 1053 | 0 |  | Visual | Christina Torok |  |  | B5-6-INT METAL |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 351 | 6.1 | 3 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
73887-26 | 18 | 2019-02-05 |  | Packaging Finished | Regular | FALSE | 73887 | Regular |  | FALSE |  | 26 | 1 | 3 | 3 | BMRLED-1000-80-35-FL-8-W-UNV-DP-1-DF | 18.3 | 1578 | 0 |  | Visual | Christina Torok |  |  | B5-8 GYP |  | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 526 | 6.1 | 3 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
78593-1 | 4 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 78593 | High Priority | PM wrong/missing info | TRUE | Sections | 1 | 1 | 3 | 3 | SL2HLED-2XSL-1000-750-80-40-SM-4-AP-UNV-DP-2-CA(36) | 18.3 | 1680 | 0 | Needs on site for Feb. 8th Must be off site by Feb. 11th - Detroit, MI | Clarus | Christina Torok | Ms:2/1 - Kaushik to advise. Edited on 1/31/2019 |  | LD | Picked - Complete | 2019-01-28 | 2019-02-01 | FALSE | FALSE | OK |  |  | Wiring Started |  | 560 | 6.1 | 0 | 3 | 1680 | 18.3 |  | 1 | 2019 | 2 | 1 | 2 | Partial | TRUE | TRUE |  | Done
78593-2 | 4 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 78593 | High Priority |  | FALSE |  | 2 | 1 | 2 | 2 | SL2HLED-2XSL-1000-750-80-40-SM-4-AP-UNV-DP-2-CA(36)-B1(BSL10LST) | 20 | 1480 | 0 | Needs on site for Feb. 8th Must be off site by Feb. 11th - Detroit, MI | Clarus | Christina Torok | Ms:2/3 - Kaushik to advise. Edited on 2/1/2019 |  | LDE | Picked - Complete | 2019-01-28 | 2019-02-01 | FALSE | FALSE | OK |  |  | Wiring Started |  | 740 | 10 | 0 | 2 | 1480 | 20 |  | 0 | 2019 | 2 | 1 | 2 | Partial | TRUE | TRUE |  | Done
78593-3 | 4 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 78593 | High Priority |  | FALSE |  | 3 | 1 | 2 | 2 | SCS-750-80-40-0.5P-6-AP-UNV-DP-1-S | 12.4 | 816 | 0 | Needs on site for Feb. 8th Must be off site by Feb. 11th - Detroit, MI | Clarus | Christina Torok | Ship: Feb 5th Edited on 2/5/2019 |  | LG | Picked - Complete | 2019-01-28 | 2019-02-01 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 408 | 6.2 | 0 | 2 | 816 | 12.4 |  | 1 | 2019 | 2 | 1 | 2 | Partial | TRUE | TRUE |  | Done
78593-4 | 4 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 78593 | High Priority |  | FALSE |  | 4 | 1 | 4 | 8 | SCDPAT-SQ-90(4)-750-80-40-0.5M-20-NL-AP-UNV-DP-1-CA(36) | 116 | 7040 | 0 | Needs on site for Feb. 8th Must be off site by Feb. 11th - Detroit, MI | Clarus | Christina Torok |  |  | LH | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 880 | 14.5 | 0 | 8 | 7040 | 116 |  | 0 | 2019 | 2 | 1 | 2 | Partial | TRUE | TRUE | Ready | Done
72101-1 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 72101 | Regular |  | FALSE |  | 1 | 1 | 38 | 228 | STFD-DSO(12'-400)-80-40-AH(6)-W-UNV-MD-1-CA(120)-RC | 1216 | 47500 | 0 |  | Ltg Spec | Christina Torok |  |  | 10 |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 208.3333 | 5.3333 | 0 | 228 | 47500 | 1216 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
76192-1 | 1 | 2019-01-30 | 2019-01-30 | Machine Shop Started | Regular | FALSE | 76192 | Regular | Others | FALSE | SUB ASSEMBLY | 1 | 1 | 2 | 2 | GPRLED-EX2W-750-80-35-RG2-7'-W-277-LT(L3D)-1-DF | 16 | 1470 | 0 | DO NOT SHIP BEFORE FEB 1ST 2019 | LS Phill | Jessica Kennedy | Not Machine Shop Finished - ETA: Extrusions? Edited on 1/29/2019 |  | FS-7' | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 735 | 8 | 0 | 2 | 1470 | 16 | Others | 1 | 2019 | 1 | 30 | 1 | Complete | TRUE | FALSE |  | Done
76192-2 | 1 | 2019-01-30 | 2019-01-30 | Machine Shop Started | Regular | FALSE | 76192 | Regular | Shortage | FALSE | Cartridge Ext?? | 2 | 1 | 2 | 2 | GPRLED-EX2W-750-80-35-RG2-9'-W-277-LT(L3D)-1-DF | 20 | 1890 | 0 | DO NOT SHIP BEFORE FEB 1ST 2019 | LS Phill | Jessica Kennedy | ETA: Extrusion: Feb 21st? - Erin, will try to expedite Edited on 1/30/2019 |  | FS-9' | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 945 | 10 | 0 | 2 | 1890 | 20 | Shortage | 0 | 2019 | 1 | 30 | 1 | Complete | TRUE | FALSE |  | Done
76192-3 | 1 | 2019-01-30 | 2019-01-30 | Machine Shop Started | Regular | FALSE | 76192 | Regular | Shortage | FALSE | Cartridge Ext?? | 3 | 1 | 2 | 2 | GPRLED-EX2W-750-80-35-RG2-12'-W-277-LT(L3D)-1-DF | 20 | 2520 | 0 | DO NOT SHIP BEFORE FEB 1ST 2019 | LS Phill | Jessica Kennedy | EX22118-8-WH Eta: 2/15 - Trying to expedite raw + paint. Edited on 1/31/2019 |  | FS-12' | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 1260 | 10 | 0 | 2 | 2520 | 20 | Shortage | 0 | 2019 | 1 | 30 | 1 | Complete | TRUE | FALSE |  | Done
76192-4 | 1 | 2019-01-30 | 2019-01-30 | Machine Shop Started | Regular | FALSE | 76192 | Regular |  | FALSE |  | 4 | 1 | 2 | 4 | GPRLED-EX2W-750-80-35-RG2-13'-W-277-LT(L3D)-1-DF | 28 | 2730 | 0 | DO NOT SHIP BEFORE FEB 1ST 2019 | LS Phill | Jessica Kennedy | ETA part: Feb 8th? (Paint) Edited on 2/5/2019 |  | FS-13' | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 682.5 | 7 | 0 | 4 | 2730 | 28 |  | 0 | 2019 | 1 | 30 | 1 | Complete | TRUE | FALSE |  | Done
76192-5 | 1 | 2019-01-30 | 2019-01-30 | Machine Shop Started | Regular | FALSE | 76192 | Regular |  | FALSE |  | 5 | 1 | 8 | 16 | GPRLED-EX2W-750-80-35-RG2-14'-W-277-LT(L3D)-1-DF | 112 | 11760 | 0 | DO NOT SHIP BEFORE FEB 1ST 2019 | LS Phill | Jessica Kennedy |  |  | FS-14' | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 735 | 7 | 0 | 16 | 11760 | 112 |  | 0 | 2019 | 1 | 30 | 1 | Complete | TRUE | FALSE |  | Done
76192-6 | 1 | 2019-01-30 | 2019-01-30 | Machine Shop Started | Regular | FALSE | 76192 | Regular |  | FALSE |  | 6 | 1 | 2 | 4 | GPRLED-EX2W-750-80-35-RG2-19'-W-277-LT(L3D)-1-DF | 32 | 3990 | 0 | DO NOT SHIP BEFORE FEB 1ST 2019 | LS Phill | Jessica Kennedy |  |  | FS-19' | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 997.5 | 8 | 0 | 4 | 3990 | 32 |  | 0 | 2019 | 1 | 30 | 1 | Complete | TRUE | FALSE |  | Done
79014-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 79014 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BILED-640-90-30-C-4'-W-UNV-DP-1-CA(48") | 9.6 | 640 | 0 |  | Internat | Rohan Srivastava |  |  | A-4' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 320 | 4.8 | 0 | 2 | 640 | 9.6 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
76592-1 | 7 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 76592 | Regular | Wrong part in BOM | TRUE | Driver | 1 | 1 | 1 | 8 | BMRLEDPAT-REC-90-1000-90-35-SO-RG-40-NL-W-277-DP-1-DS-FW(6) | 50 | 4210 | 0 | Partial | Internat | Rohan Srivastava |  |  | L6A-6'X14' | Picked - Complete | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 526.25 | 6.25 | 0 | 8 | 4210 | 50 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE | Ready
76592-2 | 7 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 76592 | Regular | Wrong part in BOM | TRUE | Driver | 2 | 1 | 1 | 8 | BMRLEDPAT-ASO-87+93+93+87-1000-90-35-SO-RG-35'-NL-W-277-DP-1-DS-FW(6) | 40 | 4027 | 0 | Partial | Internat | Rohan Srivastava |  |  | L6B-35' | Picked - Complete | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 503.375 | 5 | 0 | 8 | 4027 | 40 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE | Ready
76592-19 | 7 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 76592 | Regular |  | FALSE |  | 19 | 1 | 1 | 3 | BBPRLED-OPRI(1)-750-90-35-RG2-5' 1"X5'5 1/2"-W-277-DP-1-DS-TS(1)-FW(6) | 8.9 | 1160 | 0 | Partial | Internat | Rohan Srivastava |  |  | L7-10'6 1/2"-48.75 | Picked - Complete | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 386.6667 | 2.9667 | 0 | 3 | 1160 | 8.9 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE | Ready
76592-22 | 7 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 76592 | Regular | Wrong part in BOM | TRUE | Driver | 22 | 1 | 1 | 5 | BBPRLED-OPRI(2)-750-90-35-RG2-5' 2"X11'11 1/2"X8' 4"-W-277-DP-1-DS-TS(1)-FW(6) | 31 | 3480 | 0 | Partial | Internat | Rohan Srivastava |  |  | L7-25'5 1/2"-48.73 | Picked - Complete | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 696 | 6.2 | 0 | 5 | 3480 | 31 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE | Ready
77207-1 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 1 | 1 | 18 | 36 | TB2DILED-1000-400-80-30-SL-SO-16'-W-277-DP-2-CA(36) | 405 | 27540 | 0 |  | Internat | Rohan Srivastava |  |  | D-16' | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 765 | 11.25 | 0 | 36 | 27540 | 405 |  | 1 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-2 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular | Wrong info. In SD | TRUE | Indirect driver | 2 | 1 | 4 | 12 | TB2DILED-1000-400-80-30-SL-SO-30'-W-277-DP-2-CA(36) | 161.6 | 10880 | 0 |  | Internat | Rohan Srivastava |  |  | D-30' | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 906.6667 | 13.4667 | 0 | 12 | 10880 | 161.6 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-3 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 3 | 1 | 3 | 3 | B2SQDLED-1000-80-30-SO-2-W-277-DP-1-CA(96) | 12.6 | 390 | 0 |  | Internat | Rohan Srivastava |  |  | E-2 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 130 | 4.2 | 0 | 3 | 390 | 12.6 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-4 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 4 | 1 | 5 | 5 | B2SQDLED-1000-80-30-SO-4-W-277-DP-1-CA(96) | 21 | 1300 | 0 |  | Internat | Rohan Srivastava |  |  | E-4 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 260 | 4.2 | 0 | 5 | 1300 | 21 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-5 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 5 | 1 | 3 | 3 | B2SQDLED-1000-80-30-SO-6-W-277-DP-1-CA(96) | 20.7 | 1170 | 0 |  | Internat | Rohan Srivastava |  |  | E-6 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 390 | 6.9 | 0 | 3 | 1170 | 20.7 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-6 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 6 | 1 | 4 | 4 | B2SQDLED-1000-80-30-SO-8-W-277-DP-1-CA(96) | 27.6 | 2080 | 0 |  | Internat | Rohan Srivastava |  |  | E-8 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 520 | 6.9 | 0 | 4 | 2080 | 27.6 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-7 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 7 | 1 | 1 | 1 | B2SQDLED-1000-80-30-SO-8-W-277-DP-1+E(1)-CA(96) | 8.2 | 550 | 0 |  | Internat | Rohan Srivastava |  |  | E-8E | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 550 | 8.2 | 0 | 1 | 550 | 8.2 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-8 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 8 | 1 | 1 | 1 | BRLED-1000-80-30-FL-3-W-277-DP-1-DS-FW(6) | 4 | 195 | 0 |  | Internat | Rohan Srivastava |  |  | F-3 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 195 | 4 | 0 | 1 | 195 | 4 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-9 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 9 | 1 | 9 | 9 | BRLED-1000-80-30-FL-4-W-277-DP-1-DS-FW(6) | 36 | 2340 | 0 |  | Internat | Rohan Srivastava |  |  | F-4 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 260 | 4 | 0 | 9 | 2340 | 36 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-10 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 10 | 1 | 5 | 5 | BRLED-1000-80-30-FL-6-W-277-DP-1-DS-FW(6) | 37.5 | 1950 | 0 |  | Internat | Rohan Srivastava |  |  | F-6 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 390 | 7.5 | 0 | 5 | 1950 | 37.5 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-11 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 11 | 1 | 2 | 2 | BRLED-1000-80-30-FL-6-W-277-DP-1+E(1)-DS-FW(6) | 15.6 | 840 | 0 |  | Internat | Rohan Srivastava |  |  | F-6E | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 420 | 7.8 | 0 | 2 | 840 | 15.6 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-12 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 12 | 1 | 6 | 6 | BRLED-1000-80-30-FL-8-W-277-DP-1-DS-FW(6) | 45 | 3120 | 0 |  | Internat | Rohan Srivastava |  |  | F-8 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 520 | 7.5 | 0 | 6 | 3120 | 45 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-13 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 77207 | Regular |  | FALSE |  | 13 | 1 | 1 | 1 | BRLED-1000-80-30-FL-8-W-277-DP-1+E(1)-DS-FW(6) | 7.8 | 550 | 0 |  | Internat | Rohan Srivastava |  |  | F-8E | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 550 | 7.8 | 0 | 1 | 550 | 7.8 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | TRUE |  | Done
77207-14 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular |  | FALSE |  | 14 | 1 | 7 | 7 | BMRLED-1000-80-30-FL-6-W-277-DP-1-TG9-FW(6) | 44.1 | 2730 | 0 |  | Internat | Rohan Srivastava |  |  | H-6 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 390 | 6.3 | 0 | 7 | 2730 | 44.1 |  | 1 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE |  | Done
77207-15 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular |  | FALSE |  | 15 | 1 | 3 | 3 | BMRLED-1000-80-30-FL-8-W-277-DP-1-TG9-FW(6) | 18.9 | 1560 | 0 |  | Internat | Rohan Srivastava |  |  | H-8 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 520 | 6.3 | 0 | 3 | 1560 | 18.9 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE |  | Done
77207-16 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular |  | FALSE |  | 16 | 1 | 1 | 8 | BMRLEDPAT-REC-90(4)-1000-80-30-SO-FL-42'-EX-W-277-DP-1-DS-FW(6) | 52 | 3730 | 0 |  | Internat | Rohan Srivastava |  |  | H1-8'X13' REC | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 466.25 | 6.5 | 0 | 8 | 3730 | 52 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE | ToDo
77207-17 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular |  | FALSE |  | 17 | 1 | 1 | 1 | BMPRLED-1000-80-30-RG3-4' 8"-W-277-DP-1-DS-FW(6) | 7.2 | 303.52 | 0 |  | Internat | Rohan Srivastava |  |  | X-4' 8" | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 303.52 | 7.2 | 0 | 1 | 303.52 | 7.2 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE |  | Done
77207-18 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular |  | FALSE |  | 18 | 1 | 1 | 1 | BMPRLED-1000-80-30-RG3-7' 4"-W-277-DP-1-DS-FW(6) | 7.2 | 476.96 | 0 |  | Internat | Rohan Srivastava |  |  | X-7' 4" | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 476.96 | 7.2 | 0 | 1 | 476.96 | 7.2 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE |  | Done
77207-19 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular |  | FALSE |  | 19 | 1 | 1 | 2 | BMPRLED-1000-80-30-RG3-14'-W-277-DP-1-DS-FW(6) | 10.2 | 910.56 | 0 |  | Internat | Rohan Srivastava |  |  | X-14' | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 455.28 | 5.1 | 0 | 2 | 910.56 | 10.2 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE |  | Done
77207-20 | 4 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77207 | Regular | Others | TRUE | FIXTURE TYPE | 20 | 1 | 1 | 2 | BMPRLED-1000-80-30-RG3-19' 9"-W-277-DP-1-DS-FW(6) | 18 | 1300.8 | 0 |  | Internat | Rohan Srivastava |  |  | X-19' 9" | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 650.4 | 9 | 0 | 2 | 1300.8 | 18 |  | 0 | 2019 | 2 | 6 | 2 | Partial | TRUE | FALSE |  | Done
78050-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78050 | Regular | Wrong part in BOM | TRUE | Driver | 1 | 1 | 10 | 10 | ARSLED-600-80-30-S-4'-AP-120-DP-1-SC | 38 | 4731.5 | 0 |  | Internat | Rohan Srivastava |  |  | A-4' |  |  | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 473.15 | 3.8 | 0 | 10 | 4731.5 | 38 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
79121-1 | 4 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Replacement | FALSE | 79121 | Regular |  | FALSE |  | 1 | 1 | 10 | 10 | STSLF-ML-600-80-30-8'-BLK-277-MD-1-SB9 | 73 | 4400 | 4400 |  | Internat | Robert Lipura |  |  | LT-01-8'-23RD FL | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 440 | 7.3 | 1 | 9 | 3960 | 65.7 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
79322-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 79322 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | GPRLED-FC2W-1200-90-27-RG2-24 3/4"-W-UNV-DP-1-DF | 3 | 0 | 0 |  | prime we | Tajinder Singh |  |  | CAJ. | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 0 | 3 | 0 | 1 | 0 | 3 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
78727-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78727 | Regular |  | FALSE |  | 1 | 1 | 2 | 6 | BBPRLED-400-80-30-RG2-30'-W-UNV-DP-1-DF | 39.1 | 5760 | 0 |  | Enterpri | Jessica Pasternyk |  |  | F21-30'-ADD 1/4 |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 960 | 6.5167 | 0 | 6 | 5760 | 39.1 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78401-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78401 | High Priority |  | FALSE |  | 1 | 1 | 1 | 2 | BBDLED-750-80-35-SO-24-W-UNV-DP-1-CA(120) | 22.7 | 2118 | 0 |  | CAL | Stan Buyansky |  |  | F17A | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1059 | 11.35 | 0 | 2 | 2118 | 22.7 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78401-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 78401 | High Priority |  | FALSE |  | 2 | 1 | 1 | 1 | BBDLED-750-80-35-SO-8-W-UNV-DP-1-CA(120) | 8.7 | 706 | 0 |  | CAL | Stan Buyansky |  |  | F17B | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 706 | 8.7 | 0 | 1 | 706 | 8.7 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78854-1 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78854 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BMRLED-500-80-35-FL-4'-W-UNV-DP-1-D | 6.28 | 720 | 0 |  | Internat | Rohan Srivastava |  |  | LF02A-4' | Picked - Complete | 2019-01-27 | 2019-02-01 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 360 | 3.14 | 0 | 2 | 720 | 6.28 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
77187-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 77187 | Regular | Missing info. In SD | TRUE | Missing Info | 1 | 1 | 1 | 4 | SCDIPAT-REC-90(4)-500-400-80-30-SO-FL-40'-NL-AP-UNV-DP-2-CA(36) | 50 | 2890 | 0 |  | Internat | Gagandeep Singh |  |  | F3B-14'X6' REC | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 722.5 | 12.5 | 0 | 4 | 2890 | 50 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
77187-2 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 77187 | Regular | Missing info. In SD | TRUE | Missing Info | 2 | 1 | 1 | 1 | SCDIPAT-REC-90(4)-500-400-80-30-SO-FL-20'-NL-AP-UNV-DP-2-CA(36) | 30 | 1700 | 0 |  | Internat | Gagandeep Singh |  |  | FB-8'X2' REC | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1700 | 30 | 0 | 1 | 1700 | 30 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
72844-1 | 12 | 2019-02-07 | 2019-02-07 | Given to Shipping | Regular | FALSE | 72844 | Regular |  | FALSE |  | 1 | 1 | 8 | 8 | BBRLED-750-80-27-FL-6-W-UNV-DP-1-DF | 37.6 | 3104 | 0 |  | westernl | Sacha Lempka |  |  | R20 |  | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Given to Shipping |  | 388 | 4.7 | 8 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
76093-2 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 76093 | Regular |  | FALSE |  | 2 | 1 | 5 | 5 | WWR-SL-400-90-40-L-4-W-UNV-DP-1-DS | 24 | 2364 | 0 |  | LHI | Rajithan Sivapatharajahon |  |  | Y | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 472.8 | 4.8 | 0 | 5 | 2364 | 24 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE |  | Done
77393-1 | 1 | 2019-01-29 | 2019-01-29 | Machine Shop Finished | Regular | FALSE | 77393 | Regular | Others | FALSE | PATTERN INFORMATION/SUB ASSEMBLY | 1 | 1 | 1 | 6 | STFC-NO-DSO(24' 0"-400)-80-35-AG(5)-BLK-UNV-MD-1-CA(96)-RC | 32 | 1890 | 0 |  | JCWright | George Bacalla | MS: 01/29-Ship: Kaushik to advise Edited on 1/28/2019 ::: Ship: Jan 31st Edited on 1/29/2019 ::: Kaushik : Jan 31st Edited on 1/30/2019 - Waiting for material - Kaushik to advise ship date. Edited on 2/1/2019 |  | F12-24'-0" | Picked - Complete | 2019-01-27 | 2019-01-28 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 315 | 5.3333 | 0 | 6 | 1890 | 32 | Others | 1 | 2019 | 1 | 29 | 1 | Complete | TRUE | TRUE |  | Done
79010-1 | 12 | 2019-02-01 | 2019-02-01 | Machine Shop Started | Regular | FALSE | 79010 | Regular | Others | TRUE | MATERIAL???? | 1 | 1 | 1 | 1 | ARSLED-500-80-35-S-4'-AP-277-DP-1-SC | 3.8 | 380 | 0 |  | Enterpri | Jessica Pasternyk | Ms: 2/1 - Kaushik to advise. Edited on 2/1/2019::: Kaushik to advise Edited on 2/5/2019 |  | A-4' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 380 | 3.8 | 0 | 1 | 380 | 3.8 |  | 1 | 2019 | 2 | 1 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
72906-2 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | BRLED-1000-90-35-FL-4-W-120-DP-1-DS | 3.86 | 288 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | N1 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 288 | 3.86 | 0 | 1 | 288 | 3.86 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
72906-3 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 3 | 1 | 2 | 2 | BRLED-1000-90-35-FL-10-W-120-DP-1-DS | 20.58 | 1440 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | N2 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 720 | 10.29 | 0 | 2 | 1440 | 20.58 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
72906-4 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | BRLED-1000-90-35-FL-6-W-120-DP-1-DS | 7.3 | 432 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | N3 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 432 | 7.3 | 0 | 1 | 432 | 7.3 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
72906-5 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 5 | 1 | 2 | 10 | B2SQDLED-1000-90-35-SO-50-AP-120-DP-1-CA(36) | 81.32 | 8500 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | K50 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 850 | 8.132 | 0 | 10 | 8500 | 81.32 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
72906-6 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 6 | 1 | 1 | 2 | B2SQDLED-1000-90-35-SO-22-AP-120-DP-1-CA(36) | 18.34 | 1870 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | K22 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 935 | 9.17 | 0 | 2 | 1870 | 18.34 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
72906-7 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 7 | 1 | 1 | 2 | B2SQDLED-1000-90-35-SO-21-AP-120-DP-1-CA(36) | 18.34 | 1785 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | K21 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 892.5 | 9.17 | 0 | 2 | 1785 | 18.34 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
72906-8 | 18 | 2019-02-07 | 2019-01-09 | Machine Shop Finished | Regular | FALSE | 72906 | Regular |  | FALSE |  | 8 | 1 | 1 | 2 | B2SQDLED-1000-90-35-SO-20-AP-120-DP-1-CA(36) | 16.07 | 1700 | 0 | On site for February 15th Going To: WINNIPEG MB R2C 2Z2 | Integra | Rajithan Sivapatharajahon |  |  | K20 | Picked - Complete | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 850 | 8.035 | 0 | 2 | 1700 | 16.07 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
77607-1 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77607 | Regular |  | FALSE |  | 1 | 1 | 1 | 2 | B2SQDLED-750-90-35-SO-19-AP-120-DP-1-CA(36) | 16 | 1862 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | K19 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 931 | 8 | 0 | 2 | 1862 | 16 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
77607-2 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77607 | Regular |  | FALSE |  | 2 | 1 | 1 | 2 | B2SQDLED-750-90-35-SO-21-AP-120-DP-1-CA(36) | 18.4 | 2058 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | K21 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 1029 | 9.2 | 0 | 2 | 2058 | 18.4 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
77607-3 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77607 | Regular |  | FALSE |  | 3 | 1 | 1 | 3 | B2SQDLED-750-90-35-SO-35-AP-120-DP-1-CA(36) | 27.4 | 3430 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | K35 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 1143.3333 | 9.1333 | 0 | 3 | 3430 | 27.4 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
77607-4 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77607 | Regular |  | FALSE |  | 4 | 1 | 3 | 12 | B2SQDLED-750-90-35-SO-38-AP-120-DP-1-CA(36) | 94.8 | 11172 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | K38 | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 931 | 7.9 | 0 | 12 | 11172 | 94.8 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
77607-5 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 77607 | Regular |  | FALSE |  | 5 | 1 | 3 | 15 | BRLEDPAT-OPR-90(1)-1000-90-35-SO-FL-41-NL-W-120-DP-1-DS-C(L-SHAPE PATTERN, 15'H X 26'W) | 138 | 11400 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | N1 | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 760 | 9.2 | 0 | 15 | 11400 | 138 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE | Ready
77607-6 | 4 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77607 | Regular |  | FALSE |  | 6 | 1 | 36 | 36 | B2SQDLED-1000-90-35-SO-4-AP-120-DP-1-CA(36) | 151.2 | 14112 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | P | Picked - Complete | 2019-01-28 |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 392 | 4.2 | 0 | 36 | 14112 | 151.2 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78616-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78616 | Regular | Shortage | FALSE |  | 1 | 1 | 2 | 2 | BBDLED-750-80-40-SO-8-BLK-UNV-DP-1-CA(36") | 18 | 1440 | 0 |  | Integra | Rajithan Sivapatharajahon |  |  | D4 | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 720 | 9 | 0 | 2 | 1440 | 18 | Shortage | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE |  | Done
78279-1 | 18 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78279 | Regular | Shortage | FALSE | Extrusion | 1 | 1 | 2 | 2 | BBDILED-400-400-80-30-SO-8-BLK-UNV-DP-1-CA(48) | 23.6 | 1280 | 0 |  | Internat | Joe Brier |  |  | B |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 640 | 11.8 | 0 | 2 | 1280 | 23.6 | Shortage | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78279-2 | 18 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78279 | Regular |  | FALSE |  | 2 | 1 | 30 | 30 | BMRLED-650-80-30-FL-4-W-UNV-DP-1-TB9 | 96 | 7200 | 0 |  | Internat | Joe Brier |  |  | F |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 240 | 3.2 | 0 | 30 | 7200 | 96 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78703-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78703 | Regular | Missing parts in BOM | TRUE | Indirect Lens | 1 | 1 | 1 | 1 | SCWDI-750-500-80-35-SO-FL-4'-W-UNV-DP-1-B1(BSL10LST) | 10.5 | 660 | 0 |  | Internat | Rohan Srivastava |  |  | FT9-4' | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 660 | 10.5 | 0 | 1 | 660 | 10.5 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78699-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78699 | Regular |  | FALSE |  | 1 | 1 | 1 | 3 | BMDLED-1000-80-35-SO-26'-BLK-UNV-DP-1-CA(72") | 24 | 2030.1428 | 0 |  | SpecLAUS | Zahra Vatani |  |  | D2-26' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 676.7143 | 8 | 0 | 3 | 2030.1429 | 24 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78699-2 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78699 | Regular | Others | TRUE | SD quantity | 2 | 1 | 1 | 2 | BMDLED-1000-80-35-SO-24'-BLK-UNV-DP-1-CA(72") | 39 | 1880.1428 | 0 |  | SpecLAUS | Zahra Vatani |  |  | D2-24' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 940.0714 | 19.5 | 0 | 2 | 1880.1428 | 39 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78699-3 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78699 | Regular |  | FALSE |  | 3 | 1 | 2 | 4 | BMDLED-1000-80-35-SO-16'-BLK-UNV-DP-1-CA(72") | 29.2 | 2560.2857 | 0 |  | SpecLAUS | Zahra Vatani |  |  | D2-16' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 640.0714 | 7.3 | 0 | 4 | 2560.2857 | 29.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78699-4 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78699 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | BMDLED-1000-80-35-SO-8'-BLK-UNV-DP-1-CA(72") | 7.5 | 680.1428 | 0 |  | SpecLAUS | Zahra Vatani |  |  | D2-8' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 680.1428 | 7.5 | 0 | 1 | 680.1428 | 7.5 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78699-5 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78699 | Regular |  | FALSE |  | 5 | 1 | 1 | 1 | BMDLED-1000-80-35-SO-9'-BLK-UNV-DP-1-CA(72") | 9.8 | 755.1428 | 0 |  | SpecLAUS | Zahra Vatani |  |  | D2-9' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 755.1428 | 9.8 | 0 | 1 | 755.1428 | 9.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78699-6 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78699 | Regular |  | FALSE |  | 6 | 1 | 1 | 2 | BMDLED-1000-80-35-SO-20'-BLK-UNV-DP-1-CA(72") | 17 | 1575.1429 | 0 |  | SpecLAUS | Zahra Vatani |  |  | D2-20' |  | 2019-02-05 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 787.5714 | 8.5 | 0 | 2 | 1575.1429 | 17 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
79347-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 79347 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | B2SQDLED-750-80-30-SO-110 1/2"-W-UNV-DP-1-CT9(72)-C( ADD TO EXISITING) | 9.2 | 0 | 0 |  | RKI | Daljit Singh |  |  | ED-28' 5" |  |  | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 0 | 9.2 | 0 | 1 | 0 | 9.2 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
78943-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78943 | Regular |  | FALSE |  | 1 | 1 | 3 | 3 | SCDI-750-500-80-30-SO-FL-8'-BLK-UNV-DP-1-CA(36) | 30.6 | 2472 | 0 |  | RichardM | George Bacalla |  |  | L4A-8' | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 824 | 10.2 | 0 | 3 | 2472 | 30.6 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78328-1 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 1 | 1 | 7 | 7 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-1-CA(48) | 114.1 | 12012 | 0 |  | Performa | Stan Buyansky |  |  | P2 12' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1716 | 16.3 | 0 | 7 | 12012 | 114.1 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-2 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 2 | 1 | 7 | 7 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-2-CA(48)-B2(BSL10LST) | 196 | 14812 | 0 |  | Performa | Stan Buyansky |  |  | P2 12' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 2116 | 28 | 0 | 7 | 14812 | 196 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-3 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 3 | 1 | 5 | 10 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-2-CA(48)-B2(BSL10LST) | 210 | 19160 | 0 |  | Performa | Stan Buyansky |  |  | P2 24' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1916 | 21 | 0 | 10 | 19160 | 210 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-4 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 4 | 1 | 2 | 4 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-1-CA(48) | 64 | 6864 | 0 |  | Performa | Stan Buyansky |  |  | P2 24' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1716 | 16 | 0 | 4 | 6864 | 64 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-5 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 5 | 1 | 2 | 2 | BBLED2-SL-500-750-80-35-SO-8-W-UNV-DP-1-CA(48) | 23.6 | 2288 | 0 |  | Performa | Stan Buyansky |  |  | P3 8' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1144 | 11.8 | 0 | 2 | 2288 | 23.6 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-6 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | BRLED-750-80-35-FL-12-W-UNV-DP-1-DS-B2(BSL10LST) | 18.1 | 1260 | 0 |  | Performa | Stan Buyansky |  |  | G2E 12' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1260 | 18.1 | 0 | 1 | 1260 | 18.1 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
78328-7 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 7 | 1 | 4 | 4 | BRLED-750-80-35-FL-12-W-UNV-DP-1-DS | 41.2 | 3600 | 0 |  | Performa | Stan Buyansky |  |  | G2 12' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 900 | 10.3 | 0 | 4 | 3600 | 41.2 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-8 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 8 | 1 | 5 | 5 | BRLED-750-80-35-FL-6-W-UNV-DP-1-DS | 36.5 | 2250 | 0 |  | Performa | Stan Buyansky |  |  | G2 6' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 450 | 7.3 | 0 | 5 | 2250 | 36.5 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
78328-9 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 9 | 1 | 2 | 2 | BRLED-750-80-35-FL-6-W-UNV-DP-1-DS-B1(BSL10LST) | 22.4 | 1260 | 0 |  | Performa | Stan Buyansky |  |  | G2E 6' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 630 | 11.2 | 0 | 2 | 1260 | 22.4 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
78328-10 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 10 | 1 | 5 | 5 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-1-CA(48) | 81.5 | 8580 | 0 |  | Performa | Stan Buyansky |  |  | P2 12' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1716 | 16.3 | 0 | 5 | 8580 | 81.5 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-11 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular | Shortage | FALSE |  | 11 | 1 | 4 | 4 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-2-CA(48)-B2(BSL10LST) | 112 | 8464 | 0 |  | Performa | Stan Buyansky |  |  | P2 12' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 2116 | 28 | 0 | 4 | 8464 | 112 | Shortage | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78328-12 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 12 | 1 | 2 | 4 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-1-CA(48) | 56 | 6288 | 0 |  | Performa | Stan Buyansky |  |  | P2 18' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1572 | 14 | 0 | 4 | 6288 | 56 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78328-13 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 13 | 1 | 7 | 14 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48) | 210 | 22288 | 0 |  | Performa | Stan Buyansky |  |  | P2 18' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1592 | 15 | 0 | 14 | 22288 | 210 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-14 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 14 | 1 | 3 | 6 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48)-B3(BSL10LST) | 126 | 11172 | 0 |  | Performa | Stan Buyansky |  |  | P2E3-18' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1862 | 21 | 0 | 6 | 11172 | 126 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78328-15 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 15 | 1 | 8 | 16 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48)-B2(BSL10LST) | 304 | 28352 | 0 |  | Performa | Stan Buyansky |  |  | P2E2-18' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1772 | 19 | 0 | 16 | 28352 | 304 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-16 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 16 | 1 | 1 | 2 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-3-CA(48) | 32 | 3230.71 | 0 |  | Performa | Stan Buyansky |  |  | P2 18' 3CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1615.355 | 16 | 0 | 2 | 3230.71 | 32 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-17 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 17 | 1 | 2 | 4 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-3-CA(48)-B2(BSL10LST) | 80 | 7168 | 0 |  | Performa | Stan Buyansky |  |  | P2E 18' 3CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1792 | 20 | 0 | 4 | 7168 | 80 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
78328-18 | 7 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78328 | Regular |  | FALSE |  | 18 | 1 | 3 | 6 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-2-CA(48)-B2(BSL10LST) | 126 | 13206 | 0 |  | Performa | Stan Buyansky |  |  | P2 24' 2CKT | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 2201 | 21 | 0 | 6 | 13206 | 126 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75859-91 | 12 | 2019-02-13 |  | Scheduled/Released | Regular | FALSE | 75859 | Regular |  | FALSE |  | 91 | 1 | 2 | 2 | BMRLED-600-80-35-ASO-4-W-UNV-DP-1-DS-FW(6) | 8 | 322 | 0 | please pack by Floor - for the floor designation please look in to fixture types Produce and Ship as Scheduled LIne: 91 - Ship: UPS RED (Scheudled for 2/13) | Internat | Gagandeep Singh |  |  | F25, 4/9TH |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 161 | 4 | 0 | 2 | 322 | 8 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
74124-1 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 1 | 1 | 215 | 215 | BBRLED-1000-80-35-FL-4-W-UNV-DP-1-TG9 | 645 | 42140 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F1-4' G | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 196 | 3 | 0 | 215 | 42140 | 645 |  | 1 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-2 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 2 | 1 | 2 | 2 | BBRLED-1000-80-35-FL-8-W-UNV-DP-1-TG9 | 10 | 784 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F1-8' G | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 392 | 5 | 0 | 2 | 784 | 10 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-3 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 3 | 1 | 11 | 11 | BBRLED-1000-80-35-FL-4-W-UNV-DP-1-DF | 33 | 2156 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F1-4' DW | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 196 | 3 | 0 | 11 | 2156 | 33 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-4 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | BBRLED-1000-80-35-FL-8-W-UNV-DP-1-DF | 5 | 392 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F1-8' DW | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 392 | 5 | 0 | 1 | 392 | 5 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-5 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 5 | 1 | 1 | 2 | BBRLED-1000-80-35-FL-16-W-UNV-DP-1-DF | 10 | 784 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F1-16' DW | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 392 | 5 | 0 | 2 | 784 | 10 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-6 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 6 | 1 | 1 | 2 | BDLED-750-80-35-SO-20-W-UNV-DP-1-CA(36) | 18 | 980 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-20' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 490 | 9 | 0 | 2 | 980 | 18 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-7 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 7 | 1 | 1 | 2 | BDLED-750-80-35-SO-23-W-UNV-DP-1-CA(36) | 20 | 1127 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-23' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 563.5 | 10 | 0 | 2 | 1127 | 20 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-8 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 8 | 1 | 1 | 3 | BDLED-750-80-35-SO-26-W-UNV-DP-1-CA(36) | 25 | 1274 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-26' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 424.6667 | 8.3333 | 0 | 3 | 1274 | 25 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-9 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 9 | 1 | 1 | 3 | BDLED-750-80-35-SO-29-W-UNV-DP-1-CA(36) | 27 | 1421 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-29' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 473.6667 | 9 | 0 | 3 | 1421 | 27 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-10 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 10 | 1 | 1 | 3 | BDLED-750-80-35-SO-32-W-UNV-DP-1-CA(36) | 28 | 1568 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-32' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 522.6667 | 9.3333 | 0 | 3 | 1568 | 28 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-11 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 11 | 1 | 1 | 3 | BDLED-750-80-35-SO-35-W-UNV-DP-1-CA(36) | 30 | 1751 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-35' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 583.6667 | 10 | 0 | 3 | 1751 | 30 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-12 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 12 | 1 | 1 | 4 | BDLED-750-80-35-SO-38-W-UNV-DP-1-CA(36) | 35 | 1862 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-38' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 465.5 | 8.75 | 0 | 4 | 1862 | 35 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-13 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 13 | 1 | 1 | 4 | BDLED-750-80-35-SO-41-W-UNV-DP-1-CA(36) | 37 | 2009 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-41' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 502.25 | 9.25 | 0 | 4 | 2009 | 37 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-14 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 14 | 1 | 1 | 4 | BDLED-750-80-35-SO-44-W-UNV-DP-1-CA(36) | 37 | 2156 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-44' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 539 | 9.25 | 0 | 4 | 2156 | 37 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-15 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 15 | 1 | 1 | 4 | BDLED-750-80-35-SO-48-W-UNV-DP-1-CA(36) | 40 | 2352 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-48' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 588 | 10 | 0 | 4 | 2352 | 40 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-16 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 16 | 1 | 1 | 5 | BDLED-750-80-35-SO-51-W-UNV-DP-1-CA(36) | 45 | 2499 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-51' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 499.8 | 9 | 0 | 5 | 2499 | 45 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-17 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 17 | 1 | 1 | 5 | BDLED-750-80-35-SO-54-W-UNV-DP-1-CA(36) | 47 | 2646 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-54' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 529.2 | 9.4 | 0 | 5 | 2646 | 47 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-18 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 18 | 1 | 1 | 5 | BDLED-750-80-35-SO-57-W-UNV-DP-1-CA(36) | 50 | 2793 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-57' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 558.6 | 10 | 0 | 5 | 2793 | 50 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-19 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 19 | 1 | 1 | 5 | BDLED-750-80-35-SO-60-W-UNV-DP-1-CA(36) | 50 | 2940 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-60' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 588 | 10 | 0 | 5 | 2940 | 50 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-20 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 20 | 1 | 1 | 6 | BDLED-750-80-35-SO-64-W-UNV-DP-1-CA(36) | 54 | 3136 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F3-64' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 522.6667 | 9 | 0 | 6 | 3136 | 54 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-21 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 21 | 1 | 10 | 10 | BBDILED-640-400-80-35-SO-4-W-UNV-DP-1-CA(36) | 80 | 3000 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-4' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 300 | 8 | 0 | 10 | 3000 | 80 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-22 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 22 | 1 | 4 | 4 | BBDILED-640-400-80-35-SO-8-W-UNV-DP-1-CA(36) | 48 | 2400 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-8' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 600 | 12 | 0 | 4 | 2400 | 48 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE |  | Done
74124-23 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 23 | 1 | 10 | 20 | BBDILED-640-400-80-35-SO-16-W-UNV-DP-1-CA(36) | 230 | 12000 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-16' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 600 | 11.5 | 0 | 20 | 12000 | 230 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE |  | Done
74124-24 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 24 | 1 | 8 | 16 | BBDILED-640-400-80-35-SO-24-W-UNV-DP-2-CA(36) | 272 | 14400 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-24' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 900 | 17 | 0 | 16 | 14400 | 272 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE |  | Done
74124-25 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 25 | 1 | 4 | 4 | BBRLED-750-80-35-FL-4-W-UNV-DP-1-DF | 12 | 784 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F14-4' DW | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 196 | 3 | 0 | 4 | 784 | 12 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-26 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 26 | 1 | 3 | 3 | BBRLED-750-80-35-FL-8-W-UNV-DP-1-DF | 15 | 1176 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F14-8' DW | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 392 | 5 | 0 | 3 | 1176 | 15 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-27 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 27 | 1 | 8 | 8 | BBRLED-750-80-35-FL-12-W-UNV-DP-1-DF | 56 | 4704 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F14-12' DW | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 588 | 7 | 0 | 8 | 4704 | 56 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
74124-28 | 15 | 2019-02-12 | 2019-02-12 | Given to Shipping | Regular | FALSE | 74124 | Regular |  | FALSE |  | 28 | 1 | 8 | 16 | BBRLED-750-80-35-FL-20-W-UNV-DP-1-DF | 96 | 7840 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F14-20' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 490 | 6 | 0 | 16 | 7840 | 96 |  | 0 | 2019 | 2 | 12 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
75954-27 | 12 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 75954 | Regular |  | FALSE |  | 27 | 1 | 1 | 1 | BMPRLED-375-80-30-RG3-150 3/4"-W-UNV-DP-1-DS-TS(2)-CP | 23 | 1006 | 0 |  | KSA Ltg | Joshua Zimet |  |  | G17-150 3/4" | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1006 | 23 | 0 | 1 | 1006 | 23 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
75954-28 | 12 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 75954 | Regular |  | FALSE |  | 28 | 1 | 2 | 4 | BMPRLED-375-80-30-RG3-23'-W-UNV-DP-1-DS-TS(2)-CP | 64.4 | 3368 | 0 |  | KSA Ltg | Joshua Zimet |  |  | G17-23' | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 842 | 16.1 | 0 | 4 | 3368 | 64.4 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
75954-29 | 12 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 75954 | Regular |  | FALSE |  | 29 | 1 | 1 | 1 | BMPRLED-375-80-30-RG3-134"-W-UNV-DP-1-DS-TS(2)-CP | 16.3 | 800 | 0 |  | KSA Ltg | Joshua Zimet |  |  | G17-134" | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 800 | 16.3 | 0 | 1 | 800 | 16.3 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
75954-41 | 12 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 75954 | Regular |  | FALSE |  | 41 | 1 | 1 | 1 | BMPRLED-375-80-30-RG3-144"-W-UNV-DP-1-DS-TS(2)-CP | 16.3 | 936 | 0 |  | KSA Ltg | Joshua Zimet |  |  | G17-144" | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 936 | 16.3 | 0 | 1 | 936 | 16.3 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
75954-42 | 12 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 75954 | Regular |  | FALSE |  | 42 | 1 | 1 | 2 | BMPRLED-375-80-30-RG3-168"-W-UNV-DP-1-DS-TS(2)-CP | 23 | 775 | 0 |  | KSA Ltg | Joshua Zimet |  |  | G17-168" | Picked - Complete | 2019-01-29 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 387.5 | 11.5 | 0 | 2 | 775 | 23 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
75966-8 | 10 | 2019-02-11 | 2019-01-10 | Machine Shop Started | Regular | FALSE | 75966 | Regular | Shortage | FALSE | LN14045 | 8 | 1 | 520 | 520 | SKVLED-14-2400-80-40-2XVL-RE-W-277-DP-1-TB15-C(NLIGHT POWER PACK - NPP16-D) | 1820 | 130000 | 0 |  | KSA Ltg | Joshua Zimet |  |  | N27 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 250 | 3.5 | 58 | 462 | 115500 | 1617 | Shortage | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78534-1 | 15 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78534 | Regular |  | FALSE |  | 1 | 1 | 70 | 70 | BBRLED-950-80-35-FL-4'-W-UNV-DP-1-TG15-CP | 336 | 19320 | 0 |  | KSA Ltg | Joshua Zimet |  |  | R4 |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 276 | 4.8 | 0 | 70 | 19320 | 336 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78534-2 | 15 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78534 | Regular |  | FALSE |  | 2 | 1 | 19 | 19 | BBRLED-950-80-35-FL-2'-W-UNV-DP-1-TG15-CP | 91.2 | 3173 | 0 |  | KSA Ltg | Joshua Zimet |  |  | R4A |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 167 | 4.8 | 0 | 19 | 3173 | 91.2 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78926-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78926 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BBPRLED-400-80-35-RG2-148 3/4"-W-UNV-DP-1-TG9-FW(6)-C(LENGTH IS BETWEEN TBARS) | 10.3 | 1283 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | L5-15 |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1283 | 10.3 | 0 | 1 | 1283 | 10.3 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
77910-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77910 | Regular |  | FALSE |  | 1 | 1 | 4 | 8 | BMRLED-500-80-35-FL-16'-W-UNV-DP-1-TB15 | 51.2 | 4412 | 0 |  | KSA IA | Joshua Zimet |  |  | H | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | OK |  |  | Machine Shop Started |  | 551.5 | 6.4 | 0 | 8 | 4412 | 51.2 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
77910-2 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77910 | Regular |  | FALSE |  | 2 | 1 | 2 | 4 | BMRLED-500-80-35-FL-16'-W-UNV-DP-1+E(1)-TB15 | 26.4 | 2286 | 0 |  | KSA IA | Joshua Zimet |  |  | H-EM | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | OK |  |  | Machine Shop Started |  | 571.5 | 6.6 | 0 | 4 | 2286 | 26.4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE |  | Done
76817-1 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | SCS-300-80-35-0.5M-4-AP-UNV-DP-1-S | 3.8 | 227 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | H-4' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 227 | 3.8 | 1 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-2 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 2 | 1 | 2 | 4 | SCS-300-80-35-0.5M-14-AP-UNV-DP-1-S-B1(BSL310LP) | 32.4 | 1912 | 0 |  | RCLURIE2 | Sacha Lempka | Ship: Feb 5th Edited on 2/5/2019 |  | H/HE/H2-14' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 478 | 8.1 | 3 | 1 | 478 | 8.1 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-3 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular | Mechanical issue | TRUE | LED Tape Length | 3 | 1 | 2 | 4 | SCS-300-80-35-0.5M-22-AP-UNV-DP-1-S-B2(BSL310LP) | 48.6 | 3142 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | H/HE/H2-22' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 785.5 | 12.15 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-4 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | SCS-300-80-35-0.5M-6-AP-UNV-DP-1-S-B1(BSL310LP) | 10 | 502 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | HE/H2-6' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 502 | 10 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-5 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 5 | 1 | 2 | 2 | SCS-300-80-35-0.5M-6-AP-UNV-DP-1-S | 12.4 | 680 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | H-6' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 340 | 6.2 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-6 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 6 | 1 | 2 | 2 | SCS-300-80-35-0.5M-8-AP-UNV-DP-1-S-B1(BSL310LP) | 20 | 1232 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | H/HE-8' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 616 | 10 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-7 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 7 | 1 | 12 | 24 | SCS-400-80-35-0.5M-16-AP-UNV-DP-1-S-B1(BSL310LP) | 195.6 | 12828 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | H3/H3E-16' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 534.5 | 8.15 | 25 | -1 | -534.5 | -8.15 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-8 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 8 | 1 | 4 | 8 | SCS-400-80-35-0.5M-16-AP-UNV-DP-1-S-B2(BSL310LP) | 80 | 4924 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | H3/H3E-16' B2 | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 615.5 | 10 | 7 | 1 | 615.5 | 10 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-9 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 9 | 1 | 8 | 8 | SCDI-500-300-80-35-SO-FL-8-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) | 79.2 | 4608 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | I-8' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 576 | 9.9 | 9 | -1 | -576 | -9.9 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-10 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular | Wrong info. In SD | TRUE | Mixed Driver | 10 | 1 | 2 | 2 | SCDI-500-300-80-35-SO-FL-8-W-UNV-DP-2-CA(180)-B1(BSL310LP)-C(15FT POWER CORD & CABLES) | 27.2 | 1476 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | I/IE-8' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 738 | 13.6 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-11 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 11 | 1 | 2 | 4 | SCDI-500-300-80-35-SO-FL-18-W-UNV-DP-2-CA(180)-B1(BSL310LP)-C(15FT POWER CORD & CABLES) | 57.2 | 2916 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | I/IE/IE-18' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 729 | 14.3 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-12 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 12 | 1 | 2 | 4 | SCDI-500-300-80-35-SO-FL-18-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) | 57.2 | 2592 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | I/I2-18' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 648 | 14.3 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-13 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 13 | 1 | 1 | 2 | SCDI-500-300-80-35-SO-FL-14-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) | 22.2 | 1008 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | I/I2-14' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 504 | 11.1 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76817-14 | 4 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 76817 | Regular |  | FALSE |  | 14 | 1 | 1 | 1 | SCR-300-80-35-FL-8-W-UNV-DP-1-DS | 8.1 | 432 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | J-8' | Picked - Complete |  | 2019-01-29 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 432 | 8.1 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
79157-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 79157 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | SP000-BMRLED-100-90-30-ASO-6'-W-UNV-DP-1-TG9 | 11.8 | 960 | 0 |  | CW | Zahra Vatani |  |  | W5-6' |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 480 | 5.9 | 0 | 2 | 960 | 11.8 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
79157-2 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 79157 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | SP000-BMRLED-100-90-30-ASO-8'-W-UNV-DP-1-TG9 | 17.7 | 1920 | 0 |  | CW | Zahra Vatani |  |  | W4-8' |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 640 | 5.9 | 0 | 3 | 1920 | 17.7 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
79157-3 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 79157 | Regular |  | FALSE |  | 3 | 1 | 2 | 2 | SP000-BMRLED-100-90-30-ASO-8'-W-UNV-DP-1-DF | 11.6 | 1280 | 0 |  | CW | Zahra Vatani |  |  | W6-8' |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 640 | 5.8 | 0 | 2 | 1280 | 11.6 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78517-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78517 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | CCWL-SL-300-90-35-CL(8)-W-UNV-DP-1-C | 7.2 | 664 | 0 | UPS ORDER | RCLURIE2 | Sacha Lempka |  |  | F1-8 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 664 | 7.2 | 0 | 1 | 664 | 7.2 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78517-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78517 | Regular |  | FALSE |  | 2 | 1 | 2 | 2 | WWR-SL-400-80-35-3-W-UNV-DP-1-D-FW(6) | 6.2 | 708 | 0 | UPS ORDER | RCLURIE2 | Sacha Lempka |  |  | J-3 |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 354 | 3.1 | 0 | 2 | 708 | 6.2 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
77938-1 | 7 | 2019-02-07 | 2019-02-26 | Machine Shop Started | Regular | FALSE | 77938 | Regular | Missing parts in BOM | TRUE | Driver | 1 | 1 | 1 | 4 | SP18489(1)-STFDI-SLI-500-DSO-400-16'-90-30-AL(4')-AP-120-DP-2-CA(36")-SC | 40 | 1692 | 0 |  | Salex | Jessica Pasternyk |  |  | A-4' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 423 | 10 | 0 | 4 | 1692 | 40 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78778-1 | 4 | 2019-02-07 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78778 | Regular |  | FALSE |  | 1 | 1 | 1 | 4 | CCWH-SL-700-90-35-CL(45'8")-W-UNV-DP-1-AC | 37.8 | 3818 | 0 |  | K2SA LLC | Rajithan Sivapatharajahon |  |  | C1- 46' |  |  | 2019-02-01 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 954.5 | 9.45 | 0 | 4 | 3818 | 37.8 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
78778-2 | 4 | 2019-02-07 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78778 | Regular | Shortage | FALSE | END-CAP | 2 | 1 | 1 | 3 | CCWH-SL-700-90-35-CL(31'8")-W-UNV-DP-1-AC | 26 | 2656 | 0 |  | K2SA LLC | Rajithan Sivapatharajahon |  |  | C1-30' |  |  | 2019-02-01 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 885.3333 | 8.6667 | 0 | 3 | 2656 | 26 | Shortage | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
78964-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Replacement | FALSE | 78964 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | CCH-SL-700-80-40-CL(22)-W-277-DP-1-C-F-C (SEE PDF ATTACHED JOINING TO EXISTING FIXTURE ON SITE) | 38.6 | 910 | 0 |  | Visual | Anil Surendra Sanchara |  |  | C26C-7FT ADDER |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 455 | 19.3 | 0 | 2 | 910 | 38.6 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE
78643-5 | 15 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78643 | Regular |  | FALSE |  | 5 | 1 | 7 | 7 | TB2DILED-400-1000-80-35-SL-SO-8'-W-UNV-DP-1-CA(72) | 71.4 | 5652.85 | 0 |  | Alaska | George Bacalla |  |  | B-8' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 807.55 | 10.2 | 0 | 7 | 5652.85 | 71.4 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE |  | Done
79370-1 | 10 | 2019-02-11 | 2019-02-27 | Machine Shop Started | Regular | FALSE | 79370 | High Priority |  | FALSE |  | 1 | 1 | 29 | 29 | DIALED-22-2500-80-30-VL-W-UNV-DP-1-TB15 | 81.2 | 5639.05 | 0 | Must SHIP on FEB 11th, NO BUFFER!!! | K2SA LLC | Rajithan Sivapatharajahon |  |  | D22 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 194.45 | 2.8 | 0 | 29 | 5639.05 | 81.2 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
77908-1 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | SCDI-300-500-80-35-SO-2M-12'0"-AP-UNV-DP-1-CA(36) | 40 | 1560 | 0 |  | LS Phill | Gaurav Jain |  |  | A3-12' | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 780 | 20 | 1 | 1 | 780 | 20 |  | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-2 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 2 | 1 | 2 | 4 | SCDI-300-500-80-35-SO-2M-20'0"-AP-UNV-DP-1-CA(36) | 50 | 2600 | 0 |  | LS Phill | Gaurav Jain |  |  | A3-20' | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 650 | 12.5 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-3 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular | Wrong part in BOM | TRUE | Driver | 3 | 1 | 1 | 2 | SCDI-300-500-80-35-SO-2M-24'0"-AP-UNV-DP-1-CA(36) | 32 | 1560 | 0 |  | LS Phill | Gaurav Jain |  |  | A3-24' | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 780 | 16 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-4 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 4 | 1 | 2 | 6 | SCDI-300-500-80-35-SO-2M-28'0"-AP-UNV-DP-1-CA(36) | 68 | 3640 | 0 |  | LS Phill | Gaurav Jain |  |  | A3-28' | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 606.6667 | 11.3333 | 6 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | FALSE |  | Done
77908-5 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 5 | 1 | 2 | 6 | SCDI-300-500-80-35-SO-2M-32'0"-AP-UNV-DP-1-CA(36) | 74 | 4160 | 0 |  | LS Phill | Gaurav Jain |  |  | A3-32' | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 693.3333 | 12.3333 | 6 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-6 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 6 | 1 | 5 | 5 | SCR-500-80-35-0.5P-4'0"-W-UNV-DP-1-TB9 | 20 | 1100 | 0 |  | LS Phill | Gaurav Jain |  |  | A4 | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 220 | 4 | 5 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-7 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 7 | 1 | 4 | 4 | SCR-500-80-35-0.5P-4'0"-W-UNV-DP-1-TB9-B1(BSL10LST) | 28 | 1600 | 0 |  | LS Phill | Gaurav Jain |  |  | A4E | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 400 | 7 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-8 | 10 | 2019-02-05 | 2019-02-05 | Packaging Finished | Regular | FALSE | 77908 | Regular |  | FALSE |  | 8 | 1 | 12 | 12 | SKSLED-22-3200-80-35-GL-FL-UNV-DP-1-TB15 | 36 | 3420 | 0 |  | LS Phill | Gaurav Jain |  |  | D |  |  |  | FALSE | FALSE | OK |  |  | Packaging Finished |  | 285 | 3 | 8 | 4 | 1140 | 12 |  | 1 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-9 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular | PM wrong/missing info | TRUE | Sections | 9 | 1 | 12 | 12 | TWRWLED-SL 90/10-1250-80-35-SO-8'0"-W-UNV-DP-1-B1(BSL10LST) | 168 | 11280 | 0 |  | LS Phill | Gaurav Jain |  |  | QE | Picked - Complete | 2019-01-25 |  | FALSE | FALSE | OK |  |  | Given to Shipping |  | 940 | 14 | 8 | 4 | 3760 | 56 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
77908-10 | 7 | 2019-02-05 | 2019-02-05 | Given to Shipping | Regular | FALSE | 77908 | Regular |  | FALSE |  | 10 | 1 | 1 | 3 | SCDI-300-500-80-35-SO-2M-32'0"-AP-UNV-DP-1-CA(36)-B3(BSL10LST) | 48 | 2620 | 0 |  | LS Phill | Gaurav Jain |  |  | A3-32' EM(3) | Picked - Complete | 2019-01-25 | 2019-01-30 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 873.3333 | 16 | 3 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 2 | Partial | TRUE | TRUE |  | Done
78667-1 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Finished | Regular | FALSE | 78667 | Regular |  | FALSE |  | 1 | 1 | 1 | 2 | BMRLED-500-80-30-1.25M-16'-W-277-DP-1-TG9 | 13 | 1400 | 0 |  | LS Phill | Gaurav Jain |  |  | B1-16' |  | 2019-01-28 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 700 | 6.5 | 0 | 2 | 1400 | 13 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE |  | Done
78538-4 | 7 | 2019-02-07 | 2019-02-04 | Machine Shop Started | Regular | FALSE | 78538 | High Priority | Wrong info. In SD | TRUE | Voltage | 4 | 1 | 24 | 24 | BBS-S-8'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) | 96 | 11280 | 0 |  | CW | Zahra Vatani |  |  | L6-8' EM | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 470 | 4 | 0 | 24 | 11280 | 96 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
78538-5 | 7 | 2019-02-07 | 2019-02-04 | Machine Shop Started | Regular | FALSE | 78538 | High Priority | Wrong info. In SD | TRUE | Voltage | 5 | 1 | 12 | 12 | BBS-S-6'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) | 48 | 4680 | 0 |  | CW | Zahra Vatani |  |  | L6-6' EM | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 390 | 4 | 0 | 12 | 4680 | 48 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
78538-6 | 7 | 2019-02-07 | 2019-02-04 | Machine Shop Started | Regular | FALSE | 78538 | High Priority | Wrong info. In SD | TRUE | Voltage | 6 | 1 | 10 | 20 | BBS-S-16'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) | 40 | 7900 | 0 |  | CW | Zahra Vatani |  |  | L6-16' EM | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 395 | 2 | 0 | 20 | 7900 | 40 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
75392-1 | 12 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 75392 | Regular |  | FALSE |  | 1 | 1 | 1 | 6 | CCWH-SL-1100-80-27-CP(30')-W-120-DP-1-C | 34 | 2945 | 0 |  | Internat | Gagandeep Singh |  |  | LT19D-2'10"X25'7"X1'7" |  |  | 2019-01-30 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 490.8333 | 5.6667 | 0 | 6 | 2945 | 34 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77868-1 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77868 | Regular |  | FALSE |  | 1 | 1 | 1 | 22 | SP16308(2)-CCWH-SL-1100-80-27-CP(197' 2")-C(NATATORIUM)-120-DP-2-C | 210 | 18900 | 0 |  | Internat | Rohan Srivastava |  |  | LT-05D-21'X77' 7" RECT |  | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 859.0909 | 9.5455 | 0 | 22 | 18900 | 210 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77868-2 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 77868 | Regular |  | FALSE |  | 2 | 1 | 1 | 13 | SP16308(2)-CCH-SL-1100-80-27-CP(103' 7")-C(NATATORIUM)-120-DP-1-C | 98 | 9734 | 0 |  | Internat | Rohan Srivastava |  |  | LT-25D-80'X23' 7"- L SHAPE |  | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 748.7692 | 7.5385 | 0 | 13 | 9734 | 98 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
79043-1 | 10 | 2019-02-05 | 2019-02-12 | Packaging Finished | Regular | FALSE | 79043 | Regular |  | FALSE |  | 1 | 1 | 10 | 10 | DIALED-22-3600-80-35-VL-W-277-LT(LDE1)-1-TG9-AR | 30 | 2950 | 0 | MUST SHIP BY 2/5/2019 | Internat | Rohan Srivastava |  |  | F1-2X2 |  |  |  | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 295 | 3 | 10 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78820-1 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78820 | Regular | Shortage | FALSE |  | 1 | 1 | 7 | 7 | DIALED-22-2500-90-35-VL-W-277-LT(LDE5)-1-TB15-FW(6') | 20.3 | 1988 | 0 |  | Internat | Rohan Srivastava |  |  | LT-62 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 284 | 2.9 | 0 | 7 | 1988 | 20.3 | Shortage | 1 | 2019 | 2 | 7 | 2 | Partial | FALSE | TRUE |  | Done
78820-2 | 4 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78820 | Regular |  | FALSE |  | 2 | 1 | 14 | 14 | TB2DILED-600-500-90-35-SO-SO-4'-W-UNV-LT(LDE5)-1-CT15(60) | 98 | 8680 | 0 |  | Internat | Rohan Srivastava |  |  | LT-103.4' |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 620 | 7 | 0 | 14 | 8680 | 98 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
78820-3 | 4 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78820 | Regular |  | FALSE |  | 3 | 1 | 24 | 24 | TB2DILED-600-500-90-35-SO-SO-8'-W-UNV-LT(LDE5)-1-CT15(60) | 256.8 | 29736 | 0 |  | Internat | Rohan Srivastava |  |  | LT-103.8' |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1239 | 10.7 | 0 | 24 | 29736 | 256.8 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
78820-4 | 4 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78820 | Regular |  | FALSE |  | 4 | 1 | 24 | 24 | TB2DILED-600-500-90-35-SO-SO-4'-W-UNV-LT(LDE5)-1-CA(96) | 168 | 14880 | 0 |  | Internat | Rohan Srivastava |  |  | LT-103.4'-CA |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 620 | 7 | 0 | 24 | 14880 | 168 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
78820-5 | 4 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78820 | Regular |  | FALSE |  | 5 | 1 | 18 | 18 | TB2DILED-600-500-90-35-SO-SO-8'-W-UNV-LT(LDE5)-1-CA(96) | 192.6 | 22302 | 0 |  | Internat | Rohan Srivastava |  |  | LT-103.8'-CA |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1239 | 10.7 | 0 | 18 | 22302 | 192.6 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
73829-1 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority |  | FALSE |  | 1 | 1 | 8 | 24 | CUBLED-SL 75/25-1000-90-35-PL-36-W-UNV-DP-1-CT9(120) | 410.4 | 26756.464 | 0 |  | Resource | George Bacalla |  |  | A1 | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 1114.8527 | 17.1 | 29 | -5 | -5574.2633 | -85.5 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-2 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority |  | FALSE |  | 2 | 1 | 9 | 27 | CUBLED-SL 75/25-1000-90-35-PL-28-W-UNV-DP-1-CT9(120) | 373.5 | 23279.526 | 0 |  | Resource | George Bacalla |  |  | A2 | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 862.2047 | 13.8333 | 5 | 22 | 18968.5027 | 304.3333 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-3 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority | Others | FALSE |  | 3 | 1 | 1 | 2 | CUBLED-SL 75/25-1000-90-35-PL-24-W-UNV-DP-1-CT9(120) | 34.5 | 3694.54 | 0 |  | Resource | George Bacalla |  |  | A3 | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 1847.27 | 17.25 | 0 | 2 | 3694.54 | 34.5 | Others | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-4 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority |  | FALSE |  | 4 | 1 | 2 | 4 | SCR-500-90-35-FL-16-W-UNV-DP-1-DF | 23 | 2697.756 | 0 |  | Resource | George Bacalla |  |  | G | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 674.439 | 5.75 | 0 | 4 | 2697.756 | 23 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-5 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority |  | FALSE |  | 5 | 1 | 1 | 3 | B6RLED-500-90-35-FL-36-W-UNV-DP-1-TB9 | 27.7 | 2340 | 0 |  | Resource | George Bacalla |  |  | H | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 780 | 9.2333 | 0 | 3 | 2340 | 27.7 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-6 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority |  | FALSE |  | 6 | 1 | 1 | 1 | BBRLED-1000-90-35-FL-8-W-UNV-DP-1-DF | 4.7 | 941.283 | 0 |  | Resource | George Bacalla |  |  | L | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 941.283 | 4.7 | 0 | 1 | 941.283 | 4.7 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-7 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority |  | FALSE |  | 7 | 1 | 1 | 1 | BMRLED-1000-90-35-FL-12-W-UNV-DP-1-DF | 8.7 | 1411.926 | 0 |  | Resource | George Bacalla |  |  | M | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 1411.926 | 8.7 | 0 | 1 | 1411.926 | 8.7 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
73829-8 | 7 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 73829 | High Priority | Wrong part in BOM | TRUE | Drivers | 8 | 1 | 1 | 1 | TBDILED-650-400-90-35-SO-10-W-UNV-DP-1-CT9(36) | 12.8 | 1991.17 | 0 |  | Resource | George Bacalla |  |  | N | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 1991.17 | 12.8 | 0 | 1 | 1991.17 | 12.8 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
70411-37 | 7 | 2019-02-08 |  | Wiring Started | Regular | FALSE | 70411 | Regular | Others | TRUE | Power cord Size | 37 | 2 | 281 | 281 | SCRM-3'-(3)-1000-90-TW2750-D55-BLK-C(HS512W1186)-UNV-O(DALIDT6)-1-TB15-LBC-C(PENDANT HANGERS 120" WITH CORD) | 1405 | 71655 | 0 | HARVARD | IllumBos | Gagandeep Singh |  |  | L-01.11-3' |  |  |  | FALSE | FALSE | OK |  |  | Wiring Started |  | 255 | 5 | 53 | 228 | 58140 | 1140 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
75462-4 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 4 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | 20 | 1440 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05-10'-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 10 | 0 | 2 | 1440 | 20 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-5 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 5 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-11'8"-C(ROCKFON723)-UNV-DP-1-TG9 | 10 | 764 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05-11'8"-PATH-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 764 | 10 | 0 | 1 | 764 | 10 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-6 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 6 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | 14 | 1152 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 2 | 1152 | 14 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-7 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 7 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS | 7 | 432 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05A-6'-TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 7 | 0 | 1 | 432 | 7 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-8 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority | Wrong info. In SD | TRUE | Fixture Finish | 8 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-DS | 10 | 720 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05B-10'-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 10 | 0 | 1 | 720 | 10 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-9 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 9 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-18'-W-UNV-DP-1-DS | 16 | 1296 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05B-18'--5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 648 | 8 | 0 | 2 | 1296 | 16 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-10 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 10 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-14'-W-UNV-DP-1-DS | 14 | 1008 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05B-14'-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 504 | 7 | 0 | 2 | 1008 | 14 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-11 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority |  | FALSE |  | 11 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-4'-W-UNV-DP-1-DS | 4 | 288 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F05B-4'-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 288 | 4 | 0 | 1 | 288 | 4 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75462-14 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority | Others | FALSE | Missing Reflector Cut Length | 14 | 1 | 1 | 24 | SP18276-SCRPAT-OPR-131°+49°+71°+109°+91°+89°+87°+101°-350-80-35-FL-339-EX-W-UNV-DP-6-DS-C(ANGLED ENDS) | 622 | 20305 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F10-339'-5TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 846.0417 | 25.9167 | 0 | 24 | 20305 | 622 | Others | 0 | 2019 | 2 | 11 | 0 | Complete | FALSE | FALSE
75462-15 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75462 | High Priority | Others | FALSE | Missing Reflector Cut Length | 15 | 1 | 1 | 3 | SP18276-SCR-350-80-35-FL-46'5"-W-UNV-DP-1-DS-C(ANGLED ENDS) | 44 | 2515 | 0 | Akamai 5th Floor | IllumBos | Gagandeep Singh |  |  | F10-46'5"-5TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 838.3333 | 14.6667 | 0 | 3 | 2515 | 44 | Others | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75475-5 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 5 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | 9 | 720 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05-10'-6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 9 | 0 | 1 | 720 | 9 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75475-6 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8-C(ROCKFON723)-UNV-DP-1-TG9 | 7 | 576 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'-PATH 6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 1 | 576 | 7 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75475-7 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 7 | 1 | 4 | 4 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | 28 | 2304 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'-6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 4 | 2304 | 28 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75475-8 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 8 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-4'-C(PS541A1391)-UNV-DP-1-DS | 4 | 288 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05A-4'-PATH-6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 288 | 4 | 0 | 1 | 288 | 4 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75475-9 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 9 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | 9 | 720 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05-10'PATH-6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 9 | 0 | 1 | 720 | 9 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75475-10 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 10 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS-C(1 LONG SIDE D) | 16 | 1440 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05B-20'-6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 8 | 0 | 2 | 1440 | 16 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75475-27 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 27 | 1 | 1 | 3 | SP18276-SCR-350-80-35-FL-46'2"-W-UNV-DP-1-DS-C(ANGLED ENDS) | 44 | 2470 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F10-46'2"-ELEVATORS-6TH FL |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 823.3333 | 14.6667 | 0 | 3 | 2470 | 44 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
75475-28 | 7 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 75475 | Regular |  | FALSE |  | 28 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 | 14 | 864 | 0 | Akamai 6th Floor | IllumBos | Gagandeep Singh |  |  | F05-6'-06-30T |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 7 | 0 | 2 | 864 | 14 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
75693-4 | 7 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 75693 | Regular | Others | FALSE | sub assembly parts for lines 4 to 8 | 4 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | 14 | 1152 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh | Ms: 2/4 - Kaushik to advise. Edited on 2/1/2019 |  | F05-8'-7TH FL | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 576 | 7 | 0 | 2 | 1152 | 14 | Others | 1 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-5 | 7 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 75693 | Regular |  | FALSE |  | 5 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | 18 | 1440 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh | MS: 2/6 - Ship: Kaushik to advise?? Edited on 2/5/2019 |  | F05-10'-7TH FL | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 720 | 9 | 0 | 2 | 1440 | 18 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-6 | 7 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 75693 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-12'-W-UNV-DP-1-TG9 | 9 | 864 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F05-12'-7TH FL | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 864 | 9 | 0 | 1 | 864 | 9 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-7 | 7 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 75693 | Regular |  | FALSE |  | 7 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS | 7 | 432 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F05A-6'-7TH FL | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 432 | 7 | 0 | 1 | 432 | 7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-8 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Shortage | FALSE |  | 8 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-C(PS541A1391)-UNV-DP-1-DS | 7 | 432 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F05A-6'-PATH-7TH FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 7 | 0 | 1 | 432 | 7 | Shortage | 1 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-12 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Wrong info. In SD | TRUE | Missing Dimension | 12 | 1 | 1 | 3 | SP18435(2)-BMPRLED-OPRI(79°)-750-80-35-RG3-22'11 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(102° ANGLED END) | 20.16 | 1930 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-13'5-7/16"X9'6-5/16"-07-15H | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 643.3333 | 6.72 | 0 | 3 | 1930 | 20.16 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-13 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Wrong info. In SD | TRUE | Missing Dimension | 13 | 1 | 1 | 3 | SP18435(2)-BMPRLED-OPRI(79°)-750-80-35-RG3-19'10 5/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(102° ANGLED END) | 18.88 | 1750 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'9-3/16"X8'11-1/8"-07-15K | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 583.3333 | 6.2933 | 0 | 3 | 1750 | 18.88 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-14 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Wrong info. In SD | TRUE | SD Revision | 14 | 1 | 1 | 3 | SP18435(2)-BMPRLED-OPRI(102°)-750-80-35-RG3-17'1 5/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(79°ANGLED END) | 16.27 | 1570 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'2-7/16"X6'11-3/16"-07-15L | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 523.3333 | 5.4233 | 0 | 3 | 1570 | 16.27 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-17 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 17 | 1 | 1 | 3 | SP18435(2)-BMPRLED-OPRI(1)-750-80-35-RG3-18'8 1/2"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(74° ANGLED END) | 19.03 | 1590 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-6'7-13/16"X12'-11/16"-07-17T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 530 | 6.3433 | 0 | 3 | 1590 | 19.03 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-18 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 18 | 1 | 1 | 2 | SP18435(2)-BMPRLED-750-80-35-RG3-10'3 3/16"-W-UNV-DP-1-TG9-TS(1)-C(74° & 107° ANGLED END) | 9.28 | 1135 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'3-3/16"-07-19T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 567.5 | 4.64 | 0 | 2 | 1135 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-19 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 19 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-9'10 1/6"-W-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'10-1/16"-07-20T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-20 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 20 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-10'4 1/8"-W-UNV-DP-1-TG9-TS(1) | 9.28 | 735 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'4-1/8"-07-22T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 735 | 9.28 | 0 | 1 | 735 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-21 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 21 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-10'4 1/8"-W-UNV-DP-1-TG9-TS(1) | 9.28 | 735 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'4-1/8"-07-24T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 735 | 9.28 | 0 | 1 | 735 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-22 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 22 | 1 | 1 | 3 | SP18435(2)-BMPRLED-OPRI(107°)-750-80-35-RG3-21'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(72.5°ANGLED END) | 22.11 | 1870 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'10-5/16"X10'4-7/8"-07-17W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 623.3333 | 7.37 | 0 | 3 | 1870 | 22.11 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-23 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 23 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-9'7 3/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'7-3/8"-07-19W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-24 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Missing parts in BOM | TRUE | SD Revision | 24 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-9'5 1/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'5-1/4"-07-21W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-25 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 25 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-9'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'3-3/16"-07-23W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-26 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 26 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-9'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'3-3/16"-07-26W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-27 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 27 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-8'10"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 6.7 | 615 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-8'10"-07-28W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 615 | 6.7 | 0 | 1 | 615 | 6.7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-28 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 28 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-8'4 7/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 6.7 | 615 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-8'4 7/8"-07-30W | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 615 | 6.7 | 0 | 1 | 615 | 6.7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-29 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 29 | 1 | 1 | 2 | SP18435(2)-BMPRLED-750-80-35-RG3-22'6 5/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1)-C(98° & 82° ANGLED END) | 18.78 | 1855 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-22'6-5/8"-07-34T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 927.5 | 9.39 | 0 | 2 | 1855 | 18.78 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-30 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 30 | 1 | 1 | 3 | SP18435(2)-BMPRLED-750-80-35-RG3-24'11 1/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1)-C(98° & 75° ANGLED END) | 22.95 | 1975 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-24'11-1/8"-07-39T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 658.3333 | 7.65 | 0 | 3 | 1975 | 22.95 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-31 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 31 | 1 | 1 | 3 | SP18435(2)-BMPRLED-750-80-35-RG3-34'7 1/2"-W-UNV-DP-1-TG9-TS(1)-C(64° & 105° ANGLED END) | 28.28 | 2575 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-34'7-1/2"-07-41F | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 858.3333 | 9.4267 | 0 | 3 | 2575 | 28.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-32 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Missing info. In SD | TRUE | Missing Diamension | 32 | 1 | 1 | 8 | SP18435(2)-BMPRLED-OPRI(113°)+OPRO(113°+67°)-750-80-35-RG3-48'6" 3/8"-W-UNV-DP-1-TG9-TS(4)-C(79°&67°ANGLED END) | 57 | 4240 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-13'5"X8'4"X8'4"X18'3"-04-44M | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 530 | 7.125 | 0 | 8 | 4240 | 57 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-33 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 33 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-7'10 3/8"-W-UNV-DP-1-DS-TS(1) | 7.67 | 555 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04A-7'10-3/8"-07-22F | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 555 | 7.67 | 0 | 1 | 555 | 7.67 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-36 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular | Others | FALSE | SD revision/SUB ASSEMBLY | 36 | 1 | 1 | 3 | SP18276-SCR-350-80-35-FL-45'5"-W-UNV-DP-1-DS-C(85°&46° ANGLED ENDS) | 43.2 | 2470 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F10-46'5"-ELEC LOBBY-7TH FL | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 823.3333 | 14.4 | 0 | 3 | 2470 | 43.2 | Others | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-40 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 40 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-10'-W-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-10'-07-19T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-41 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 41 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-8'-W-UNV-DP-1-TG9-TS(1) | 6.7 | 555 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-8'-07-20T & 22T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 555 | 6.7 | 0 | 1 | 555 | 6.7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-42 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 42 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-7'8"-W-UNV-DP-1-TG9-TS(1) | 6.7 | 555 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-7'8"-07-24T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 555 | 6.7 | 0 | 1 | 555 | 6.7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-43 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 43 | 1 | 1 | 2 | BMPRLED-750-80-35-RG3-17'8"-W-UNV-DP-1-TG9-TS(1) | 16.2 | 1155 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-17'8"-07-24T | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 577.5 | 8.1 | 0 | 2 | 1155 | 16.2 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-44 | 7 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 75693 | Regular |  | FALSE |  | 44 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-C(ROCKFON723)-UNV-DP-1-DS | 7 | 432 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F05-6'-PATH-7TH FL | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 432 | 7 | 0 | 1 | 432 | 7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75693-45 | 7 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 75693 | Regular |  | FALSE |  | 45 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-12'2"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 9.28 | 795 | 0 | Akamai 7th Floor | IllumBos | Gagandeep Singh |  |  | F04-12'2"-07-15D | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 795 | 9.28 | 0 | 1 | 795 | 9.28 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
75745-5 | 7 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75745 | Regular |  | FALSE |  | 5 | 1 | 4 | 4 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | 28 | 2304 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh | Eta:1/28 Edited on 1/28/2019 |  | F05-8'-8TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 4 | 2304 | 28 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
75745-6 | 7 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75745 | Regular |  | FALSE |  | 6 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-16'-W-UNV-DP-1-TG9 | 13 | 1152 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh |  |  | F05-16'-8TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 6.5 | 0 | 2 | 1152 | 13 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
75745-7 | 7 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75745 | Regular | Wrong part in BOM | TRUE | Driver | 7 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8'-C(ROCKFON723)-UNV-DP-1-TG9 | 7 | 576 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'-PATH-8TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 1 | 576 | 7 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
75745-8 | 7 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75745 | Regular |  | FALSE |  | 8 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | 9 | 720 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh |  |  | F05-10'PATH -8TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 9 | 0 | 1 | 720 | 9 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
75745-9 | 7 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75745 | Regular |  | FALSE |  | 9 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS-C(1 LONG SIDE D) | 16 | 1440 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh |  |  | F05B-20'-8TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 8 | 0 | 2 | 1440 | 16 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
75745-13 | 1 | 2019-01-28 |  | Wiring Started | Regular | FALSE | 75745 | Regular | Shortage | FALSE | Store lost EN19793J-WH | 13 | 1 | 1 | 5 | SP18435(2)-BMPRLED-OPRI(119°)-750-80-35-RG3-36'6"-W-UNV-DP-1-TG9-TS(2)-C(140.6° ANGLED END) | 31.8 | 2770 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh | Wrong parts in bom - Sukhwinder to follow Edited on 1/28/2019 :: Ship: Jan 31st Edited on 1/29/2019 - Ship: 2/4 Edited on 2/1/2019::: Sent wrong part for paint ; - Erin to advise eta? Edited on 2/5/2019 |  | F04-6'4-11/16"X30'1-15/16"-08-39Q | Picked - Complete | 2019-01-25 | 2019-01-23 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 554 | 6.36 | 4 | 1 | 554 | 6.36 | Shortage | 1 | 2019 | 1 | 28 | 1 | Complete | TRUE | TRUE | Ready | Done
75745-21 | 7 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75745 | Regular | Others | FALSE | SD Revision | 21 | 1 | 1 | 3 | SP18276-SCR-350-80-35-FL-46'5"-W-UNV-DP-1-DS-C(133° & 85° ANGLED ENDS) | 43.22 | 2515 | 0 | Akamai 8th Floor | IllumBos | Gagandeep Singh |  |  | F10-46'5"-ELEV LOBBY-8TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 838.3333 | 14.4067 | 0 | 3 | 2515 | 43.22 | Others | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
75746-5 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 5 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 | 7 | 432 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F05-6'-10TH FL | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 7 | 0 | 1 | 432 | 7 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
75746-6 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | 7 | 576 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'-10TH FL | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 1 | 576 | 7 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
75746-7 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 7 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 | 9 | 720 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F05-10'-10TH FL | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 9 | 0 | 1 | 720 | 9 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
75746-8 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 8 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS | 4 | 1440 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F05A-6'-10TH FL | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 2 | 0 | 2 | 1440 | 4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
75746-22 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 22 | 1 | 1 | 1 | BMPRLED-750-80-35-RG3-9'8 1/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | 9.28 | 675 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'8-1/8"-10-33X | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 675 | 9.28 | 0 | 1 | 675 | 9.28 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
75746-24 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 24 | 1 | 1 | 3 | BMPRLED-OPRI(1)-750-80-35-RG3-17'6"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | 24 | 1330 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F04-8'7-1/8"X8'10-7/8"-10-29T | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 443.3333 | 8 | 0 | 3 | 1330 | 24 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE | ToDo
75746-25 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 25 | 1 | 1 | 3 | BMPRLED-OPRI(1)-750-80-35-RG3-19'6 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | 24 | 1450 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F04-8'7-1/8"X9'3-16/16"-10-32T | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 483.3333 | 8 | 0 | 3 | 1450 | 24 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE | ToDo
75746-26 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 26 | 1 | 1 | 4 | BMPRLED-750-80-35-RG3-38'-W-UNV-DP-1-TG9-TS(1) | 4 | 2355 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F04-38'-10-41L | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 588.75 | 1 | 0 | 4 | 2355 | 4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
75746-29 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular | Others | FALSE |  | 29 | 1 | 1 | 3 | SP18276-SCR-350-80-35-FL-46'1"-W-UNV-DP-1-DS-C(32° & 85° ANGLED ENDS) | 43.2 | 2470 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F10-46'1"-ELEV LOBBY-10TH FL | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 823.3333 | 14.4 | 0 | 3 | 2470 | 43.2 | Others | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
75746-31 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular | Missing info. In SD | TRUE | Missing Driver Info. | 31 | 1 | 1 | 3 | BMPRLED-OPRI(1)-750-80-35-RG3-19'6 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | 24 | 1360 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F04-9'6 7/8"X9'11-15/16"-10-34T | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 453.3333 | 8 | 0 | 3 | 1360 | 24 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE | ToDo
75746-34 | 1 | 2019-02-11 |  | Machine Shop Started | Regular | FALSE | 75746 | Regular |  | FALSE |  | 34 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-8'-C(ROCKFON723)-UNV-DP-1-TG9 | 7 | 576 | 0 | Akamai 10th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'PATH-10TH FL | Picked - Complete | 2019-01-17 | 2019-01-17 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 1 | 576 | 7 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
76203-28 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 76203 | Regular | Wrong info. In SD | TRUE | Type Lable | 28 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | 18 | 1440 | 0 | Akamai 9th Floor | IllumBos | Gagandeep Singh |  |  | F05-10'PATH-9TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 720 | 9 | 0 | 2 | 1440 | 18 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE |  | Done
76203-29 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 76203 | Regular |  | FALSE |  | 29 | 1 | 1 | 2 | SP18369-WWR-SL-750-80-35-L-18'-W-UNV-DP-1-TG9 | 7 | 1296 | 0 | Akamai 9th Floor | IllumBos | Gagandeep Singh |  |  | F05-18'-9TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 648 | 3.5 | 0 | 2 | 1296 | 7 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE |  | Done
76203-30 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 76203 | Regular |  | FALSE |  | 30 | 1 | 1 | 1 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 | 7 | 432 | 0 | Akamai 9th Floor | IllumBos | Gagandeep Singh |  |  | F05-6'-9TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 7 | 0 | 1 | 432 | 7 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE |  | Done
76203-31 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 76203 | Regular |  | FALSE |  | 31 | 1 | 4 | 4 | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | 28 | 2304 | 0 | Akamai 9th Floor | IllumBos | Gagandeep Singh |  |  | F05-8'-9TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 576 | 7 | 0 | 4 | 2304 | 28 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE |  | Done
76203-32 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 76203 | Regular |  | FALSE |  | 32 | 1 | 2 | 2 | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS | 14 | 864 | 0 | Akamai 9th Floor | IllumBos | Gagandeep Singh |  |  | F05A-6'-9TH FL | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 7 | 0 | 2 | 864 | 14 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE |  | Done
78744-1 | 15 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78744 | Regular |  | FALSE |  | 1 | 1 | 18 | 18 | SCD-500-90-40-FL-4'-W-UNV-DP-1-CA(72) | 82.8 | 4320 | 0 |  | Enterpri | Jessica Pasternyk |  |  | JL1-4' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 240 | 4.6 | 0 | 18 | 4320 | 82.8 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78645-1 | 12 | 2019-02-01 | 2019-02-01 | Packaging Finished | Regular | FALSE | 78645 | High Priority | Mechanical issue | TRUE | Sensor | 1 | 1 | 1 | 1 | TB2DILED-750-500-80-40-SO-L-6-W-UNV-LT(LDE1)-1-CA(48)-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | 11 | 1077 | 0 | URGENT ORDER - MUST SHIP WITH SO# 78661 | PSGI | Sacha Lempka | Try for 2/1 Edited on 1/31/2019 Ship:2/4 Edited on 2/1/2019 |  | L5-A |  |  |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 1077 | 11 | 1 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78645-2 | 12 | 2019-02-01 | 2019-02-01 | Packaging Finished | Regular | FALSE | 78645 | High Priority | Electrical issue | TRUE | Driver donn't Fit | 2 | 1 | 1 | 1 | TB2DILED-750-500-80-40-SO-L-6-W-UNV-LT(LDE1)-2-CA(48)-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | 11 | 1102 | 0 | URGENT ORDER - MUST SHIP WITH SO# 78661 | PSGI | Sacha Lempka | Ship: feb 5th Edited on 2/5/2019 |  | L5-NL |  |  |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 1102 | 11 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78661-1 | 12 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 78661 | High Priority | Mechanical issue | FALSE |  | 1 | 1 | 1 | 1 | WWR-SL-750-80-40-8-W-UNV-LT(LDE1)-1-TG9-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | 7 | 805 | 0 | URGENT ORDER - MUST SHIP WITH SO# 78645 | PSGI | Sacha Lempka |  |  | L7 |  | 2019-01-23 |  | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 805 | 7 | 0 | 1 | 805 | 7 | Mechanical issue | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | FALSE |  | Done
78661-2 | 12 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 78661 | High Priority |  | FALSE |  | 2 | 1 | 2 | 2 | BBRLED-750-80-40-FL-4-W-UNV-LT(LDE1)-1-TG9-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | 10 | 830 | 0 | URGENT ORDER - MUST SHIP WITH SO# 78645 | PSGI | Sacha Lempka | Ship:2/4 Edited on 2/1/2019 :: Ship: feb 5th Edited on 2/5/2019 |  | L12 |  | 2019-01-23 |  | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 415 | 5 | 0 | 2 | 830 | 10 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
79048-1 | 1 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Mockup/Samples | FALSE | 79048 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | CLKLED-900-90-35-SO-4'-W-UNV-DP-1-AC-C(PLUG AND CORD ONLY) | 4.3 | 100 | 0 |  | Curtis S | Jessica Kennedy |  |  | SAMPLE-4' | Picked - Complete |  |  | FALSE | FALSE | OK |  |  | Machine Shop Started |  | 100 | 4.3 | 0 | 1 | 100 | 4.3 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
79311-1 | 4 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 79311 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | CCH-SL-1100-80-35-CL(26")-W-UNV-DP-1-C-C(23 7/16" LENGTH TO ADD TO EXISTING) | 4.3 | 150 | 0 |  | RKI | Daljit Singh |  |  | CL1L-23 7/16" |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 150 | 4.3 | 0 | 1 | 150 | 4.3 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
79311-2 | 4 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 79311 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | CCH-SL-1100-80-35-CL(48")-W-UNV-DP-1-C-C(46 3/4" LENGTH TO ADD TO EXISTING) | 4.3 | 300 | 0 |  | RKI | Daljit Singh |  |  | CL1L-46 3/4" |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 300 | 4.3 | 0 | 1 | 300 | 4.3 |  | 0 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
79085-1 | 10 | 2019-02-05 | 2019-02-05 | Given to Shipping | Replacement | FALSE | 79085 | Regular |  | FALSE |  | 1 | 1 | 88 | 88 | BBRLED-1000-90-40-FL-2-W-UNV-DP-1-TB15 | 220 | 17600 | 0 | Mark: ATTN: Andrew -254-498-0596 Notify: Andrew -254-498-0596 | RKI | Daljit Singh |  |  | LR2-2' |  | 2019-01-27 |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 200 | 2.5 | 100 | -12 | -2400 | -30 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78047-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78047 | Regular |  | FALSE |  | 1 | 1 | 9 | 9 | BBDILED-640-400-80-35-SO-4'-W-UNV-DP-1-CT9(36) | 67.5 | 4320 | 0 |  | IllumBos | Philip Halsey |  |  | LT-02 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 480 | 7.5 | 0 | 9 | 4320 | 67.5 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78047-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78047 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | BBDILED-640-400-80-35-SO-8'-W-UNV-DP-1-CT9(36) | 11.8 | 960 | 0 |  | IllumBos | Philip Halsey |  |  | LT-02A | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 960 | 11.8 | 0 | 1 | 960 | 11.8 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78047-3 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78047 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | ARWLED-600-80-35-S-2'-W-UNV-DP-1 | 3.8 | 240 | 0 |  | IllumBos | Philip Halsey |  |  | LT-05 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 240 | 3.8 | 0 | 1 | 240 | 3.8 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78047-4 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78047 | Regular |  | FALSE |  | 4 | 1 | 3 | 3 | BBRLED-400-80-35-1.5M-4'-W-UNV-DP-1-TB9 | 7.5 | 1050 | 0 |  | IllumBos | Philip Halsey |  |  | LT-18 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 350 | 2.5 | 0 | 3 | 1050 | 7.5 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78047-5 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78047 | Regular |  | FALSE |  | 5 | 1 | 2 | 2 | BBRLED-400-80-35-1.5M-4'-W-UNV-DP-1-TB9-B1(BSL310LP) | 12.8 | 1060 | 0 |  | IllumBos | Philip Halsey |  |  | LT-18EM | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 530 | 6.4 | 0 | 2 | 1060 | 12.8 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78664-1 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78664 | Regular |  | FALSE |  | 1 | 1 | 4 | 8 | STD-SO-400-80-30-12'-W-UNV-MD-1-CT9(36)-RC | 36 | 3849.4 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-12' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 481.175 | 4.5 | 0 | 8 | 3849.4 | 36 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78664-2 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78664 | Regular |  | FALSE |  | 2 | 1 | 3 | 9 | STD-SO-400-80-30-15'-W-UNV-MD-1-CT9(36)-RC | 40.5 | 3585.3 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-15' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 398.3667 | 4.5 | 0 | 9 | 3585.3 | 40.5 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78664-3 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78664 | Regular | Shortage | FALSE |  | 3 | 1 | 4 | 16 | STD-SO-400-80-30-25'-W-UNV-MD-1-CT9(36)-RC | 90 | 8105.4 | 0 |  | KSA Ltg | Joshua Zimet |  |  | F4-25' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 506.5875 | 5.625 | 0 | 16 | 8105.4 | 90 | Shortage | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78729-1 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78729 | High Priority |  | FALSE |  | 1 | 1 | 58 | 58 | WBRLED-750-80-35-S-2'-W-UNV-DP-1-DF | 203 | 18560 | 0 |  | CW | Zahra Vatani |  |  | Z2-2' |  |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 320 | 3.5 | 0 | 58 | 18560 | 203 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78272-1 | 12 | 2019-01-31 | 2019-01-31 | Machine Shop Finished | Regular | FALSE | 78272 | Regular | Shortage | TRUE | TEK6-LED-EC-LG-WH | 1 | 1 | 6 | 6 | TEK6LED-R-580-90-35-S-4-W-120-D-1-TG9-FW(6) | 19.2 | 3480 | 0 |  | Internat | Rohan Srivastava |  |  | L16-4' |  | 2019-01-25 | 2019-01-28 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 580 | 3.2 | 0 | 6 | 3480 | 19.2 |  | 1 | 2019 | 1 | 31 | 2 | Partial | TRUE | FALSE |  | Done
78272-2 | 12 | 2019-01-31 | 2019-01-31 | Machine Shop Started | Regular | FALSE | 78272 | Regular | Shortage | TRUE | TEK6-LED-EC-LG-WH | 2 | 1 | 3 | 3 | TEK6LED-R-580-90-35-S-4-W-120-D-1-TG9-B1(BSL310LP)-FW(6) | 33 | 2475 | 0 |  | Internat | Rohan Srivastava | MS: 01/31 - Ship: ? Edited on 1/30/2019 - Tek parts are in stock, Need to be picked from Stores. Ms:2/3 - Kaushik to advise. Edited on 2/1/2019::: Per Marc - part was found Edited on 2/5/2019 |  | L16-4' EM |  | 2019-01-25 | 2019-01-28 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 825 | 11 | 0 | 3 | 2475 | 33 |  | 1 | 2019 | 1 | 31 | 2 | Partial | TRUE | FALSE |  | Done
78110-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78110 | Regular | Wrong info. In SD | TRUE | Sections | 1 | 1 | 9 | 9 | BMDLED-1000-90-35-SO-8'-W-UNV-DP-1-CA(60) | 74.5 | 5139 | 0 |  | KSA Ltg | Joshua Zimet |  |  | B-8' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 571 | 8.2778 | 0 | 9 | 5139 | 74.5 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78110-2 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78110 | Regular |  | FALSE |  | 2 | 1 | 10 | 10 | BMDLED-1000-90-35-SO-8'-W-UNV-DP-2-CA(60) | 118.4 | 6170 | 0 |  | KSA Ltg | Joshua Zimet |  |  | B-2C | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 617 | 11.84 | 0 | 10 | 6170 | 118.4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | TRUE
78110-3 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78110 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | BMRLED-1000-90-35-RG-8'-W-UNV-DP-1-TG9-CP | 9.7 | 605 | 0 |  | KSA Ltg | Joshua Zimet |  |  | B-8R | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 605 | 9.7 | 0 | 1 | 605 | 9.7 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
79220-1 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 79220 | Regular |  | FALSE |  | 1 | 1 | 21 | 21 | POLED-22-3000-80-35-VL-W-120-DP-1-ST | 54.6 | 6177.9984 | 0 |  | Performa | Stan Buyansky |  |  | F6 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 294.1904 | 2.6 | 0 | 21 | 6177.9984 | 54.6 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
79133-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Replacement | FALSE | 79133 | High Priority | Wrong info. In SD | TRUE | POWER LOCATION IS WRONG | 1 | 1 | 1 | 1 | SCWD-300-80-35-FL-5' 6"-AP-UNV-DP-1 | 6.2 | 520 | 520 | UPS Acct# 25768W | CAL | Tajinder Singh |  |  | F7A S3-7 | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 520 | 6.2 | 0 | 1 | 520 | 6.2 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
75398-1 | 4 | 2019-01-16 | 2019-01-16 | Wiring Started | Regular | FALSE | 75398 | High Priority | Missing parts in BOM | TRUE | HARNESS | 1 | 1 | 3 | 3 | SP000-B2SQILED-1100-80-TW2750-SL-4-BLK-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 26.46 | 1470 | 0 | (VERY URGENT - CONFIRMED BY HOWARD & JOHN R.) | Performa | Stan Buyansky | Create new part number for harness - Erin, to advise eta? Edited on 1/16/2019 - Affects only Lines: 1-2-3 Edited on 1/16/2019 |  | L01A - 4 | Picked - Complete | 2019-01-08 | 2019-01-17 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 490 | 8.82 | 0 | 3 | 1470 | 26.46 |  | 1 | 2019 | 1 | 16 | 2 | Partial | TRUE | TRUE |  | Done
75398-2 | 4 | 2019-01-16 | 2019-01-16 | Wiring Started | Regular | FALSE | 75398 | High Priority | Others | FALSE | Light Direction/DIMMING ISSUE | 2 | 1 | 43 | 129 | SP000-B2SQILED-1100-80-TW2750-SLA-26-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 1470.6 | 156520 | 0 | (VERY URGENT - CONFIRMED BY HOWARD & JOHN R.) | Performa | Stan Buyansky | Lines: 1-2-3 - Elizabeth to follow up: Issue: Cartage, Light Guide - needs to be re-cut - Will receive more Harness: 01/29 Edited on 1/28/2019 |  | L01B - 26 | Picked - Complete | 2019-01-08 | 2019-01-17 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 1213.3333 | 11.4 | 115 | 14 | 16986.6667 | 159.6 | Others | 0 | 2019 | 1 | 16 | 2 | Partial | TRUE | TRUE |  | Done
75398-3 | 4 | 2019-01-16 | 2019-01-16 | Wiring Started | Regular | FALSE | 75398 | High Priority | Others | TRUE | HARNESS | 3 | 1 | 1 | 1 | SP000-B2SQILED-1100-80-TW2750-SLA-4' 6 1/2"-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 8.89 | 585 | 0 | (VERY URGENT - CONFIRMED BY HOWARD & JOHN R.) | Performa | Stan Buyansky | Harness Balance: Jan 30th Edited on 1/29/2019 |  | L01B - 4.5 | Picked - Complete | 2019-01-08 | 2019-01-17 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 585 | 8.89 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 1 | 16 | 2 | Partial | TRUE | TRUE |  | Done
75398-4 | 4 | 2019-01-16 | 2019-01-16 | Packaging Finished | Regular | FALSE | 75398 | High Priority | Mechanical issue | TRUE | HARNESS | 4 | 1 | 4 | 4 | SP000-CCH-SL-1100-80-TW2750-CL(2)-W-277-O(ELDOLED)-1-C-C(NIO EZ-CCT. NLIGHT) | 40 | 1080 | 0 | (VERY URGENT - CONFIRMED BY HOWARD & JOHN R.) | Performa | Stan Buyansky | Ship: Feb 5th Edited on 1/30/2019 |  | L02 - 2' | Picked - Complete | 2019-01-08 | 2019-01-17 | FALSE | FALSE | OK |  |  | Packaging Finished |  | 270 | 10 | 0 | 4 | 1080 | 40 |  | 1 | 2019 | 1 | 16 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
75398-5 | 4 | 2019-01-16 | 2019-01-16 | Packaging Finished | Regular | FALSE | 75398 | High Priority | Mechanical issue | TRUE | HARNESS | 5 | 1 | 16 | 16 | SP000-CCH-SL-1100-80-TW2750-CL(8)-W-277-O(ELDOLED)-1-C-C(ZIO EZ-CCT. NLIGHT) | 115.2 | 12480 | 0 | (VERY URGENT - CONFIRMED BY HOWARD & JOHN R.) | Performa | Stan Buyansky |  |  | L02 - 8' | Picked - Complete | 2019-01-08 | 2019-01-17 | FALSE | FALSE | OK |  |  | Packaging Finished |  | 780 | 7.2 | 0 | 16 | 12480 | 115.2 |  | 0 | 2019 | 1 | 16 | 2 | Partial | #N/A | #N/A | #N/A | #N/A
75811-1 | 7 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 75811 | Regular | Mechanical issue | FALSE | sub assembly parts | 1 | 1 | 4 | 12 | STD-SO-300-80-35-20-AP-UNV-MD-1-CA(36)-RC | 63.2 | 6400 | 0 |  | Performa | Stan Buyansky | Extrusion eta:2/1 Edited on 1/31/2019 Extrusion eta: 2/5 Edited on 2/1/2019 |  | L1-20' | Picked - Complete | 2019-01-25 | 2019-02-05 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 533.3333 | 5.2667 | 0 | 12 | 6400 | 63.2 | Mechanical issue | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
75811-2 | 7 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 75811 | Regular | Mechanical issue | TRUE | Extrusion Ex15667 8Ft | 2 | 1 | 3 | 9 | STD-SO-300-80-35-20-AP-UNV-MD-1+E(1)-CA(36)-RC | 51 | 4950 | 0 |  | Performa | Stan Buyansky | Ship: Feb 6th Edited on 2/5/2019 |  | L1-EMCKT-20' | Picked - Complete | 2019-01-25 | 2019-02-05 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 550 | 5.6667 | 0 | 9 | 4950 | 51 |  | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
75811-3 | 7 | 2019-02-01 | 2019-02-01 | Wiring Started | Regular | FALSE | 75811 | Regular | Others | FALSE | BLANK COVER | 3 | 1 | 1 | 3 | STD-SO-300-80-35-20-AP-UNV-MD-1+E(2)-CA(36)-RC | 18.3 | 1650 | 0 |  | Performa | Stan Buyansky |  |  | L1-EMCKT2 | Picked - Complete | 2019-01-25 | 2019-02-05 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 550 | 6.1 | 0 | 3 | 1650 | 18.3 | Others | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
77945-1 | 4 | 2019-01-22 | 2019-01-22 | Machine Shop Finished | Regular | FALSE | 77945 | High Priority | Mechanical issue | FALSE | Machining | 1 | 1 | 3 | 3 | SP000-B2SQILED-1100-80-TW2750-SL-6-BLK-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 23.67 | 2370 | 0 |  | Performa | Stan Buyansky | ETA: 1/23 - 1/24 - 1/25 Edited on 1/22/2019 |  | L01A - 6 | Picked - Complete | 2019-01-15 | 2019-01-23 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 790 | 7.89 | 0 | 3 | 2370 | 23.67 | Mechanical issue | 1 | 2019 | 1 | 22 | 1 | Complete | TRUE | TRUE |  | Done
77945-2 | 4 | 2019-01-22 | 2019-01-22 | Machine Shop Finished | Regular | FALSE | 77945 | High Priority | Mechanical issue | TRUE | Machining | 2 | 1 | 7 | 21 | SP000-B2SQILED-1100-80-TW2750-SLA-32-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 187.67 | 33670 | 0 |  | Performa | Stan Buyansky |  |  | L01B - 32 | Picked - Complete | 2019-01-15 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1603.3333 | 8.9367 | 0 | 21 | 33670 | 187.67 |  | 0 | 2019 | 1 | 22 | 1 | Complete | TRUE | TRUE |  | Done
77945-3 | 4 | 2019-01-22 | 2019-01-22 | Machine Shop Finished | Regular | FALSE | 77945 | High Priority | Shortage | TRUE | HARNESS | 3 | 1 | 1 | 2 | SP000-B2SQILED-1100-80-TW2750-SLA-18-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 17.45 | 3150 | 0 |  | Performa | Stan Buyansky | Harness: 1/25 - Kaushik to advise Edited on 1/24/2019 ::: Rahul & Sukhwinder to follow - Ship: Feb 5th? Edited on 1/30/2019::: Ship Feb 6th - Pending Cartiage Edited on 2/5/2019 |  | L01B - 18 | Picked - Complete | 2019-01-15 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1575 | 8.725 | 0 | 2 | 3150 | 17.45 |  | 0 | 2019 | 1 | 22 | 1 | Complete | TRUE | TRUE |  | Done
77947-1 | 4 | 2019-01-22 | 2019-01-22 | Machine Shop Finished | Regular | FALSE | 77947 | High Priority | Mechanical issue | TRUE | HARNESS (Board to Board) | 1 | 1 | 1 | 3 | SP000-B2SQILED-1100-80-TW2750-SLA-34-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 29.09 | 5520 | 0 |  | Performa | Stan Buyansky | ETA; 1/23- 1/24- 1/25 Edited on 1/22/2019 |  | L01B - 34 | Picked - Complete | 2019-01-15 | 2019-01-23 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1840 | 9.6967 | 0 | 3 | 5520 | 29.09 |  | 1 | 2019 | 1 | 22 | 1 | Complete | TRUE | TRUE |  | Done
77947-2 | 4 | 2019-01-22 | 2019-01-22 | Machine Shop Finished | Regular | FALSE | 77947 | High Priority | Mechanical issue | TRUE | Machining | 2 | 1 | 4 | 8 | SP000-B2SQILED-1100-80-TW2750-SLA-24-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 78.96 | 16960 | 0 |  | Performa | Stan Buyansky |  |  | L01B - 24 | Picked - Complete | 2019-01-15 | 2019-01-23 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 2120 | 9.87 | 0 | 8 | 16960 | 78.96 |  | 0 | 2019 | 1 | 22 | 1 | Complete | TRUE | TRUE |  | Done
77947-15 | 4 | 2019-01-22 | 2019-01-22 | Machine Shop Finished | Regular | FALSE | 77947 | High Priority | Mechanical issue | TRUE | Machining | 15 | 1 | 1 | 4 | SP000-B2SQILED-1100-80-TW2750-SLA-37' 5"-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | 33.71 | 6010 | 0 |  | Performa | Stan Buyansky | Rahul & Sukhwinder to follow - Ship: Feb 5th? Edited on 1/30/2019::: Ship: Feb 6th / Pending Cartiage Edited on 2/5/2019 |  | L01B-37 | Picked - Complete | 2019-01-15 | 2019-01-23 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 1502.5 | 8.4275 | 0 | 4 | 6010 | 33.71 |  | 0 | 2019 | 1 | 22 | 1 | Complete | TRUE | TRUE |  | Done
77060-2 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77060 | Regular |  | FALSE |  | 2 | 1 | 12 | 12 | B3RLED-SL-750-80-30-FL-4-W-UNV-DP-1-TG15 | 36 | 4080 | 0 |  | Vanguard | Philip Halsey |  |  | F5-R2 |  |  | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 340 | 3 | 0 | 12 | 4080 | 36 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE |  | Done
78663-1 | 12 | 2019-02-05 | 2019-01-31 | Machine Shop Started | Regular | FALSE | 78663 | Regular |  | FALSE |  | 1 | 1 | 3 | 3 | SCDI-500-500-80-35-SO-0.5M-8-AP-UNV-DP-1-CA(36)-B1(BSL10LST) | 30.6 | 2818.65 | 0 |  | KSA Ltg | Joshua Zimet | MS: Feb 4th - Kaushik to advise?? Edited on 2/5/2019 |  | F5 | Picked - Complete |  | 2019-01-30 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 939.55 | 10.2 | 0 | 3 | 2818.65 | 30.6 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | FALSE |  | Done
78388-1 | 12 | 2019-02-01 | 2019-02-01 | Machine Shop Finished | Regular | FALSE | 78388 | High Priority | Others | FALSE | sub assembly parts | 1 | 1 | 4 | 4 | STSLR-SO-400-80-35-6-AP-UNV-MD-1-SB9 | 22 | 1800 | 0 |  | SpecLAUS | Zahra Vatani | Ms:2/3 - Ship:2/4 Edited on 2/1/2019::: Kaushik to advise Edited on 2/5/2019 |  | H | Picked - Complete | 2019-01-25 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 450 | 5.5 | 0 | 4 | 1800 | 22 | Others | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
79049-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 79049 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BILED-640-90-40-C-8'-W-277-DP-1-CT15(48") | 7.6 | 560 | 0 |  | SpecLAUS | Zahra Vatani |  |  | A-8' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 560 | 7.6 | 0 | 1 | 560 | 7.6 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
79049-2 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 79049 | Regular |  | FALSE |  | 2 | 1 | 5 | 5 | BILED-640-90-40-C-5'-W-277-DP-1-CT15(48") | 38 | 1750 | 0 |  | SpecLAUS | Zahra Vatani |  |  | A-5' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 350 | 7.6 | 0 | 5 | 1750 | 38 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
79307-5 | 12 | 2019-02-08 |  | Machine Shop Started | Replacement | FALSE | 79307 | Regular |  | FALSE |  | 5 | 1 | 1 | 1 | SCS-400-80-35-FL-K(L4X4)-W-UNV-DP-1-S | 0 | 775 | 0 |  | Smart Li | Daljit Singh |  |  | L15A-L | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 775 | 0 | 0 | 1 | 775 | 0 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
79264-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 79264 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BBWDLED-400-80-40-SO-4-W-UNV-DP-1 | 8.86 | 560 | 0 |  | Repco II | Gaurav Jain |  |  | SC1, 4' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 280 | 4.43 | 0 | 2 | 560 | 8.86 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE |  | Done
77142-1 | 7 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 77142 | High Priority |  | FALSE |  | 1 | 1 | 1 | 1 | ZELED-SL 50/50-1050-80-35-MSO-8-W-UNV-MD-2-CT15(48) | 13.5 | 776 | 0 | PLEASE SHIP 1+2 NO LATER THAN FEB 11TH - toronto | Salex | Jessica Pasternyk |  |  | LT4-8' | Picked - Complete |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 776 | 13.5 | 0 | 1 | 776 | 13.5 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
77142-2 | 7 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 77142 | High Priority |  | FALSE |  | 2 | 1 | 3 | 3 | STSLF-SO-300-80-30-6-BLK-120-MD-1-SG15 | 21.9 | 1740 | 0 | PLEASE SHIP 1+2 NO LATER THAN FEB 11TH - toronto | Salex | Jessica Pasternyk |  |  | LT6 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 580 | 7.3 | 0 | 3 | 1740 | 21.9 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
77615-1 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 77615 | Regular |  | FALSE |  | 1 | 1 | 5 | 5 | TB2DILED-600-500-80-35-SO-SO-12-W-277-DP-1-CT9(36) | 70 | 4800 | 0 |  | QLS NC | Jessica Kennedy |  |  | A1-12' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 960 | 14 | 0 | 5 | 4800 | 70 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
77615-2 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 77615 | Regular |  | FALSE |  | 2 | 1 | 8 | 16 | TB2DILED-600-500-80-35-SO-SO-16-W-277-DP-1-CT9(36) | 160 | 10240 | 0 |  | QLS NC | Jessica Kennedy |  |  | A1-16' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 640 | 10 | 0 | 16 | 10240 | 160 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
77615-3 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 77615 | Regular |  | FALSE |  | 3 | 1 | 6 | 12 | TB2DILED-600-500-80-35-SO-SO-20-W-277-DP-1-CT9(36) | 144 | 9600 | 0 |  | QLS NC | Jessica Kennedy |  |  | A1-20' | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 800 | 12 | 0 | 12 | 9600 | 144 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
77615-4 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 4 | 1 | 94 | 94 | CLKLED-500-80-35-SO-6-W-UNV-DP-1-TG9 | 846 | 39480 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-6' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 420 | 9 | 0 | 94 | 39480 | 846 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-5 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 5 | 1 | 25 | 25 | BBRLED-500-80-35-FL-4-W-277-DP-1-TB9 | 75 | 6000 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-4' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 240 | 3 | 0 | 25 | 6000 | 75 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-6 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 6 | 1 | 7 | 7 | BBRLED-500-80-35-FL-8-W-277-DP-1-TB9 | 35 | 3360 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-8' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 480 | 5 | 0 | 7 | 3360 | 35 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-7 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 7 | 1 | 10 | 10 | BBRLED-500-80-35-FL-12-W-277-DP-1-TB9 | 70 | 7200 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-12' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 720 | 7 | 0 | 10 | 7200 | 70 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-8 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 8 | 1 | 3 | 6 | BBRLED-500-80-35-FL-16-W-277-DP-1-TB9 | 30 | 2880 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-16' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 480 | 5 | 0 | 6 | 2880 | 30 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-9 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 9 | 1 | 5 | 10 | BBRLED-500-80-35-FL-20-W-277-DP-1-TB9 | 60 | 6000 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-20' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 600 | 6 | 0 | 10 | 6000 | 60 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-10 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 10 | 1 | 1 | 2 | BBRLED-500-80-35-FL-24-W-277-DP-1-TB9 | 14 | 1440 | 0 |  | QLS NC | Jessica Kennedy |  |  | B1-24' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 720 | 7 | 0 | 2 | 1440 | 14 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
77615-11 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 77615 | Regular |  | FALSE |  | 11 | 1 | 17 | 17 | PWWLED-800-90-35-S-4-W-277-DP-1 | 68 | 4335 | 0 |  | QLS NC | Jessica Kennedy |  |  | S1 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 255 | 4 | 0 | 17 | 4335 | 68 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
77615-12 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 77615 | Regular |  | FALSE |  | 12 | 1 | 8 | 8 | PWWLED-800-90-35-S-4-W-UNV-DP-1 | 32 | 2040 | 0 |  | QLS NC | Jessica Kennedy |  |  | S2 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 255 | 4 | 0 | 8 | 2040 | 32 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
77615-13 | 4 | 2019-02-07 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77615 | Regular |  | FALSE |  | 13 | 1 | 12 | 12 | WBRLED-500-80-35-S-6-W-UNV-DP-1-DF | 84 | 6000 | 0 |  | QLS NC | Jessica Kennedy |  |  | X4-6' | Picked - Complete |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 500 | 7 | 0 | 12 | 6000 | 84 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78607-1 | 7 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78607 | Regular |  | FALSE |  | 1 | 1 | 11 | 22 | STFC-NO-DSO(4'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | 121 | 4510 | 0 |  | Clarus | Christina Torok |  |  | L30-2X2 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 205 | 5.5 | 0 | 22 | 4510 | 121 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78607-2 | 7 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78607 | Regular |  | FALSE |  | 2 | 1 | 9 | 18 | STFC-NO-DSO(10'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | 135 | 7110 | 0 |  | Clarus | Christina Torok |  |  | L30-5X5 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 395 | 7.5 | 0 | 18 | 7110 | 135 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78607-3 | 7 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78607 | Regular |  | FALSE |  | 3 | 1 | 3 | 6 | STFC-NO-DSO(6'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | 33 | 1620 | 0 |  | Clarus | Christina Torok |  |  | L30-3X3 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 270 | 5.5 | 0 | 6 | 1620 | 33 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78607-4 | 7 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78607 | Regular |  | FALSE |  | 4 | 1 | 3 | 6 | STFC-NO-DSO(8'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC | 36 | 1950 | 0 |  | Clarus | Christina Torok |  |  | L30-4X4 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 325 | 6 | 0 | 6 | 1950 | 36 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78759-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78759 | Regular |  | FALSE |  | 1 | 1 | 6 | 6 | BRLED-300-90-35-FL-10'-W-UNV-DP-1-TB15 | 54 | 6000 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | 10 FT | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 1000 | 9 | 0 | 6 | 6000 | 54 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78759-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78759 | Regular |  | FALSE |  | 2 | 1 | 4 | 4 | BRLED-300-90-35-FL-8'-W-UNV-DP-1-TB15 | 25.6 | 3200 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | 8 FT | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 800 | 6.4 | 0 | 4 | 3200 | 25.6 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78806-1 | 10 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78806 | High Priority |  | FALSE |  | 1 | 1 | 2 | 2 | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-DS | 10 | 640 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | F1-4' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 320 | 5 | 0 | 2 | 640 | 10 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | FALSE |  | Done
78806-2 | 10 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78806 | High Priority |  | FALSE |  | 2 | 1 | 5 | 5 | SCR-500-80-35-FL-8'-W-UNV-DP-1-MFTB9 | 27.5 | 2600 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | F2-8' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 520 | 5.5 | 0 | 5 | 2600 | 27.5 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78806-3 | 10 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Regular | FALSE | 78806 | High Priority |  | FALSE |  | 3 | 1 | 4 | 4 | SCD-500-80-35-FL-6'-BLK-UNV-DP-1-CA(36") | 28 | 1840 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | K-6' |  | 2019-01-25 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 460 | 7 | 0 | 4 | 1840 | 28 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
79034-1 | 4 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Replacement | FALSE | 79034 | High Priority | Shortage | TRUE | Extrusion | 1 | 1 | 1 | 4 | ZESQDI-SL 25/75-1050-80-35-MSO-44-BLK-UNV-MD-1-CA(96)-B2(BSL10LST) | 74 | 3568 | 3568 | Parts short shipped, customer need 2 of A44em but recieved only 1 unit. entered only 1 qty on the order, when PO requests 2 | HOUSE | Robert Lipura | Ship: Feb 6th Edited on 2/5/2019 |  | A- 44'EM | Picked - Complete | 2019-01-27 |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 892 | 18.5 | 0 | 4 | 3568 | 74 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
77011-1 | 18 | 2019-01-17 | 2019-01-17 | Given to Shipping | Regular | FALSE | 77011 | High Priority | On Hold | FALSE | SHIPMENT | 1 | 1 | 13 | 13 | SP16169(2)-WBRLED-750-30-S-12'-W-UNV-DP-1-DS-TF | 77.48 | 14352 | 0 | **DO NOT SHIP UNTIL FEBRUARY 11th** | Performa | Stan Buyansky |  |  | F10-12 | Picked - Complete | 2019-01-13 | 2019-01-16 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 1104 | 5.96 | 0 | 13 | 14352 | 77.48 | On Hold | 1 | 2019 | 1 | 17 | 1 | Complete | TRUE | TRUE |  | Done
79234-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 79234 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BMRLED-700-80-40-FL-12'-W-UNV-DP-1-DF | 8.7 | 650 | 0 | Note:.****Ship to arrive on February 19, 2019**** Going To; Blach Springs TX 75180 | HOUSE | Joe Brier |  |  | A-12' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 650 | 8.7 | 0 | 1 | 650 | 8.7 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE |  | Done
78220-1 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 1 | 1 | 4 | 8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") | 80 | 5440 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-16'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 680 | 10 | 0 | 8 | 5440 | 80 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-2 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 2 | 1 | 1 | 2 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | 20 | 1190 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-14'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 595 | 10 | 0 | 2 | 1190 | 20 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-3 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 3 | 1 | 16 | 32 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") | 219.2 | 16320 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-12'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 510 | 6.85 | 0 | 32 | 16320 | 219.2 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-4 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 4 | 1 | 1 | 2 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-10-W-UNV-DP-1-CT9(36") | 13.7 | 850 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-10'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 425 | 6.85 | 0 | 2 | 850 | 13.7 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-5 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 5 | 1 | 3 | 3 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") | 30.3 | 2040 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-8'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 680 | 10.1 | 0 | 3 | 2040 | 30.3 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-6 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 6 | 1 | 4 | 4 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-6-W-UNV-DP-1-CT9(36") | 40.4 | 2040 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-6'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 510 | 10.1 | 0 | 4 | 2040 | 40.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-7 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 7 | 1 | 2 | 4 | WWR-SL-750-80-30-13-W-UNV-DP-1-DS | 33 | 1950 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-13'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 487.5 | 8.25 | 0 | 4 | 1950 | 33 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-8 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 8 | 1 | 1 | 2 | WWR-SL-750-80-30-10-W-UNV-DP-1-DS | 9.8 | 750 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-10'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 375 | 4.9 | 0 | 2 | 750 | 9.8 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-9 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 9 | 1 | 1 | 1 | WWR-SL-750-80-30-6-W-UNV-DP-1-DS | 7.8 | 450 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-6'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 450 | 7.8 | 0 | 1 | 450 | 7.8 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-10 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 10 | 1 | 10 | 10 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | 48 | 1500 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3B-2'-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 150 | 4.8 | 0 | 10 | 1500 | 48 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-11 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 11 | 1 | 1 | 4 | BBPRLED-300-80-30-FL-26' 6"-W-UNV-DP-1+E(2)-TG9 | 18.3 | 1714 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-26' 6"-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 428.5 | 4.575 | 0 | 4 | 1714 | 18.3 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-12 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 12 | 1 | 1 | 12 | BBPRLED-300-80-30-FL-92' 11"-W-UNV-DP-2+E(6)-TG9 | 61 | 5806 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-92' 11"-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 483.8333 | 5.0833 | 0 | 12 | 5806 | 61 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-13 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 13 | 1 | 1 | 5 | BBPRLED-300-80-30-FL-39' 5"-W-UNV-DP-1+E(3)-DF | 26.2 | 2520 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-39' 5"-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 504 | 5.24 | 0 | 5 | 2520 | 26.2 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-14 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 14 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-19' 5"-W-UNV-DP-1+E(1)-TG9 | 12.5 | 1218 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-19' 5"-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 406 | 4.1667 | 0 | 3 | 1218 | 12.5 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78220-15 | 4 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78220 | High Priority |  | FALSE |  | 15 | 1 | 1 | 4 | BBPRLED-300-80-30-FL-26' 5"-W-UNV-DP-1+E(2)-DF | 18.3 | 1714 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-26' 5"-15TH | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 428.5 | 4.575 | 0 | 4 | 1714 | 18.3 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
78221-1 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular | PM wrong/missing info | TRUE | Wrong SD in Epicor | 1 | 1 | 2 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-22-W-UNV-DP-1-CT9(36") | 55 | 3740 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-22'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 623.3333 | 9.1667 | 0 | 6 | 3740 | 55 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78221-2 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular | Shortage | FALSE | Extrusion L1,2&4 | 2 | 1 | 6 | 12 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | 120.6 | 7140 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-14'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 595 | 10.05 | 0 | 12 | 7140 | 120.6 | Shortage | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78221-3 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 3 | 1 | 3 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") | 41.1 | 3060 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-12'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 510 | 6.85 | 0 | 6 | 3060 | 41.1 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-4 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 4 | 1 | 2 | 2 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") | 20.2 | 1360 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-8'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 680 | 10.1 | 0 | 2 | 1360 | 20.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78221-5 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 5 | 1 | 15 | 15 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | 45 | 2250 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3B-2'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 150 | 3 | 0 | 15 | 2250 | 45 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-6 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 6 | 1 | 2 | 4 | WWR-SL-750-80-30-10-W-UNV-DP-1-DS | 14 | 1500 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-10'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 375 | 3.5 | 0 | 4 | 1500 | 14 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-7 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 7 | 1 | 1 | 1 | WWR-SL-750-80-30-6-W-UNV-DP-1-DS | 5.2 | 450 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-6'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 450 | 5.2 | 0 | 1 | 450 | 5.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-8 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 8 | 1 | 1 | 13 | BBPRLED-300-80-30-FL-97'-W-UNV-DP-2+E(7)-TG9 | 64.2 | 6054 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-97'-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 465.6923 | 4.9385 | 0 | 13 | 6054 | 64.2 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-9 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 9 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-18' 8"-W-UNV-DP-1+E(2)-DF | 12.8 | 1218 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 8"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 406 | 4.2667 | 0 | 3 | 1218 | 12.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-10 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 10 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-23' 8"-W-UNV-DP-1+E(2)-DF | 14.8 | 1528 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-23' 8"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 509.3333 | 4.9333 | 0 | 3 | 1528 | 14.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-11 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 11 | 1 | 1 | 10 | BBPRLED-300-80-30-FL-76' 2"-W-UNV-DP-2+E(5)-TG9 | 48.7 | 4752 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-76' 2"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 475.2 | 4.87 | 0 | 10 | 4752 | 48.7 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-12 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 12 | 1 | 1 | 4 | BBPRLED-300-80-30-FL-18' 9"-W-UNV-DP-1+E(2)-DF | 12.8 | 1218 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 9"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 304.5 | 3.2 | 0 | 4 | 1218 | 12.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-13 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 13 | 1 | 1 | 2 | BBPRLED-300-80-30-FL-11' 5"-W-UNV-DP-1+E(1)-DF | 6.9 | 722 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-11' 5"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 361 | 3.45 | 0 | 2 | 722 | 6.9 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-14 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 14 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-17' 11"-W-UNV-DP-1+E(2)-DF | 12.8 | 784 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-17' 11"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 261.3333 | 4.2667 | 0 | 3 | 784 | 12.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-15 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 15 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-18' 3"-W-UNV-DP-1+E(2)-DF | 12.8 | 1156 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 3"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 385.3333 | 4.2667 | 0 | 3 | 1156 | 12.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78221-16 | 4 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78221 | Regular |  | FALSE |  | 16 | 1 | 1 | 11 | BBPRLED-300-80-30-FL-75' 9"-W-UNV-DP-2+E(5)-TG9 | 48.7 | 4752 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-75' 9"-16TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 432 | 4.4273 | 0 | 11 | 4752 | 48.7 |  | 0 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
78225-1 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 1 | 1 | 2 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-22-W-UNV-DP-1-CT9(36") | 55 | 3740 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-22'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 623.3333 | 9.1667 | 0 | 6 | 3740 | 55 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-2 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 2 | 1 | 15 | 30 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") | 300 | 20400 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-16'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 680 | 10 | 0 | 30 | 20400 | 300 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-3 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 3 | 1 | 5 | 10 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | 100 | 5950 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-14'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 595 | 10 | 0 | 10 | 5950 | 100 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-4 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 4 | 1 | 6 | 6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") | 60.6 | 4080 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-8'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 680 | 10.1 | 0 | 6 | 4080 | 60.6 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-5 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 5 | 1 | 1 | 1 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-6-W-UNV-DP-1-CT9(36") | 10.1 | 510 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-6'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 510 | 10.1 | 0 | 1 | 510 | 10.1 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-6 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 6 | 1 | 24 | 24 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | 69.6 | 4320 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3B-2'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 180 | 2.9 | 0 | 24 | 4320 | 69.6 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-7 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 7 | 1 | 2 | 4 | WWR-SL-750-80-30-13-W-UNV-DP-1-DS | 33 | 1950 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-13'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 487.5 | 8.25 | 0 | 4 | 1950 | 33 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-8 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Finished | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 8 | 1 | 1 | 2 | WWR-SL-750-80-30-14-W-UNV-DP-1-DS | 16.5 | 1050 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3-1B-14'-17TH | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 525 | 8.25 | 0 | 2 | 1050 | 16.5 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78225-9 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Started | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 9 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-18' 9"-W-UNV-DP-1+E(3)-TG9 | 13.3 | 1218 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 9"-17TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 406 | 4.4333 | 0 | 3 | 1218 | 13.3 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78225-10 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Started | Regular | FALSE | 78225 | High Priority | Wrong info. In SD | TRUE | NUMBER OF SECTIONS | 10 | 1 | 1 | 13 | BBPRLED-300-80-30-FL-97' 3"-W-UNV-DP-2+E(7)-TG9 | 64.8 | 6054 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-97' 3"-17TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 465.6923 | 4.9846 | 0 | 13 | 6054 | 64.8 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78225-11 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Started | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 11 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-18' 10"-W-UNV-DP-1+E(1)-TG9 | 12.5 | 1218 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 10"-17TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 406 | 4.1667 | 0 | 3 | 1218 | 12.5 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78225-12 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Started | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 12 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-18' 6"-W-UNV-DP-1+E(2)-DF | 12.9 | 1156 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 6"-17TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 385.3333 | 4.3 | 0 | 3 | 1156 | 12.9 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78225-13 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Started | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 13 | 1 | 1 | 5 | BBPRLED-300-80-30-FL-38' 1"-W-UNV-DP-1+E(2)-DF | 25.7 | 2396 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-38' 1"-17TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 479.2 | 5.14 | 0 | 5 | 2396 | 25.7 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78225-14 | 7 | 2019-02-08 | 2019-02-14 | Machine Shop Started | Regular | FALSE | 78225 | High Priority |  | FALSE |  | 14 | 1 | 1 | 7 | BBPRLED-300-80-30-FL-55' 9"-W-UNV-DP-2+E(4)-TG9 | 36 | 3512 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-55' 9"-17TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 501.7143 | 5.1429 | 0 | 7 | 3512 | 36 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78226-1 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Finished | Regular | FALSE | 78226 | High Priority |  | FALSE |  | 1 | 1 | 4 | 8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") | 80.4 | 5440 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-16'-18TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 680 | 10.05 | 0 | 8 | 5440 | 80.4 |  | 1 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78226-2 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority | Shortage | FALSE | Extrusion | 2 | 1 | 14 | 28 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | 281.4 | 16660 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-14'-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 595 | 10.05 | 0 | 28 | 16660 | 281.4 | Shortage | 1 | 2019 | 2 | 8 | 2 | Partial | FALSE | FALSE |  | Done
78226-3 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Finished | Regular | FALSE | 78226 | High Priority |  | FALSE |  | 3 | 1 | 10 | 10 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") | 137 | 10200 | 0 |  | HOUSE | Zahra Vatani |  |  | F1-12'-18TH | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 1020 | 13.7 | 0 | 10 | 10200 | 137 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78226-4 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority | Shortage | FALSE | LED Boards | 4 | 1 | 45 | 45 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 | 135 | 6750 | 0 |  | HOUSE | Zahra Vatani |  |  | F4-3B-2'-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 150 | 3 | 0 | 45 | 6750 | 135 | Shortage | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | TRUE |  | Done
78226-5 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority |  | FALSE |  | 5 | 1 | 1 | 4 | BBPRLED-300-80-30-FL-28' 6"-W-UNV-DP-1+E(3)-TG9 | 20.6 | 1776 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-28' 6"-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 444 | 5.15 | 0 | 4 | 1776 | 20.6 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78226-6 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority |  | FALSE |  | 6 | 1 | 1 | 12 | BBPRLED-300-80-30-FL-90' 6"-W-UNV-DP-2+E(6)-TG9 | 59 | 5682 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-90' 6"-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 473.5 | 4.9167 | 0 | 12 | 5682 | 59 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78226-7 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority |  | FALSE |  | 7 | 1 | 1 | 3 | BBPRLED-300-80-30-FL-18' 11"-W-UNV-DP-1+E(2)-TG9 | 11.4 | 1094 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-18' 11"-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 364.6667 | 3.8 | 0 | 3 | 1094 | 11.4 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78226-8 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority | Others | TRUE | Sections | 8 | 1 | 1 | 10 | BBPRLED-300-80-30-FL-73' 5"-W-UNV-DP-2+E(6)-TG9 | 49.5 | 4566 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-73' 5"-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 456.6 | 4.95 | 0 | 10 | 4566 | 49.5 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78226-9 | 4 | 2019-02-08 | 2019-02-19 | Machine Shop Started | Regular | FALSE | 78226 | High Priority |  | FALSE |  | 9 | 1 | 1 | 4 | BBPRLED-300-80-30-FL-28'-W-UNV-DP-1+E(3)-TG9 | 18.8 | 1776 | 0 |  | HOUSE | Zahra Vatani |  |  | F3C-28'-18TH | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 444 | 4.7 | 0 | 4 | 1776 | 18.8 |  | 0 | 2019 | 2 | 8 | 2 | Partial | TRUE | FALSE |  | Done
78469-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78469 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | BMRLED-750-90-30-FL-7'4"-W-120-DP-1-DF | 12.2 | 1280 | 0 |  | IllumBos | Philip Halsey |  |  | J17 7'4" |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 640 | 6.1 | 0 | 2 | 1280 | 12.2 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78469-2 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78469 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | BMRLED-750-90-30-FL-8'-W-120-DP-1-DF | 6.1 | 640 | 0 |  | IllumBos | Philip Halsey |  |  | J17 8' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 640 | 6.1 | 0 | 1 | 640 | 6.1 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
77378-1 | 12 | 2019-02-06 | 2019-02-06 | Machine Shop Started | Regular | FALSE | 77378 | Priority | Mechanical issue | FALSE | BOTTOM VIEW (KARUNA FOLLOWS) | 1 | 1 | 1 | 10 | BMWILEDPAT-REC-90(4)-750-90-30-C-58' 1/2"-NL-W-UNV-DP-1 | 60 | 5000 | 0 |  | CHARRON | Sacha Lempka |  |  | SL1-8'X10' RECT |  | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 500 | 6 | 0 | 10 | 5000 | 60 | Mechanical issue | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | ToDo
78694-1 | 1 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78694 | Regular |  | FALSE |  | 1 | 1 | 10 | 20 | BBDILED-400-750-90-35-SO-16-W-UNV-DP-1-CA(132) | 230 | 21160 | 0 |  | Performa | Stan Buyansky |  |  | D |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 1058 | 11.5 | 0 | 20 | 21160 | 230 |  | 1 | 2019 | 2 | 12 | 2 | Partial | TRUE | TRUE |  | Done
78694-2 | 1 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78694 | Regular |  | FALSE |  | 2 | 1 | 8 | 8 | BBRLED-1000-90-35-1.5M-8-W-UNV-DP-1-TB9 | 37.6 | 7384 | 0 |  | Performa | Stan Buyansky |  |  | K |  | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 923 | 4.7 | 0 | 8 | 7384 | 37.6 |  | 1 | 2019 | 2 | 12 | 2 | Partial | TRUE | FALSE |  | Done
78694-3 | 1 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78694 | Regular |  | FALSE |  | 3 | 1 | 10 | 20 | BBDILED-400-750-90-35-SO-16-W-UNV-DP-1-CA(132)-B1(BSL10LST) | 270 | 23865.28 | 0 |  | Performa | Stan Buyansky |  |  | DE |  | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 1193.264 | 13.5 | 0 | 20 | 23865.28 | 270 |  | 0 | 2019 | 2 | 12 | 2 | Partial | TRUE | TRUE |  | Done
78707-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78707 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | SCD-500-80-35-FL-K(4X4)-W-UNV-DP-1-CT9(48) | 22.3 | 883 | 0 |  | Performa | Stan Buyansky |  |  | F12 | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 883 | 22.3 | 0 | 1 | 883 | 22.3 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
77356-1 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Finished | Regular | FALSE | 77356 | Regular |  | FALSE |  | 1 | 1 | 95 | 95 | BBDLED-750-80-35-SO-2' 0"-W-UNV-DP-1-SA(120) | 513 | 18430 | 0 |  | Repco II | Gaurav Jain |  |  | L1-2' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 194 | 5.4 | 0 | 95 | 18430 | 513 |  | 1 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-2 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Finished | Regular | FALSE | 77356 | Regular |  | FALSE |  | 2 | 1 | 89 | 89 | BBDLED-750-80-35-SO-4' 0"-W-UNV-DP-1-SA(120) | 480.6 | 19224 | 0 |  | Repco II | Gaurav Jain |  |  | L1-4' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 216 | 5.4 | 0 | 89 | 19224 | 480.6 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-3 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Finished | Regular | FALSE | 77356 | Regular |  | FALSE |  | 3 | 1 | 5 | 5 | BBDLED-750-80-35-ASO-2' 0"-W-UNV-DP-1-SA(120) | 26.5 | 920 | 0 |  | Repco II | Gaurav Jain |  |  | L1A | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 184 | 5.3 | 0 | 5 | 920 | 26.5 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-4 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 4 | 1 | 3 | 3 | BBDILED-400-640-80-35-SO-8' 0"-W-UNV-DP-2-CT15(36) | 39.6 | 2040 | 0 |  | Repco II | Gaurav Jain |  |  | F3 | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 680 | 13.2 | 0 | 3 | 2040 | 39.6 |  | 1 | 2019 | 2 | 11 | 2 | Partial | TRUE | FALSE |  | Done
77356-5 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 5 | 1 | 15 | 15 | WBRLED-750-80-35-S-4' 0"-AP-UNV-DP-1-DS | 81 | 5145 | 0 |  | Repco II | Gaurav Jain |  |  | F5A | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 343 | 5.4 | 0 | 15 | 5145 | 81 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | FALSE |  | Done
77356-6 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 6 | 1 | 8 | 8 | BBRLED-400-80-35-FL-4' 0"-W-UNV-DP-1-DS | 40 | 1728 | 0 |  | Repco II | Gaurav Jain |  |  | F10-4' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 216 | 5 | 0 | 8 | 1728 | 40 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-7 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 7 | 1 | 10 | 10 | BBRLED-400-80-35-FL-5' 0"-W-UNV-DP-1-DS | 83 | 2700 | 0 |  | Repco II | Gaurav Jain |  |  | F10-5' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 270 | 8.3 | 0 | 10 | 2700 | 83 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-8 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 8 | 1 | 3 | 3 | BBRLED-400-80-35-FL-6' 0"-W-UNV-DP-1-DS | 24.9 | 969 | 0 |  | Repco II | Gaurav Jain |  |  | F10-6' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 323 | 8.3 | 0 | 3 | 969 | 24.9 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-9 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 9 | 1 | 10 | 10 | BBRLED-400-80-35-FL-7' 0"-W-UNV-DP-1-DS | 83 | 3780 | 0 |  | Repco II | Gaurav Jain |  |  | F10-7' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 378 | 8.3 | 0 | 10 | 3780 | 83 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-10 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 10 | 1 | 2 | 2 | BBRLED-400-80-35-FL-8' 0"-W-UNV-DP-1-DS | 16.6 | 864 | 0 |  | Repco II | Gaurav Jain |  |  | F10-8' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 432 | 8.3 | 0 | 2 | 864 | 16.6 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-11 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 11 | 1 | 1 | 1 | BBRLED-400-80-35-FL-9' 0"-W-UNV-DP-1-DS | 10.5 | 486 | 0 |  | Repco II | Gaurav Jain |  |  | F10-9' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 486 | 10.5 | 0 | 1 | 486 | 10.5 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-12 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 12 | 1 | 2 | 2 | BBRLED-400-80-35-FL-10' 0"-W-UNV-DP-1-TB15 | 13 | 1080 | 0 |  | Repco II | Gaurav Jain |  |  | F10-10' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 540 | 6.5 | 0 | 2 | 1080 | 13 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-13 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 13 | 1 | 7 | 7 | BBRLED-400-80-35-FL-11' 0"-W-UNV-DP-1-DS | 72.8 | 4158 | 0 |  | Repco II | Gaurav Jain |  |  | F10-11' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 594 | 10.4 | 0 | 7 | 4158 | 72.8 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-14 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 14 | 1 | 1 | 1 | BBRLED-400-80-35-FL-12' 0"-W-UNV-DP-1-DS | 10.4 | 648 | 0 |  | Repco II | Gaurav Jain |  |  | F10-12' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 648 | 10.4 | 0 | 1 | 648 | 10.4 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-15 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 15 | 1 | 2 | 4 | BBRLED-400-80-35-FL-13' 0"-W-UNV-DP-1-DS | 34.4 | 1404 | 0 |  | Repco II | Gaurav Jain |  |  | F10-13' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 351 | 8.6 | 0 | 4 | 1404 | 34.4 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-16 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 16 | 1 | 1 | 2 | BBRLED-400-80-35-FL-14' 0"-W-UNV-DP-1-DS | 17.2 | 756 | 0 |  | Repco II | Gaurav Jain |  |  | F10-14' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 378 | 8.6 | 0 | 2 | 756 | 17.2 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-17 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 17 | 1 | 1 | 2 | BBRLED-400-80-35-FL-13' 0"-W-UNV-DP-1-TB15 | 9.9 | 702 | 0 |  | Repco II | Gaurav Jain |  |  | F10-13' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 351 | 4.95 | 0 | 2 | 702 | 9.9 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-18 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 18 | 1 | 8 | 16 | BBRLED-400-80-35-FL-15' 0"-W-UNV-DP-1-DS | 137.6 | 6480 | 0 |  | Repco II | Gaurav Jain |  |  | F10-15' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 405 | 8.6 | 0 | 16 | 6480 | 137.6 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-19 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 19 | 1 | 1 | 2 | BBRLED-400-80-35-FL-15' 0"-W-UNV-DP-1-TB15 | 9.9 | 810 | 0 |  | Repco II | Gaurav Jain |  |  | F10-15' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 405 | 4.95 | 0 | 2 | 810 | 9.9 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-20 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 20 | 1 | 1 | 2 | BBRLED-400-80-35-FL-24' 0"-W-UNV-DP-1-DS | 21.7 | 1296 | 0 |  | Repco II | Gaurav Jain |  |  | F10-24' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 648 | 10.85 | 0 | 2 | 1296 | 21.7 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-21 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 21 | 1 | 1 | 3 | BBRLED-400-80-35-FL-28' 0"-W-UNV-DP-1-DS | 28.5 | 1712 | 0 |  | Repco II | Gaurav Jain |  |  | F10-28' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 570.6667 | 9.5 | 0 | 3 | 1712 | 28.5 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-22 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 22 | 1 | 1 | 3 | BBRLED-400-80-35-FL-33' 0"-W-UNV-DP-1-TB15 | 21.2 | 1782 | 0 |  | Repco II | Gaurav Jain |  |  | F10-33' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 594 | 7.0667 | 0 | 3 | 1782 | 21.2 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-23 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 23 | 1 | 1 | 5 | BBRLED-400-80-35-FL-52' 0"-W-UNV-DP-1-DS | 51 | 2808 | 0 |  | Repco II | Gaurav Jain |  |  | F10-52' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 561.6 | 10.2 | 0 | 5 | 2808 | 51 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
77356-25 | 18 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 77356 | Regular |  | FALSE |  | 25 | 1 | 2 | 2 | BBRLED-400-80-35-FL-10' 0"-W-UNV-DP-1-DS | 20.8 | 1080 | 0 |  | Repco II | Gaurav Jain |  |  | F10-10' | Picked - Complete |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 540 | 10.4 | 0 | 2 | 1080 | 20.8 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
75090-1 | 1 | 2019-02-11 | 2019-02-11 | Machine Shop Finished | Regular | FALSE | 75090 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | TB-S-10-NL-T5HO-2-W-UNV-D(MARK7)-1-CA(36) | 10 | 1350 | 0 |  | Internat | Rohan Srivastava |  |  | L6-10' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 1350 | 10 | 0 | 1 | 1350 | 10 |  | 1 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
75090-2 | 1 | 2019-02-11 | 2019-02-11 | Machine Shop Finished | Regular | FALSE | 75090 | Regular |  | FALSE |  | 2 | 1 | 2 | 4 | ZESQDI-SL 50/50-1200-80-35-SO-15-AP-UNV-MD-1-CA(36) | 37.4 | 4350 | 0 |  | Internat | Rohan Srivastava |  |  | L7-15' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 1087.5 | 9.35 | 0 | 4 | 4350 | 37.4 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
75090-3 | 1 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 75090 | Regular | Others | FALSE |  | 3 | 1 | 3 | 12 | SKPE-10005-SL 60/40-CIR-AL(7'10 1/4")-1000-80-35-SO-W-277-D-1-CTS(36) | 54 | 6600 | 0 |  | Internat | Rohan Srivastava |  |  | L9-7'10 1/2" | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 550 | 4.5 | 0 | 12 | 6600 | 54 | Others | 1 | 2019 | 2 | 11 | 2 | Partial | TRUE | FALSE |  | Done
75090-4 | 1 | 2019-02-11 | 2019-02-11 | Machine Shop Finished | Regular | FALSE | 75090 | Regular |  | FALSE |  | 4 | 1 | 2 | 4 | ZESQDI-SL 50/50-1200-80-35-SO-20-AP-UNV-MD-1-CA(36) | 45.6 | 5800 | 0 |  | Internat | Rohan Srivastava |  |  | L7-20' | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 1450 | 11.4 | 0 | 4 | 5800 | 45.6 |  | 0 | 2019 | 2 | 11 | 2 | Partial | TRUE | TRUE |  | Done
78798-1 | 1 | 2019-02-12 | 2019-02-15 | Machine Shop Started | Regular | FALSE | 78798 | Regular |  | FALSE |  | 1 | 1 | 8 | 8 | CLKLED-500-80-30-SO-4'-W-120-DP-1-TG9-FW(6) | 36 | 3040 | 0 |  | Internat | Joe Brier |  |  | LF02-27TH FL |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 380 | 4.5 | 0 | 8 | 3040 | 36 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78798-2 | 1 | 2019-02-12 | 2019-02-15 | Machine Shop Started | Regular | FALSE | 78798 | Regular |  | FALSE |  | 2 | 1 | 28 | 28 | CLKLED-500-80-30-SO-4'-W-120-DP-1-TG9-FW(6) | 126 | 10640 | 0 |  | Internat | Joe Brier |  |  | LF02D-27TH FL |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 380 | 4.5 | 0 | 28 | 10640 | 126 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
74294-4 | 1 | 2019-01-08 | 2019-01-08 | Machine Shop Finished | Regular | FALSE | 74294 | Regular | Shortage | FALSE | AY20303A (Feb 22nd) | 4 | 1 | 4 | 32 | CCH-SL-700-90-TC1680-CP(26)-W-UNV-DMX-1-C | 141.68 | 13000 | 0 |  | TampaBay | Joshua Zimet | --Eta of Part: Jan 30th - Ship Partial Edited on 1/21/2019:: Update ETA: Feb 22nd Edited on 1/29/2019 |  | L20A | Picked - Complete | 2018-12-27 | 2019-01-03 | FALSE | TRUE | OK |  |  | Machine Shop Finished -Ready |  | 406.25 | 4.4275 | 0 | 32 | 13000 | 141.68 | Shortage | 1 | 2019 | 1 | 8 | 1 | Complete | TRUE | TRUE | Ready | Done
78640-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78640 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BRLED-536-90-40-FL-4-W-277-DP-1-DF | 3.26 | 347 | 0 |  | Performa | Stan Buyansky |  |  | H-4' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 347 | 3.26 | 0 | 1 | 347 | 3.26 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
78640-3 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78640 | Regular |  | FALSE |  | 3 | 1 | 1 | 3 | BRLED-536-90-40-FL-32'-W-277-DP-1-DF | 26 | 2774 | 0 |  | Performa | Stan Buyansky |  |  | H-32 | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 924.6667 | 8.6667 | 0 | 3 | 2774 | 26 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
78171-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 78171 | Regular |  | FALSE |  | 1 | 1 | 7 | 7 | WWR-SL-500-90-40-4'0"-W-UNV-DP-1-TB15 | 20.3 | 2912 | 0 |  | CHARRON | Sacha Lempka |  |  | AW1 | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 416 | 2.9 | 0 | 7 | 2912 | 20.3 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
79110-1 | 10 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 79110 | High Priority |  | FALSE |  | 1 | 1 | 3 | 3 | POLED-22-4400-90-35-VL-W-UNV-DP-1-ST | 5.2 | 540 | 0 |  | CW | Zahra Vatani |  |  | FT10-2X2 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 180 | 1.7333 | 0 | 3 | 540 | 5.2 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78106-1 | 12 | 2019-02-11 | 2019-02-14 | Scheduled/Released | Regular | FALSE | 78106 | Regular |  | FALSE |  | 1 | 1 | 3 | 3 | BBRLED-500-80-35-FL-4'-W-UNV-DP-1-ST | 7.5 | 1110 | 0 |  | IllumBos | Philip Halsey |  |  | GL2 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 370 | 2.5 | 0 | 3 | 1110 | 7.5 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78106-2 | 12 | 2019-02-11 | 2019-02-14 | Scheduled/Released | Regular | FALSE | 78106 | Regular |  | FALSE |  | 2 | 1 | 2 | 2 | BBPRLED-500-80-35-RG4-6' 9"-W-UNV-DP-1-ST-TS(1) | 10.8 | 1540 | 0 |  | IllumBos | Philip Halsey |  |  | WL3, 6' 9" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 770 | 5.4 | 0 | 2 | 1540 | 10.8 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78106-3 | 12 | 2019-02-11 | 2019-02-14 | Scheduled/Released | Regular | FALSE | 78106 | Regular |  | FALSE |  | 3 | 1 | 2 | 2 | BBPRLED-500-80-35-RG4-10' 10"-W-UNV-DP-1-ST-TS(1) | 14.4 | 2338 | 0 |  | IllumBos | Philip Halsey |  |  | WL3, 10' 10" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1169 | 7.2 | 0 | 2 | 2338 | 14.4 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78106-4 | 12 | 2019-02-11 | 2019-02-14 | Scheduled/Released | Regular | FALSE | 78106 | Regular |  | FALSE |  | 4 | 1 | 1 | 3 | BBPRLED-OPRI(1)-500-80-35-FL-16'-W-UNV-DP-1-DS-TS(1)-C( 9FT 8.6IN X 6FT) | 21 | 1950 | 0 |  | IllumBos | Philip Halsey |  |  | WL2 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 650 | 7 | 0 | 3 | 1950 | 21 |  | 0 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78165-1 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 1 | 1 | 1 | 9 | BRLEDPAT-OPI-90(4)-400-80-35-SO-FL-34-NL-W-UNV-DP-1-DB | 43 | 7778 | 0 |  | Clarus | Christina Torok |  |  | B | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 864.2222 | 4.7778 | 0 | 9 | 7778 | 43 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE | ToDo
78165-2 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 2 | 1 | 1 | 9 | BRLEDPAT-OPI-90(4)-400-80-35-SO-FL-32-NL-W-UNV-DP-1-DB | 43 | 7445 | 0 |  | Clarus | Christina Torok |  |  | B1 | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 827.2222 | 4.7778 | 0 | 9 | 7445 | 43 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE | ToDo
78165-3 | 10 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 3 | 1 | 11 | 11 | SKFLED-22-3200-80-35-FL-W-120-DP-1-TB9 | 25.3 | 4345 | 0 |  | Clarus | Christina Torok |  |  | C |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 395 | 2.3 | 0 | 11 | 4345 | 25.3 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78165-4 | 10 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 4 | 1 | 5 | 5 | SKFLED-22-3200-80-35-1SF-W-120-DP-1-TB9 | 11.5 | 1975 | 0 |  | Clarus | Christina Torok |  |  | C1 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 395 | 2.3 | 0 | 5 | 1975 | 11.5 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78165-5 | 10 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 5 | 1 | 7 | 7 | SKFLED-22-3200-80-35-2SF-W-120-DP-1-TB9 | 16.1 | 2765 | 0 |  | Clarus | Christina Torok |  |  | C2 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 395 | 2.3 | 0 | 7 | 2765 | 16.1 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78165-6 | 10 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 6 | 1 | 7 | 7 | SKFLED-22-3200-80-35-3SF-W-120-DP-1-TB9 | 16.1 | 2765 | 0 |  | Clarus | Christina Torok |  |  | C3 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 395 | 2.3 | 0 | 7 | 2765 | 16.1 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
78165-7 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78165 | Regular |  | FALSE |  | 7 | 1 | 2 | 2 | B6RLED-750-80-35-2M-8-W-UNV-DP-1-TB9 | 11.8 | 1476 | 0 |  | Clarus | Christina Torok |  |  | F | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 738 | 5.9 | 0 | 2 | 1476 | 11.8 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78680-1 | 18 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 78680 | High Priority |  | FALSE |  | 1 | 1 | 9 | 9 | TWRWLED-SL 90/10-750-80-40-SO-4'-W-UNV-DP-1 | 38.7 | 3060 | 0 |  | SpecLAUS | Zahra Vatani |  |  | L106-4' | Picked - Complete | 2019-01-30 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 340 | 4.3 | 0 | 9 | 3060 | 38.7 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE
78715-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78715 | Regular | Shortage | FALSE |  | 1 | 1 | 1 | 2 | ZESQDI-SL 75/25-900-80-35-MAL-16-W-UNV-MD-1-CA(36) | 30.3 | 1728 | 0 |  | LtgUnlim | Rajithan Sivapatharajahon |  |  | P |  |  | 2019-02-04 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 864 | 15.15 | 0 | 2 | 1728 | 30.3 | Shortage | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78521-1 | 12 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 78521 | Regular | Mechanical issue | FALSE |  | 1 | 1 | 1 | 1 | WWR-SL-1000-80-30-2-W-UNV-DP-1-DF | 2.9 | 240 | 0 |  | Performa | Stan Buyansky |  |  | H |  | 2019-01-27 | 2019-01-30 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 240 | 2.9 | 0 | 1 | 240 | 2.9 | Mechanical issue | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78442-1 | 12 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 78442 | Regular | Shortage | FALSE | Extrusion | 1 | 1 | 2 | 2 | TB2WDILED-750-750-90-35-SLA-SO-6'-AP-UNV-DP-1 | 20 | 1344 | 0 |  | RCLURIE2 | Sacha Lempka | Ms:2/1 - Kaushik to advise. Edited on 2/1/2019::: Ship: Kaushik to advise?? Edited on 2/5/2019 |  | FF-6 |  |  | 2019-01-29 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 672 | 10 | 0 | 2 | 1344 | 20 | Shortage | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | FALSE |  | Done
79005-1 | 10 | 2019-02-05 | 2019-02-05 | Packaging Finished | Regular | FALSE | 79005 | Regular |  | FALSE |  | 1 | 1 | 3 | 3 | AULED-24-3100-80-30-SO-W-UNV-DP-1-TB9 | 8.517 | 870 | 0 |  | LHI | Rajithan Sivapatharajahon |  |  | A2 |  |  |  | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 290 | 2.839 | 3 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 5 | 1 | Complete | FALSE | FALSE
77922-1 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 1 | 1 | 1 | 1 | TB4DILED-640-400-80-35-SL-SO-8'-W-UNV-DP-2-CA(120) | 10 | 1291.81 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-8' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1291.81 | 10 | 0 | 1 | 1291.81 | 10 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-2 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 2 | 1 | 5 | 5 | TB4DILED-640-400-80-35-SL-SO-12'-W-UNV-DP-2-CA(120) | 65 | 9617.95 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-12' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1923.59 | 13 | 0 | 5 | 9617.95 | 65 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-3 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 3 | 1 | 10 | 20 | TB4DILED-640-400-80-35-SL-SO-18'-W-UNV-DP-2-CA(120) | 260 | 28712.7 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-18' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1435.635 | 13 | 0 | 20 | 28712.7 | 260 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-4 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 4 | 1 | 4 | 8 | TB4DILED-640-400-80-35-SL-SO-20'-W-UNV-DP-2-CA(120) | 104 | 12748.68 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-20' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1593.585 | 13 | 0 | 8 | 12748.68 | 104 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-5 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 5 | 1 | 8 | 16 | TB4DILED-640-400-80-35-SL-SO-22'-W-UNV-DP-2-CA(120) | 224 | 28024.48 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-22' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1751.53 | 14 | 0 | 16 | 28024.48 | 224 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-6 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 6 | 1 | 3 | 6 | TB4DILED-640-400-80-35-SL-SO-24'-W-UNV-DP-2-CA(120) | 87 | 11456.88 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-24' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1909.48 | 14.5 | 0 | 6 | 11456.88 | 87 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-7 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 7 | 1 | 3 | 9 | TB4DILED-640-400-80-35-SL-SO-28'-W-UNV-DP-2-CA(120) | 108 | 13352.25 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-28' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1483.5833 | 12 | 0 | 9 | 13352.25 | 108 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-8 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 8 | 1 | 22 | 22 | TB2WDILED-1100-1000-80-35-SO-SO-4'-W-UNV-DP-1 | 154 | 11484 | 0 |  | Smart Li | Zahra Vatani |  |  | S1-4' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 522 | 7 | 0 | 22 | 11484 | 154 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-9 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 9 | 1 | 1 | 2 | CCH-SL-900-80-35-CL(23)-W-UNV-DP-1-C | 18 | 2668.21 | 0 |  | Smart Li | Zahra Vatani |  |  | C2-23' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 1334.105 | 9 | 0 | 2 | 2668.21 | 18 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-10 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 10 | 1 | 2 | 2 | TB4DILED-640-400-80-35-SL-SO-10'-W-UNV-DP-2-CA(120) | 26 | 4478.96 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-10' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 2239.48 | 13 | 0 | 2 | 4478.96 | 26 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77922-11 | 4 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 77922 | Priority |  | FALSE |  | 11 | 1 | 4 | 8 | TB4DILED-640-400-80-35-SL-SO-16'-W-UNV-DP-2-CA(120) | 88 | 11485.12 | 0 |  | Smart Li | Zahra Vatani |  |  | P4-16' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1435.64 | 11 | 0 | 8 | 11485.12 | 88 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
77440-1 | 7 | 2019-02-01 | 2019-02-01 | Given to Shipping | Regular | FALSE | 77440 | Regular | Wrong part in BOM | TRUE | WAITING FOR CARTRIDGES | 1 | 1 | 2 | 12 | STFC-I(6-175)-DSO(12-400)-80-35-AH(6)-W-UNV-MD-1-CA(36)-RC | 64 | 1324 | 0 |  | Rocky Mt | Sacha Lempka | Ship: Feb 5th Edited on 2/5/2019 |  |  | Picked - Complete | 2019-02-07 | 2019-02-03 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 110.3333 | 5.3333 | 12 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
76528-1 | 12 | 2019-01-28 | 2019-01-28 | Machine Shop Finished | Mockup/Samples | FALSE | 76528 | Regular | Others | FALSE | SUB ASSEMBLY | 1 | 1 | 1 | 1 | SCML-6-BW-700-MLB(6)-1000-BLK-80-35-BLK-UNV-DP-2-CA(36)-C(CORD, PLUG & DIMMER) | 8.6 | 1060 | 1060 |  | Clarus | Christina Torok | Ship: Jan 29th Edited on 1/28/2019 :: Ship: Jan 30th Edited on 1/29/2019 ::: Ship: Jan 31st Edited on 1/30/2019 - Elizabeth to follow up Sub Assembly. Edited on 2/1/2019 |  | A |  |  | 2019-01-24 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 1060 | 8.6 | 0 | 1 | 1060 | 8.6 | Others | 1 | 2019 | 1 | 28 | 1 | Complete | TRUE | TRUE |  | Done
78423-8 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 8 | 1 | 3 | 3 | SP19018(1)-SCR-1000-80-35-FL-5' 4"-W-UNV-DP-1-TG9 | 16.5 | 1712.963 | 0 |  | Vanguard | Philip Halsey |  |  | F1 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 570.9877 | 5.5 | 0 | 3 | 1712.963 | 16.5 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78423-9 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 9 | 1 | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-5' 4"-W-UNV-DP-1-TG9-B1(BSL10LST) | 18.6 | 1570.2161 | 0 |  | Vanguard | Philip Halsey |  |  | F1 EM | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 785.108 | 9.3 | 0 | 2 | 1570.2161 | 18.6 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78423-10 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 10 | 1 | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-6' 3"-W-UNV-DP-1-TG9 | 11 | 1296.6178 | 0 |  | Vanguard | Philip Halsey |  |  | F2 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 648.3089 | 5.5 | 0 | 2 | 1296.6178 | 11 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78423-11 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 11 | 1 | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-6' 3"-W-UNV-DP-1-TG9-B1(BSL10LST) | 18.6 | 1724.8586 | 0 |  | Vanguard | Philip Halsey |  |  | F2 EM | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 862.4293 | 9.3 | 0 | 2 | 1724.8586 | 18.6 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78423-12 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 12 | 1 | 2 | 2 | SP19018(1)-SCR-1000-80-35-FL-5' 6"-W-UNV-DP-1-TG9 | 11 | 1141.9753 | 0 |  | Vanguard | Philip Halsey |  |  | F3 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 570.9877 | 5.5 | 0 | 2 | 1141.9753 | 11 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78423-13 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 13 | 1 | 1 | 1 | SP19018(1)-SCD-1000-80-35-FL-6' 3"-W-UNV-DP-1-SA(18) | 5.5 | 606.6744 | 0 |  | Vanguard | Philip Halsey |  |  | F4 | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 606.6744 | 5.5 | 0 | 1 | 606.6744 | 5.5 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78423-14 | 7 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78423 | Regular |  | FALSE |  | 14 | 1 | 1 | 1 | SP19018(1)-SCD-1000-80-35-FL-6' 3"-W-UNV-DP-1-SA(18)-B1(BSL10LST) | 9.3 | 820.7948 | 0 |  | Vanguard | Philip Halsey |  |  | F4 EM | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 820.7948 | 9.3 | 0 | 1 | 820.7948 | 9.3 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
74695-1 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 74695 | Regular |  | FALSE |  | 1 | 1 | 28 | 28 | DIALED-22-2500-80-35-VL-W-UNV-DP-1-TB9 | 78.4 | 4060 | 0 |  | JCWright | George Bacalla |  |  | AR8 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 145 | 2.8 | 0 | 28 | 4060 | 78.4 |  | 1 | 2019 | 2 | 7 | 2 | Partial | FALSE | TRUE |  | Done
74695-2 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 74695 | Regular |  | FALSE |  | 2 | 1 | 14 | 14 | DIALED-11-1600-80-35-VL-W-UNV-DP-1-DF | 30.8 | 2030 | 0 |  | JCWright | George Bacalla |  |  | AS3 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 145 | 2.2 | 0 | 14 | 2030 | 30.8 |  | 0 | 2019 | 2 | 7 | 2 | Partial | FALSE | TRUE |  | Done
74695-3 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 74695 | Regular |  | FALSE |  | 3 | 1 | 8 | 8 | DIALED-11-1600-80-35-VL-W-UNV-DP-E(1)-DF-B1 | 48 | 2912 | 0 |  | JCWright | George Bacalla |  |  | AS3E |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 364 | 6 | 0 | 8 | 2912 | 48 |  | 0 | 2019 | 2 | 7 | 2 | Partial | FALSE | TRUE |  | Done
74695-4 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 74695 | Regular |  | FALSE |  | 4 | 1 | 3 | 3 | DIALED-14-4000-80-30-VL-W-UNV-DP-1-DF | 9.3 | 537 | 0 |  | JCWright | George Bacalla |  |  | AS5 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 179 | 3.1 | 0 | 3 | 537 | 9.3 |  | 0 | 2019 | 2 | 7 | 2 | Partial | FALSE | TRUE |  | Done
74695-5 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 74695 | Regular |  | FALSE |  | 5 | 1 | 3 | 3 | BMDLED-750-80-35-SO-4'-BLK-UNV-DP-1-CT9(36) | 14.4 | 615 | 0 |  | JCWright | George Bacalla |  |  | L1-4' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 205 | 4.8 | 0 | 3 | 615 | 14.4 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | TRUE |  | Done
79411-1 | 10 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 79411 | High Priority |  | FALSE |  | 1 | 1 | 37 | 37 | DAYFLED-22-3000-80-35-SO-W-UNV-DP-1-TB15 | 85.1 | 6105 | 0 |  | IllumBos | Philip Halsey |  |  | L6 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 165 | 2.3 | 0 | 37 | 6105 | 85.1 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE
76823-1 | 4 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 76823 | Priority | Mechanical issue | TRUE | DIMMING ISSUE | 1 | 1 | 13 | 13 | ZERLED-TR-400-80-35-4-W-UNV-DP-1-TG9 | 65.13 | 4784 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka | Material needs to be picked from Stores - Elizabeth follow diming issue. Edited on 2/1/2019 |  | A4-4FT | Picked - Complete | 2019-01-25 | 2019-02-01 | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 368 | 5.01 | 0 | 13 | 4784 | 65.13 |  | 1 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-3 | 4 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 76823 | Priority | Mechanical issue | FALSE | END CAP | 3 | 1 | 20 | 20 | ZERLED-TR-400-80-35-8-W-UNV-DP-1-TG9 | 163.8 | 14720 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka | Ship: Feb 6th Edited on 2/5/2019 |  | A4-8FT | Picked - Complete | 2019-01-25 | 2019-02-01 | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 736 | 8.19 | 0 | 20 | 14720 | 163.8 | Mechanical issue | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-4 | 4 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 76823 | Priority |  | FALSE |  | 4 | 1 | 9 | 9 | ZERLED-TR-400-80-35-12-W-UNV-DP-1-TG9 | 103.68 | 9936 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | A4-12FT | Picked - Complete | 2019-01-25 | 2019-02-01 | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 1104 | 11.52 | 0 | 9 | 9936 | 103.68 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-5 | 4 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 76823 | Priority |  | FALSE |  | 5 | 1 | 1 | 2 | ZERLED-TR-400-80-35-16-W-UNV-DP-1-TG9 | 16.3 | 1472 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | A4-16FT | Picked - Complete | 2019-01-25 | 2019-02-01 | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 736 | 8.15 | 0 | 2 | 1472 | 16.3 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-6 | 4 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 76823 | Priority |  | FALSE |  | 6 | 1 | 2 | 4 | ZERLED-TR-400-80-35-20-W-UNV-DP-1-TG9 | 39.64 | 3680 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | A4-20FT | Picked - Complete | 2019-01-25 | 2019-02-01 | FALSE | TRUE | NO |  |  | Machine Shop Finished - Incomplete |  | 920 | 9.91 | 0 | 4 | 3680 | 39.64 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-7 | 7 | 2019-02-04 | 2019-02-04 | Wiring Started | Regular | FALSE | 76823 | Priority | Mechanical issue | FALSE | EN16073-SL | 7 | 1 | 6 | 24 | STFD-DSO(16-400)-80-35-AL(3)-AP-120-MD-1-CA(72)-RC | 132 | 8250 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | C1-16FT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 343.75 | 5.5 | 24 | 0 | 0 | 0 | Mechanical issue | 1 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-8 | 7 | 2019-02-04 | 2019-02-04 | Wiring Started | Regular | FALSE | 76823 | Priority | Mechanical issue | FALSE | EN16073-SL | 8 | 1 | 3 | 15 | STFD-DSO(20-400)-80-35-AL(4)-AP-120-MD-1-CA(72)-RC | 81 | 5130 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | C1-20FT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 342 | 5.4 | 15 | 0 | 0 | 0 | Mechanical issue | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-9 | 7 | 2019-02-04 | 2019-02-04 | Wiring Started | Regular | FALSE | 76823 | Priority |  | FALSE |  | 9 | 1 | 1 | 2 | STD-SO-400-80-35-16-AP-120-MD-1-CA(72)-RC | 16 | 1190 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | C2-16FT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 595 | 8 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-10 | 7 | 2019-02-04 | 2019-02-04 | Wiring Started | Regular | FALSE | 76823 | Priority |  | FALSE |  | 10 | 1 | 1 | 3 | STD-SO-400-80-35-20-AP-120-MD-1-CA(72)-RC | 16 | 1470 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | C2-20FT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 490 | 5.3333 | 3 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-11 | 7 | 2019-02-04 | 2019-02-04 | Wiring Started | Regular | FALSE | 76823 | Priority |  | FALSE |  | 11 | 1 | 9 | 81 | STFD-DSO(36-400)-80-35-AH(4)+AY(2)-AP-120-MD-1-CA(72)-RC | 441 | 27450 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | C3 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 338.8889 | 5.4444 | 90 | -9 | -3050 | -49 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-12 | 7 | 2019-02-04 | 2019-02-04 | Wiring Started | Regular | FALSE | 76823 | Priority |  | FALSE |  | 12 | 1 | 4 | 24 | STFD-DSO(12-400)-80-35-AH(6)-AP-120-MD-1-CA(72)-RC | 132 | 4920 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | C4 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 205 | 5.5 | 15 | 9 | 1845 | 49.5 |  | 0 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
76823-13 | 7 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Regular | FALSE | 76823 | Priority |  | FALSE |  | 13 | 1 | 10 | 10 | ZESQDI-SL-50/50-800-80-35-SO-12-AP-UNV-MD-1-CA(72) | 120 | 11040 | 0 | LINE 1-6: NOT BEFORE FEB.4TH (LINE 1 IS RELEASE 1 ONLY) LINE 7-13: NOT BEFORE FEB.4TH | Lumilux | Sacha Lempka |  |  | D-12FT | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 1104 | 12 | 0 | 10 | 11040 | 120 |  | 1 | 2019 | 2 | 4 | 3 | Partial | TRUE | TRUE |  | Done
79035-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Replacement | FALSE | 79035 | Regular | Others | FALSE |  | 1 | 1 | 1 | 2 | SCRPAT-ASO-90-300-80-35-0.5M-10'-EX-W-120-DP-1-MFTB9 | 11 | 630 | 0 |  | Lumilux | Robert Lipura |  |  | L1-4 & L1-2-4'X6' | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 315 | 5.5 | 0 | 2 | 630 | 11 | Others | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
78994-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78994 | Regular | Wrong part in BOM | TRUE | Driver | 1 | 1 | 2 | 2 | SCDI-300-400-80-35-SO-FL-6-W-UNV-DP-1-CT15(72) | 19.4 | 1200 | 0 |  | Fortrem | Sacha Lempka |  |  | C6 | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 600 | 9.7 | 0 | 2 | 1200 | 19.4 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
78994-2 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78994 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | SCDI-300-400-80-35-SO-FL-8-W-UNV-DP-1-CA(72)-C(4.5 CANOPIES) | 9.7 | 800 | 0 |  | Fortrem | Sacha Lempka |  |  | C8 | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 800 | 9.7 | 0 | 1 | 800 | 9.7 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
78861-1 | 10 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78861 | Regular |  | FALSE |  | 1 | 1 | 8 | 8 | DIALED-22-4000-90-30-VL-W-120-DP-1-TB9 | 22.4 | 1344 | 0 |  | Internat | Rohan Srivastava |  |  | G-2X2 |  |  |  | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 168 | 2.8 | 8 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE |  | Done
78861-2 | 10 | 2019-02-06 | 2019-02-06 | Wiring Started | Regular | FALSE | 78861 | Regular |  | FALSE |  | 2 | 1 | 5 | 5 | DIALED-22-3000-90-30-VL-W-120-BI-1-TB9 | 14 | 840 | 0 |  | Internat | Rohan Srivastava |  |  | G1-2X2 |  |  |  | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 168 | 2.8 | 2 | 3 | 504 | 8.4 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE |  | Done
78988-1 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78988 | High Priority | Shortage | FALSE | Extrusion | 1 | 1 | 17 | 17 | BBR-S-FL-8'-NL-T5-2-W-UNV-ERS-1-TB9 | 96.9 | 10217 | 0 | MUST BE ON SITE FEB 21ST | Smart Li | Zahra Vatani |  |  | A-8' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 601 | 5.7 | 0 | 17 | 10217 | 96.9 | Shortage | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78988-2 | 12 | 2019-02-12 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 78988 | High Priority |  | FALSE |  | 2 | 1 | 7 | 7 | BBR-S-FL-4-NL-T5-2-W-UNV-ERS-1-TB9 | 21 | 2296 | 0 | MUST BE ON SITE FEB 21ST | Smart Li | Zahra Vatani |  |  | A1-4' |  | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 328 | 3 | 0 | 7 | 2296 | 21 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE |  | Done
78968-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Finished | Regular | FALSE | 78968 | Regular |  | FALSE |  | 1 | 1 | 4 | 4 | BDLED-750-80-30-SO-4'-AP-120-DP-1-CT9(96") | 19.2 | 1312 | 0 |  | Salex | Jessica Pasternyk |  |  | A-4' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Finished - Incomplete |  | 328 | 4.8 | 0 | 4 | 1312 | 19.2 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE |  | Done
77432-1 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority |  | FALSE |  | 1 | 1 | 20 | 20 | BRLED-400-80-35-FL-4-W-UNV-DP-1-DS | 78 | 5920 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F22-4'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 296 | 3.9 | 0 | 20 | 5920 | 78 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
77432-2 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority |  | FALSE |  | 2 | 1 | 16 | 16 | BRLED-400-80-35-FL-6-W-UNV-DP-1-DS | 116.8 | 7072 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F22A-6'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 442 | 7.3 | 0 | 16 | 7072 | 116.8 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
77432-3 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority |  | FALSE |  | 3 | 1 | 14 | 42 | BDLED-400-80-35-SO-24'6"-W-UNV-DP-1-CA(60) | 343 | 24766 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F27-24'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 589.6667 | 8.1667 | 0 | 42 | 24766 | 343 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
77432-4 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority | Shortage | FALSE | Extrusion | 4 | 1 | 8 | 8 | BRLED-750-80-35-FL-6' 0"-DMLED(2)-C(RAL#7004)-UNV-DP-2-D | 78.4 | 5296 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F44-6'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 662 | 9.8 | 0 | 8 | 5296 | 78.4 | Shortage | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
77432-5 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority |  | FALSE |  | 5 | 1 | 6 | 6 | BRLED-1000-80-35-FL-6' 0"-DMLED(2)-C(RAL#7004)-UNV-DP-2-D | 58.8 | 3972 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F45-6'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 662 | 9.8 | 0 | 6 | 3972 | 58.8 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
77432-6 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority |  | FALSE |  | 6 | 1 | 4 | 4 | BRLED-750-80-35-FL-8-C(RAL#7004)-UNV-DP-1-D | 25.6 | 2360 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F45A-8'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 590 | 6.4 | 0 | 4 | 2360 | 25.6 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
77432-7 | 1 | 2019-02-13 |  | Machine Shop Started | Regular | FALSE | 77432 | High Priority |  | FALSE |  | 7 | 1 | 26 | 26 | SLWLED-SL 75/25-800-80-35-VL-8' 0"-W-UNV-DP-1 | 187.2 | 26000 | 0 | Order re-scheduled must ship. | Internat | Gagandeep Singh |  |  | F50-8'-0" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1000 | 7.2 | 0 | 26 | 26000 | 187.2 |  | 0 | 2019 | 2 | 13 | 1 | Complete | TRUE | TRUE
75103-3 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 3 | 1 | 6 | 6 | TWRWLED-SL 90/10-1000-80-35-SO-4-W-120-DP-1 | 30 | 2880 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | B4-NIV5 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 480 | 5 | 0 | 6 | 2880 | 30 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-4 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 4 | 1 | 5 | 5 | TWRWLED-SL 90/10-1000-80-35-SO-6-W-120-DP-1 | 40 | 3600 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | B6-NIV5 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 720 | 8 | 0 | 5 | 3600 | 40 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-5 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 5 | 1 | 12 | 12 | TWRWLED-SL 90/10-1000-80-35-SO-8-W-120-DP-1 | 96 | 11520 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | B8-NIV5 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 960 | 8 | 0 | 12 | 11520 | 96 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-6 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 6 | 1 | 7 | 7 | TWRLED-SL 90/10-1250-80-35-SO-4-W-120-DP-1-CTS(36) | 35 | 3360 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | M4-NIV5 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 480 | 5 | 0 | 7 | 3360 | 35 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-7 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 7 | 1 | 3 | 3 | TWRLED-SL 90/10-1250-80-35-SO-6-W-120-DP-1-CTS(36) | 24 | 2160 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | M6-NIV5 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 720 | 8 | 0 | 3 | 2160 | 24 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-10 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 10 | 1 | 1 | 1 | TWRWLED-SL 90/10-1000-80-35-SO-4-W-120-DP-1 | 5 | 480 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | B4-NIV6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 480 | 5 | 0 | 1 | 480 | 5 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-11 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 11 | 1 | 4 | 4 | TWRWLED-SL 90/10-1000-80-35-SO-6-W-120-DP-1 | 32 | 2880 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | B6-NIV6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 720 | 8 | 0 | 4 | 2880 | 32 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-12 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 12 | 1 | 1 | 1 | TWRWLED-SL 90/10-1000-80-35-SO-8-W-120-DP-1 | 8 | 960 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | B8-NIV6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 960 | 8 | 0 | 1 | 960 | 8 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-13 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 13 | 1 | 1 | 1 | TWRLED-SL 90/10-1250-80-35-SO-4-W-120-DP-1-CTS(36) | 10 | 480 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | M4-NIV6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 480 | 10 | 0 | 1 | 480 | 10 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-14 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 14 | 1 | 1 | 1 | TWRLED-SL 90/10-1250-80-35-SO-6-W-120-DP-1-CTS(36) | 8 | 720 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | M6-NIV6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 720 | 8 | 0 | 1 | 720 | 8 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
75103-15 | 4 | 2019-02-06 | 2019-01-14 | Machine Shop Finished | Regular | FALSE | 75103 | Priority |  | FALSE |  | 15 | 1 | 1 | 1 | TWRLED-SL 90/10-1250-80-35-SO-8-W-120-DP-1-CTS(36) | 8 | 960 | 0 | RELEASE 2 - TYPE B4, B6, B8, M4, M6, M8 - SHIP WHEN READY | HiTec QC | Sacha Lempka |  |  | M8-NIV6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 960 | 8 | 0 | 1 | 960 | 8 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | TRUE |  | Done
78686-1 | 12 | 2019-01-31 | 2019-01-31 | Packaging Finished | Regular | FALSE | 78686 | Priority | Others | FALSE | SHIPMENT | 1 | 1 | 1 | 1 | SCD-300-90-35-FL-8-W-120-DP-1-CA(36)-C(4.5 CANOPIES) | 7 | 600 | 0 | PICK UP ORDER PACAKAGE INDIVIDUALLY PLEASE | HiTec QC | Sacha Lempka |  |  | B8 | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO |  |  | Packaging Finished |  | 600 | 7 | 0 | 1 | 600 | 7 | Others | 1 | 2019 | 1 | 31 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
78686-2 | 12 | 2019-01-31 | 2019-01-31 | Packaging Finished | Regular | FALSE | 78686 | Priority |  | FALSE |  | 2 | 1 | 1 | 1 | SCD-300-90-35-FL-8-W-120-DP-1-CT9(36) | 7 | 600 | 0 | PICK UP ORDER PACAKAGE INDIVIDUALLY PLEASE | HiTec QC | Sacha Lempka |  |  | B8A | Picked - Complete |  | 2019-01-28 | FALSE | FALSE | NO |  |  | Packaging Finished |  | 600 | 7 | 0 | 1 | 600 | 7 |  | 0 | 2019 | 1 | 31 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
79431-1 | 10 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Quick Ship+ | FALSE | 79431 | High Priority |  | FALSE |  | 1 | 1 | 75 | 75 | AULED-22-4400-80-35-SO-W-277-DP-1-TG9 | 180 | 14794.5 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | A |  |  |  | FALSE | FALSE | NO | Material |  | Scheduled/Released |  | 197.26 | 2.4 | 0 | 75 | 14794.5 | 180 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
77175-17 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular | Others | TRUE | sub assembly | 17 | 1 | 45 | 45 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 | 130.5 | 13500 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A-14TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 300 | 2.9 | 0 | 45 | 13500 | 130.5 |  | 1 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-18 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular | Others | TRUE | sub assembly | 18 | 1 | 12 | 12 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 | 58.8 | 5400 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A1-14TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 450 | 4.9 | 0 | 12 | 5400 | 58.8 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-19 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 19 | 1 | 4 | 4 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF | 21.2 | 2560 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A2-14TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 640 | 5.3 | 0 | 4 | 2560 | 21.2 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-20 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 20 | 1 | 2 | 2 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF | 5.8 | 640 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A3-DF-14TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 320 | 2.9 | 0 | 2 | 640 | 5.8 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-21 | 18 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 77175 | Regular |  | FALSE |  | 21 | 1 | 1 | 3 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC | 87 | 1616 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A4-14TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 538.6667 | 29 | 0 | 3 | 1616 | 87 |  | 1 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
77175-22 | 18 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 77175 | Regular |  | FALSE |  | 22 | 1 | 2 | 4 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC | 98 | 1712 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A4A-14TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 428 | 24.5 | 0 | 4 | 1712 | 98 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
77175-23 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 23 | 1 | 3 | 3 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF | 25.5 | 2700 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy | MS:2/5 - Ship: Kaushik to advise?? Edited on 2/5/2019 |  | A9-DWF-14TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 900 | 8.5 | 0 | 3 | 2700 | 25.5 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE |  | Done
77175-24 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 24 | 1 | 18 | 18 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) | 72 | 4950 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | P4-14TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 275 | 4 | 0 | 18 | 4950 | 72 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE |  | Done
77175-25 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 25 | 1 | 8 | 8 | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC | 58.4 | 4040 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | P8-14TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 505 | 7.3 | 0 | 8 | 4040 | 58.4 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-26 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 26 | 1 | 4 | 8 | SCS-750-80-35-0.5P-16-BLK-UNV-DP-1-SC-FW(6) | 50.4 | 4220 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | P16A-14TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 527.5 | 6.3 | 0 | 8 | 4220 | 50.4 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE |  | Done
77175-27 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular | Others | TRUE | sub assembly | 27 | 1 | 49 | 49 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 | 142.1 | 14700 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A-15TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 300 | 2.9 | 0 | 49 | 14700 | 142.1 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-28 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 28 | 1 | 18 | 18 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 | 88.2 | 8100 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A1-15TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 450 | 4.9 | 0 | 18 | 8100 | 88.2 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-29 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 29 | 1 | 5 | 5 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF | 26.5 | 3200 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A2-15TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 640 | 5.3 | 0 | 5 | 3200 | 26.5 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-30 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 30 | 1 | 3 | 3 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF | 8.7 | 960 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A3-DF-15TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 320 | 2.9 | 0 | 3 | 960 | 8.7 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-31 | 18 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 77175 | Regular |  | FALSE |  | 31 | 1 | 1 | 3 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC | 87 | 1616 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A4-15TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 538.6667 | 29 | 0 | 3 | 1616 | 87 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
77175-32 | 18 | 2019-02-04 |  | Machine Shop Started | Regular | FALSE | 77175 | Regular |  | FALSE |  | 32 | 1 | 1 | 2 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC | 49 | 856 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A4A-15TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 428 | 24.5 | 0 | 2 | 856 | 49 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE
77175-33 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 33 | 1 | 18 | 18 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) | 72 | 4950 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | P4-15TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 275 | 4 | 0 | 18 | 4950 | 72 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE |  | Done
77175-34 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular | Others | TRUE | sub assembly | 34 | 1 | 4 | 4 | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC | 29.2 | 2020 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | P8-15TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 505 | 7.3 | 0 | 4 | 2020 | 29.2 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-143 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 143 | 1 | 8 | 8 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 | 24 | 2560 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A3-GRID-14TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 320 | 3 | 0 | 8 | 2560 | 24 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-144 | 18 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 144 | 1 | 10 | 10 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 | 30 | 3200 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A3-GRID-15TH |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 320 | 3 | 0 | 10 | 3200 | 30 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | TRUE |  | Done
77175-145 | 15 | 2019-02-04 |  | Machine Shop Finished | Regular | FALSE | 77175 | Regular |  | FALSE |  | 145 | 1 | 2 | 2 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF | 17 | 1800 | 0 | Floors 14-15 Ship Feb 4th Floors 16-17 February 8th Floors 18-19 February 14th Floor 20 February 20th | BODWELL | Jessica Kennedy |  |  | A9-DWF-15TH | Picked - Complete |  | 2019-02-01 | FALSE | FALSE | NO | Material |  | Machine Shop Finished - Incomplete |  | 900 | 8.5 | 0 | 2 | 1800 | 17 |  | 0 | 2019 | 2 | 4 | 2 | Partial | TRUE | FALSE |  | Done
77180-1 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 1 | 1 | 6 | 6 | SCR-300-80-35-FL-4'-W-UNV-DP-1-DF | 18.36 | 1440 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | D-4' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 240 | 3.06 | 0 | 6 | 1440 | 18.36 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-2 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 2 | 1 | 6 | 6 | SCR-300-80-35-FL-8'-W-UNV-DP-1-DF | 32.7 | 2880 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | D-8' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 5.45 | 0 | 6 | 2880 | 32.7 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-3 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 3 | 1 | 2 | 2 | SCR-300-80-35-FL-8'-W-UNV-DP-1-DF-B1(BSL310LP) | 18.52 | 960 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | D-8' (1)EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 9.26 | 0 | 2 | 960 | 18.52 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-4 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 4 | 1 | 4 | 8 | SCR-300-80-35-FL-16'-W-UNV-DP-1-DF | 46.2 | 3840 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | D-16' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 5.775 | 0 | 8 | 3840 | 46.2 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-5 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 5 | 1 | 4 | 12 | SCR-300-80-35-FL-28'-W-UNV-DP-1-DF-B2(BSL310LP) | 110.04 | 6720 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | D-28' (2)EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 560 | 9.17 | 0 | 12 | 6720 | 110.04 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-6 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular | Shortage | FALSE |  | 6 | 1 | 4 | 4 | SCR-300-80-35-FL-4'-C(BLK)-UNV-DP-1-DF | 12.24 | 960 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | F-4' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 240 | 3.06 | 0 | 4 | 960 | 12.24 | Shortage | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-7 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 7 | 1 | 5 | 5 | SCR-300-80-35-FL-8'-C(BLK)-UNV-DP-1-DF | 27.25 | 2400 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | F-8' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 5.45 | 0 | 5 | 2400 | 27.25 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-8 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 8 | 1 | 5 | 5 | SCR-300-80-35-FL-8'-C(BLK)-UNV-DP-1-DF-B1(BSL310LP) | 46.3 | 2400 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | F-8' EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 9.26 | 0 | 5 | 2400 | 46.3 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-9 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 9 | 1 | 9 | 9 | SCR-300-80-40-FL-4'-W-UNV-DP-1-DF | 27.54 | 2160 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | SC-4' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 240 | 3.06 | 0 | 9 | 2160 | 27.54 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-10 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 10 | 1 | 2 | 2 | SCR-300-80-40-FL-4'-W-UNV-DP-1-DF-B1(BSL310LP) | 13.76 | 480 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | SC-4' (1)EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 240 | 6.88 | 0 | 2 | 480 | 13.76 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-11 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 11 | 1 | 3 | 3 | SCR-300-80-40-FL-8'-W-UNV-DP-1-DF | 16.35 | 1440 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | SC-8' |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 5.45 | 0 | 3 | 1440 | 16.35 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
77180-12 | 7 | 2019-02-12 | 2019-01-23 | Machine Shop Started | Regular | FALSE | 77180 | Regular |  | FALSE |  | 12 | 1 | 3 | 3 | SCR-300-80-40-FL-8'-W-UNV-DP-1-DF-B1(BSL310LP) | 27.78 | 1440 | 0 | DO NOT SHIP BEFORE FEBRUARY 12, 2019 NO UPS GROUND/FEDEX GROUND TO SITE | RCLURIE2 | Sacha Lempka |  |  | SC-8' (1)EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 480 | 9.26 | 0 | 3 | 1440 | 27.78 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE
78515-1 | 12 | 2019-02-07 | 2019-02-07 | Given to Shipping | Regular | FALSE | 78515 | Regular |  | FALSE |  | 1 | 1 | 5 | 5 | BSLED-400-80-30-SO-6-AP-120-DP-1-S | 35 | 2335 | 0 |  | RCLURIE2 | Sacha Lempka |  |  | A |  |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 467 | 7 | 5 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE |  | Done
78506-1 | 7 | 2019-02-08 | 2019-02-15 | Machine Shop Started | Regular | FALSE | 78506 | High Priority |  | FALSE |  | 1 | 1 | 6 | 6 | STLDI-I-500-DSO-400-8'-80-35-W-UNV-DP-1-CTS(60)-RC | 48 | 5400 | 0 | MUST MUST SHIP FEB 8TH, NO BUFFER | ALA | Zahra Vatani |  |  | A1-8' | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 900 | 8 | 0 | 6 | 5400 | 48 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
78506-2 | 7 | 2019-02-08 | 2019-02-15 | Machine Shop Started | Regular | FALSE | 78506 | High Priority | Missing parts in BOM | TRUE | Driver | 2 | 1 | 3 | 3 | STLDI-I-500-DSO-400-4'-80-35-W-UNV-DP-1-CTS(36)-RC | 15 | 1440 | 0 | MUST MUST SHIP FEB 8TH, NO BUFFER | ALA | Zahra Vatani |  |  | A2-4' | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 480 | 5 | 0 | 3 | 1440 | 15 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
78506-3 | 7 | 2019-02-08 | 2019-02-15 | Machine Shop Started | Regular | FALSE | 78506 | High Priority |  | FALSE |  | 3 | 1 | 2 | 8 | STFC-NO-DSO(8-400)-80-35-AL(4)-W-UNV-MD-1-CA(76)-RC-C(SWIVEL GRIP LOCK) | 38 | 2480 | 0 | MUST MUST SHIP FEB 8TH, NO BUFFER | ALA | Zahra Vatani |  |  | C | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 310 | 4.75 | 0 | 8 | 2480 | 38 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
78506-4 | 7 | 2019-02-08 | 2019-02-15 | Machine Shop Started | Regular | FALSE | 78506 | High Priority |  | FALSE |  | 4 | 1 | 1 | 4 | STFC-NO-DSO(16-400)-80-35-AL(4)-W-UNV-MD-1-CA(70)-RC-C(SWIVEL GRIP LOCK) | 19 | 760 | 0 | MUST MUST SHIP FEB 8TH, NO BUFFER | ALA | Zahra Vatani |  |  | B | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 190 | 4.75 | 0 | 4 | 760 | 19 |  | 0 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
78796-1 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78796 | Regular |  | FALSE |  | 1 | 1 | 6 | 6 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9 | 18 | 1770 | 0 |  | Internat | Joe Brier |  |  | F8 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 295 | 3 | 0 | 6 | 1770 | 18 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78796-2 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78796 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9-B1(BSL310LP) | 9 | 1620 | 0 |  | Internat | Joe Brier |  |  | F8 EM |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 540 | 3 | 0 | 3 | 1620 | 9 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78796-3 | 10 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 78796 | Regular |  | FALSE |  | 3 | 1 | 5 | 5 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-SM | 15 | 1850 | 0 |  | Internat | Joe Brier |  |  | F12 |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 370 | 3 | 0 | 5 | 1850 | 15 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78731-1 | 10 | 2019-02-06 |  | Packaging Finished | Regular | FALSE | 78731 | Regular |  | FALSE |  | 1 | 1 | 12 | 12 | DIALED-14-2400-80-35-VL-W-277-DP-1-TG9 | 38.4 | 5520 | 0 |  | Vanguard | Philip Halsey |  |  | SS |  |  |  | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 460 | 3.2 | 12 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 6 | 1 | Complete | FALSE | FALSE
74964-1 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 1 | 1 | 2 | 6 | GPRLED-FC2W-500-90-35-RG2-35'5"-W-120-DP-1-DS | 62 | 10733.34 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10800MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1788.89 | 10.3333 | 0 | 6 | 10733.34 | 62 |  | 1 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-2 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 2 | 1 | 13 | 26 | GPRLED-EX2W-500-90-35-RG2-16-W-120-DP-1-TB15 | 145.6 | 31893.16 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(4890MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1226.66 | 5.6 | 0 | 26 | 31893.16 | 145.6 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-3 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 3 | 1 | 4 | 12 | GPRLED-FC2W-500-90-35-RG2-34'8"-W-120-DP-1-DS | 124 | 21466.68 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10560MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1788.89 | 10.3333 | 0 | 12 | 21466.68 | 124 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-4 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 4 | 1 | 2 | 8 | GPRLED-FC2W-500-90-35-RG2-36'7"-W-120-DP-1-DS | 75.4 | 11346.66 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(11156MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1418.3325 | 9.425 | 0 | 8 | 11346.66 | 75.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-5 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 5 | 1 | 2 | 8 | GPRLED-FC2W-500-90-35-RG2-37'1"-W-120-DP-1-DS | 75.4 | 11346.66 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(11300MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1418.3325 | 9.425 | 0 | 8 | 11346.66 | 75.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-6 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 6 | 1 | 1 | 3 | GPRLED-FC2W-500-90-35-RG2-35'4"-W-120-DP-1-DS | 31 | 5366.67 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10761MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1788.89 | 10.3333 | 0 | 3 | 5366.67 | 31 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-7 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 7 | 1 | 5 | 15 | GPRLED-FC2W-500-90-35-RG2-33'2"-W-120-DP-1-DS | 155 | 25300 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10113MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1686.6667 | 10.3333 | 0 | 15 | 25300 | 155 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-8 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 8 | 1 | 7 | 21 | GPRLED-FC2W-500-90-35-RG2-33'7"-W-120-DP-1-DS | 217 | 36493.31 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10226MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1737.7767 | 10.3333 | 0 | 21 | 36493.31 | 217 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-9 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 9 | 1 | 1 | 3 | GPRLED-FC2W-500-90-35-RG2-35'6"-W-120-DP-1-DS | 31 | 5520 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10830MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1840 | 10.3333 | 0 | 3 | 5520 | 31 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-10 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 10 | 1 | 2 | 8 | GPRLED-FC2W-500-90-35-RG2-36'9"-W-120-DP-1-DS | 75.4 | 10746.66 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(11198MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1343.3325 | 9.425 | 0 | 8 | 10746.66 | 75.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-11 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 11 | 1 | 2 | 6 | GPRLED-FC2W-500-90-35-RG2-34'6"-W-120-DP-1-DS | 62 | 10733.34 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(10524MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1788.89 | 10.3333 | 0 | 6 | 10733.34 | 62 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-12 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 12 | 1 | 2 | 2 | GPRLED-EX2W-500-90-35-RG2-12'-W-120-DP-1-TB15 | 14.4 | 3680 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(3670MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1840 | 7.2 | 0 | 2 | 3680 | 14.4 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-13 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 13 | 1 | 1 | 3 | GPRLED-FC2W-500-90-35-RG2-27'-W-120-DP-1-DS | 27 | 4293.33 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1-(8229MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1431.11 | 9 | 0 | 3 | 4293.33 | 27 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-14 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 14 | 1 | 1 | 3 | GPRLED-FC2W-500-90-35-RG2-27'10"-W-120-DP-1-TB15 | 19 | 4293.33 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1A-(8490MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1431.11 | 6.3333 | 0 | 3 | 4293.33 | 19 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-15 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 15 | 1 | 1 | 3 | GPRLED-FC2W-500-90-35-RG2-34'-W-120-DP-1-TB15 | 23 | 5213.33 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1A-(9747MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1737.7767 | 7.6667 | 0 | 3 | 5213.33 | 23 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-16 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 16 | 1 | 1 | 3 | GPRLED-FC2W-500-90-35-RG2-27'9"-W-120-DP-1-TB15 | 19 | 4293.33 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1A-(8447MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1431.11 | 6.3333 | 0 | 3 | 4293.33 | 19 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
74964-17 | 1 | 2019-02-08 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 17 | 1 | 9 | 18 | CLKLED-750-90-35-SO-12-W-120-DP-1-ST | 76.5 | 13680 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | LS1-12FT | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 760 | 4.25 | 0 | 18 | 13680 | 76.5 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
74964-18 | 1 | 2019-02-08 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 74964 | High Priority | Shortage | FALSE |  | 18 | 1 | 55 | 110 | CLKLED-750-90-35-SO-16-W-120-DP-1-ST | 924 | 108216.35 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | LS1-16FT | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 983.785 | 8.4 | 0 | 110 | 108216.35 | 924 | Shortage | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
74964-19 | 1 | 2019-02-08 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 19 | 1 | 5 | 5 | SP18407-ARCLED-SL 23/77-800-80-35-SO-8-W-120-DP-1-CTS(36) | 43.5 | 4426.65 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | SL1-8FT | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 885.33 | 8.7 | 0 | 5 | 4426.65 | 43.5 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
74964-20 | 1 | 2019-02-08 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 20 | 1 | 3 | 3 | SP18407-ARCLED-SL 23/77-800-80-35-SO-4-W-120-DP-1-CTS(36) | 15 | 1327.98 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | SL3 | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 442.66 | 5 | 0 | 3 | 1327.98 | 15 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
74964-21 | 1 | 2019-02-08 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 21 | 1 | 1 | 1 | SP18407-ARCWLED-SL 23/77-800-80-35-SO-8-W-120-DP-1 | 8.7 | 885.33 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | W1-8FT | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 885.33 | 8.7 | 0 | 1 | 885.33 | 8.7 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
74964-22 | 1 | 2019-02-08 | 2019-02-12 | Machine Shop Started | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 22 | 1 | 1 | 3 | SP18407-ARCWLED-SL 23/77-800-80-35-SO-18-W-120-DP-1 | 20.8 | 1992 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | W1-18FT | Picked - Complete | 2019-02-04 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 664 | 6.9333 | 0 | 3 | 1992 | 20.8 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
74964-23 | 1 | 2019-02-12 | 2019-02-12 | Scheduled/Released | Regular | FALSE | 74964 | High Priority |  | FALSE |  | 23 | 1 | 1 | 3 | GPRLED-EXNW-500-90-35-RG2-27' 11 1/2"-W-120-DP-1-TB15 | 19 | 4293.33 | 0 | MUST SHIP CANNOT BE LATE!!!!! TORONTO. 1ST SHIPMENT NO LATER THAN FEB 18TH LINES: 17-18-19-20-21-22 2ND SHIPMENT NO LATER THAN MARCH 1ST-LINES: 1-2-3-4-5-6-7-8-9-10-11-12-13-14-15-16-23 | Salex | Jessica Pasternyk |  |  | C1A-(8528MM) | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Scheduled/Released |  | 1431.11 | 6.3333 | 0 | 3 | 4293.33 | 19 |  | 0 | 2019 | 2 | 12 | 1 | Complete | FALSE | FALSE
75212-30 | 18 | 2019-02-01 |  | Given to Shipping | Regular | FALSE | 75212 | Regular | Shortage | FALSE | CARTRIDGE/EXTRUSION | 30 | 1 | 14 | 14 | BMRLED-1000-80-30-ASO-4'-W-UNV-DP-1-D | 41.58 | 2800 | 0 |  | IllumBos | Philip Halsey | BD-JBK-CNR-WH Eta: 2/4 - Qty adjusment. Edited on 1/31/2019 Edited on 2/1/2019 ::: Kaushik to advise ??? Edited on 2/5/2019 |  | R10, 4' |  |  |  | FALSE | FALSE | NO |  |  | Given to Shipping |  | 200 | 2.97 | 14 | 0 | 0 | 0 | Shortage | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | FALSE |  | Done
75212-38 | 18 | 2019-02-12 |  | Machine Shop Started | Regular | FALSE | 75212 | Regular |  | FALSE |  | 38 | 1 | 4 | 8 | BMRLED-1000-80-30-ASO-24'-W-UNV-DP-1+E(1)-TB15 | 71.32 | 4800 | 0 |  | IllumBos | Philip Halsey |  |  | R10, 24' EM |  |  |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 600 | 8.915 | 0 | 8 | 4800 | 71.32 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | FALSE
77939-3 | 7 | 2019-01-31 | 2019-01-31 | Machine Shop Finished | Regular | FALSE | 77939 | Regular | Others | FALSE | SUB ASSEMBLY | 3 | 1 | 1 | 6 | STSFR-SO(32-200)-80-35-AL(4)+AI(2)-W-UNV-MD-1-SB15 | 31.3 | 3680 | 0 |  | Vanguard | Philip Halsey | Elizabeth to follow up Sub assembly. Edited on 2/1/2019 |  | F-12X4 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 613.3333 | 5.2167 | 0 | 6 | 3680 | 31.3 | Others | 1 | 2019 | 1 | 31 | 1 | Complete | TRUE | FALSE |  | Done
77939-4 | 7 | 2019-01-31 | 2019-01-31 | Machine Shop Finished | Regular | FALSE | 77939 | Regular | Shortage | TRUE | INSTALLATION PART | 4 | 1 | 1 | 6 | STSFR-SO(36-200)-80-35-AL(4)+AI(2)-W-UNV-MD-1-SB15 | 35.4 | 4140 | 0 |  | Vanguard | Philip Halsey | ETA: Feb 1st - MS: ? Ship: ? Edited on 1/30/2019::: Elizabeth to follow Edited on 2/5/2019 |  | F-12X6 |  | 2019-01-28 | 2019-02-05 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 690 | 5.9 | 0 | 6 | 4140 | 35.4 |  | 0 | 2019 | 1 | 31 | 1 | Complete | TRUE | FALSE |  | Done
78170-1 | 4 | 2019-02-06 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78170 | Regular |  | FALSE |  | 1 | 1 | 1 | 10 | SCRPAT-REC-90(4)-500-80-30-2M-58'-EX-W-UNV-DP-1-TB9-B4(BSL10LST) | 4.3 | 5000 | 0 | Expedite Request: ok per Production Meeting | Vanguard | Philip Halsey |  |  | D, REC | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 500 | 0.43 | 0 | 10 | 5000 | 4.3 |  | 1 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | ToDo
78170-2 | 4 | 2019-02-06 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 78170 | Regular |  | FALSE |  | 2 | 1 | 1 | 5 | SCRPAT-OPR-90(2)-300-80-30-2P-29'-EX-W-UNV-DP-1-TB9 | 30 | 2540 | 0 | Expedite Request: ok per Production Meeting | Vanguard | Philip Halsey |  |  | D1, "U" | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 508 | 6 | 0 | 5 | 2540 | 30 |  | 0 | 2019 | 2 | 6 | 1 | Complete | TRUE | FALSE | ToDo
79116-1 | 12 | 2019-02-11 | 2019-02-11 | Machine Shop Started | Regular | FALSE | 79116 | Priority |  | FALSE |  | 1 | 1 | 4 | 4 | B6R-S-FL-4-NL4-T8-2-W-120-E-1-TG9 | 11.2 | 1093.96 | 0 |  | HiTec QC | Sacha Lempka |  |  | D2B | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | OK |  |  | Machine Shop Started |  | 273.49 | 2.8 | 0 | 4 | 1093.96 | 11.2 |  | 1 | 2019 | 2 | 11 | 1 | Complete | TRUE | FALSE
79284-1 | 12 | 2019-02-01 | 2019-02-01 | Packaging Finished | Mockup/Samples | FALSE | 79284 | High Priority | Others | TRUE | QC Rejected Fixture | 1 | 1 | 1 | 1 | B2SQWILED-1100-80-35-SLA-2-W-UNV-DP-1-C(AXIS CORD PLUG DIMMER) | 5.1 | 240 | 240 | Rush Sample - MS:1/30 Ship:2/1 - Ok per Production meeting. | IllumBos | Lazer Framovitz | Missing lens from Stores - Ship:2/4 Edited on 2/1/2019::: Ship: Feb 5th Edited on 2/5/2019 |  | W8 SAMPLE | Picked - Complete |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Packaging Finished |  | 240 | 5.1 | 0 | 1 | 240 | 5.1 |  | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
76468-1 | 7 | 2019-02-07 | 2019-02-07 | Order UnShipped | Regular | FALSE | 76468 | Regular | Shortage | TRUE | Extrusion | 1 | 1 | 29 | 29 | PWWLED-800-80-35-S-2-W-UNV-DP-1-F | 118.9 | 6264 | 0 |  | KSA Cent | Joshua Zimet |  |  | L1-2' | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO | Material |  | Order UnShipped |  | 216 | 4.1 | 28 | 1 | 216 | 4.1 |  | 1 | 2019 | 2 | 7 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
76468-2 | 7 | 2019-02-07 | 2019-02-07 | Order UnShipped | Regular | FALSE | 76468 | Regular |  | FALSE |  | 2 | 1 | 2 | 2 | PWWLED-800-80-35-S-4-W-UNV-DP-1-F | 8.2 | 690 | 0 |  | KSA Cent | Joshua Zimet |  |  | L1-4' | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO | Material |  | Order UnShipped |  | 345 | 4.1 | 2 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 7 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
76468-3 | 7 | 2019-02-07 | 2019-02-07 | Order UnShipped | Regular | FALSE | 76468 | Regular |  | FALSE |  | 3 | 1 | 65 | 65 | B6RLED-500-80-35-FL-4-W-UNV-DP-1-TB15-C(F) | 227.5 | 17290 | 0 |  | KSA Cent | Joshua Zimet |  |  | L2-4' | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO | Material |  | Order UnShipped |  | 266 | 3.5 | 78 | -13 | -3458 | -45.5 |  | 0 | 2019 | 2 | 7 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
76468-4 | 7 | 2019-02-07 | 2019-02-07 | Order UnShipped | Regular | FALSE | 76468 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | PWWLED-800-80-35-S-2-W-UNV-DP-1-F | 4.1 | 216 | 0 |  | KSA Cent | Joshua Zimet |  |  | L1-2/SPARE | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO | Material |  | Order UnShipped |  | 216 | 4.1 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 7 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
76468-5 | 7 | 2019-02-07 | 2019-02-07 | Order UnShipped | Regular | FALSE | 76468 | Regular |  | FALSE |  | 5 | 1 | 1 | 1 | PWWLED-800-80-35-S-4-W-UNV-DP-1-F | 4.1 | 345 | 0 |  | KSA Cent | Joshua Zimet |  |  | L1-4/SPARE | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO | Material |  | Order UnShipped |  | 345 | 4.1 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 7 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
76468-6 | 7 | 2019-02-07 | 2019-02-07 | Order UnShipped | Regular | FALSE | 76468 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | B6RLED-500-80-35-FL-4-W-UNV-DP-1-TB15-C(F) | 3.5 | 266 | 0 |  | KSA Cent | Joshua Zimet |  |  | L2/SPARE | Picked - Complete | 2019-02-03 | 2019-01-31 | FALSE | FALSE | NO | Material |  | Order UnShipped |  | 266 | 3.5 | 1 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 7 | 1 | Complete | #N/A | #N/A | #N/A | #N/A
79011-2 | 12 | 2019-02-01 | 2019-02-01 | Wiring Started | Replacement | FALSE | 79011 | Regular | Others | FALSE | LENS | 2 | 1 | 1 | 1 | SKPLED-22-3200-80-35-0.5-W-UNV-DP-2-TB9 | 2 | 195 | 0 | UPS acct# 9769V8 | CAL | Tajinder Singh |  |  | F42DM-AT17 | Picked - Complete | 2019-02-03 | 2019-01-29 | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 195 | 2 | 0 | 1 | 195 | 2 | Others | 1 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
79011-3 | 12 | 2019-02-01 | 2019-02-01 | Wiring Started | Replacement | FALSE | 79011 | Regular | Others | FALSE | LENS | 3 | 1 | 1 | 1 | SKPLED-22-3200-80-35-0.5-W-UNV-DP-2-TB15 | 2 | 195 | 0 | UPS acct# 9769V8 | CAL | Tajinder Singh |  |  | F42DM-AT13 | Picked - Complete | 2019-02-03 | 2019-01-29 | FALSE | FALSE | NO | Material |  | Wiring Issue |  | 195 | 2 | 0 | 1 | 195 | 2 | Others | 0 | 2019 | 2 | 1 | 1 | Complete | TRUE | TRUE |  | Done
78825-1 | 15 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78825 | High Priority |  | FALSE |  | 1 | 1 | 20 | 20 | WBSLED-500-80-35-S-4'-W-UNV-DP-1-SC-C(END FEED) | 92 | 8800 | 0 | SHIP NOT BEFORE WEEK OF 2-11-19 | LHI | Rajithan Sivapatharajahon |  |  | F3 |  |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 440 | 4.6 | 0 | 20 | 8800 | 92 |  | 1 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE |  | Done
78825-2 | 15 | 2019-02-12 | 2019-02-12 | Machine Shop Finished | Regular | FALSE | 78825 | High Priority |  | FALSE |  | 2 | 1 | 10 | 10 | WBSLED-500-80-35-S-4'-W-UNV-DP-E(1)-SC-C(End Feed) | 59 | 4800 | 0 | SHIP NOT BEFORE WEEK OF 2-11-19 | LHI | Rajithan Sivapatharajahon |  |  | F3E |  |  |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 480 | 5.9 | 0 | 10 | 4800 | 59 |  | 0 | 2019 | 2 | 12 | 1 | Complete | TRUE | TRUE |  | Done
77693-1 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 1 | 1 | 13 | 13 | SCD-500-80-40-FL-4'0"-BLK-UNV-DP-1-CA(12) | 58.5 | 3890.77 | 0 |  | IllumBos | Philip Halsey |  |  | LT2A |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 299.29 | 4.5 | 10 | 3 | 897.87 | 13.5 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-2 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | SCD-500-80-40-FL-6'0"-BLK-UNV-DP-1-CA(12) | 21 | 1336.05 | 0 |  | IllumBos | Philip Halsey |  |  | LT2B |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 445.35 | 7 | 0 | 3 | 1336.05 | 21 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-3 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 3 | 1 | 6 | 6 | SCD-500-80-40-FL-8'0"-BLK-UNV-DP-1-CA(12) | 42 | 3591.42 | 0 |  | IllumBos | Philip Halsey |  |  | LT2C |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 598.57 | 7 | 0 | 6 | 3591.42 | 42 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-4 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 4 | 1 | 8 | 8 | ARLED-800-80-35-S-4'0"-BLK-UNV-DP-1-CA(48) | 31.2 | 2565.2 | 0 |  | IllumBos | Philip Halsey |  |  | LT3 |  |  |  | FALSE | FALSE | NO | +Cartridge |  | Wiring Issue |  | 320.65 | 3.9 | 8 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-5 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 5 | 1 | 7 | 7 | SCDI-500-300-80-40-SO-0.5M-4'0"-BLK-UNV-DP-1-CA(48) | 46.9 | 2933 | 0 |  | IllumBos | Philip Halsey |  |  | LT11A |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 419 | 6.7 | 7 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-6 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 6 | 1 | 2 | 2 | SCDI-500-300-80-40-SO-0.5M-6'0"-BLK-UNV-DP-1-CA(48) | 19.8 | 1257.02 | 0 |  | IllumBos | Philip Halsey |  |  | LT11B |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 628.51 | 9.9 | 0 | 2 | 1257.02 | 19.8 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-7 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 7 | 1 | 5 | 5 | SCDI-500-300-80-40-SO-0.5M-8'0"-BLK-UNV-DP-1-CA(48) | 49.5 | 4190.05 | 0 |  | IllumBos | Philip Halsey |  |  | LT11C |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 838.01 | 9.9 | 0 | 5 | 4190.05 | 49.5 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-8 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 8 | 1 | 30 | 30 | SCDI-500-300-80-40-SO-FL-4'0"-BLK-UNV-DP-1-CA(48) | 201 | 12185.4 | 0 |  | IllumBos | Philip Halsey |  |  | LT12A |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 406.18 | 6.7 | 15 | 15 | 6092.7 | 100.5 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-9 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 9 | 1 | 20 | 20 | SCDI-500-300-80-40-SO-FL-6'0"-BLK-UNV-DP-1-CA(48) | 198 | 12185.4 | 0 |  | IllumBos | Philip Halsey |  |  | LT12B |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 609.27 | 9.9 | 0 | 20 | 12185.4 | 198 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-10 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 10 | 1 | 12 | 12 | SCDI-500-300-80-40-SO-FL-8'0"-BLK-UNV-DP-1-CA(48) | 118.8 | 9748.2 | 0 |  | IllumBos | Philip Halsey |  |  | LT12C |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 812.35 | 9.9 | 0 | 12 | 9748.2 | 118.8 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77693-11 | 18 | 2019-02-05 | 2019-02-05 | Wiring Started | Regular | FALSE | 77693 | Regular |  | FALSE |  | 11 | 1 | 5 | 5 | SCD-500-80-40-FL-4'0"-BLK-UNV-DP-1-CA(12) | 22.5 | 1496.45 | 0 |  | IllumBos | Philip Halsey |  |  | LT12D |  |  |  | FALSE | FALSE | NO |  |  | Wiring Issue |  | 299.29 | 4.5 | 0 | 5 | 1496.45 | 22.5 |  | 0 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
77926-1 | 10 | 2019-02-11 | 2019-02-11 | Scheduled/Released | Regular | FALSE | 77926 | Regular |  | FALSE |  | 1 | 1 | 72 | 72 | SKFLED-22-2400-80-35-4SF-W-UNV-DP-1-TG9 | 161.28 | 18000 | 0 | Note:****Material required on Job Site February 1, 2019***** | IllumBos | Philip Halsey |  |  | AL4-4SF |  |  |  | FALSE | FALSE | NO | Material |  | Scheduled/Released |  | 250 | 2.24 | 0 | 72 | 18000 | 161.28 |  | 1 | 2019 | 2 | 11 | 1 | Complete | FALSE | FALSE
79017-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 79017 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | SCR-400-80-35-FL-8' 11"-W-UNV-DP-1-DF | 7.5 | 765 | 0 |  | Internat | Rohan Srivastava |  |  | A-8'-11" | Picked - Complete |  | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 765 | 7.5 | 0 | 1 | 765 | 7.5 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE
77765-1 | 1 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 77765 | Regular |  | FALSE |  | 1 | 1 | 8 | 16 | SCRPAT-OPI-90(1)-300-80-30-FL-9'0"-NL-W-UNV-DP-1-DS | 72 | 6965.04 | 0 |  | IllumBos | Philip Halsey |  |  | D | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 435.315 | 4.5 | 0 | 16 | 6965.04 | 72 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE | Ready
77765-2 | 1 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 77765 | Regular |  | FALSE |  | 2 | 1 | 1 | 5 | SCRPAT-OPI-90(2)-500-80-30-FL-26'4"-NL-W-UNV-DP-1-DS | 30 | 2743.1 | 0 |  | IllumBos | Philip Halsey |  |  | D-10 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 548.62 | 6 | 0 | 5 | 2743.1 | 30 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE | Ready
77765-4 | 10 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 77765 | Regular |  | FALSE |  | 4 | 1 | 1 | 1 | AULED-22-3000-80-30-SO-W-UNV-DP-1-TB9-B1(BSL310LP) | 6 | 381.65 | 0 |  | IllumBos | Philip Halsey |  |  | EE |  |  |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 381.65 | 6 | 0 | 1 | 381.65 | 6 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
77765-5 | 1 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 77765 | Regular |  | FALSE |  | 5 | 1 | 4 | 4 | SCD-300-80-30-FL-6'10"-BLK-UNV-DP-1-CTS(48) | 28 | 2003.64 | 0 |  | IllumBos | Philip Halsey |  |  | H-7 | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 500.91 | 7 | 0 | 4 | 2003.64 | 28 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE |  | Done
77765-22 | 1 | 2019-02-07 |  | Machine Shop Started | Regular | FALSE | 77765 | Regular | Missing info. In SD | TRUE | FIXTURE TYPE | 22 | 1 | 1 | 5 | SCRPAT-OPI-90(2)-500-80-30-FL-26'4"-NL-W-UNV-DP-1-DS | 30 | 2743.1 | 0 |  | IllumBos | Philip Halsey |  |  | D-10S | Picked - Complete | 2019-02-03 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 548.62 | 6 | 0 | 5 | 2743.1 | 30 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | TRUE | Ready
78448-1 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | SCR-300-80-30-FL-1'3"-W-UNV-DP-1-DS | 10 | 254 | 0 |  | IllumBos | Philip Halsey |  |  | D2-1'3" F | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 127 | 5 | 0 | 2 | 254 | 10 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-2 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | SCR-300-80-30-FL-10'2"-W-UNV-DP-1-DS | 10.2 | 632 | 0 |  | IllumBos | Philip Halsey |  |  | D2-10'2" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 632 | 10.2 | 0 | 1 | 632 | 10.2 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-3 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 3 | 1 | 1 | 1 | SCR-300-80-30-FL-6'10"-W-UNV-DP-1-DS-B1(BSL310LP) | 11.9 | 632 | 0 |  | IllumBos | Philip Halsey |  |  | D2E-6'10" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 632 | 11.9 | 0 | 1 | 632 | 11.9 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-4 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 4 | 1 | 2 | 2 | SCD-300-80-30-FL-10'7 3/4"-BLK-UNV-DP-1-CA(48)-C(BLK CANOPIES AND CORD) | 18 | 1506 | 0 |  | IllumBos | Philip Halsey |  |  | D1-11-10'7 3/4" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 753 | 9 | 0 | 2 | 1506 | 18 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-5 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 5 | 1 | 2 | 4 | SCD-300-80-30-FL-16'8 1/2"-BLK-UNV-DP-1-CA(48)-C(BLK CANOPIES AND CORD) | 32 | 2328 | 0 |  | IllumBos | Philip Halsey |  |  | D1-16-16'8 1/2" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 582 | 8 | 0 | 4 | 2328 | 32 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-6 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 6 | 1 | 1 | 1 | SCD-300-80-30-FL-10'7 3/4"-BLK-UNV-DP-1-CA(48)-B1(BSL310LP)-C(BLK CANOPIES AND CORD) | 13 | 943 | 0 |  | IllumBos | Philip Halsey |  |  | D1E-11-10'7 3/4" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 943 | 13 | 0 | 1 | 943 | 13 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-7 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 7 | 1 | 2 | 4 | SCD-300-80-30-FL-16'8 1/2"-BLK-UNV-DP-1-CA(48)-B1(BSL310LP)-C(BLK CANOPIES AND CORD) | 40 | 2706 | 0 |  | IllumBos | Philip Halsey |  |  | D1E-16-16'8 1/2" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 676.5 | 10 | 0 | 4 | 2706 | 40 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
78448-8 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 8 | 1 | 1 | 8 | SCRPAT-REC-90(4)-300-80-30-FL-55'4"-NL-W-UNV-DP-1-DS-C(RECT 13' 6" X 14' 2") | 50 | 3927 | 0 |  | IllumBos | Philip Halsey |  |  | D2-RECT162-7/16"X170-3/4" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 490.875 | 6.25 | 0 | 8 | 3927 | 50 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE | ToDo
78448-9 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 9 | 1 | 1 | 8 | SCRPAT-REC-90(4)-300-80-30-FL-48'0"-NL-W-UNV-DP-1-DS-C(RECT 12' 3" X 10' 8") | 45 | 3453 | 0 |  | IllumBos | Philip Halsey |  |  | D2-RECT147-3/8"X128-5/8" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 431.625 | 5.625 | 0 | 8 | 3453 | 45 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE | ToDo
78448-10 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 10 | 1 | 1 | 1 | SCRV-300-80-30-FL-1'0"-W-UNV-DP-1-DS-C(DRIVER TO BE REMOTE, NO FLANGE ON ONE END) | 5 | 137 | 0 |  | IllumBos | Philip Halsey |  |  | D3-1' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 137 | 5 | 0 | 1 | 137 | 5 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-11 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 11 | 1 | 2 | 2 | SCRV-300-80-30-FL-2'0"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | 10 | 254 | 0 |  | IllumBos | Philip Halsey |  |  | D3-2' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 127 | 5 | 0 | 2 | 254 | 10 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-12 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 12 | 1 | 4 | 4 | SCRV-300-80-30-FL-3'0"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | 20 | 760 | 0 |  | IllumBos | Philip Halsey |  |  | D3-3' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 190 | 5 | 0 | 4 | 760 | 20 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-13 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 13 | 1 | 2 | 2 | SCRV-300-80-30-FL-5'0"-W-UNV-DP-1-Ds-C(NO FLANGE ON ONE END) | 14 | 632 | 0 |  | IllumBos | Philip Halsey |  |  | D3-5' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 316 | 7 | 0 | 2 | 632 | 14 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-14 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular | Shortage | FALSE | Extrusion | 14 | 1 | 22 | 22 | ZESQDI-SL 25/75-1050-80-30-MSO-8'-BLK-UNV-MD-1-CA(48) | 275 | 17600 | 0 |  | IllumBos | Philip Halsey |  |  | H-8' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | Material |  | Machine Shop Started |  | 800 | 12.5 | 0 | 22 | 17600 | 275 | Shortage | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-15 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular | Missing parts in BOM | TRUE | Remote Parts | 15 | 1 | 18 | 18 | ZESQDI-SL 25/75-1050-80-30-MSO-8'-BLK-UNV-MD-1-CA(48)-B1(BSL310LP) | 297 | 17820 | 0 |  | IllumBos | Philip Halsey |  |  | HE-8' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 990 | 16.5 | 0 | 18 | 17820 | 297 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-16 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 16 | 1 | 1 | 8 | SCRPAT-REC-90(4)-300-80-30-FL-53'10 6/8"-NL-W-UNV-DP-1-DS-C(RECT 15' 4" 3/8"X 11' 7") | 49 | 3750 | 0 |  | IllumBos | Philip Halsey |  |  | D2-RECT184-3/8 8"X139" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 468.75 | 6.125 | 0 | 8 | 3750 | 49 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE | ToDo
78448-17 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 17 | 1 | 1 | 1 | SCRV-300-80-30-FL-3'0"-W-UNV-DP-1-DS | 5 | 240 | 0 |  | IllumBos | Philip Halsey |  |  | D3-3' F | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 240 | 5 | 0 | 1 | 240 | 5 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-18 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 18 | 1 | 3 | 3 | SCRV-300-80-30-FL-2'0"-W-UNV-DP-1-DS | 15 | 630 | 0 |  | IllumBos | Philip Halsey |  |  | D3-2' | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 210 | 5 | 0 | 3 | 630 | 15 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-19 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 19 | 1 | 1 | 1 | SCR-300-80-30-FL-10'2"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | 9 | 770 | 0 |  | IllumBos | Philip Halsey |  |  | D2-10'2" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 770 | 9 | 0 | 1 | 770 | 9 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78448-20 | 1 | 2019-02-08 |  | Machine Shop Started | Regular | FALSE | 78448 | Regular |  | FALSE |  | 20 | 1 | 1 | 1 | SCR-300-80-30-FL-1'3"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) | 5 | 180 | 0 |  | IllumBos | Philip Halsey |  |  | D2-1'3" | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 180 | 5 | 0 | 1 | 180 | 5 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE |  | Done
78525-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 78525 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | SCDI-300-500-80-35-SO-FL-K(2X6)-BLK-UNV-DP-1-CA(48")-C(SWIVEL MOUNTING) | 34 | 1700 | 0 |  | LS Phill | Gaurav Jain |  |  | A-2'X6' RECT | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1700 | 34 | 0 | 1 | 1700 | 34 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
77211-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77211 | Regular |  | FALSE |  | 1 | 1 | 12 | 12 | BBWDILED-640-400-80-40-SO-8-W-UNV-DP-1-D | 121 | 11520 | 0 | Do Not Ship Before Feb 8th. | RichardM | George Bacalla |  |  | F1-8' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 960 | 10.0833 | 0 | 12 | 11520 | 121 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
77211-2 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Finished | Regular | FALSE | 77211 | Regular |  | FALSE |  | 2 | 1 | 8 | 8 | BBWDILED-640-400-80-40-SO-4-W-UNV-DP-1-D | 56 | 3840 | 0 | Do Not Ship Before Feb 8th. | RichardM | George Bacalla |  |  | F2-4' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 480 | 7 | 0 | 8 | 3840 | 56 |  | 0 | 2019 | 2 | 8 | 1 | Complete | TRUE | TRUE |  | Done
78930-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Replacement | FALSE | 78930 | High Priority | PM wrong/missing info | TRUE |  | 1 | 1 | 1 | 3 | BMSLEDPAT-OPR-90-600-80-35-SO-16'5 3/4"-EX-W-UNV-DP-1-S | 5.2 | 1050 | 0 |  | IllumBos | Daljit Singh |  |  | F6-L3-1FL-A | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 350 | 1.7333 | 0 | 3 | 1050 | 5.2 |  | 1 | 2019 | 2 | 7 | 1 | Complete | FALSE | FALSE | ToDo
79125-1 | 12 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 79125 | Regular |  | FALSE |  | 1 | 1 | 2 | 2 | WBRLED-500-80-40-S-5'-AP-UNV-DP-1-DF | 12.2 | 2200 | 0 |  | SpecLSA | Zahra Vatani |  |  | D-5' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 1100 | 6.1 | 0 | 2 | 2200 | 12.2 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE |  | Done
75692-11 | 1 | 2019-01-16 |  | Wiring Started | Regular | FALSE | 75692 | High Priority | Shortage | FALSE | EN19793G-9005 | 11 | 1 | 1 | 5 | SP18435(2)-BMPRLED-OPRO(158°)-750-80-35-RG3-40'2 1/8"-C(BLK)-UNV-DP-1-DS-TS(2)-C(127° ANGLED END) | 39.35 | 3010 | 0 | Akamai 3rd Floor | IllumBos | Gagandeep Singh | Eta of parts for Line: 11 - Erin to advise. Ship balance: 2/5 Edited on 2/1/2019 ::: ETA: Feb 12th Edited on 2/5/2019 |  | F04A-26'10-11/16"X13'3-7/16"-3RD FL | Picked - Complete | 2019-01-14 | 2019-01-14 | FALSE | FALSE | NO |  |  | Wiring Issue |  | 602 | 7.87 | 0 | 5 | 3010 | 39.35 | Shortage | 1 | 2019 | 1 | 16 | 1 | Complete | TRUE | TRUE | Ready | Done
79168-1 | 12 | 2019-02-08 | 2019-02-08 | Machine Shop Started | Regular | FALSE | 79168 | Regular |  | FALSE |  | 1 | 1 | 6 | 6 | B6RLED-400-80-35-RG-4'-W-120-DP-1-D | 19.2 | 2280 | 0 |  | RichardM | George Bacalla |  |  | C-4' | Picked - Complete | 2019-02-03 | 2019-02-05 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Started |  | 380 | 3.2 | 0 | 6 | 2280 | 19.2 |  | 1 | 2019 | 2 | 8 | 1 | Complete | TRUE | FALSE
78971-1 | 12 | 2019-02-05 | 2019-02-05 | Machine Shop Finished | Mockup/Samples | FALSE | 78971 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | BMWDLED-500-80-35-SO-4'-AP-UNV-DP-1-C(CORD & PLUG) | 4.2 | 300 | 0 |  | ERW Ltg | George Bacalla | Ship: Feb 6th Edited on 2/5/2019 |  | A-4' | Picked - Complete | 2019-02-03 | 2019-01-30 | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 300 | 4.2 | 0 | 1 | 300 | 4.2 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | TRUE |  | Done
78098-1 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78098 | High Priority | PM wrong/missing info | TRUE | WRONG SD ATTACHED | 1 | 1 | 12 | 12 | TB3DILED-700-700-80-35-SL-SO-8-BLK-UNV-DP-1-CT9(36) | 111.6 | 8040 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-01-8 | Picked - Complete | 2019-01-29 |  | FALSE | TRUE | NO |  |  | Machine Shop Started |  | 670 | 9.3 | 0 | 12 | 8040 | 111.6 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-2 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78098 | High Priority | PM wrong/missing info | TRUE | WRONG SD ATTACHED | 2 | 1 | 4 | 4 | TB3DILED-700-700-80-35-SL-SO-12-BLK-UNV-DP-1-CT9(36) | 52 | 3840 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-01-12 | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 960 | 13 | 0 | 4 | 3840 | 52 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-3 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 3 | 1 | 2 | 2 | TB3DILED-700-700-80-35-SL-SO-12-BLK-UNV-DP-1+E(1)-CT9(36) | 28 | 2120 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-01-12-EM | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1060 | 14 | 0 | 2 | 2120 | 28 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-4 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 4 | 1 | 3 | 6 | TB3DILED-700-700-80-35-SL-SO-16-BLK-UNV-DP-1-CT9(36) | 54.9 | 3600 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-01-16 | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 600 | 9.15 | 0 | 6 | 3600 | 54.9 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-5 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Started | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 5 | 1 | 1 | 1 | TB3DILED-700-700-80-35-SL-SO-16-BLK-UNV-DP-1+E(1)-CT9(36) | 20 | 1300 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-01-16-EM | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 1300 | 20 | 0 | 1 | 1300 | 20 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-6 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 6 | 1 | 1 | 1 | BBPRLED-700-80-35-RG4-3-W-UNV-DP-1-DS | 5 | 270 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-3-GYP | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 270 | 5 | 0 | 1 | 270 | 5 |  | 1 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-7 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 7 | 1 | 1 | 1 | BBPRLED-700-80-35-RG4-5-W-UNV-DP-1-DS | 8.3 | 375 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-5-GYP | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 375 | 8.3 | 0 | 1 | 375 | 8.3 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-8 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 8 | 1 | 2 | 2 | BBPRLED-700-80-35-RG4-6-W-UNV-DP-1-TB9 | 9.2 | 900 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-6 | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 450 | 4.6 | 0 | 2 | 900 | 9.2 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-9 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 9 | 1 | 3 | 3 | BBPRLED-700-80-35-RG4-6-W-UNV-DP-1-DS | 24.6 | 1350 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-6-GYP | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 450 | 8.2 | 0 | 3 | 1350 | 24.6 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78098-10 | 18 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78098 | High Priority |  | FALSE |  | 10 | 1 | 1 | 1 | BBPRLED-700-80-35-RG4-8-W-UNV-DP-1-DS | 8.2 | 600 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-8-GYP | Picked - Complete | 2019-01-29 |  | FALSE | FALSE | NO |  |  | Machine Shop Finished - Incomplete |  | 600 | 8.2 | 0 | 1 | 600 | 8.2 |  | 0 | 2019 | 2 | 7 | 2 | Partial | TRUE | FALSE |  | Done
78866-1 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78866 | High Priority |  | FALSE |  | 1 | 1 | 1 | 1 | BBPRLED-700-80-35-RG4-4'-W-UNV-DP-1-TB9 | 2.5 | 356 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-4' | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 356 | 2.5 | 0 | 1 | 356 | 2.5 |  | 1 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
78866-2 | 12 | 2019-02-07 | 2019-02-07 | Machine Shop Finished | Regular | FALSE | 78866 | High Priority |  | FALSE |  | 2 | 1 | 1 | 1 | BBPRLED-700-80-35-RG4-8'-W-UNV-DP-1-DS | 8.3 | 712 | 0 | order must be on site no later than Feb 11th - McLean, VA must must must ship | Visual | Christina Torok |  |  | F-04-8'-GYP | Picked - Complete | 2019-02-03 | 2019-02-04 | FALSE | FALSE | NO | +Cartridge |  | Machine Shop Finished - Incomplete |  | 712 | 8.3 | 0 | 1 | 712 | 8.3 |  | 0 | 2019 | 2 | 7 | 1 | Complete | TRUE | FALSE
79019-1 | 12 | 2019-02-05 | 2019-02-05 | Machine Shop Started | Replacement | FALSE | 79019 | High Priority |  | FALSE |  | 1 | 1 | 1 | 1 | SCR-500-90-40-FL-TR60X4-W-277-DP-1-MFTG9 | 15 | 930 | 930 | FIXTURE GOT DAMAGE DURING TRNSPORT. | Visual | Anil Surendra Sanchara | MS: Feb 5th - Kaushik to advise Edited on 2/5/2019 |  | FR5 - REPLACE | Picked - Complete | 2019-01-28 | 2019-01-30 | FALSE | FALSE | NO |  |  | Machine Shop Started |  | 930 | 15 | 0 | 1 | 930 | 15 |  | 1 | 2019 | 2 | 5 | 1 | Complete | TRUE | FALSE
78864-1 | 12 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Replacement | FALSE | 78864 | Regular |  | FALSE |  | 1 | 1 | 1 | 1 | ZESQDI-SL 25/75-1050-80-35-SO-8-AP-UNV-MD-1-CA(96") | 9.4 | 280 | 0 |  | Smart Li | Daljit Singh | Ship:2/5 Edited on 2/1/2019 |  | C2-8'-96" |  | 2019-01-25 | 2019-01-29 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 280 | 9.4 | 0 | 1 | 280 | 9.4 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
78864-2 | 12 | 2019-02-04 | 2019-02-04 | Machine Shop Finished | Replacement | FALSE | 78864 | Regular |  | FALSE |  | 2 | 1 | 1 | 1 | ZESQDI-SL 25/75-1050-80-35-SO-4-AP-UNV-MD-1-CA(120") | 5.6 | 145 | 0 |  | Smart Li | Daljit Singh |  |  | C1-4'-96" |  | 2019-01-25 | 2019-01-29 | FALSE | FALSE | OK |  |  | Machine Shop Finished -Ready |  | 145 | 5.6 | 0 | 1 | 145 | 5.6 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
77608-1 | 12 | 2019-01-31 | 2019-01-31 | Wiring Started | Regular | FALSE | 77608 | High Priority | Others | TRUE | sub assembly | 1 | 1 | 3 | 3 | SCML-6-SO-300-SO-500-MLA(6)-500-W-80-35-W-UNV-DP-1-CA(36) | 21 | 1890 | 0 | UPS RED COVER BY AXIS | ALA | Zahra Vatani | Given to Ind. Eng., - Elizabeth to follow Edited on 2/5/2019 |  |  | Picked - Complete |  |  | FALSE | TRUE | NO | Material |  | Wiring Issue |  | 630 | 7 | 0 | 3 | 1890 | 21 |  | 1 | 2019 | 1 | 31 | 1 | Complete | TRUE | TRUE |  | Done
78386-1 | 18 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 78386 | Regular |  | FALSE |  | 1 | 1 | 3 | 3 | BDLED-1000-90-40-SO-5-W-UNV-DP-1-CA(56)-C(OVERALL LENGTH) | 22.8 | 1095 | 0 |  | KSA IA | Joshua Zimet | Kaushik to advise. Edited on 2/1/2019 |  | C5'/C5'EM |  |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 365 | 7.6 | 3 | 0 | 0 | 0 |  | 1 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
78386-2 | 18 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 78386 | Regular |  | FALSE |  | 2 | 1 | 3 | 3 | BDLED-1000-90-40-SO-6-W-UNV-DP-1-CA(56)-C(OVERALL LENGTH) | 22.8 | 1314 | 0 |  | KSA IA | Joshua Zimet | Ship: Feb 5th Edited on 2/5/2019 |  | C6'/C6'EM |  |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 438 | 7.6 | 3 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
78386-3 | 18 | 2019-02-04 | 2019-02-04 | Given to Shipping | Regular | FALSE | 78386 | Regular |  | FALSE |  | 3 | 1 | 13 | 13 | BDLED-1000-90-40-SO-4-W-UNV-DP-1-CA(56) | 62.4 | 3796 | 0 |  | KSA IA | Joshua Zimet |  |  | CP/CPEM |  |  | 2019-02-01 | FALSE | FALSE | NO |  |  | Given to Shipping |  | 292 | 4.8 | 13 | 0 | 0 | 0 |  | 0 | 2019 | 2 | 4 | 1 | Complete | TRUE | TRUE |  | Done
76021-1 | 18 | 2019-02-13 | 2019-02-13 | Machine Shop Started | Regular | FALSE | 76021 | Regular |  | FALSE |  | 1 | 1 | 10 | 10 | WBRLED-500-80-40-S-2-W-UNV-DP-1-DF-EF | 36 | 3420 | 0 |  | RLM | Jessica Pasternyk |  |  | K-2' |  |  |  | FALSE | FALSE | NO | Material+Cartridge |  | Machine Shop Started |  | 342 | 3.6 | 0 | 10 | 3420 | 36 |  | 1 | 2019 | 2 | 13 | 1 | Complete | TRUE | FALSE
72049-3 | 1 | 2019-01-29 | 2018-12-18 | Packaging Finished | Regular | FALSE | 72049 | Regular | Shortage | FALSE | LENS | 3 | 1 | 2 | 8 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(28' 1 1/4")-550-80-35-SO-C(RAL5017)-UNV-DP-1-CT15(36)-B2(BSL10LST) | 200 | 14720 | 0 |  | LtgDynam | Joshua Zimet | MS: 01/29 Edited on 1/28/2019 |  | DL |  |  |  | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 1840 | 25 | 12 | -4 | -7360 | -100 | Shortage | 1 | 2019 | 1 | 29 | 1 | Complete | TRUE | TRUE |  | Done
72049-4 | 1 | 2019-01-29 | 2018-12-18 | Packaging Finished | Regular | FALSE | 72049 | Regular | Shortage | TRUE | EXTRUSION ??? | 4 | 1 | 2 | 4 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(19' 9 1/4")-550-80-35-SO-C(RAL5017)-UNV-DP-1-CT15(36) | 42 | 10000 | 0 |  | LtgDynam | Joshua Zimet | MS: 01/30 - Ship: ? Edited on 1/29/2019 |  | DS |  |  |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 2500 | 10.5 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 1 | 29 | 1 | Complete | TRUE | TRUE |  | Done
72049-15 | 1 | 2019-01-29 | 2018-12-18 | Packaging Finished | Regular | FALSE | 72049 | Regular | Shortage | FALSE | LENS | 15 | 1 | 2 | 8 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(28' 1 1/4")-550-80-35-SO-C(RAL6017)-UNV-DP-1-CT15(36)-B2(BSL10LST) | 42 | 14720 | 0 |  | LtgDynam | Joshua Zimet | MS: - Sukhwinder to follow up Edited on 1/30/2019 Ms:2/1 Kaushik to advise. Edited on 1/31/2019 - Ms: 2/3 - Kaushik to advise. Edited on 2/1/2019 |  | DL |  |  |  | FALSE | FALSE | NO | Material |  | Packaging Finished |  | 1840 | 5.25 | 12 | -4 | -7360 | -21 | Shortage | 0 | 2019 | 1 | 29 | 1 | Complete | TRUE | TRUE |  | Done
72049-16 | 1 | 2019-01-29 | 2018-12-18 | Packaging Finished | Regular | FALSE | 72049 | Regular |  | FALSE |  | 16 | 1 | 2 | 4 | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(19' 9 1/4")-550-80-35-SO-C(RAL6017)-UNV-DP-1-CT15(36) | 42 | 10000 | 0 |  | LtgDynam | Joshua Zimet | Ship: Feb 6th Edited on 2/5/2019 |  | DS |  |  |  | FALSE | FALSE | NO |  |  | Packaging Finished |  | 2500 | 10.5 | 4 | 0 | 0 | 0 |  | 0 | 2019 | 1 | 29 | 1 | Complete | TRUE | TRUE |  | Done
78624-4 | 10 | 2019-02-08 | 2019-03-05 | Scheduled/Released | Regular | FALSE | 78624 | Regular |  | FALSE |  | 4 | 1 | 25 | 25 | SKFLED-22-2000-80-30-2SF-W-UNV-DP-1-DF | 669 | 8625 | 0 |  | Lightin1 | Rajithan Sivapatharajahon |  |  | F4 |  |  |  | FALSE | FALSE | NO | Material |  | Scheduled/Released |  | 345 | 26.76 | 0 | 25 | 8625 | 669 |  | 1 | 2019 | 2 | 8 | 1 | Complete | FALSE | FALSE
78588-1 | 12 | 2019-02-13 | 2019-02-13 | Scheduled/Released | Regular | FALSE | 78588 | High Priority |  | FALSE |  | 1 | 1 | 1 | 4 | SCIPAT-REC-90(4)-500-80-30-SO-26-NL-C(RAL6022)-UNV-DP-1-CA(48) | 18.5 | 2820 | 0 | Rockefeller | Internat | Gagandeep Singh |  |  | ELEV LOBBY-6'X12' NORTH | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO |  |  | Scheduled/Released |  | 705 | 4.625 | 0 | 4 | 2820 | 18.5 |  | 1 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
78588-2 | 12 | 2019-02-13 | 2019-02-13 | Scheduled/Released | Regular | FALSE | 78588 | High Priority |  | FALSE |  | 2 | 1 | 1 | 4 | SCIPAT-REC-90(4)-500-80-30-SO-26-NL-C(RAL6022)-UNV-DP-1-CA(48) | 18.5 | 2820 | 0 | Rockefeller | Internat | Gagandeep Singh |  |  | ELEV LOBBY-6'X12' SOUTH | Picked - Complete | 2019-02-05 |  | FALSE | FALSE | NO |  |  | Scheduled/Released |  | 705 | 4.625 | 0 | 4 | 2820 | 18.5 |  | 0 | 2019 | 2 | 13 | 1 | Complete | FALSE | FALSE
Formulas:
Schedule Date = IFNA(VLOOKUP(Table9[[#This Row],[order-line]],Table6[],2,FALSE),"")

## Order Material
Job No. | Order | PartNum | Line | Rel | Sched Date Priority | Scheduled Ship Date | Sections | Assembly Line | Status | Non Conformance Reason | Issue Solved | DWG vs BOM | Materials | Housing | Lens | Cartridges | Programmable Drivers | Axis Label | Power Cord | Material Kit (Machine Shop) | Ready to Bring to ass'y | Delivered Date (MS) | Cartridge Location | CartridgesDate | LED Staging | CNC Cartridge | SAW Cartridge | MC Status | Material | Cartridge | Reason | open Value
58763-1 | 58763 | PRMLED-S | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 15 | Machine Shop Started | Shortage | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
59584-10 | 59584 | SCULPT-61'11" | 10 | 1 | High Priority | 2019-02-06 | 1900-01-06 | 1 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #1 | 2019-02-04 | 2w1-b |  |  | NO | Material |  | Material
59584-12 | 59584 | SCULPT-226'3/8" | 12 | 1 | High Priority | 2019-02-06 | 1900-01-20 | 1 | Machine Shop Started | Missing parts in BOM | TRUE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #1 | 2019-02-04 | 2w1-b |  |  | NO | Material |  | Material
59584-66 | 59584 | SCULPT-35'5" | 66 | 1 | High Priority | 2019-02-06 | 1900-01-04 | 1 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #1 | 2019-02-04 | 2w1-b |  |  | NO | Material |  | Material
59584-67 | 59584 | SCULPT-211'11 1/4 | 67 | 1 | High Priority | 2019-02-06 | 1900-01-21 | 1 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #3 | 2019-02-04 | 2w1-b |  |  | NO | Material |  | Material
63435-2 | 63435 | SCULPT-K(4X2) | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
63435-7 | 63435 | SCULPT-K(4X2) | 7 | 1 | Regular | 2019-02-21 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
64752-10 | 64752 | B3LED-30 | 10 | 1 | Regular | 2019-02-05 | 1900-01-02 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 | 51 | 2019-01-31 | 2s3-b |  |  | NO
64752-11 | 64752 | B3LED-36 | 11 | 1 | Regular | 2019-02-05 | 1900-01-02 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 | 51 | 2019-01-31 | 2s3-b |  |  | NO
64752-12 | 64752 | B3LED-46 | 12 | 1 | Regular | 2019-02-05 | 1900-01-03 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 | 29 | 2019-01-31 | 2s3-b |  |  | NO
64752-13 | 64752 | B3LED-60 | 13 | 1 | Regular | 2019-02-05 | 1900-01-04 | 24:00 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:39 | 29 | 2019-01-31 | 2s3-b |  |  | NO
64752-14 | 64752 | B3LED-6 | 14 | 1 | Regular | 2019-02-05 | 1899-12-31 | 24:00 | Wiring Started | Shortage | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 09:33 | 29 | 2019-01-31 | 2s3-b |  |  | NO | Material |  | Material
64752-15 | 64752 | B3LED-8 | 15 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started | Wrong info. In SD | TRUE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:39 | 3 | 2019-01-31 | 2s3-b |  |  | NO
64752-16 | 64752 | B3LED-10 | 16 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 | 3 | 2019-01-31 | 2s3-b |  |  | NO
64752-17 | 64752 | B3LED-14 | 17 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 | 3 | 2019-01-31 | 2s3-b |  |  | NO
64752-18 | 64752 | B3LED-16 | 18 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 | 3 | 2019-01-31 | 2s3-b |  |  | NO
64752-19 | 64752 | B3LED-18 | 19 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 |  | 2019-01-31 | 2s3-b |  |  | NO
64752-20 | 64752 | B3LED-20 | 20 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 |  | 2019-01-31 | 2s3-b |  |  | NO
64752-22 | 64752 | PRMLED-10 | 22 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started | Wrong part in BOM | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 11:39 | 38 | 2019-01-27 | 2w1-b |  |  | NO
64752-23 | 64752 | PRMLED-16 | 23 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Machine Shop Finished | Shortage | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 11:39 | 38 | 2019-01-27 | 2w1-b |  |  | NO
64752-24 | 64752 | PRMLED-28 | 24 | 1 | Regular | 2019-02-05 | 1900-01-03 | 1 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 11:39 | 38 | 2019-01-27 | 2w1-b |  |  | NO
64752-25 | 64752 | DIALED-22 | 25 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
64752-26 | 64752 | DIALED-24 | 26 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
64752-30 | 64752 | B4LED-5 | 30 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started | Others | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 11:40 | 38 | 2019-01-27 | 2w1-b |  |  | NO
64752-31 | 64752 | B3LED-6 | 31 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 |  | 2019-01-31 | 2s3-b |  |  | NO
64752-32 | 64752 | DIALED-24 | 32 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
64752-33 | 64752 | DIALED-24 | 33 | 1 | Regular | 2019-02-15 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
64752-37 | 64752 | B3LED-4 | 37 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 11:40 |  | 2019-01-31 | 2s3-b |  |  | NO
64752-38 | 64752 | DIALED-22 | 38 | 1 | Regular | 2019-02-15 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
64752-39 | 64752 | DIALED-22 | 39 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
64752-40 | 64752 | B3LED-6 | 40 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 09:33 |  | 2019-01-31 | 2s3-b |  |  | NO
64752-8 | 64752 | B3LED-16 | 8 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 51 | 2019-01-31 | 2s3-b |  |  | NO
64752-9 | 64752 | B3LED-20 | 9 | 1 | Regular | 2019-02-15 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done |  | Done |  |  | NA | FALSE | FALSE |  | 51 | 2019-01-31 |  |  |  | NO
66961-1 | 66961 | B4LED-42' 1/2" | 1 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | Yes | FALSE | FALSE | [6 empty] | NO | Material |  | Material
66961-2 | 66961 | B4LED-350' 1/4" | 2 | 1 | Regular | 2019-02-18 | 1900-02-02 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
66961-3 | 66961 | B4LED-40' | 3 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | Yes | FALSE | FALSE | [6 empty] | NO | Material |  | Material
66961-4 | 66961 | B4LED-39' 11 3/4" | 4 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | Yes | FALSE | FALSE | [6 empty] | NO | Material |  | Material
66961-5 | 66961 | B4LED-40' 10 3/4" | 5 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
67150-41 | 67150 | B6LED-15 | 41 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-42 | 67150 | B6LED-15 | 42 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-43 | 67150 | B6LED-10 | 43 | 24:00 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-44 | 67150 | B6LED-15 | 44 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-45 | 67150 | B6LED-5 | 45 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-46 | 67150 | B6LED-10 | 46 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-47 | 67150 | B6LED-15 | 47 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-48 | 67150 | B6LED-5 | 48 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-49 | 67150 | B6LED-10 | 49 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-50 | 67150 | B6LED-15 | 50 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-51 | 67150 | B6LED-5 | 51 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-52 | 67150 | B6LED-10 | 52 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-53 | 67150 | B6LED-15 | 53 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-55 | 67150 | B6LED-4 | 55 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-56 | 67150 | B6LED-5 | 56 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-57 | 67150 | B6LED-10 | 57 | 1 | Regular | 2019-02-11 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-58 | 67150 | B2LED-14 | 58 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-59 | 67150 | B2LED-18 | 59 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-60 | 67150 | B2LED-17 | 60 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67150-61 | 67150 | B2LED-18 | 61 | 1 | Regular | 2019-02-11 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
67875-1 | 67875 | CCL | 1 | 1 | Regular | 2019-02-11 | 1900-01-13 | 12 | Machine Shop Started |  | FALSE | Yes |  | Done |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
69215-1 | 69215 | SKETCH-AL(15'8 1/2") | 1 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69215-2 | 69215 | SKETCH-AL(23'6 3/4") | 2 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69215-3 | 69215 | SCULPT-20 | 3 | 1 | Regular | 2019-02-14 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69215-4 | 69215 | SCULPT-28 | 4 | 1 | Regular | 2019-02-14 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69215-5 | 69215 | SCULPT-48 | 5 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69215-6 | 69215 | SCULPT-48 | 6 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69215-7 | 69215 | SCULPT-70 | 7 | 1 | Regular | 2019-02-14 | 1900-01-05 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
69363-1 | 69363 | STENCL-STFC | 1 | 1 | Regular | 2019-02-18 | 1900-02-14 | 7 | Machine Shop Started | Shortage | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69773-1 | 69773 | B3LED-4 | 1 | 1 | High Priority | 2019-02-14 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69773-2 | 69773 | B3LED-8 | 2 | 1 | High Priority | 2019-02-14 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-10 | 69828 | SCULPT-32' | 10 | 1 | Regular | 2019-03-04 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-1 | 69828 | B4LED-8' | 1 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-11 | 69828 | B6LED-4' | 11 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-12 | 69828 | B6LED-36' | 12 | 1 | Regular | 2019-03-04 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-13 | 69828 | B6LED-48' | 13 | 24:00 | Regular | 2019-03-04 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-14 | 69828 | B3LED-8' | 14 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-15 | 69828 | SCULPT-7' | 15 | 24:00 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-16 | 69828 | SCULPT-12'6" | 16 | 1 | Regular | 2019-03-04 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-17 | 69828 | SCULPT-14'6" | 17 | 1 | Regular | 2019-03-04 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-18 | 69828 | SCULPT-31'6" | 18 | 1 | Regular | 2019-03-04 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-2 | 69828 | SCULPT-8' | 2 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-3 | 69828 | B6LED-8 | 3 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-4 | 69828 | SCULPT-12' | 4 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-5 | 69828 | SCULPT-11' | 5 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-6 | 69828 | SCULPT-3' | 6 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-7 | 69828 | SCULPT-4' | 7 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-8 | 69828 | SCULPT-6' | 8 | 24:00 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69828-9 | 69828 | SCULPT-8' | 9 | 1 | Regular | 2019-03-04 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69855-1 | 69855 | SLMLED-33 | 1 | 1 | Regular | 2019-02-25 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
69855-2 | 69855 | SLMLED-32 | 2 | 1 | Regular | 2019-02-25 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
69855-5 | 69855 | SLMLED-21 | 5 | 1 | Regular | 2019-02-25 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
69855-6 | 69855 | SLMLED-36 | 6 | 1 | Regular | 2019-02-25 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
69953-1 | 69953 | WDILED-5' | 1 | 1 | Regular | 2019-03-06 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69953-2 | 69953 | WDILED-5' | 2 | 1 | Regular | 2019-03-06 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69953-8 | 69953 | WDILED-5' | 8 | 1 | Regular | 2019-03-06 | 1899-12-31 | 12 | Scheduled/Released | PM wrong/missing info | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69953-9 | 69953 | WDILED-5' | 9 | 1 | Regular | 2019-03-06 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
69983-15 | 69983 | PERFKT-CCH | 15 | 1 | Regular | 2019-02-21 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
69983-29 | 69983 | PERFKT-CCH | 29 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
69983-35 | 69983 | PERFKT-CCH | 35 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
70162-1 | 70162 | AULED-24 | 1 | 1 | Regular | 2019-02-14 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
70162-7 | 70162 | B4LED-8' | 7 | 1 | Regular | 2019-02-14 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | [7 empty] | Yes | TRUE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-10 | 70328 | B3LED-1'8" | 10 | 1 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-11 | 70328 | B3LED-35 5/32" | 11 | 1 | Priority | 2019-02-19 | 1899-12-31 | 288:00 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-12 | 70328 | B3LED-2'6 11/32" | 12 | 24:00 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-13 | 70328 | B3LED-2'6 11/32" | 13 | 24:00 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-6 | 70328 | B3LED-11'2 5/8" | 6 | 1 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started | PM wrong/missing info | TRUE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-7 | 70328 | B3LED-1'8" | 7 | 1 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-8 | 70328 | B3LED-35 5/32" | 8 | 1 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70328-9 | 70328 | B3LED-11'2 5/8" | 9 | 1 | Priority | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
70411-2 | 70411 | SCULPT-4' | 2 | 3 | Regular | 2019-03-08 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
70411-2 | 70411 | SCULPT-4' | 2 | 4 | Regular | 2019-03-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE |  |  | 2019-01-08 |  |  |  | NO | Material |  | Material
70411-33 | 70411 | SCULPT-4 | 33 | 2 | Regular | 2019-02-22 | 1899-12-31 | 168:00 | Machine Shop Started |  | FALSE |  | Yes | Done |  |  |  | Yes | NA | FALSE | FALSE |  |  | 2018-12-31 | ASK TEJA(I.E) BEFORE PRINT |  |  | NO |  | +Cartridge | +Cartridge
70411-33 | 70411 | SCULPT-4 | 33 | 3 | Regular | 2019-03-01 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | ASK TEJA(I.E) BEFORE PRINT |  |  | NO | Material | +Cartridge | Material+Cartridge
70411-37 | 70411 | SCULPT-3 | 37 | 2 | Regular | 2019-02-08 | 1899-12-31 | 7 | Wiring Started | Others | TRUE | Yes | Yes | Done | Done | Yes |  | Yes | NA | TRUE | FALSE | 2019-02-04 17:03 |  | 2019-01-02 | 2s2-a |  |  | OK
70411-5 | 70411 | SCULPT-3' | 5 | 2 | Regular | 2019-02-15 | 1899-12-31 | 168:00 | Machine Shop Started | Wrong info. In SD | FALSE |  | Yes | Done |  | Done | Yes |  | NA | FALSE | FALSE |  |  | 2019-01-07 | 2w1-a |  |  | NO
70428-1 | 70428 | SKLPTP-5' 2" | 1 | 1 | Regular | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-2 | 70428 | SKLPTP-5'11 1/2" | 2 | 1 | Regular | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-3 | 70428 | SKLPTP-9' 1/4" | 3 | 1 | Regular | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-4 | 70428 | SKLPTP-17'5 3/4" | 4 | 1 | Regular | 2019-02-19 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-5 | 70428 | SKLPTP-9'1 3/4" | 5 | 1 | Regular | 2019-02-19 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-6 | 70428 | SKLPTP-13' 3/4" | 6 | 1 | Regular | 2019-02-19 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-7 | 70428 | SKLPTP-18' 2" | 7 | 1 | Regular | 2019-02-19 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70428-9 | 70428 | SKLPTP-13' 9" | 9 | 1 | Regular | 2019-02-19 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
70634-1 | 70634 | PERFKT-CCH | 1 | 1 | High Priority | 2019-02-01 | 1900-01-19 | 4 | Machine Shop Finished |  | TRUE | Yes | Yes | Done | Done | NA | Yes | Yes | NA | TRUE | TRUE | 2019-02-01 14:52 |  | 2019-01-25 | 2t1-b |  |  | OK
70634-2 | 70634 | PERFKT-CCH | 2 | 1 | High Priority | 2019-02-01 | 1900-01-27 | 4 | Machine Shop Finished | Wrong part in BOM | TRUE | Yes | Yes | Done | Done | NA | Yes | Yes | NA | TRUE | TRUE | 2019-02-01 14:52 |  | 2019-01-25 | 2t1-b |  |  | OK
70634-3 | 70634 | PERFKT-CCH | 3 | 1 | High Priority | 2019-02-01 | 1900-01-20 | 4 | Machine Shop Finished | Wrong part in BOM | TRUE | Yes | Yes | Done | Done | NA | Yes | Yes | NA | TRUE | TRUE | 2019-02-01 14:52 |  | 2019-01-25 | 2t1-b |  |  | OK
70634-4 | 70634 | PERFKT-CCH | 4 | 1 | High Priority | 2019-02-01 | 1900-01-27 | 4 | Machine Shop Finished | Wrong info. In SD | TRUE | Yes | Yes | Done | Done | NA | Yes | Yes | NA | TRUE | TRUE | 2019-02-01 14:52 |  | 2019-01-25 | 2t1-b |  |  | OK
70875-1 | 70875 | STFD | 1 | 1 | Regular | 2019-02-11 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-10 | 71700 | B6LED-28 | 10 | 1 | Regular | 2019-02-21 | 1900-01-02 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-1 | 71700 | B3LED-28 | 1 | 1 | Regular | 2019-02-21 | 1900-01-02 | 15 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-11 | 71700 | B6LED-12 | 11 | 1 | Regular | 2019-02-21 | 1899-12-31 | 360:00 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-12 | 71700 | B6LED-12 | 12 | 1 | Regular | 2019-02-21 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-13 | 71700 | B6LED-20 | 13 | 1 | Regular | 2019-02-21 | 1900-01-01 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-14 | 71700 | B6LED-20 | 14 | 1 | Regular | 2019-02-21 | 1900-01-01 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-2 | 71700 | B6LED-4 | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-3 | 71700 | B6LED-16 | 3 | 24:00 | Regular | 2019-02-21 | 1900-01-01 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-4 | 71700 | B6LED-20 | 4 | 1 | Regular | 2019-02-21 | 1900-01-01 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-5 | 71700 | B6LED-28 | 5 | 1 | Regular | 2019-02-21 | 1900-01-02 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-6 | 71700 | B6LED-16 | 6 | 1 | Regular | 2019-02-21 | 1900-01-01 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71700-9 | 71700 | B3LED-28 | 9 | 24:00 | Regular | 2019-02-21 | 1900-01-02 | 15 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-10 | 71803 | ZEN-8 | 10 | 24:00 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
71803-1 | 71803 | B3LED-7 | 1 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-11 | 71803 | STFI | 11 | 1 | Regular | 2019-03-04 | 1900-01-04 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-12 | 71803 | STFI | 12 | 24:00 | Regular | 2019-03-04 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-14 | 71803 | WB4LED-8' | 14 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-15 | 71803 | WB4LED-6' | 15 | 1 | Regular | 2019-03-04 | 1900-01-02 | 96:00 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-16 | 71803 | WB4LED-30' | 16 | 1 | Regular | 2019-03-04 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-17 | 71803 | WB4LED-20' | 17 | 1 | Regular | 2019-03-04 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-18 | 71803 | WB4LED-10' | 18 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-2 | 71803 | B3LED-8 | 2 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-3 | 71803 | B4LED-5 | 3 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-4 | 71803 | B3LED-5 | 4 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-5 | 71803 | B3LED-10 | 5 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-6 | 71803 | B3LED-12 | 6 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-7 | 71803 | B4LED-4 | 7 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-8 | 71803 | B3LED-8 | 8 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
71803-9 | 71803 | B3LED-4 | 9 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72049-15 | 72049 | SKETCH-AL(28' 1 1/4") | 15 | 1 | Regular | 2019-01-29 | 1900-01-03 | 1 | Packaging Finished | Shortage | FALSE | Yes |  | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | #2 | 2018-12-19 |  |  |  | NO | Material |  | Material
72049-16 | 72049 | SKETCH-AL(19' 9 1/4") | 16 | 1 | Regular | 2019-01-29 | 1900-01-01 | 1 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 12:37 | #2 | 2018-12-19 |  |  | ToDo | NO
72049-3 | 72049 | SKETCH-AL(28' 1 1/4") | 3 | 1 | Regular | 2019-01-29 | 1900-01-03 | 1 | Packaging Finished | Shortage | FALSE | Yes |  | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | #2 | 2018-12-19 |  |  |  | NO | Material |  | Material
72049-4 | 72049 | SKETCH-AL(19' 9 1/4") | 4 | 1 | Regular | 2019-01-29 | 1900-01-01 | 1 | Packaging Finished | Shortage | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 12:37 | #2 | 2018-12-19 |  |  | ToDo | NO
72070-1 | 72070 | B4LED-ASO | 1 | 1 | High Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72070-2 | 72070 | B4LED-ASO | 2 | 1 | High Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72070-3 | 72070 | B4LED-ASO | 3 | 1 | High Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72070-6 | 72070 | B4LED-ASO | 6 | 1 | High Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-1 | 72089 | SCULPT-K(3X3) | 1 | 1 | Regular | 2019-04-03 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-2 | 72089 | AULED-22 | 2 | 1 | Regular | 2019-04-03 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
72089-3 | 72089 | SCULPT-20 | 3 | 24:00 | Regular | 2019-04-03 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-4 | 72089 | SCULPT-22 | 4 | 1 | Regular | 2019-04-03 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-5 | 72089 | SCULPT-24 | 5 | 1 | Regular | 2019-04-03 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-6 | 72089 | SCULPT-25 | 6 | 1 | Regular | 2019-04-03 | 1900-01-02 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-7 | 72089 | SCULPT-26 | 7 | 24:00 | Regular | 2019-04-03 | 1900-01-02 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72089-8 | 72089 | SCULPT-30 | 8 | 1 | Regular | 2019-04-03 | 1900-01-02 | 360:00 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72101-1 | 72101 | STENCL-STFD | 1 | 1 | Regular | 2019-02-13 | 1900-01-05 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72221-1 | 72221 | B2LED-4 | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE |  | 5 | 2019-02-04 | 2W1-A |  |  | NO | Material |  | Material
72221-2 | 72221 | B2LED-6 | 2 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE |  | 5 | 2019-02-04 | 2W1-A |  |  | NO | Material |  | Material
72221-3 | 72221 | B2LED-8 | 3 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE |  | 5 | 2019-02-04 | 2W1-A |  |  | NO | Material |  | Material
72221-4 | 72221 | B2LED-8 | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 168:00 | Machine Shop Finished |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE |  | 5 | 2019-02-04 | 2W1-A |  |  | NO | Material |  | Material
72722-10 | 72722 | STENCL-STFD | 10 | 24:00 | Regular | 2019-02-15 | 1900-01-13 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-1 | 72722 | AIRLED-2 | 1 | 24:00 | Regular | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-11 | 72722 | STENCL-STFD | 11 | 1 | Regular | 2019-02-15 | 1900-01-13 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-2 | 72722 | AIRLED-4 | 2 | 1 | Regular | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-3 | 72722 | AIRLED-8 | 3 | 1 | Regular | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-4 | 72722 | B4LED-8 | 4 | 1 | Regular | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-5 | 72722 | STFD | 5 | 1 | Regular | 2019-02-15 | 1900-01-03 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-6 | 72722 | STENCL-STFD | 6 | 1 | Regular | 2019-02-15 | 1900-01-12 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-7 | 72722 | STENCL-STFD | 7 | 1 | Regular | 2019-02-15 | 1900-01-13 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-8 | 72722 | STENCL-STFD | 8 | 24:00 | Regular | 2019-02-15 | 1900-02-27 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72722-9 | 72722 | AIRLED-4 | 9 | 24:00 | Regular | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72844-1 | 72844 | B4LED-6 | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Given to Shipping |  | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE |  | 9 | 2019-02-03 | 2w1-b |  |  | NO | Material |  | Material
72891-1 | 72891 | WB4LED-5 | 1 | 1 | Regular | 2019-03-07 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72891-2 | 72891 | WB4LED-2 | 2 | 1 | Regular | 2019-03-07 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72891-3 | 72891 | MINLED-4 | 3 | 1 | Regular | 2019-03-07 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72891-4 | 72891 | MINLED-8 | 4 | 1 | Regular | 2019-03-07 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
72906-2 | 72906 | B2LED-4 | 2 | 1 | Regular | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 07:58 | 30 | 2019-02-01 | 2T1-B |  |  | NO
72906-3 | 72906 | B2LED-10 | 3 | 1 | Regular | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 07:58 | 30 | 2019-02-01 | 2T1-B |  |  | NO
72906-4 | 72906 | B2LED-6 | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 07:58 | 30 | 2019-02-01 | 2T1-B |  |  | NO
72906-5 | 72906 | B2SLED-50 | 5 | 1 | Regular | 2019-02-07 | 1900-01-04 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 07:58 |  | 2019-02-01 | 2T1-B |  |  | NO
72906-6 | 72906 | B2SLED-22 | 6 | 1 | Regular | 2019-02-07 | 1900-01-01 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 07:58 |  | 2019-02-01 | 2T1-B |  |  | NO
72906-7 | 72906 | B2SLED-21 | 7 | 1 | Regular | 2019-02-07 | 1900-01-01 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 07:58 |  | 2019-02-01 | 2T1-B |  |  | NO
72906-8 | 72906 | B2SLED-20 | 8 | 1 | Regular | 2019-02-07 | 1900-01-01 | 18 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 07:58 |  | 2019-02-01 | 2T1-B |  |  | NO
73065-1 | 73065 | BEAM4-2 | 1 | 1 | Regular | 2019-03-01 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73065-2 | 73065 | BEAM4-4 | 2 | 1 | Regular | 2019-03-01 | 1899-12-31 | 15 | Scheduled/Released | Wrong info. In SD | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-10 | 73251 | B3PLED-22'9 7/8" | 10 | 1 | High Priority | 2019-02-19 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-1 | 73251 | B3PLED-4'5" | 1 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-11 | 73251 | B3PLED-36'11 3/4" | 11 | 1 | High Priority | 2019-02-19 | 1900-01-04 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-15 | 73251 | SKLPTP-28' 3/4" | 15 | 1 | High Priority | 2019-02-19 | 1900-01-04 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-16 | 73251 | SKLPTP-32'8" | 16 | 1 | High Priority | 2019-02-19 | 1900-01-04 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-17 | 73251 | B3PLED-3'7" | 17 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-18 | 73251 | B3LED-111'8" | 18 | 1 | High Priority | 2019-02-19 | 1900-01-09 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-19 | 73251 | B3PLED-25'10" | 19 | 1 | High Priority | 2019-02-19 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-20 | 73251 | B3LED-2 | 20 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-2 | 73251 | B3PLED-8'2 5/8" | 2 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-21 | 73251 | B3LED-56" | 21 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-22 | 73251 | B3PLED-37'1" | 22 | 1 | High Priority | 2019-02-19 | 1900-01-04 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-23 | 73251 | B3PLED-40'7 3/4" | 23 | 1 | High Priority | 2019-02-19 | 1900-01-04 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-27 | 73251 | B3LED-27'1 1/4" | 27 | 1 | High Priority | 2019-02-19 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-28 | 73251 | B3LED-83'7 1/8" | 28 | 1 | High Priority | 2019-02-07 | 1900-01-06 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-29 | 73251 | B3LED-97" | 29 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-30 | 73251 | B3LED-2 | 30 | 24:00 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-31 | 73251 | B3LED-57 1/2" | 31 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-32 | 73251 | B3PLED-32'3 7/8" | 32 | 24:00 | High Priority | 2019-02-07 | 1900-01-03 | 7 | Machine Shop Started | Shortage | FALSE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 | 2w1-a |  |  | NO
73251-33 | 73251 | B3PLED-42'1/4" | 33 | 1 | High Priority | 2019-02-07 | 1900-01-03 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 | 2w1-a |  |  | NO
73251-36 | 73251 | B3LED-13'5 5/8" | 36 | 1 | High Priority | 2019-02-07 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-37 | 73251 | B3LED-31'1" | 37 | 1 | High Priority | 2019-02-07 | 1900-01-03 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-38 | 73251 | SKLPTP-28'1 1/4" | 38 | 1 | High Priority | 2019-02-19 | 1900-01-04 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-39 | 73251 | B3PLED-34'9" | 39 | 1 | High Priority | 2019-02-19 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73251-40 | 73251 | B3LED-23'1 5/8" | 40 | 1 | High Priority | 2019-02-19 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-4 | 73251 | B3LED-28'8 1/2" | 4 | 1 | High Priority | 2019-02-19 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-41 | 73251 | B3LED-96 3/4" | 41 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-42 | 73251 | B3LED-57 3/4" | 42 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO |  | +Cartridge | +Cartridge
73251-43 | 73251 | B3PLED-28'7 1/4" | 43 | 1 | High Priority | 2019-02-07 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 | 2w1-a |  |  | NO
73251-5 | 73251 | B3LED-73'2 7/8" | 5 | 1 | High Priority | 2019-02-19 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-6 | 73251 | B3LED-95'6" | 6 | 1 | High Priority | 2019-02-19 | 1900-01-07 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-7 | 73251 | B3LED-2 | 7 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73251-9 | 73251 | B3LED-4 | 9 | 1 | High Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-20 | 73699 | B2SLED-30 | 20 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-21 | 73699 | B2SLED-35 | 21 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-22 | 73699 | B4LED-3 | 22 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started | Shortage | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-28 | 73699 | TB2LED-49' 1 1/2" | 28 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-29 | 73699 | TB2LED-32' 10 1/4" | 29 | 1 | Regular | 2019-02-18 | 1900-01-06 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-30 | 73699 | TB2LED-53' 5 1/2" | 30 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-31 | 73699 | TB2LED-38' 5 1/4" | 31 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-32 | 73699 | TB2LED-42' 4 5/8" | 32 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-33 | 73699 | TB2LED-41' 2 1/4" | 33 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-34 | 73699 | TB2LED-34' 4 1/8" | 34 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-35 | 73699 | TB2LED-28' 1 1/2" | 35 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73699-36 | 73699 | TB2LED-28' 10 7/8" | 36 | 1 | Regular | 2019-02-18 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73799-10 | 73799 | SCULPT-8 | 10 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-1 | 73799 | WALED-11 | 1 | 1 | Regular | 2019-02-20 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73799-11 | 73799 | SCULPT-4 | 11 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-12 | 73799 | SCULPT-4 | 12 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-13 | 73799 | SCULPT-3 | 13 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-14 | 73799 | SCULPT-8' | 14 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-15 | 73799 | SCULPT-8' | 15 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-16 | 73799 | SCULPT-8' | 16 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-17 | 73799 | SCULPT-4 | 17 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-18 | 73799 | SCULPT-4 | 18 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-19 | 73799 | B3SLED-4' | 19 | 1 | Regular | 2019-02-14 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73799-20 | 73799 | B3LED-168' | 20 | 1 | Regular | 2019-02-14 | 1900-01-13 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73799-2 | 73799 | WALED-14 | 2 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73799-21 | 73799 | B3LED-132' | 21 | 1 | Regular | 2019-02-14 | 1900-01-10 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73799-22 | 73799 | B3LED-148' | 22 | 1 | Regular | 2019-02-14 | 1900-01-12 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
73799-3 | 73799 | WALED-14 | 3 | 1 | Regular | 2019-02-20 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
73799-4 | 73799 | SCULPT-4 | 4 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-5 | 73799 | SCULPT-4 | 5 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-6 | 73799 | SCULPT-8 | 6 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started | Wrong info. In SD | TRUE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-7 | 73799 | SCULPT-8 | 7 | 1 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started | Wrong info. In SD | TRUE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-8 | 73799 | SCULPT-8 | 8 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started | Wrong info. In SD | TRUE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73799-9 | 73799 | SCULPT-2 | 9 | 24:00 | Regular | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
73827-1 | 73827 | B3LED-4 | 1 | 1 | Regular | 2019-03-11 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done |  |  |  | NA | TRUE | FALSE |  |  |  | 2W1-B |  |  | NO |  | +Cartridge | +Cartridge
73829-1 | 73829 | CUBLED-36 | 1 | 1 | High Priority | 2019-02-06 | 1900-01-02 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:59 | 44 | 2019-01-31 |  |  |  | NO
73829-2 | 73829 | CUBLED-28 | 2 | 1 | High Priority | 2019-02-06 | 1900-01-02 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:59 | 44 | 2019-01-31 |  |  |  | NO
73829-3 | 73829 | CUBLED-24 | 3 | 1 | High Priority | 2019-02-06 | 1900-01-01 | 7 | Wiring Started | Others | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE | 2019-02-05 14:49 | 1 | 2019-01-31 |  |  |  | NO
73829-4 | 73829 | SCULPT-216 | 4 | 24:00 | High Priority | 2019-02-06 | 1900-01-01 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 07:59 | #5 | 2019-01-30 |  |  |  | NO
73829-5 | 73829 | B6LED-36 | 5 | 24:00 | High Priority | 2019-02-06 | 1900-01-02 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 07:59 | 1 | 2019-01-31 |  |  |  | NO
73829-6 | 73829 | B4LED-8 | 6 | 24:00 | High Priority | 2019-02-06 | 1899-12-31 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 07:59 | 1 | 2019-01-31 |  |  |  | NO
73829-7 | 73829 | B3LED-12 | 7 | 1 | High Priority | 2019-02-06 | 1899-12-31 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 07:59 | 15 | 2019-01-31 |  |  |  | NO
73829-8 | 73829 | TB2LED-10 | 8 | 1 | High Priority | 2019-02-06 | 1899-12-31 | 7 | Wiring Started | Wrong part in BOM | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:59 | 15 | 2019-01-31 |  |  |  | NO
73887-10 | 73887 | B3LED-20 | 10 | 1 | Regular | 2019-02-05 | 1900-01-01 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-1 | 73887 | B3LED-4 | 1 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 08:23 | 6 | 2019-01-28 | 2t1-b |  |  | NO
73887-11 | 73887 | B3LED-6 | 11 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-12 | 73887 | B3LED-4 | 12 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 08:24 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-13 | 73887 | B3LED-8 | 13 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 08:24 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-15 | 73887 | STENCL-STFD | 15 | 1 | Regular | 2019-02-05 | 1900-01-06 | 18 | Machine Shop Finished | Others | TRUE |  | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-02-01 08:24 |  |  | 2t1-b |  |  | NO |  | +Cartridge | +Cartridge
73887-16 | 73887 | B3LED-4 | 16 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:24 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-18 | 73887 | B3LED-8 | 18 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:24 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-19 | 73887 | B3LED-8 | 19 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-20 | 73887 | B3LED-12 | 20 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-21 | 73887 | B3LED-4 | 21 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:24 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-23 | 73887 | B3LED-6 | 23 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:24 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-24 | 73887 | B3LED-6 | 24 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-26 | 73887 | B3LED-8 | 26 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 |  | 2019-01-28 | 2t1-b |  |  | NO
73887-3 | 73887 | B3LED-4 | 3 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-29 13:49 | 6 | 2019-01-28 | 2t1-b |  |  | NO
73887-4 | 73887 | B3LED-8 | 4 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 6 | 2019-01-28 | 2t1-b |  |  | NO
73887-5 | 73887 | B3LED-16 | 5 | 1 | Regular | 2019-02-05 | 1900-01-01 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 6 | 2019-01-28 | 2t1-b |  |  | NO
73887-6 | 73887 | B3LED-12 | 6 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 36 | 2019-01-28 | 2t1-b |  |  | NO
73887-7 | 73887 | B3LED-4 | 7 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished | Others | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-29 13:50 | 36 | 2019-01-28 | 2t1-b |  |  | NO
73887-8 | 73887 | B3LED-12 | 8 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 36 | 2019-01-28 | 2t1-b |  |  | NO
73887-9 | 73887 | B3LED-16 | 9 | 1 | Regular | 2019-02-05 | 1900-01-01 | 18 | Packaging Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 36 | 2019-01-28 | 2t1-b |  |  | NO
74123-1 | 74123 | MINI-3 | 1 | 1 | High Priority | 2019-03-07 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74123-1 | 74123 | MINI-3 | 1 | 2 | High Priority | 2019-04-04 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74124-10 | 74124 | B2LED-32 | 10 | 1 | Regular | 2019-02-12 | 1900-01-02 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 | 2 | 2019-01-30 |  |  |  | NO
74124-1 | 74124 | B4LED-4 | 1 | 24:00 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-29 16:58 | 42 | 2019-01-30 |  |  |  | NO
74124-11 | 74124 | B2LED-35 | 11 | 1 | Regular | 2019-02-12 | 1900-01-02 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 | 2 | 2019-01-30 |  |  |  | NO
74124-12 | 74124 | B2LED-38 | 12 | 1 | Regular | 2019-02-12 | 1900-01-03 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-13 | 74124 | B2LED-41 | 13 | 1 | Regular | 2019-02-12 | 1900-01-03 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-14 | 74124 | B2LED-44 | 14 | 1 | Regular | 2019-02-12 | 1900-01-03 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-15 | 74124 | B2LED-48 | 15 | 1 | Regular | 2019-02-12 | 1900-01-03 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-16 | 74124 | B2LED-51 | 16 | 1 | Regular | 2019-02-12 | 1900-01-04 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-17 | 74124 | B2LED-54 | 17 | 1 | Regular | 2019-02-12 | 1900-01-04 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-18 | 74124 | B2LED-57 | 18 | 1 | Regular | 2019-02-12 | 1900-01-04 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-19 | 74124 | B2LED-60 | 19 | 1 | Regular | 2019-02-12 | 1900-01-04 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-20 | 74124 | B2LED-64 | 20 | 1 | Regular | 2019-02-12 | 1900-01-05 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-2 | 74124 | B4LED-8 | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 | 42 | 2019-01-30 |  |  |  | NO
74124-21 | 74124 | B4LED-4 | 21 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
74124-22 | 74124 | B4LED-8 | 22 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
74124-23 | 74124 | B4LED-16 | 23 | 1 | Regular | 2019-02-12 | 1900-01-01 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
74124-24 | 74124 | B4LED-24 | 24 | 1 | Regular | 2019-02-12 | 1900-01-01 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
74124-25 | 74124 | B4LED-4 | 25 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-26 | 74124 | B4LED-8 | 26 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-27 | 74124 | B4LED-12 | 27 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-28 | 74124 | B4LED-20 | 28 | 1 | Regular | 2019-02-12 | 1900-01-01 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 |  | 2019-01-30 |  |  |  | NO
74124-3 | 74124 | B4LED-4 | 3 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 | 42 | 2019-01-30 |  |  |  | NO
74124-4 | 74124 | B4LED-8 | 4 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:53 | 9 | 2019-01-30 |  |  |  | NO
74124-5 | 74124 | B4LED-16 | 5 | 1 | Regular | 2019-02-12 | 1900-01-01 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 15:52 | 9 | 2019-01-30 |  |  |  | NO
74124-6 | 74124 | B2LED-20 | 6 | 1 | Regular | 2019-02-12 | 1900-01-01 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 | 9 | 2019-01-30 |  |  |  | NO
74124-7 | 74124 | B2LED-23 | 7 | 1 | Regular | 2019-02-12 | 1900-01-01 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 | 9 | 2019-01-30 |  |  |  | NO
74124-8 | 74124 | B2LED-26 | 8 | 1 | Regular | 2019-02-12 | 1900-01-02 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 | 2 | 2019-01-30 |  |  |  | NO
74124-9 | 74124 | B2LED-29 | 9 | 1 | Regular | 2019-02-12 | 1900-01-02 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 15:53 | 2 | 2019-01-30 |  |  |  | NO
74276-1 | 74276 | BEAM4-4 | 1 | 2 | High Priority | 2019-02-26 | 1899-12-31 | 18 | Machine Shop Started | Shortage | FALSE |  |  |  |  | NA |  |  | Yes | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74276-1 | 74276 | BEAM4-4 | 1 | 3 | High Priority | 2019-05-29 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | Yes | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74276-1 | 74276 | BEAM4-4 | 1 | 4 | High Priority | 2019-08-28 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74276-1 | 74276 | BEAM4-4 | 1 | 5 | High Priority | 2020-01-01 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74276-1 | 74276 | BEAM4-4 | 1 | 6 | High Priority | 2020-03-27 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74276-2 | 74276 | BEAM4-4 | 2 | 2 | High Priority | 2019-02-26 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
74294-4 | 74294 | PERFKT-CCH | 4 | 1 | Regular | 2019-01-08 | 1900-01-07 | 1 | Machine Shop Finished | Shortage | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE | 2019-01-17 09:35 | 14 | 2019-01-02 | Yvonne 2V2-B |  |  | OK
74540-1 | 74540 | TB2LED-8 | 1 | 1 | High Priority | 2019-05-02 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74540-2 | 74540 | TB2LED-12 | 2 | 1 | High Priority | 2019-05-02 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74695-1 | 74695 | DIALED-22 | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
74695-2 | 74695 | DIALED-11 | 2 | 1 | Regular | 2019-02-07 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
74695-3 | 74695 | DIALED-11 | 3 | 1 | Regular | 2019-02-07 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
74695-4 | 74695 | DIALED-14 | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
74695-5 | 74695 | B3LED-4' | 5 | 1 | Regular | 2019-02-07 | 1899-12-31 | 10 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 4 | 2019-02-04 | 2V1-B |  |  | NO
74740-1 | 74740 | PRMLED-6 | 1 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74740-2 | 74740 | PRMLED-2 | 2 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74740-3 | 74740 | B4LED-12 | 3 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74740-4 | 74740 | SL2LED-6 | 4 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE |  |  | 2018-12-11 |  |  |  | NO | Material |  | Material
74740-5 | 74740 | SL2LED-8 | 5 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE |  |  | 2018-12-11 |  |  |  | NO | Material |  | Material
74740-6 | 74740 | SL2LED-8 | 6 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE |  |  | 2018-12-11 |  |  |  | NO | Material |  | Material
74740-7 | 74740 | PERFKT-CCH | 7 | 1 | Regular | 2019-03-13 | 1900-01-07 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE |  |  | 2018-12-11 |  |  |  | NO | Material |  | Material
74740-8 | 74740 | PERFKT-CCH | 8 | 1 | Regular | 2019-03-13 | 1900-01-11 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE |  |  | 2018-12-11 |  |  |  | NO | Material |  | Material
74740-9 | 74740 | PRMLED-6 | 9 | 1 | Regular | 2019-03-13 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74964-10 | 74964 | GRAZE-36'9" | 10 | 1 | High Priority | 2019-02-12 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-1 | 74964 | GRAZE-35'5" | 1 | 24:00 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-11 | 74964 | GRAZE-34'6" | 11 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-12 | 74964 | GRAZE-12' | 12 | 1 | High Priority | 2019-02-12 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-13 | 74964 | GRAZE-27' | 13 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-14 | 74964 | GRAZE-27'10" | 14 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-15 | 74964 | GRAZE-34' | 15 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-16 | 74964 | GRAZE-27'9" | 16 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-17 | 74964 | CLICK-12 | 17 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  |  | NA | FALSE | FALSE |  |  | 2019-01-31 | 2v1-b |  | ToDo | NO | Material |  | Material
74964-18 | 74964 | CLICK-16 | 18 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 1 | Machine Shop Started | Shortage | FALSE | Yes |  |  |  | NA |  |  | NA | FALSE | FALSE |  |  | 2019-01-31 | 2v1-b |  |  | NO | Material |  | Material
74964-19 | 74964 | ARCLED-8 | 19 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [6 empty] | Yes | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-20 | 74964 | ARCLED-4 | 20 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [6 empty] | Yes | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-2 | 74964 | GRAZE-16 | 2 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-21 | 74964 | ARCLED-8 | 21 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [6 empty] | Yes | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-22 | 74964 | ARCLED-18 | 22 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | Yes | [6 empty] | Yes | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-23 | 74964 | GRAZE-27' 11 1/2" | 23 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-3 | 74964 | GRAZE-34'8" | 3 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-4 | 74964 | GRAZE-36'7" | 4 | 1 | High Priority | 2019-02-12 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-5 | 74964 | GRAZE-37'1" | 5 | 1 | High Priority | 2019-02-12 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-6 | 74964 | GRAZE-35'4" | 6 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-7 | 74964 | GRAZE-33'2" | 7 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-8 | 74964 | GRAZE-33'7" | 8 | 24:00 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74964-9 | 74964 | GRAZE-35'6" | 9 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
74968-1 | 74968 | SKETCH-AL(#23' 9 1/4") | 1 | 1 | High Priority | 2019-01-29 | 1900-01-03 | 1 | Machine Shop Started | Others | FALSE | Yes | Yes |  | Done |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
74968-2 | 74968 | SKETCH-AL(#14' 10 | 2 | 24:00 | High Priority | 2019-01-29 | 1900-01-02 | 1 | Machine Shop Started | Others | TRUE | Yes | Yes |  | Done |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
74968-3 | 74968 | SKETCH-AL(# 16' 10 | 3 | 1 | High Priority | 2019-01-29 | 1900-01-02 | 1 | Machine Shop Started | Shortage | TRUE | Yes | Yes | Yes | Done |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
74971-1 | 74971 | B4LED-16 | 1 | 24:00 | Regular | 2019-02-27 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74971-2 | 74971 | B4LED-22 | 2 | 1 | Regular | 2019-02-27 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74971-3 | 74971 | B4LED-12 | 3 | 24:00 | Regular | 2019-02-27 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
74971-4 | 74971 | B4LED-30 | 4 | 24:00 | Regular | 2019-02-27 | 1900-01-02 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75090-1 | 75090 | TBEAM2-10 | 1 | 24:00 | Regular | 2019-02-11 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
75090-2 | 75090 | ZENSQ-15 | 2 | 24:00 | Regular | 2019-02-11 | 1900-01-01 | 1 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
75090-3 | 75090 | SKETCH-AL(7'10 1/4") | 3 | 24:00 | Regular | 2019-02-11 | 1900-01-03 | 1 | Machine Shop Started | Others | FALSE | Yes |  |  | Done |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75090-4 | 75090 | ZENSQ-20 | 4 | 24:00 | Regular | 2019-02-11 | 1900-01-01 | 1 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
75103-10 | 75103 | TWGLED-4 | 10 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-11 | 75103 | TWGLED-6 | 11 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-12 | 75103 | TWGLED-8 | 12 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-13 | 75103 | TWGLED-4 | 13 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-14 | 75103 | TWGLED-6 | 14 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-15 | 75103 | TWGLED-8 | 15 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-3 | 75103 | TWGLED-4 | 3 | 1 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-4 | 75103 | TWGLED-6 | 4 | 1 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-5 | 75103 | TWGLED-8 | 5 | 1 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-6 | 75103 | TWGLED-4 | 6 | 24:00 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75103-7 | 75103 | TWGLED-6 | 7 | 1 | Priority | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  |  | Yes | TRUE | FALSE | 2019-02-04 17:08 |  | 2019-01-25 |  |  |  | OK
75212-30 | 75212 | B3LED-4' | 30 | 24:00 | Regular | 2019-02-01 | 1899-12-31 | 18 | Given to Shipping | Shortage | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 08:38 |  | 2019-01-22 | 2v1-b |  |  | NO
75212-38 | 75212 | B3LED-24' | 38 | 24:00 | Regular | 2019-02-12 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-22 |  |  |  | NO
75218-1 | 75218 | B3LED-16 | 1 | 24:00 | Regular | 2019-03-04 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75218-2 | 75218 | B3LED-28 | 2 | 1 | Regular | 2019-03-04 | 1900-01-02 | 96:00 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75218-3 | 75218 | B3LED-36 | 3 | 24:00 | Regular | 2019-03-04 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75218-4 | 75218 | B3LED-40 | 4 | 1 | Regular | 2019-03-04 | 1900-01-03 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75218-5 | 75218 | B3LED-42 | 5 | 1 | Regular | 2019-03-04 | 1900-01-03 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75218-6 | 75218 | B3LED-44 | 6 | 1 | Regular | 2019-03-04 | 1900-01-03 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75218-7 | 75218 | SL2LED-24 | 7 | 1 | Regular | 2019-03-04 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75218-8 | 75218 | SCULPT-K(4X4) | 8 | 1 | Regular | 2019-03-04 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75368-1 | 75368 | B4LED-14 | 1 | 1 | Regular | 2019-02-15 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75368-2 | 75368 | B4LED-24 | 2 | 1 | Regular | 2019-02-15 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75392-1 | 75392 | PERFKT-CCWH | 1 | 1 | Regular | 2019-02-05 | 1900-01-05 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE | 2019-01-31 17:11 |  | 2019-01-25 |  |  |  | OK
75398-1 | 75398 | B2SLED-4 | 1 | 1 | High Priority | 2019-01-16 | 1899-12-31 | 4 | Wiring Started | Missing parts in BOM | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:46 | 17 | 2019-02-01 | 2t2-b |  |  | NO
75398-2 | 75398 | B2SLED-26 | 2 | 1 | High Priority | 2019-01-16 | 1900-01-02 | 4 | Wiring Started | Others | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:46 |  | 2019-02-01 | 2t2-b |  |  | NO
75398-3 | 75398 | B2SLED-4' 6 1/2" | 3 | 1 | High Priority | 2019-01-16 | 1899-12-31 | 96:00 | Wiring Started | Others | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:46 |  | 2019-02-01 | 2t2-b |  |  | NO
75398-4 | 75398 | PERFKT-CCH | 4 | 1 | High Priority | 2019-01-16 | 1899-12-31 | 4 | Packaging Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE |  |  | 2019-01-04 | 2t2-b |  |  | OK
75398-5 | 75398 | PERFKT-CCH | 5 | 1 | High Priority | 2019-01-16 | 1899-12-31 | 4 | Packaging Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE |  |  | 2019-01-04 | 2t2-b |  |  | OK
75462-10 | 75462 | WWPRFK-14' | 10 | 1 | High Priority | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-11 | 75462 | WWPRFK-4' | 11 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-14 | 75462 | SCULPT-339 | 14 | 24:00 | High Priority | 2019-02-11 | 1900-01-23 | 1 | Machine Shop Started | Others | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  |  | 2v2-b |  |  | NO | Material | +Cartridge | Material+Cartridge
75462-15 | 75462 | SCULPT-46'5" | 15 | 24:00 | High Priority | 2019-02-13 | 1900-01-02 | 7 | Machine Shop Started | Others | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-4 | 75462 | WWPRFK-10' | 4 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-5 | 75462 | WWPRFK-11'8" | 5 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-6 | 75462 | WWPRFK-8' | 6 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-7 | 75462 | WWPRFK-6' | 7 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 168:00 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-8 | 75462 | WWPRFK-10' | 8 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 168:00 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75462-9 | 75462 | WWPRFK-18' | 9 | 1 | High Priority | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75467-6 | 75467 | NPI-N18003-04 | 6 | 1 | Regular | 2018-11-29 | 1900-01-01 | 4 | Wiring Started | Others | FALSE | Yes |  | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2018-12-04 16:05 | [5 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-10 | 75475 | WWPRFK-20' | 10 | 24:00 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-27 | 75475 | SCULPT-46'2" | 27 | 24:00 | Regular | 2019-02-13 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-28 | 75475 | WWPRFK-6' | 28 | 24:00 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-5 | 75475 | WWPRFK-10' | 5 | 24:00 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-6 | 75475 | WWPRFK-8 | 6 | 24:00 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-7 | 75475 | WWPRFK-8' | 7 | 24:00 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-8 | 75475 | WWPRFK-4' | 8 | 24:00 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75475-9 | 75475 | WWPRFK-10' | 9 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-11 | 75504 | B4PLED-8 5 3/4"' | 11 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-12 | 75504 | B4PLED-9' 2 5/8" | 12 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-15 | 75504 | B4PLED-6' 3 5/8" | 15 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-16 | 75504 | B4PLED-6' 3 1/4" | 16 | 24:00 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-20 | 75504 | B4PLED-8' 5 5/8"' | 20 | 24:00 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-23 | 75504 | B4PLED-8' 5 7/8"' | 23 | 24:00 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-24 | 75504 | B4PLED-8' 10 7/8"' | 24 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-25 | 75504 | B4PLED-9' 0 5/8"' | 25 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-28 | 75504 | B4PLED-9' 4 1/4" | 28 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-31 | 75504 | B4PLED-9' 4 1/2" | 31 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-34 | 75504 | B4PLED-9' 4 3/8" | 34 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-37 | 75504 | B4PLED-9' 7 5/8" | 37 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-38 | 75504 | B4PLED-6' 3 3/8" | 38 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-39 | 75504 | B4PLED-9' 7 7/8" | 39 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-42 | 75504 | B4PLED-9' 11 3/4" | 42 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-44 | 75504 | SCULPT-10' 10 1/2" | 44 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-45 | 75504 | SCULPT-14' 2 3/8" | 45 | 1 | High Priority | 2019-02-15 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-8 | 75504 | B4PLED-5' 11 3/4" | 8 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-85 | 75504 | SCULPT-9' 9 5/8" | 85 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75504-9 | 75504 | B4PLED-6' 3 1/8" | 9 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75556-1 | 75556 | TB2LED-8 | 1 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75556-2 | 75556 | TB2LED-8' | 2 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75556-3 | 75556 | TB2LED-8 | 3 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75556-4 | 75556 | TB2LED-8' | 4 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75675-1 | 75675 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75675-2 | 75675 | STENCL-STCO | 2 | 1 | Regular | 2019-02-14 | 1900-01-04 | 1 | Machine Shop Started | Wrong info. In SD | TRUE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75692-11 | 75692 | B3PLED-40'2 1/8" | 11 | 1 | High Priority | 2019-01-16 | 1900-01-04 | 1 | Wiring Started | Shortage | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-28 16:05 | 13 | 2019-01-08 |  |  |  | NO
75693-12 | 75693 | B3PLED-22'11 3/4" | 12 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started | Wrong info. In SD | TRUE |  |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-13 | 75693 | B3PLED-19'10 5/16" | 13 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started | Wrong info. In SD | TRUE |  |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 19 | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-14 | 75693 | B3PLED-17'1 5/8" | 14 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started | Wrong info. In SD | TRUE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 19 | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-17 | 75693 | B3PLED-18'8 1/2" | 17 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 41 | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-18 | 75693 | B3PLED-10'3 3/16" | 18 | 1 | Regular | 2019-02-04 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 41 | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-19 | 75693 | B3PLED-9'10 1/6" | 19 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-20 | 75693 | B3PLED-10'4 1/8" | 20 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-21 | 75693 | B3PLED-10'4 1/8" | 21 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-22 | 75693 | B3PLED-21'3 3/16" | 22 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-23 | 75693 | B3PLED-9'7 3/8" | 23 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-24 | 75693 | B3PLED-9'5 1/4" | 24 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started | Missing parts in BOM | TRUE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-25 | 75693 | B3PLED-9'3 3/16" | 25 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-26 | 75693 | B3PLED-9'3 3/16" | 26 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-27 | 75693 | B3PLED-8'10" | 27 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-28 | 75693 | B3PLED-8'4 7/8" | 28 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-29 | 75693 | B3PLED-22'6 5/8" | 29 | 1 | Regular | 2019-02-04 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-30 | 75693 | B3PLED-24'11 1/8" | 30 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-31 | 75693 | B3PLED-34'7 1/2" | 31 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-32 | 75693 | B3PLED-48'6" 3/8" | 32 | 1 | Regular | 2019-02-04 | 1900-01-07 | 7 | Machine Shop Started | Missing info. In SD | TRUE |  |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-33 | 75693 | B3PLED-7'10 3/8" | 33 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-36 | 75693 | SCULPT-45'5" | 36 | 1 | Regular | 2019-02-04 | 1900-01-02 | 7 | Machine Shop Started | Others | FALSE | [6 empty] | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75693-40 | 75693 | B3PLED-10' | 40 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-4 | 75693 | WWPRFK-8' | 4 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Finished | Others | FALSE |  |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75693-41 | 75693 | B3PLED-8' | 41 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-42 | 75693 | B3PLED-7'8" | 42 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-43 | 75693 | B3PLED-17'8" | 43 | 1 | Regular | 2019-02-04 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-44 | 75693 | WWPRFK-6' | 44 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE |  |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75693-45 | 75693 | B3PLED-12'2" | 45 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-A |  |  | NO | Material |  | Material
75693-5 | 75693 | WWPRFK-10' | 5 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE |  |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75693-6 | 75693 | WWPRFK-12' | 6 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE |  |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75693-7 | 75693 | WWPRFK-6' | 7 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE |  |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75693-8 | 75693 | WWPRFK-6' | 8 | 1 | Regular | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Started | Shortage | FALSE |  |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
75697-1 | 75697 | PRMLED-4 | 1 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 12:51 | 45 | 2019-01-28 | 2t1-b |  |  | NO
75697-2 | 75697 | PRMLED-4 | 2 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 12:51 | 45 | 2019-01-28 | 2t1-b |  |  | NO
75697-3 | 75697 | PRMLED-8 | 3 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 12:51 | 45 | 2019-01-28 | 2t1-b |  |  | NO
75697-4 | 75697 | PRMLED-12 | 4 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 12:51 | 45 | 2019-01-28 | 2t1-b |  |  | NO
75728-1 | 75728 | SCULPT-4 | 1 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO |  | +Cartridge | +Cartridge
75728-2 | 75728 | SCULPT-8 | 2 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO |  | +Cartridge | +Cartridge
75728-3 | 75728 | SCULPT-8 | 3 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO |  | +Cartridge | +Cartridge
75728-4 | 75728 | SCULPT-36 | 4 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO |  | +Cartridge | +Cartridge
75728-5 | 75728 | SCULPT-16 | 5 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO |  | +Cartridge | +Cartridge
75728-9 | 75728 | SCULPT-159' | 9 | 1 | High Priority | 2019-02-08 | 1900-01-15 | 18 | Machine Shop Started |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r1-b |  |  | NO |  | +Cartridge | +Cartridge
75738-1 | 75738 | B3LED-4 | 1 | 2 | Regular | 2019-02-04 | 1899-12-31 | 12 | Given to Shipping | Mechanical issue | TRUE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 12:55 | 35 | 2019-01-31 |  |  |  | NO
75738-2 | 75738 | B3LED-2 | 2 | 2 | Regular | 2019-02-04 | 1899-12-31 | 12 | Given to Shipping | Wrong info. In SD | TRUE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 12:55 | 35 | 2019-01-31 |  |  |  | NO
75745-13 | 75745 | B3PLED-36'6" | 13 | 1 | Regular | 2019-01-28 | 1900-01-04 | 1 | Wiring Started | Shortage | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-31 15:52 | 50 | 2019-01-23 | 2s1-b |  |  | NO
75745-21 | 75745 | SCULPT-46'5" | 21 | 1 | Regular | 2019-02-11 | 1900-01-02 | 7 | Machine Shop Started | Others | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75745-5 | 75745 | WWPRFK-8' | 5 | 1 | Regular | 2019-02-11 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75745-6 | 75745 | WWPRFK-16' | 6 | 1 | Regular | 2019-02-11 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75745-7 | 75745 | WWPRFK-8' | 7 | 1 | Regular | 2019-02-11 | 1899-12-31 | 7 | Machine Shop Started | Wrong part in BOM | TRUE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75745-8 | 75745 | WWPRFK-10' | 8 | 1 | Regular | 2019-02-11 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75745-9 | 75745 | WWPRFK-20' | 9 | 1 | Regular | 2019-02-11 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75746-22 | 75746 | B3PLED-9'8 1/8" | 22 | 1 | Regular | 2019-02-11 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
75746-23 | 75746 | B3PLED-18'5 7/16" | 23 | 1 | Regular | 2019-02-21 | 1900-01-02 | 0 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75746-24 | 75746 | B3PLED-17'6" | 24 | 1 | Regular | 2019-02-11 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
75746-25 | 75746 | B3PLED-19'6 3/4" | 25 | 1 | Regular | 2019-02-11 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
75746-26 | 75746 | B3PLED-38' | 26 | 1 | Regular | 2019-02-11 | 1900-01-03 | 1 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
75746-29 | 75746 | SCULPT-46'1" | 29 | 1 | Regular | 2019-02-11 | 1900-01-02 | 1 | Machine Shop Started | Others | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  |  |  | ToDo |  | NO | Material | +Cartridge | Material+Cartridge
75746-31 | 75746 | B3PLED-19'6 3/4" | 31 | 1 | Regular | 2019-02-11 | 1900-01-02 | 1 | Machine Shop Started | Missing info. In SD | TRUE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
75746-34 | 75746 | WWPRFK-8' | 34 | 1 | Regular | 2019-02-11 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [5 empty] | ToDo | NO | Material | +Cartridge | Material+Cartridge
75746-5 | 75746 | WWPRFK-6' | 5 | 1 | Regular | 2019-02-11 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  | 2019-01-15 |  |  | ToDo | NO | Material | +Cartridge | Material+Cartridge
75746-6 | 75746 | WWPRFK-8' | 6 | 1 | Regular | 2019-02-11 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  | 2019-01-15 |  |  | ToDo | NO | Material | +Cartridge | Material+Cartridge
75746-7 | 75746 | WWPRFK-10' | 7 | 1 | Regular | 2019-02-11 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  | 2019-01-15 |  |  | ToDo | NO | Material | +Cartridge | Material+Cartridge
75746-8 | 75746 | WWPRFK-20' | 8 | 1 | Regular | 2019-02-11 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  | 2019-01-15 |  |  | ToDo | NO | Material | +Cartridge | Material+Cartridge
75801-10 | 75801 | CLICK-14 | 10 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-1 | 75801 | CLICK-5 | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started | Others | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-11 | 75801 | CLICK-15 | 11 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-12 | 75801 | CLICK-16 | 12 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-13 | 75801 | CLICK-18 | 13 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-14 | 75801 | CLICK-19 | 14 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started | Shortage | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-18 | 75801 | CLICK-4 | 18 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-19 | 75801 | CLICK-5 | 19 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-20 | 75801 | CLICK-14 | 20 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-2 | 75801 | CLICK-13 | 2 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started | Others | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-21 | 75801 | CLICK-15 | 21 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-23 | 75801 | CLICK-18 | 23 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-24 | 75801 | CLICK-19 | 24 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-26 | 75801 | B2LED-8 | 26 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started | Others | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75801-27 | 75801 | B2LED-12 | 27 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75801-30 | 75801 | CLICK-6 | 30 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-3 | 75801 | CLICK-14 | 3 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started | Others | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-31 | 75801 | CLICK-8 | 31 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-32 | 75801 | CLICK-9 | 32 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-33 | 75801 | CLICK-14 | 33 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-34 | 75801 | CLICK-15 | 34 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-35 | 75801 | CLICK-19 | 35 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-4 | 75801 | CLICK-15 | 4 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-43 | 75801 | B2LED-8 | 43 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75801-44 | 75801 | B2LED-12 | 44 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75801-45 | 75801 | CLICK-5 | 45 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-46 | 75801 | CLICK-14 | 46 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-47 | 75801 | CLICK-15 | 47 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-48 | 75801 | CLICK-18 | 48 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-5 | 75801 | CLICK-19 | 5 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-51 | 75801 | B2LED-8 | 51 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75801-52 | 75801 | B2LED-12 | 52 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75801-53 | 75801 | CLICK-19' | 53 | 1 | Regular | 2019-02-18 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-56 | 75801 | CLICK-8' | 56 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-57 | 75801 | CLICK-12' | 57 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-58 | 75801 | CLICK-4' | 58 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-59 | 75801 | CLICK-5' | 59 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-61 | 75801 | CLICK-9' 10" | 61 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-62 | 75801 | CLICK-13' | 62 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-8 | 75801 | CLICK-8 | 8 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75801-9 | 75801 | CLICK-12 | 9 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75811-1 | 75811 | STENCL-20 | 1 | 1 | Regular | 2019-02-01 | 1900-01-02 | 7 | Wiring Started | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-05 10:02 | big buggy | 2019-02-05 |  |  |  | NO
75811-2 | 75811 | STENCL-20 | 2 | 1 | Regular | 2019-02-01 | 1900-01-02 | 7 | Wiring Started | Mechanical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-05 10:02 |  | 2019-02-05 |  |  |  | NO
75811-3 | 75811 | STENCL-20 | 3 | 1 | Regular | 2019-02-01 | 1900-01-02 | 7 | Wiring Started | Others | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-05 10:02 |  | 2019-02-05 |  |  |  | NO
75841-1 | 75841 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-100 | 75859 | B3LED-4 | 100 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-104 | 75859 | TB2LED-140' | 104 | 1 | Regular | 2019-03-28 | 1900-01-11 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-105 | 75859 | TB2LED-66' | 105 | 1 | Regular | 2019-03-28 | 1900-01-08 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-106 | 75859 | TB2LED-66' | 106 | 1 | Regular | 2019-03-28 | 1900-01-04 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-115 | 75859 | B2LED-42' | 115 | 1 | Regular | 2019-02-28 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-36 | 75859 | B2LED-12' | 36 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-39 | 75859 | B2LED-12' | 39 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-4 | 75859 | TB2LED-52' | 4 | 1 | Regular | 2019-03-28 | 1900-01-07 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-42 | 75859 | B2LED-16' | 42 | 1 | Regular | 2019-02-28 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-61 | 75859 | B2LED-8' | 61 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-62 | 75859 | B2LED-8' | 62 | 1 | Regular | 2019-03-28 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-64 | 75859 | B2LED-10' | 64 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-66 | 75859 | B2LED-12' | 66 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-67 | 75859 | B2LED-12' | 67 | 1 | Regular | 2019-03-28 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-69 | 75859 | B2LED-14' | 69 | 1 | Regular | 2019-02-28 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-70 | 75859 | B2LED-14' | 70 | 1 | Regular | 2019-03-28 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-71 | 75859 | B2LED-14' | 71 | 1 | Regular | 2019-02-28 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-73 | 75859 | B2LED-18' | 73 | 1 | Regular | 2019-02-28 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-74 | 75859 | B2LED-18' | 74 | 1 | Regular | 2019-03-28 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75859-79 | 75859 | B2LED-42' | 79 | 1 | Regular | 2019-02-28 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-81 | 75859 | B2LED-42' | 81 | 1 | Regular | 2019-02-28 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-82 | 75859 | B2LED-42' | 82 | 1 | Regular | 2019-02-28 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-91 | 75859 | B3LED-4 | 91 | 1 | Regular | 2019-02-13 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-97 | 75859 | B3LED-4 | 97 | 1 | Regular | 2019-02-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | FLOOR |  |  | NO | Material | +Cartridge | Material+Cartridge
75859-98 | 75859 | B3LED-4 | 98 | 1 | Regular | 2019-03-28 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-10 | 75954 | B2LED-16 | 10 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-1 | 75954 | B2LED-8 | 1 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-11 | 75954 | B2LED-18 | 11 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-12 | 75954 | B2LED-20 | 12 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-15 | 75954 | B2LED-23 | 15 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-16 | 75954 | SCULPT-18 | 16 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-17 | 75954 | B2LED-4 | 17 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-18 | 75954 | B2LED-5 | 18 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-19 | 75954 | B2LED-6 | 19 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-20 | 75954 | B2LED-16 | 20 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-2 | 75954 | B2LED-10 | 2 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-21 | 75954 | B2LED-18 | 21 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-23 | 75954 | B3PLED-8'5" | 23 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75954-24 | 75954 | B3PLED-8'7" | 24 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75954-25 | 75954 | B3PLED-12' | 25 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75954-26 | 75954 | B3PLED-142" | 26 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
75954-27 | 75954 | B3PLED-150 3/4" | 27 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 34 | 2019-02-03 | 2x1-a |  |  | NO
75954-28 | 75954 | B3PLED-23' | 28 | 1 | Regular | 2019-02-07 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 34 | 2019-02-03 | 2x1-a |  |  | NO
75954-29 | 75954 | B3PLED-134" | 29 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 34 | 2019-02-03 | 2x1-a |  |  | NO
75954-32 | 75954 | B2LED-56 | 32 | 1 | Regular | 2019-02-27 | 1900-01-04 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-34 | 75954 | B2LED-0' 245" | 34 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-35 | 75954 | B2LED-0' 317" | 35 | 1 | Regular | 2019-02-27 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-36 | 75954 | SCULPT-8 | 36 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-37 | 75954 | B2LED-0' 244" | 37 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-4 | 75954 | B2LED-12 | 4 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-41 | 75954 | B3PLED-144" | 41 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 34 | 2019-02-03 | 2x1-a |  |  | NO
75954-42 | 75954 | B3PLED-168" | 42 | 1 | Regular | 2019-02-07 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 34 | 2019-02-03 | 2x1-a |  |  | NO
75954-5 | 75954 | B2LED-14 | 5 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-6 | 75954 | B2LED-16 | 6 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-7 | 75954 | B2LED-20 | 7 | 1 | Regular | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-8 | 75954 | B2LED-5 | 8 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75954-9 | 75954 | B2LED-6 | 9 | 1 | Regular | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
75966-8 | 75966 | SKVLED-14 | 8 | 1 | Regular | 2019-02-11 | 1899-12-31 | 10 | Machine Shop Started | Shortage | FALSE |  |  |  |  | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2018-12-28 |  |  |  | NO | Material |  | Material
76021-1 | 76021 | WB4LED-2 | 1 | 1 | Regular | 2019-02-13 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE | [6 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76028-32 | 76028 | PERFKT-CCH | 32 | 1 | High Priority | 2019-02-08 | 1900-01-04 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO
76028-44 | 76028 | PERFKT-CCH | 44 | 1 | High Priority | 2019-02-08 | 1900-01-08 | 4 | Scheduled/Released |  | FALSE |  | Yes |  |  | NA |  |  | NA | FALSE | FALSE |  |  | 2019-02-04 |  |  |  | NO
76076-1 | 76076 | B2LED-6' | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 | [5 empty] | NO |  | +Cartridge | +Cartridge
76076-2 | 76076 | B2LED-4' | 2 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 | [5 empty] | NO |  | +Cartridge | +Cartridge
76076-3 | 76076 | B2LED-5' | 3 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 | [5 empty] | NO |  | +Cartridge | +Cartridge
76076-4 | 76076 | B2LED-8' | 4 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 | [5 empty] | NO |  | +Cartridge | +Cartridge
76080-10 | 76080 | B3LED-18 | 10 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 33 | 2019-01-25 |  |  |  | NO
76080-1 | 76080 | B3LED-16 | 1 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 35 | 2019-01-25 |  |  |  | NO
76080-11 | 76080 | B3LED-18 | 11 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 33 | 2019-01-25 |  |  |  | NO
76080-12 | 76080 | B3LED-24 | 12 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 33 | 2019-01-25 |  |  |  | NO
76080-13 | 76080 | B3LED-24 | 13 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 2 | 2019-01-25 |  |  |  | NO
76080-14 | 76080 | B3LED-12 | 14 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 2 | 2019-01-25 |  |  |  | NO
76080-15 | 76080 | B3LED-16 | 15 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 2 | 2019-01-25 |  |  |  | NO
76080-16 | 76080 | B3LED-6 | 16 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 2 | 2019-01-25 |  |  |  | NO
76080-17 | 76080 | B3LED-12 | 17 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 2 | 2019-01-25 |  |  |  | NO
76080-18 | 76080 | B3LED-20 | 18 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 3 | 2019-01-25 |  |  |  | NO
76080-19 | 76080 | B3LED-32 | 19 | 1 | Regular | 2019-03-04 | 1900-01-02 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 3 | 2019-01-25 |  |  |  | NO
76080-20 | 76080 | B3LED-12 | 20 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 3 | 2019-01-25 |  |  |  | NO
76080-2 | 76080 | B3LED-8 | 2 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 35 | 2019-01-25 |  |  |  | NO
76080-21 | 76080 | B3LED-24 | 21 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 3 | 2019-01-25 |  |  |  | NO
76080-22 | 76080 | B3LED-4 | 22 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished | Others | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 | 3 | 2019-01-25 |  |  |  | NO
76080-26 | 76080 | B3LED-8 | 26 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 | 3 | 2019-01-25 |  |  |  | NO
76080-27 | 76080 | B3LED-16 | 27 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-28 | 76080 | B3LED-40 | 28 | 1 | Regular | 2019-03-04 | 1900-01-03 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-29 | 76080 | B3LED-24 | 29 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-30 | 76080 | B3LED-8 | 30 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-3 | 76080 | B3LED-14 | 3 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 35 | 2019-01-25 |  |  |  | NO
76080-31 | 76080 | B3LED-12 | 31 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-32 | 76080 | B3LED-20 | 32 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-34 | 76080 | B3LED-12 | 34 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-35 | 76080 | B3LED-20 | 35 | 1 | Regular | 2019-03-04 | 1900-01-01 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-36 | 76080 | B3LED-6 | 36 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished | Others | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-37 | 76080 | B3LED-6 | 37 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-27 11:31 |  | 2019-01-25 |  |  |  | NO
76080-5 | 76080 | B3LED-6 | 5 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 53 | 2019-01-25 |  |  |  | NO
76080-6 | 76080 | B3LED-6 | 6 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 53 | 2019-01-25 |  |  |  | NO
76080-7 | 76080 | B3LED-6 | 7 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 53 | 2019-01-25 |  |  |  | NO
76080-8 | 76080 | B3LED-12 | 8 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 53 | 2019-01-25 |  |  |  | NO
76080-9 | 76080 | B3LED-12 | 9 | 1 | Regular | 2019-03-04 | 1899-12-31 | 7 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-27 11:31 | 33 | 2019-01-25 |  |  |  | NO
76093-2 | 76093 | WWPRFK-4 | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
76134-10 | 76134 | B3LED-60 | 10 | 1 | Regular | 2019-04-24 | 1900-01-04 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-1 | 76134 | SCULPT-36 | 1 | 1 | Regular | 2019-04-24 | 1900-01-05 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-11 | 76134 | B3LED-59 | 11 | 1 | Regular | 2019-04-24 | 1900-01-04 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-12 | 76134 | B3LED-4 | 12 | 1 | Regular | 2019-04-24 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-13 | 76134 | B3LED-8 | 13 | 1 | Regular | 2019-04-24 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-14 | 76134 | B3LED-20 | 14 | 1 | Regular | 2019-04-24 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-15 | 76134 | B3LED-16 | 15 | 1 | Regular | 2019-04-24 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-2 | 76134 | SCULPT-30 | 2 | 1 | Regular | 2019-04-24 | 1900-01-05 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-3 | 76134 | SCULPT-48 | 3 | 1 | Regular | 2019-04-24 | 1900-01-05 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-4 | 76134 | SCULPT-34 | 4 | 1 | Regular | 2019-04-24 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-5 | 76134 | B3LED-16 | 5 | 1 | Regular | 2019-04-24 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-6 | 76134 | B3LED-35 | 6 | 1 | Regular | 2019-04-24 | 1900-01-02 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-7 | 76134 | B3LED-52 | 7 | 1 | Regular | 2019-04-24 | 1900-01-04 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-8 | 76134 | B3LED-8 | 8 | 1 | Regular | 2019-04-24 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76134-9 | 76134 | B3LED-12 | 9 | 1 | Regular | 2019-04-24 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76155-1 | 76155 | SLMLED-8 | 1 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76155-2 | 76155 | SLMLED-8 | 2 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76155-3 | 76155 | SLMLED-8 | 3 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76155-4 | 76155 | SLMLED-8 | 4 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76155-5 | 76155 | SLMLED-12 | 5 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76155-6 | 76155 | SLMLED-12 | 6 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76155-7 | 76155 | SLMLED-12 | 7 | 1 | Priority | 2019-02-22 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76181-1 | 76181 | STENCL-STFD | 1 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  |  | ToDo |  | NO | Material | +Cartridge | Material+Cartridge
76181-2 | 76181 | PERFKT-CCL | 2 | 1 | Regular | 2019-02-18 | 1900-01-17 | 4 | Machine Shop Finished |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76181-3 | 76181 | STENCL-STFD | 3 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  |  | ToDo |  | NO | Material | +Cartridge | Material+Cartridge
76181-4 | 76181 | STENCL-STFD | 4 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  |  | ToDo |  | NO | Material | +Cartridge | Material+Cartridge
76191-1 | 76191 | ZEN-8 | 1 | 1 | Regular | 2019-01-17 | 1899-12-31 | 4 | Machine Shop Started | Mechanical issue | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-01-17 10:47 |  | 2019-01-10 |  |  |  | OK
76192-1 | 76192 | GRAZE-7' | 1 | 1 | Regular | 2019-01-30 | 1899-12-31 | 1 | Machine Shop Started | Others | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 11:19 |  |  | 2s1-b | ToDo | ToDo | NO |  | +Cartridge | +Cartridge
76192-2 | 76192 | GRAZE-9' | 2 | 1 | Regular | 2019-01-30 | 1899-12-31 | 1 | Machine Shop Started | Shortage | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 11:19 |  |  | 2s1-b | ToDo | ToDo | NO |  | +Cartridge | +Cartridge
76192-3 | 76192 | GRAZE-12' | 3 | 1 | Regular | 2019-01-30 | 1899-12-31 | 1 | Machine Shop Started | Shortage | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 11:19 |  |  | 2s1-b | ToDo | ToDo | NO |  | +Cartridge | +Cartridge
76192-4 | 76192 | GRAZE-13' | 4 | 1 | Regular | 2019-01-30 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 11:19 |  |  | 2s1-b | ToDo | ToDo | NO |  | +Cartridge | +Cartridge
76192-5 | 76192 | GRAZE-14' | 5 | 1 | Regular | 2019-01-30 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 11:19 |  |  | 2s1-b | ToDo | ToDo | NO |  | +Cartridge | +Cartridge
76192-6 | 76192 | GRAZE-19' | 6 | 1 | Regular | 2019-01-30 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 11:19 |  |  | 2s1-b | ToDo | ToDo | NO |  | +Cartridge | +Cartridge
76203-28 | 76203 | WWPRFK-10' | 28 | 1 | Regular | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started | Wrong info. In SD | TRUE |  |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76203-29 | 76203 | WWPRFK-18' | 29 | 1 | Regular | 2019-02-13 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76203-30 | 76203 | WWPRFK-6' | 30 | 1 | Regular | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76203-31 | 76203 | WWPRFK-8' | 31 | 1 | Regular | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76203-32 | 76203 | WWPRFK-6' | 32 | 1 | Regular | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76241-10 | 76241 | B4LED-6 | 10 | 1 | Regular | 2019-02-21 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76241-6 | 76241 | B4LED-12 | 6 | 1 | Regular | 2019-02-21 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76241-7 | 76241 | B4LED-16 | 7 | 1 | Regular | 2019-02-21 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76241-8 | 76241 | B4LED-18'9" | 8 | 1 | Regular | 2019-02-21 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76241-9 | 76241 | B4LED-29 | 9 | 1 | Regular | 2019-02-21 | 1900-01-02 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76285-2 | 76285 | B4LED-26 | 2 | 1 | Regular | 2019-02-21 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76291-29 | 76291 | B4LED-8 | 29 | 1 | Regular | 2019-02-28 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76291-30 | 76291 | B4LED-8 | 30 | 1 | Regular | 2019-02-28 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76294-1 | 76294 | SKETCH-AL(32') | 1 | 1 | Regular | 2019-03-11 | 1900-01-05 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76294-2 | 76294 | B3LED-4 | 2 | 1 | Regular | 2019-03-11 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76294-3 | 76294 | B3LED-4 | 3 | 1 | Regular | 2019-03-11 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76372-1 | 76372 | STENCL-STFD | 1 | 1 | Regular | 2019-02-19 | 1900-02-10 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76372-2 | 76372 | STNCLS-STSFF | 2 | 1 | Regular | 2019-02-19 | 1900-02-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76372-3 | 76372 | STENCL-STFD | 3 | 1 | Regular | 2019-02-19 | 1900-01-14 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-10 | 76465 | WDILED-4 | 10 | 1 | Regular | 2019-02-19 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-11 | 76465 | WDILED-4 | 11 | 1 | Regular | 2019-02-19 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-12 | 76465 | WDILED-4 | 12 | 1 | Regular | 2019-02-19 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-4 | 76465 | WDILED-2' | 4 | 1 | Regular | 2019-02-19 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-5 | 76465 | B2LED-20' | 5 | 1 | Regular | 2019-02-19 | 1900-01-03 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-6 | 76465 | B2LED-52' | 6 | 1 | Regular | 2019-02-19 | 1900-01-07 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-8 | 76465 | WDILED-4' | 8 | 1 | Regular | 2019-02-19 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76465-9 | 76465 | WDILED-4 | 9 | 1 | Regular | 2019-02-19 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76468-1 | 76468 | PRMLED-2 | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Order UnShipped | Shortage | TRUE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:20 | 33 | 2019-01-31 | 2T1-B |  |  | NO | Material |  | Material
76468-2 | 76468 | PRMLED-4 | 2 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Order UnShipped |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:20 | 33 | 2019-01-31 | 2T1-B |  |  | NO | Material |  | Material
76468-3 | 76468 | B6LED-4 | 3 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Order UnShipped |  | FALSE | Yes |  |  |  | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 07:19 | 33 | 2019-01-31 | 2T1-B |  |  | NO | Material |  | Material
76468-4 | 76468 | PRMLED-2 | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Order UnShipped |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:20 | 33 | 2019-01-31 | 2T1-B |  |  | NO | Material |  | Material
76468-5 | 76468 | PRMLED-4 | 5 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Order UnShipped |  | FALSE | Yes |  |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 07:20 | 33 | 2019-01-31 | 2T1-B |  |  | NO | Material |  | Material
76468-6 | 76468 | B6LED-4 | 6 | 1 | Regular | 2019-02-07 | 1899-12-31 | 7 | Order UnShipped |  | FALSE | Yes |  |  |  | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 07:20 | 33 | 2019-01-31 | 2T1-B |  |  | NO | Material |  | Material
76472-1 | 76472 | B3LED-12 | 1 | 1 | Regular | 2019-04-01 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76472-2 | 76472 | B3LED-4 | 2 | 1 | Regular | 2019-04-01 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76528-1 | 76528 | SCULPT-SCML | 1 | 1 | Regular | 2019-01-28 | 1899-12-31 | 12 | Machine Shop Finished | Others | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE | 2019-01-29 09:43 |  | 2019-01-29 | 2w1-a |  |  | OK
76550-10 | 76550 | STENCL-STFC | 10 | 1 | Priority | 2019-02-20 | 1900-01-06 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-1 | 76550 | TB4LED-6 | 1 | 1 | Priority | 2019-03-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-11 | 76550 | STENCL-STFC | 11 | 1 | Priority | 2019-02-20 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-12 | 76550 | STENCL-STFC | 12 | 1 | Priority | 2019-02-20 | 1900-01-05 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-13 | 76550 | STENCL-34 | 13 | 1 | Priority | 2019-02-20 | 1900-01-04 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-2 | 76550 | TB4LED-12 | 2 | 1 | Priority | 2019-03-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-3 | 76550 | TB4LED-56 | 3 | 1 | Priority | 2019-03-25 | 1900-01-04 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-4 | 76550 | STENCL-STFC | 4 | 1 | Priority | 2019-02-20 | 1900-01-05 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-5 | 76550 | STENCL-STFC | 5 | 1 | Priority | 2019-02-20 | 1900-01-13 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-6 | 76550 | STENCL-STFC | 6 | 1 | Priority | 2019-02-20 | 1900-01-10 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-7 | 76550 | STENCL-4 | 7 | 1 | Priority | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-8 | 76550 | STENCL-STFC | 8 | 1 | Priority | 2019-02-20 | 1900-01-13 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76550-9 | 76550 | STENCL-STFC | 9 | 1 | Priority | 2019-02-20 | 1900-01-13 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76592-1 | 76592 | B3LED-40 | 1 | 1 | Regular | 2019-02-08 | 1900-01-07 | 7 | Machine Shop Started | Wrong part in BOM | TRUE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 43 | 2019-01-23 | 2s1-b |  |  | NO
76592-19 | 76592 | B4PLED-5' 1"X5'5 1/2" | 19 | 1 | Regular | 2019-02-08 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-23 | 2s1-b |  |  | NO
76592-2 | 76592 | B3LED-35' | 2 | 1 | Regular | 2019-02-08 | 1900-01-07 | 7 | Machine Shop Started | Wrong part in BOM | TRUE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 43 | 2019-01-23 | 2s1-b |  |  | NO
76592-22 | 76592 | B4PLED-5' 2"X11'11 1/2"X8' 4" | 22 | 1 | Regular | 2019-02-08 | 1900-01-04 | 7 | Machine Shop Started | Wrong part in BOM | TRUE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-23 | 2s1-b |  |  | NO
76659-1 | 76659 | TB2LED-4 | 1 | 1 | Regular | 2019-03-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76659-2 | 76659 | B3LED-4 | 2 | 1 | Regular | 2019-03-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76659-3 | 76659 | B3LED-4 | 3 | 1 | Regular | 2019-03-28 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76659-4 | 76659 | B3LED-4 | 4 | 1 | Regular | 2019-03-28 | 1899-12-31 | 12 | Scheduled/Released | PM wrong/missing info | TRUE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-10 | 76687 | LTLED-12 | 10 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-1 | 76687 | DIALED-22 | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76687-11 | 76687 | CLICK-4 | 11 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76687-12 | 76687 | CLICK-4 | 12 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76687-13 | 76687 | CLICK-8 | 13 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76687-2 | 76687 | LTLED-4 | 2 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-3 | 76687 | LTLED-8 | 3 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-4 | 76687 | LTLED-8 | 4 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-5 | 76687 | LTLED-8 | 5 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-6 | 76687 | LTLED-8 | 6 | 1 | Regular | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-7 | 76687 | LTLED-12 | 7 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-8 | 76687 | LTLED-12 | 8 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76687-9 | 76687 | LTLED-12 | 9 | 1 | Regular | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76692-1 | 76692 | B4LED-6 | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76692-2 | 76692 | B4LED-4 | 2 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76692-3 | 76692 | B4LED-4 | 3 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76704-1 | 76704 | B2LED-12' 6" | 1 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE |  | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
76762-10 | 76762 | B3LED-4'X4' | 10 | 1 | High Priority | 2019-02-18 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  |  |  | Done |  |  | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-B |  |  | NO | Material |  | Material
76762-4 | 76762 | B3LED-48 | 4 | 1 | High Priority | 2019-02-06 | 1900-01-15 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 17 | 2019-02-05 | 2X1-A(2S2-A BOARD) |  |  | NO
76762-5 | 76762 | B3LED-48 | 5 | 1 | High Priority | 2019-02-06 | 1900-01-15 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 17 | 2019-02-05 | 2X1-A(2S2-A BOARD) |  |  | NO
76762-6 | 76762 | B3LED-28 | 6 | 1 | High Priority | 2019-02-06 | 1900-01-08 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 17 | 2019-02-05 | 2X1-A(2S2-A BOARD) |  |  | NO
76762-7 | 76762 | B3LED-12'X20' | 7 | 1 | High Priority | 2019-02-06 | 1900-01-09 | 7 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2X1-A(2S2-A BOARD) |  |  | NO
76762-8 | 76762 | B3LED-9'X25' | 8 | 1 | High Priority | 2019-02-06 | 1900-01-09 | 7 | Machine Shop Started | Wrong part in BOM | TRUE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2X1-A(2S2-A BOARD) |  |  | NO
76762-9 | 76762 | B3LED-4'X4' | 9 | 1 | High Priority | 2019-02-18 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  |  |  | Done |  |  | NA | FALSE | FALSE |  |  | 2019-02-05 | 2T1-B |  |  | NO | Material |  | Material
76817-10 | 76817 | SCULPT-8 | 10 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping | Wrong info. In SD | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-1 | 76817 | SCULPT-4 | 1 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-11 | 76817 | SCULPT-18 | 11 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-12 | 76817 | SCULPT-18 | 12 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-13 | 76817 | SCULPT-14 | 13 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-14 | 76817 | SCULPT-8 | 14 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-2 | 76817 | SCULPT-14 | 2 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-3 | 76817 | SCULPT-22 | 3 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping | Mechanical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-4 | 76817 | SCULPT-6 | 4 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-5 | 76817 | SCULPT-6 | 5 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-6 | 76817 | SCULPT-8 | 6 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-7 | 76817 | SCULPT-16 | 7 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-8 | 76817 | SCULPT-16 | 8 | 1 | Regular | 2019-02-04 | 1900-01-01 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76817-9 | 76817 | SCULPT-8 | 9 | 1 | Regular | 2019-02-04 | 1899-12-31 | 4 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-30 11:39 | #8 | 2019-01-27 | 2s1-b |  |  | NO
76823-10 | 76823 | STENCL-20 | 10 | 1 | Priority | 2019-02-04 | 1900-01-02 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:33 | 13 | 2019-02-03 | 2V2-A | ToDo |  | NO
76823-1 | 76823 | ZEN-4 | 1 | 1 | Priority | 2019-02-04 | 1899-12-31 | 4 | Machine Shop Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 21 | 2019-01-31 |  |  |  | NO
76823-11 | 76823 | STENCL-STFD | 11 | 1 | Priority | 2019-02-04 | 1900-01-08 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:33 | 13 | 2019-02-03 | 2V2-A | ToDo |  | NO
76823-12 | 76823 | STENCL-STFD | 12 | 1 | Priority | 2019-02-04 | 1900-01-05 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:33 | 13 | 2019-02-03 | 2V2-A | ToDo |  | NO
76823-13 | 76823 | ZENSQ-12 | 13 | 1 | Priority | 2019-02-04 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-02-01 12:38 |  | 2019-01-25 | 2V2-A |  |  | OK
76823-3 | 76823 | ZEN-8 | 3 | 1 | Priority | 2019-02-04 | 1899-12-31 | 4 | Machine Shop Finished | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 21 | 2019-01-31 |  |  |  | NO
76823-4 | 76823 | ZEN-12 | 4 | 1 | Priority | 2019-02-04 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 21 | 2019-01-31 |  |  |  | NO
76823-5 | 76823 | ZEN-16 | 5 | 1 | Priority | 2019-02-04 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 21 | 2019-01-31 |  |  |  | NO
76823-6 | 76823 | ZEN-20 | 6 | 1 | Priority | 2019-02-04 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 08:23 | 21 | 2019-01-31 |  |  |  | NO
76823-7 | 76823 | STENCL-STFD | 7 | 1 | Priority | 2019-02-04 | 1900-01-03 | 7 | Wiring Started | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:32 | 13 | 2019-02-03 | 2V2-A | ToDo |  | NO
76823-8 | 76823 | STENCL-STFD | 8 | 1 | Priority | 2019-02-04 | 1900-01-04 | 7 | Wiring Started | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:32 | 13 | 2019-02-03 | 2V2-A | ToDo |  | NO
76823-9 | 76823 | STENCL-16 | 9 | 1 | Priority | 2019-02-04 | 1900-01-01 | 7 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:33 | 13 | 2019-02-03 | 2V2-A | ToDo |  | NO
76853-10 | 76853 | TB4LED-12 | 10 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-1 | 76853 | TB4LED-6 | 1 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-11 | 76853 | TB4LED-14 | 11 | 1 | Regular | 2019-02-22 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-12 | 76853 | TB4LED-18 | 12 | 1 | Regular | 2019-02-22 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-13 | 76853 | TB4LED-22 | 13 | 1 | Regular | 2019-02-22 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-14 | 76853 | TB4LED-24 | 14 | 1 | Regular | 2019-02-22 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-15 | 76853 | TB4LED-28 | 15 | 1 | Regular | 2019-02-22 | 1900-01-02 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-16 | 76853 | TB4LED-6 | 16 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-2 | 76853 | TB4LED-4 | 2 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-3 | 76853 | TB4LED-4 | 3 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-4 | 76853 | TB4LED-10 | 4 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-5 | 76853 | TB4LED-14 | 5 | 1 | Regular | 2019-02-22 | 1900-01-01 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-6 | 76853 | TB4LED-6 | 6 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-7 | 76853 | TB4LED-8 | 7 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-8 | 76853 | TB4LED-10 | 8 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76853-9 | 76853 | TB4LED-10 | 9 | 1 | Regular | 2019-02-22 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76884-1 | 76884 | NPI-18008-01 | 1 | 1 | Regular | 2019-02-06 | 1900-01-01 | 1 | Wiring Started | Mechanical issue | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-10 | 76910 | CLICK-8 | 10 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76910-11 | 76910 | CLICK-8 | 11 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76910-13 | 76910 | B3LED-3 | 13 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-16 | 76910 | B3LED-6 | 16 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-17 | 76910 | B3LED-6 | 17 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-18 | 76910 | GRAZE-8'6" | 18 | 1 | Priority | 2019-02-27 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-19 | 76910 | GRAZE-10'6" | 19 | 1 | Priority | 2019-02-27 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-20 | 76910 | GRAZE-11'6" | 20 | 1 | Priority | 2019-02-27 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-2 | 76910 | B3LED-3 | 2 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-21 | 76910 | B3LED-3 | 21 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-22 | 76910 | B3LED-3 | 22 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-23 | 76910 | B3LED-4 | 23 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-24 | 76910 | SCULPT-3 | 24 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-25 | 76910 | SCULPT-4 | 25 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-26 | 76910 | SCULPT-5 | 26 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-28 | 76910 | B3LED-3 | 28 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-3 | 76910 | B3LED-4 | 3 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-5 | 76910 | B3LED-18 | 5 | 1 | Priority | 2019-02-18 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76910-6 | 76910 | CLICK-4 | 6 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started | Shortage | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76910-7 | 76910 | CLICK-4 | 7 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76910-8 | 76910 | CLICK-6 | 8 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76910-9 | 76910 | CLICK-6 | 9 | 1 | Priority | 2019-02-18 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76914-1 | 76914 | B3LED-12 | 1 | 1 | Regular | 2019-03-20 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  |  | NA | TRUE | FALSE | 2019-02-05 10:34 | [5 empty] | NO | Material | +Cartridge | Material+Cartridge
76938-10 | 76938 | B4LED-4 | 10 | 1 | Regular | 2019-02-14 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76938-9 | 76938 | B4LED-4 | 9 | 1 | Regular | 2019-02-14 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76939-2 | 76939 | B2LED-12 | 2 | 1 | High Priority | 2019-02-12 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76939-3 | 76939 | B2LED-16 | 3 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76939-4 | 76939 | B2LED-34 | 4 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76943-1 | 76943 | STENCL-8' | 1 | 1 | High Priority | 2019-02-22 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76943-2 | 76943 | STENCL-8' | 2 | 1 | High Priority | 2019-02-22 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-1 | 76963 | SCULPT-SCRML | 1 | 1 | Regular | 2019-02-21 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-2 | 76963 | SCULPT-SCRML | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-3 | 76963 | SCULPT-SCRML | 3 | 1 | Regular | 2019-02-21 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-4 | 76963 | SCULPT-SCRML | 4 | 1 | Regular | 2019-02-21 | 1900-01-04 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-5 | 76963 | SCULPT-SCRML | 5 | 1 | Regular | 2019-02-21 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-6 | 76963 | SCULPT-SCRML | 6 | 1 | Regular | 2019-02-21 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-7 | 76963 | SCULPT-SCRML | 7 | 1 | Regular | 2019-02-21 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-8 | 76963 | SCULPT-SCRML | 8 | 1 | Regular | 2019-02-21 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76963-9 | 76963 | SCULPT-SCRML | 9 | 1 | Regular | 2019-02-21 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
76965-1 | 76965 | ARCLED-4 | 1 | 1 | Regular | 2019-02-20 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
76983-1 | 76983 | WWPRFK-16' | 1 | 1 | Regular | 2019-01-31 | 1900-01-01 | 12 | Machine Shop Finished | Shortage | FALSE | Yes |  | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-01-30 11:23 |  |  | 2T2-A |  |  | NO | Material | +Cartridge | Material+Cartridge
77011-1 | 77011 | WB4LED-W | 1 | 1 | High Priority | 2019-01-17 | 1899-12-31 | 18 | Given to Shipping | On Hold | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-16 15:52 | 44 | 2019-01-13 | 2s1-a |  |  | NO
77060-2 | 77060 | B3SLED-4 | 2 | 1 | Regular | 2019-02-06 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes |  |  |  | Done |  | Yes | NA | FALSE | FALSE |  | 23 | 2019-02-04 | 2v1-a |  |  | NO | Material |  | Material
77140-10 | 77140 | B4PLED-6 | 10 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-1 | 77140 | PERFKT-CCH | 1 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77140-11 | 77140 | B4PLED-8 | 11 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-12 | 77140 | B4PLED-9 | 12 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-13 | 77140 | B4PLED-11 | 13 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-14 | 77140 | B4PLED-15 | 14 | 1 | Regular | 2019-02-26 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-15 | 77140 | B2LED-14 | 15 | 1 | Regular | 2019-02-26 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-16 | 77140 | B2LED-15 | 16 | 1 | Regular | 2019-02-26 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-17 | 77140 | B2LED-10 | 17 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-18 | 77140 | B2LED-21 | 18 | 1 | Regular | 2019-02-26 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-2 | 77140 | B2LED-10 | 2 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-3 | 77140 | B2LED-12 | 3 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-4 | 77140 | B2LED-19 | 4 | 1 | Regular | 2019-02-26 | 1900-01-01 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-6 | 77140 | B2LED-4 | 6 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-7 | 77140 | B2LED-6 | 7 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-8 | 77140 | B2LED-8 | 8 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77140-9 | 77140 | WWPRFK-10 | 9 | 1 | Regular | 2019-02-26 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77142-1 | 77142 | ZEN-8 | 1 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE |  |  |  | 2t2-b |  |  | NO | Material |  | Material
77142-2 | 77142 | STNCLS-6 | 2 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2t2-b |  |  | NO | Material | +Cartridge | Material+Cartridge
77149-1 | 77149 | CLICK-6' | 1 | 1 | Regular | 2019-02-19 | 1899-12-31 | 18 | Machine Shop Started | Shortage | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77149-2 | 77149 | CLICK-8' | 2 | 1 | Regular | 2019-02-19 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77149-3 | 77149 | CLICK-14' | 3 | 1 | Regular | 2019-02-19 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77175-143 | 77175 | WWPRFK-4 | 143 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:22 |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-144 | 77175 | WWPRFK-4 | 144 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:22 |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-145 | 77175 | B3LED-12 | 145 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
77175-146 | 77175 | WWPRFK-4 | 146 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-147 | 77175 | WWPRFK-4 | 147 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-148 | 77175 | WWPRFK-4 | 148 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-149 | 77175 | ACCENT-18 | 149 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-150 | 77175 | WWPRFK-4 | 150 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-151 | 77175 | B3LED-12 | 151 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-152 | 77175 | WWPRFK-4 | 152 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-153 | 77175 | B3LED-16 | 153 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-17 | 77175 | B3SLED-4 | 17 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished | Others | TRUE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 16 | 2019-02-05 |  |  |  | NO
77175-18 | 77175 | B3SLED-6 | 18 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished | Others | TRUE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 16 | 2019-02-05 |  |  |  | NO
77175-19 | 77175 | WWPRFK-8 | 19 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:22 | 33 | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-20 | 77175 | WWPRFK-4 | 20 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:22 | 33 | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-21 | 77175 | ACCENT-28 | 21 | 1 | Regular | 2019-02-04 | 1900-01-02 | 18 | Machine Shop Started |  | FALSE |  |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | 42 | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-22 | 77175 | ACCENT-18 | 22 | 1 | Regular | 2019-02-04 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | 42 | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-23 | 77175 | B3LED-12 | 23 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77175-24 | 77175 | SCULPT-4 | 24 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #9 | 2019-01-30 |  |  |  | NO
77175-25 | 77175 | STENCL-BLK | 25 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | No | TRUE | FALSE | 2019-02-05 10:21 |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-26 | 77175 | SCULPT-16 | 26 | 1 | Regular | 2019-02-04 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #9 | 2019-01-30 |  |  |  | NO
77175-27 | 77175 | B3SLED-4 | 27 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished | Others | TRUE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77175-28 | 77175 | B3SLED-6 | 28 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77175-29 | 77175 | WWPRFK-8 | 29 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:22 |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-30 | 77175 | WWPRFK-4 | 30 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:22 |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-31 | 77175 | ACCENT-28 | 31 | 1 | Regular | 2019-02-04 | 1900-01-02 | 18 | Machine Shop Started |  | FALSE |  |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-32 | 77175 | ACCENT-18 | 32 | 1 | Regular | 2019-02-04 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-33 | 77175 | SCULPT-4 | 33 | 1 | Regular | 2019-02-04 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #9 | 2019-01-30 |  |  |  | NO
77175-34 | 77175 | STENCL-BLK | 34 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Machine Shop Finished | Others | TRUE |  |  | Done | Done | Done |  | Yes | No | TRUE | FALSE | 2019-02-05 10:22 |  | 2019-02-05 | 2S1-B |  |  | NO | Material |  | Material
77175-35 | 77175 | B3SLED-4 | 35 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-36 | 77175 | B3SLED-6 | 36 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-37 | 77175 | WWPRFK-8 | 37 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-38 | 77175 | WWPRFK-4 | 38 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-39 | 77175 | ACCENT-28 | 39 | 1 | Regular | 2019-02-14 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-40 | 77175 | ACCENT-18 | 40 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-41 | 77175 | B3LED-12 | 41 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-42 | 77175 | SCULPT-4 | 42 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-43 | 77175 | STENCL-BLK | 43 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-45 | 77175 | B3SLED-4 | 45 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-46 | 77175 | B3SLED-6 | 46 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-47 | 77175 | WWPRFK-8 | 47 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-48 | 77175 | WWPRFK-4 | 48 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-49 | 77175 | ACCENT-18 | 49 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-50 | 77175 | ACCENT-28 | 50 | 1 | Regular | 2019-02-14 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-51 | 77175 | WWPRFK-20 | 51 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-52 | 77175 | SCULPT-4 | 52 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-53 | 77175 | STENCL-BLK | 53 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-54 | 77175 | B3SLED-4 | 54 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-55 | 77175 | B3SLED-6 | 55 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-56 | 77175 | WWPRFK-8 | 56 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-57 | 77175 | WWPRFK-4 | 57 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-59 | 77175 | B3LED-12 | 59 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-60 | 77175 | SCULPT-4 | 60 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-61 | 77175 | STENCL-BLK | 61 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-62 | 77175 | SCULPT-16 | 62 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-63 | 77175 | B3SLED-4 | 63 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-64 | 77175 | B3SLED-6 | 64 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-65 | 77175 | WWPRFK-8 | 65 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-66 | 77175 | WWPRFK-4 | 66 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-68 | 77175 | ACCENT-18 | 68 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-69 | 77175 | SCULPT-4 | 69 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-70 | 77175 | STENCL-BLK | 70 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material | +Cartridge | Material+Cartridge
77175-71 | 77175 | B3SLED-4 | 71 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-72 | 77175 | WWPRFK-8 | 72 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-73 | 77175 | WWPRFK-12 | 73 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-74 | 77175 | WWPRFK-4 | 74 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-75 | 77175 | ACCENT-28 | 75 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-76 | 77175 | ACCENT-18 | 76 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-77 | 77175 | B3SLED-8 | 77 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-78 | 77175 | B3LED-12 | 78 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-79 | 77175 | WWPRFK-20 | 79 | 1 | Regular | 2019-02-20 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-80 | 77175 | SCULPT-4 | 80 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77175-81 | 77175 | STENCL-BLK | 81 | 1 | Regular | 2019-02-20 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77180-10 | 77180 | SCULPT-4' | 10 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #7 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-1 | 77180 | SCULPT-4' | 1 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-11 | 77180 | SCULPT-8' | 11 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #7 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-12 | 77180 | SCULPT-8' | 12 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #7 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-2 | 77180 | SCULPT-8' | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-3 | 77180 | SCULPT-8' | 3 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-4 | 77180 | SCULPT-16' | 4 | 1 | Regular | 2019-02-12 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-5 | 77180 | SCULPT-28' | 5 | 1 | Regular | 2019-02-12 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-6 | 77180 | SCULPT-4' | 6 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started | Shortage | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-7 | 77180 | SCULPT-8' | 7 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-8 | 77180 | SCULPT-8' | 8 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #10 | 2019-02-01 |  |  |  | NO | Material |  | Material
77180-9 | 77180 | SCULPT-4' | 9 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #7 | 2019-02-01 |  |  |  | NO | Material |  | Material
77187-1 | 77187 | SCULPT-40' | 1 | 1 | Regular | 2019-02-07 | 1900-01-03 | 12 | Machine Shop Started | Missing info. In SD | TRUE | Yes | Yes |  |  | Done |  | Yes | Yes | FALSE | FALSE |  | #4 | 2019-02-04 | 2v1-b |  |  | NO
77187-2 | 77187 | SCULPT-20' | 2 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Machine Shop Started | Missing info. In SD | TRUE | Yes | Yes |  |  | Done |  | Yes | Yes | FALSE | FALSE |  | #4 | 2019-02-04 | 2v1-b |  |  | NO
77195-1 | 77195 | SKETCH-AL(15' 8 1/2") | 1 | 1 | Regular | 2019-03-05 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77207-10 | 77207 | B2LED-6 | 10 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-1 | 77207 | TB2LED-16' | 1 | 1 | Regular | 2019-02-06 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 | 49 | 2019-01-29 |  |  |  | NO
77207-11 | 77207 | B2LED-6 | 11 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-12 | 77207 | B2LED-8 | 12 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-13 | 77207 | B2LED-8 | 13 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-14 | 77207 | B3LED-6 | 14 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-15 | 77207 | B3LED-8 | 15 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-16 | 77207 | B3LED-42' | 16 | 1 | Regular | 2019-02-06 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-17 | 77207 | B3PLED-4' 8" | 17 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-18 | 77207 | B3PLED-7' 4" | 18 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-19 | 77207 | B3PLED-12' | 19 | 1 | Regular | 2019-02-06 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-20 | 77207 | B3PLED-20' | 20 | 1 | Regular | 2019-02-06 | 1900-01-01 | 4 | Machine Shop Started | Others | TRUE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO
77207-2 | 77207 | TB2LED-30' | 2 | 1 | Regular | 2019-02-06 | 1900-01-02 | 4 | Machine Shop Finished | Wrong info. In SD | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 | 49 | 2019-01-29 |  |  |  | NO
77207-3 | 77207 | B2SLED-2 | 3 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 | 49 | 2019-01-29 |  |  |  | NO
77207-4 | 77207 | B2SLED-4 | 4 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 | 49 | 2019-01-29 |  |  |  | NO
77207-5 | 77207 | B2SLED-6 | 5 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 | 49 | 2019-01-29 |  |  |  | NO
77207-6 | 77207 | B2SLED-8 | 6 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-7 | 77207 | B2SLED-8 | 7 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-8 | 77207 | B2LED-3 | 8 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77207-9 | 77207 | B2LED-4 | 9 | 1 | Regular | 2019-02-06 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 13:17 |  | 2019-01-29 |  |  |  | NO
77211-1 | 77211 | B4LED-8 | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:27 | 1 | 2019-02-05 | 2V1-A |  |  | NO
77211-2 | 77211 | B4LED-4 | 2 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:27 | 1 | 2019-02-05 | 2V1-A |  |  | NO
77249-10 | 77249 | EDGE2-6 | 10 | 1 | High Priority | 2019-01-24 | 1899-12-31 | 4 | Machine Shop Started | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 20 | 2019-01-22 |  |  |  | NO
77249-1 | 77249 | SCULPT-SCML | 1 | 1 | High Priority | 2019-01-18 | 1899-12-31 | 1 | Machine Shop Finished | Others | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-28 09:44 | #1 | 2019-01-17 |  |  |  | NO
77249-11 | 77249 | EDGE2-6 | 11 | 1 | High Priority | 2019-01-24 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 20 | 2019-01-22 |  |  |  | NO
77249-15 | 77249 | EDGE2-4 | 15 | 1 | High Priority | 2019-01-24 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 20 | 2019-01-22 |  |  |  | NO
77249-2 | 77249 | STNCLS-STSFF | 2 | 1 | High Priority | 2019-01-10 | 1900-01-06 | 1 | Machine Shop Finished | Missing info. In SD | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-11 10:01 |  | 2019-01-29 |  | ToDo |  | NO
77249-3 | 77249 | EDGE2-8 | 3 | 1 | High Priority | 2019-01-24 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 20 | 2019-01-22 |  |  |  | NO
77249-4 | 77249 | SCULPT-6X8 | 4 | 1 | High Priority | 2019-01-18 | 1900-01-03 | 1 | Machine Shop Finished | Wrong info. In SD | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-28 09:44 | #1 | 2019-01-17 | 2w1-b |  |  | NO
77293-1 | 77293 | WB4LED-8 | 1 | 1 | Regular | 2019-02-14 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-1 | 77314 | STENCL-STFD | 1 | 1 | Regular | 2019-02-22 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-2 | 77314 | STENCL-STFD | 2 | 1 | Regular | 2019-02-22 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-3 | 77314 | STENCL-STFD | 3 | 1 | Regular | 2019-02-22 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-4 | 77314 | B2SLED-4 | 4 | 1 | Regular | 2019-02-22 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-5 | 77314 | SCULPT-4 | 5 | 1 | Regular | 2019-02-22 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-6 | 77314 | STENCL-STFD | 6 | 1 | Regular | 2019-02-22 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77314-7 | 77314 | STENCL-5 | 7 | 1 | Regular | 2019-02-22 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77323-1 | 77323 | B4LED-10 | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77323-2 | 77323 | B4LED-2 | 2 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77323-3 | 77323 | B4LED-12 | 3 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77334-2 | 77334 | SCULPT-5 | 2 | 1 | Priority | 2019-02-28 | 1899-12-31 | 0 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77334-3 | 77334 | SCULPT-2 | 3 | 1 | Priority | 2019-02-28 | 1899-12-31 | 0 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77334-4 | 77334 | SCULPT-5 | 4 | 1 | Priority | 2019-02-28 | 1899-12-31 | 0 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77334-5 | 77334 | SCULPT-5 | 5 | 1 | Priority | 2019-02-28 | 1899-12-31 | 0 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77351-1 | 77351 | B4LED-24' 0" | 1 | 1 | Regular | 2019-02-15 | 1900-01-01 | 12 | Machine Shop Finished |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77356-10 | 77356 | B4LED-8' 0" | 10 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-1 | 77356 | B4LED-2' 0" | 1 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-11 | 77356 | B4LED-9' 0" | 11 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-12 | 77356 | B4LED-10' 0" | 12 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-13 | 77356 | B4LED-11' 0" | 13 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-14 | 77356 | B4LED-12' 0" | 14 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-15 | 77356 | B4LED-13' 0" | 15 | 1 | Regular | 2019-02-11 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-16 | 77356 | B4LED-14' 0" | 16 | 1 | Regular | 2019-02-11 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-17 | 77356 | B4LED-13' 0" | 17 | 1 | Regular | 2019-02-11 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-18 | 77356 | B4LED-15' 0" | 18 | 1 | Regular | 2019-02-11 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-19 | 77356 | B4LED-15' 0" | 19 | 1 | Regular | 2019-02-11 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-20 | 77356 | B4LED-24' 0" | 20 | 1 | Regular | 2019-02-11 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-2 | 77356 | B4LED-4' 0" | 2 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-21 | 77356 | B4LED-28' 0" | 21 | 1 | Regular | 2019-02-11 | 1900-01-02 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-22 | 77356 | B4LED-33' 0" | 22 | 1 | Regular | 2019-02-11 | 1900-01-02 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-23 | 77356 | B4LED-52' 0" | 23 | 1 | Regular | 2019-02-11 | 1900-01-04 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-25 | 77356 | B4LED-10' 0" | 25 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-3 | 77356 | B4LED-2' 0" | 3 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-4 | 77356 | B4LED-8' 0" | 4 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-5 | 77356 | WB4LED-4' 0" | 5 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-6 | 77356 | B4LED-4' 0" | 6 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-7 | 77356 | B4LED-5' 0" | 7 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-8 | 77356 | B4LED-6' 0" | 8 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77356-9 | 77356 | B4LED-7' 0" | 9 | 1 | Regular | 2019-02-11 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77367-10 | 77367 | B4LED-6' | 10 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-1 | 77367 | B4LED-4' | 1 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-11 | 77367 | WB4LED-4' | 11 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-12 | 77367 | B4LED-2' | 12 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-13 | 77367 | B4LED-2' | 13 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-2 | 77367 | B4LED-10' | 2 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-3 | 77367 | B4LED-20' | 3 | 1 | Regular | 2019-02-25 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-4 | 77367 | B4LED-4' | 4 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-6 | 77367 | B4LED-10' | 6 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-7 | 77367 | B4LED-12' | 7 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-8 | 77367 | B4LED-6' | 8 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77367-9 | 77367 | B4LED-8' | 9 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77370-1 | 77370 | WB4LED-8' 0" | 1 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77370-2 | 77370 | WDILED-WBDIWLED | 2 | 1 | High Priority | 2019-02-15 | 1900-01-01 | 4 | Scheduled/Released | PM wrong/missing info | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77375-1 | 77375 | B3PLED-15'0" | 1 | 1 | Regular | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 45 | 2019-01-28 | 2w1-a |  |  | NO | Material |  | Material
77375-2 | 77375 | B3PLED-21'0" | 2 | 1 | Regular | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 45 | 2019-01-28 | 2w1-a |  |  | NO | Material |  | Material
77375-3 | 77375 | B3PLED-23'0" | 3 | 1 | Regular | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 45 | 2019-01-28 | 2w1-a |  |  | NO | Material |  | Material
77375-5 | 77375 | B3PLED-7' 5" | 5 | 1 | Regular | 2019-02-12 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 45 | 2019-01-28 | 2w1-a |  |  | NO | Material |  | Material
77375-6 | 77375 | B2SLED-95'0" | 6 | 1 | Regular | 2019-02-12 | 1900-01-07 | 4 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-28 | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
77375-7 | 77375 | B2LED-105'0" | 7 | 1 | Regular | 2019-02-12 | 1900-01-08 | 4 | Machine Shop Started | Shortage | FALSE | Yes |  |  | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
77375-8 | 77375 | TB2LED-3'5" | 8 | 1 | Regular | 2019-02-12 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  |  | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 45 | 2019-01-28 | 2w1-a |  |  | NO | Material |  | Material
77378-1 | 77378 | B3LED-58' 1/2" | 1 | 1 | Priority | 2019-02-06 | 1900-01-09 | 12 | Machine Shop Started | Mechanical issue | FALSE | Yes |  |  |  | Done |  | Yes | Yes | FALSE | FALSE |  | 22 | 2019-01-29 |  |  |  | NO | Material |  | Material
77393-1 | 77393 | STENCL-STFC | 1 | 1 | Regular | 2019-01-29 | 1900-01-05 | 1 | Machine Shop Finished | Others | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
77417-1 | 77417 | B3LED-34 | 1 | 1 | Regular | 2019-02-27 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77417-2 | 77417 | B3LED-32 | 2 | 1 | Regular | 2019-02-27 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77432-1 | 77432 | B2LED-4 | 1 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77432-2 | 77432 | B2LED-6 | 2 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77432-3 | 77432 | B2LED-24'6" | 3 | 1 | High Priority | 2019-02-13 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Yes |  | Yes | Yes | TRUE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77432-4 | 77432 | B2LED-6 | 4 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started | Shortage | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77432-5 | 77432 | B2LED-6 | 5 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77432-6 | 77432 | B2LED-8 | 6 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77432-7 | 77432 | SLMLED-8 | 7 | 1 | High Priority | 2019-02-13 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO
77440-1 | 77440 | STENCL-STFC | 1 | 1 | Regular | 2019-02-01 | 1900-01-05 | 7 | Given to Shipping | Wrong part in BOM | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 09:39 |  | 2019-02-05 | 2s2-a |  |  | NO
77441-1 | 77441 | SKVLED-22 | 1 | 1 | Regular | 2019-03-08 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77441-2 | 77441 | SKVLED-22 | 2 | 1 | Regular | 2019-03-08 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77456-1 | 77456 | B6LED-2' 0" | 1 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released | PM wrong/missing info | TRUE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-12 | 77456 | B6LED-12' | 12 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-13 | 77456 | B6LED-12' | 13 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-14 | 77456 | B6LED-12' | 14 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-2 | 77456 | B6LED-10' 0" | 2 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-3 | 77456 | B6LED-16' 0" | 3 | 1 | Regular | 2019-02-26 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-4 | 77456 | B6LED-4' 0" | 4 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-5 | 77456 | B6LED-4' 0" | 5 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-6 | 77456 | B6LED-8' 0" | 6 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-7 | 77456 | B6LED-8' 0" | 7 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77456-8 | 77456 | B6LED-8' 0" | 8 | 1 | Regular | 2019-02-26 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77458-1 | 77458 | B4LED-352' 0" | 1 | 1 | Regular | 2019-02-25 | 1900-02-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77479-1 | 77479 | B3LED-12' 0" | 1 | 1 | Regular | 2019-04-15 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77497-11 | 77497 | SKLPTP-170" | 11 | 1 | High Priority | 2019-03-05 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77497-12 | 77497 | SKLPTP-168" | 12 | 1 | High Priority | 2019-03-05 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-10 | 77526 | TB2LED-4' 0" | 10 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-1 | 77526 | SCULPT-4' 0" | 1 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-11 | 77526 | TB2LED-6' 0" | 11 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-12 | 77526 | TB2LED-8' 0" | 12 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-13 | 77526 | TB2LED-8' 0" | 13 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-14 | 77526 | TB2LED-16' 0" | 14 | 1 | High Priority | 2019-02-20 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-15 | 77526 | TB2LED-16' 0" | 15 | 1 | High Priority | 2019-02-20 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-16 | 77526 | AIRLED-4' 0" | 16 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-2 | 77526 | SCULPT-8' 0" | 2 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-3 | 77526 | SCULPT-16' 0" | 3 | 1 | High Priority | 2019-02-20 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-4 | 77526 | SCULPT-16' 0" | 4 | 1 | High Priority | 2019-02-20 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-5 | 77526 | B4LED-4' 0" | 5 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-6 | 77526 | B4LED-6' 0" | 6 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-7 | 77526 | B4LED-8' 0" | 7 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-8 | 77526 | B4LED-12' 0" | 8 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77526-9 | 77526 | TB2LED-4' 0" | 9 | 1 | High Priority | 2019-02-20 | 1899-12-31 | 4 | Machine Shop Started | Shortage | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77560-1 | 77560 | WB4LED-8' 0" | 1 | 1 | Regular | 2019-02-06 | 1899-12-31 | 15 | Machine Shop Finished | Others | TRUE |  | Yes | Yes | Yes | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 07:11 | 34 | 2019-01-28 | 2w1-b |  |  | NO
77602-1 | 77602 | SLMLED-16' 0" | 1 | 1 | Regular | 2019-02-22 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77607-1 | 77607 | B2SLED-19 | 1 | 1 | Regular | 2019-02-08 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2V1-B |  |  | OK
77607-2 | 77607 | B2SLED-21 | 2 | 1 | Regular | 2019-02-08 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2V1-B |  |  | OK
77607-3 | 77607 | B2SLED-35 | 3 | 1 | Regular | 2019-02-08 | 1900-01-02 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2V1-B |  |  | OK
77607-4 | 77607 | B2SLED-38 | 4 | 1 | Regular | 2019-02-08 | 1900-01-03 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2V1-B |  |  | OK
77607-5 | 77607 | B2LED-41 | 5 | 1 | Regular | 2019-02-08 | 1900-01-04 | 4 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77607-6 | 77607 | B2SLED-4 | 6 | 1 | Regular | 2019-02-08 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Yes |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2V1-B |  |  | OK
77608-1 | 77608 | SCULPT-SCML | 1 | 1 | High Priority | 2019-01-31 | 1899-12-31 | 12 | Wiring Started | Others | TRUE | Yes |  | Done | Done | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-28 | 2w1-a |  |  | NO | Material |  | Material
77615-10 | 77615 | B4LED-24 | 10 | 1 | Regular | 2019-02-07 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77615-1 | 77615 | TB2LED-12 | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE |  | 31 | 2019-02-05 | 2s1-a |  |  | NO
77615-11 | 77615 | PRMLED-4 | 11 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE |  | 20 | 2019-02-05 | 2s1-a |  |  | NO
77615-12 | 77615 | PRMLED-4 | 12 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE |  | 10 | 2019-02-05 | 2s1-a |  |  | NO
77615-13 | 77615 | WB4LED-6 | 13 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | No | TRUE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77615-2 | 77615 | TB2LED-16 | 2 | 1 | Regular | 2019-02-07 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE |  | 31 | 2019-02-05 | 2s1-a |  |  | NO
77615-3 | 77615 | TB2LED-20 | 3 | 1 | Regular | 2019-02-07 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE |  | 31 | 2019-02-05 | 2s1-a |  |  | NO
77615-4 | 77615 | CLICK-6 | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
77615-5 | 77615 | B4LED-4 | 5 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77615-6 | 77615 | B4LED-8 | 6 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77615-7 | 77615 | B4LED-12 | 7 | 1 | Regular | 2019-02-07 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77615-8 | 77615 | B4LED-16 | 8 | 1 | Regular | 2019-02-07 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77615-9 | 77615 | B4LED-20 | 9 | 1 | Regular | 2019-02-07 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO
77630-1 | 77630 | SCULPT-TR45X2 | 1 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE | [6 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77630-2 | 77630 | AIRLED-4 | 2 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  | Done |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77630-3 | 77630 | AIRLED-4 | 3 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  | Done |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-10 | 77636 | SCULPT-6' | 10 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-1 | 77636 | SCULPT-2' | 1 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-11 | 77636 | SCULPT-8' | 11 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-12 | 77636 | SCULPT-8' | 12 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-14 | 77636 | B4LED-6 | 14 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-16 | 77636 | SCULPT-2' | 16 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-17 | 77636 | SCULPT-4' | 17 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-18 | 77636 | SCULPT-4' | 18 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-19 | 77636 | SCULPT-4' | 19 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-20 | 77636 | SCULPT-4' | 20 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-2 | 77636 | SCULPT-4' | 2 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-21 | 77636 | SCULPT-4' | 21 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-22 | 77636 | SCULPT-4' | 22 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-23 | 77636 | SCULPT-6' | 23 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-24 | 77636 | SCULPT-6' | 24 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-25 | 77636 | SCULPT-6' | 25 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-26 | 77636 | SCULPT-6' | 26 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-27 | 77636 | SCULPT-8' | 27 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-28 | 77636 | SCULPT-8' | 28 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-30 | 77636 | B4LED-6 | 30 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-3 | 77636 | SCULPT-4' | 3 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-32 | 77636 | SCULPT-2' | 32 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-33 | 77636 | SCULPT-4' | 33 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-34 | 77636 | SCULPT-4' | 34 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-35 | 77636 | SCULPT-4' | 35 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-36 | 77636 | SCULPT-4' | 36 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-37 | 77636 | SCULPT-4' | 37 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-38 | 77636 | SCULPT-6' | 38 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-39 | 77636 | SCULPT-6' | 39 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-40 | 77636 | SCULPT-6' | 40 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-4 | 77636 | SCULPT-4' | 4 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-41 | 77636 | SCULPT-6' | 41 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-42 | 77636 | SCULPT-6' | 42 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-43 | 77636 | SCULPT-8' | 43 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-44 | 77636 | SCULPT-8' | 44 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-46 | 77636 | B4LED-6 | 46 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-5 | 77636 | SCULPT-4' | 5 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-6 | 77636 | SCULPT-4' | 6 | 1 | Regular | 2019-03-06 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-7 | 77636 | SCULPT-6' | 7 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-8 | 77636 | SCULPT-6' | 8 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77636-9 | 77636 | SCULPT-6' | 9 | 1 | Regular | 2019-02-26 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77693-10 | 77693 | SCULPT-8'0" | 10 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-1 | 77693 | SCULPT-4'0" | 1 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-11 | 77693 | SCULPT-4'0" | 11 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-2 | 77693 | SCULPT-6'0" | 2 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-3 | 77693 | SCULPT-8'0" | 3 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-4 | 77693 | AIRLED-4'0" | 4 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | [5 empty] | NO |  | +Cartridge | +Cartridge
77693-5 | 77693 | SCULPT-4'0" | 5 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-6 | 77693 | SCULPT-6'0" | 6 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-7 | 77693 | SCULPT-8'0" | 7 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-8 | 77693 | SCULPT-4'0" | 8 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77693-9 | 77693 | SCULPT-6'0" | 9 | 1 | Regular | 2019-02-05 | 1899-12-31 | 18 | Wiring Started |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 17:14 | #7 | 2019-01-27 |  |  |  | NO
77741-10 | 77741 | SCULPT-16 | 10 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | Yes | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 | 2t1-a |  |  | NO
77741-11 | 77741 | SCULPT-12 | 11 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 | 2t1-a |  |  | NO
77741-12 | 77741 | SCULPT-12 | 12 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 | 2t1-a |  |  | NO
77741-13 | 77741 | SCULPT-12 | 13 | 1 | Regular | 2019-02-05 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 | 2t1-a |  |  | NO
77741-15 | 77741 | SCULPT-5 | 15 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 | 2t1-a |  |  | NO
77741-17 | 77741 | SCULPT-30 | 17 | 1 | Regular | 2019-02-05 | 1900-01-02 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 |  |  |  | NO
77741-18 | 77741 | SCULPT-4' | 18 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 |  |  |  | NO
77741-19 | 77741 | SCULPT-8' | 19 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 |  |  |  | NO
77741-5 | 77741 | B3LED-4' | 5 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | Yes | FALSE | FALSE |  | 30 | 2019-02-01 |  |  |  | NO
77741-6 | 77741 | B3LED-5' | 6 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | Yes | FALSE | FALSE |  | 30 | 2019-02-01 |  |  |  | NO
77741-8 | 77741 | SCULPT-12' | 8 | 1 | Regular | 2019-02-05 | 1899-12-31 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 |  |  |  | NO
77741-9 | 77741 | SCULPT-12' | 9 | 1 | Regular | 2019-02-05 | 1900-01-02 | 1 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | #5 | 2019-01-31 |  |  |  | NO
77765-1 | 77765 | SCULPT-9'0" | 1 | 1 | Regular | 2019-02-07 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77765-2 | 77765 | SCULPT-26'4" | 2 | 1 | Regular | 2019-02-07 | 1900-01-04 | 1 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77765-22 | 77765 | SCULPT-26'4" | 22 | 1 | Regular | 2019-02-07 | 1900-01-04 | 1 | Machine Shop Started | Missing info. In SD | TRUE | Yes | Yes | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77765-4 | 77765 | AULED-22 | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
77765-5 | 77765 | SCULPT-6'10" | 5 | 1 | Regular | 2019-02-07 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
77784-1 | 77784 | B3LED-12' | 1 | 1 | Regular | 2019-03-15 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-1 | 77790 | DIALED-22 | 1 | 1 | Regular | 2019-02-22 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77790-2 | 77790 | WB4LED-4 | 2 | 1 | Regular | 2019-02-22 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-3 | 77790 | B3LED-12' | 3 | 1 | Regular | 2019-02-22 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-4 | 77790 | B4LED-4 | 4 | 1 | Regular | 2019-02-22 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-5 | 77790 | B4LED-6 | 5 | 1 | Regular | 2019-02-22 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-6 | 77790 | B4LED-8 | 6 | 1 | Regular | 2019-02-22 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-7 | 77790 | B4LED-16 | 7 | 1 | Regular | 2019-02-22 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77790-8 | 77790 | B4LED-22 | 8 | 1 | Regular | 2019-02-22 | 1900-01-01 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-14 | 77793 | B4LED-27' 1" | 14 | 1 | High Priority | 2019-02-25 | 0 | 4 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-22 | 77793 | B4LED-78' 2 3/8" | 22 | 1 | High Priority | 2019-02-25 | 1900-01-13 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-23 | 77793 | B4LED-78' 1.5" | 23 | 1 | High Priority | 2019-02-25 | 1900-01-13 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-26 | 77793 | B4LED-96' 3/4" | 26 | 1 | High Priority | 2019-02-25 | 1900-01-16 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-30 | 77793 | B4LED-233' 8" | 30 | 1 | High Priority | 2019-02-25 | 1900-02-07 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-31 | 77793 | B4LED-234' 6 1/2" | 31 | 1 | High Priority | 2019-02-25 | 1900-02-08 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-33 | 77793 | B4LED-70' 4 1/2" | 33 | 1 | High Priority | 2019-02-25 | 1900-01-11 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-34 | 77793 | B4LED-70' 6" | 34 | 1 | High Priority | 2019-02-25 | 1900-01-11 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-35 | 77793 | B4LED-70' 2 1/2" | 35 | 1 | High Priority | 2019-02-25 | 1900-01-11 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-36 | 77793 | B4LED-68' 11 1/2" | 36 | 1 | High Priority | 2019-02-25 | 1900-01-11 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77793-37 | 77793 | B4LED-96' 8 7/8" | 37 | 1 | High Priority | 2019-02-25 | 1900-01-16 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77806-1 | 77806 | STNCLS-5 | 1 | 1 | Priority | 2019-02-14 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
77808-1 | 77808 | PRMLED-4 | 1 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Order UnShipped |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 09:20 | 18 | 2019-01-29 | 1w1-a |  |  | NO
77808-2 | 77808 | PRMLED-4 | 2 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Order UnShipped |  | FALSE | [7 empty] | Yes | TRUE | FALSE | 2019-01-31 09:20 |  |  | 2w2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
77833-1 | 77833 | WWPRFK-4 | 1 | 1 | Regular | 2019-02-25 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77833-2 | 77833 | WWPRFK-8 | 2 | 1 | Regular | 2019-02-25 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77840-1 | 77840 | SCULPT-4' | 1 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77853-1 | 77853 | SLMLED-4 | 1 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77853-2 | 77853 | SLMLED-8 | 2 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77853-3 | 77853 | SLMLED-12 | 3 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77853-4 | 77853 | SLMLED-4 | 4 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77853-5 | 77853 | SLMLED-8 | 5 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 4 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-10 | 77854 | B2LED-28' 2 1/2" | 10 | 1 | High Priority | 2019-02-27 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-1 | 77854 | B3LED-4' | 1 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-12 | 77854 | B3PLED-10' 4 1/4" | 12 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-13 | 77854 | B3PLED-15' 1/4" | 13 | 1 | High Priority | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-14 | 77854 | B3PLED-109" | 14 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-15 | 77854 | B3PLED-14'5" | 15 | 1 | High Priority | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-16 | 77854 | B2LED-25' 6 1/2" | 16 | 1 | High Priority | 2019-02-27 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-17 | 77854 | TB3LED-UNV | 17 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-18 | 77854 | SLMLED-5' | 18 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-19 | 77854 | SCULPT-72' | 19 | 1 | High Priority | 2019-02-27 | 1900-01-07 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-20 | 77854 | SKLPTP-43' 4 3/8" | 20 | 1 | High Priority | 2019-02-27 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-2 | 77854 | SKLPTP-13' 7 1/2" | 2 | 1 | High Priority | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-21 | 77854 | SKLPTP-9' 5 3/4" | 21 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-22 | 77854 | SKLPTP-11' 10 5/8" | 22 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-23 | 77854 | SKLPTP-69' 4 7/8" | 23 | 1 | High Priority | 2019-02-27 | 1900-01-05 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-24 | 77854 | B3PLED-9' 7 5/8" | 24 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-25 | 77854 | B3PLED-8' 8 3/4" | 25 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-26 | 77854 | B3PLED-114 7/8" | 26 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-27 | 77854 | B3PLED-111" | 27 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-28 | 77854 | B3PLED-115 1/8" | 28 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-29 | 77854 | B3PLED-115" | 29 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-30 | 77854 | B3PLED-115 3/8" | 30 | 1 | High Priority | 2019-02-27 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77854-3 | 77854 | SKLPTP-21' 8" | 3 | 1 | High Priority | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-6 | 77854 | SKLPTP-64' 2 3/4" | 6 | 1 | High Priority | 2019-02-27 | 1900-01-05 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-7 | 77854 | SKLPTP-139' 5 3/8" | 7 | 1 | High Priority | 2019-02-27 | 1900-01-11 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-8 | 77854 | B2LED-13' 7 1/2" | 8 | 1 | High Priority | 2019-02-27 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77854-9 | 77854 | B2LED-24' 1" | 9 | 1 | High Priority | 2019-02-27 | 1900-01-02 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77856-1 | 77856 | B4LED-8' | 1 | 1 | Regular | 2019-03-20 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77856-2 | 77856 | B4LED-4' | 2 | 1 | Regular | 2019-03-20 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77868-1 | 77868 | PERFKT-CCWH | 1 | 1 | Regular | 2019-02-12 | 1900-01-21 | 4 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
77868-2 | 77868 | PERFKT-CCH | 2 | 1 | Regular | 2019-02-12 | 1900-01-12 | 4 | Machine Shop Started |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
77891-1 | 77891 | STNCLS-10' | 1 | 1 | Regular | 2019-02-14 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2v2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
77892-1 | 77892 | PERFKT-CCL | 1 | 1 | Regular | 2019-02-18 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77892-2 | 77892 | PERFKT-CCL | 2 | 1 | Regular | 2019-02-18 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77892-3 | 77892 | PERFKT-CCL | 3 | 1 | Regular | 2019-02-18 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-10 | 77900 | SLMLED-36' | 10 | 1 | Regular | 2019-02-21 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-1 | 77900 | SLMLED-4 | 1 | 1 | Regular | 2019-02-21 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-2 | 77900 | SLMLED-4 | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-3 | 77900 | SLMLED-4 | 3 | 1 | Regular | 2019-02-21 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-4 | 77900 | SLMLED-4' | 4 | 1 | Regular | 2019-02-21 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-5 | 77900 | B4LED-4 | 5 | 1 | Regular | 2019-02-21 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77900-6 | 77900 | SLMLED-28' | 6 | 1 | Regular | 2019-02-21 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-7 | 77900 | SLMLED-36' | 7 | 1 | Regular | 2019-02-21 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-8 | 77900 | SLMLED-12 | 8 | 1 | Regular | 2019-02-21 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77900-9 | 77900 | SLMLED-28' | 9 | 1 | Regular | 2019-02-21 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77908-10 | 77908 | SCULPT-32'0" | 10 | 1 | Regular | 2019-02-05 | 1900-01-02 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-1 | 77908 | SCULPT-12'0" | 1 | 1 | Regular | 2019-02-05 | 1899-12-31 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-2 | 77908 | SCULPT-20'0" | 2 | 1 | Regular | 2019-02-05 | 1900-01-01 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-3 | 77908 | SCULPT-24'0" | 3 | 1 | Regular | 2019-02-05 | 1900-01-01 | 7 | Given to Shipping | Wrong part in BOM | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-4 | 77908 | SCULPT-28'0" | 4 | 1 | Regular | 2019-02-05 | 1900-01-02 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:02 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-5 | 77908 | SCULPT-32'0" | 5 | 1 | Regular | 2019-02-05 | 1900-01-02 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-6 | 77908 | SCULPT-4'0" | 6 | 1 | Regular | 2019-02-05 | 1899-12-31 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-7 | 77908 | SCULPT-4'0" | 7 | 1 | Regular | 2019-02-05 | 1899-12-31 | 7 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-31 17:06 | #6 | 2019-02-01 | 2t1-a |  |  | NO
77908-8 | 77908 | SKSLED-22 | 8 | 1 | Regular | 2019-02-05 | 1899-12-31 | 10 | Packaging Finished |  | FALSE |  | Yes | Done | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-25 |  |  |  | OK
77908-9 | 77908 | TWGLED-8'0" | 9 | 1 | Regular | 2019-02-05 | 1899-12-31 | 7 | Given to Shipping | PM wrong/missing info | TRUE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:02 |  | 2019-01-25 | 2t1-a |  |  | OK
77910-1 | 77910 | B3LED-16' | 1 | 1 | Regular | 2019-02-11 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2v1-a |  |  | OK
77910-2 | 77910 | B3LED-16' | 2 | 1 | Regular | 2019-02-11 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Yes |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 | 2v1-a |  |  | OK
77922-10 | 77922 | TB4LED-10' | 10 | 1 | Priority | 2019-02-13 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-1 | 77922 | TB4LED-8' | 1 | 1 | Priority | 2019-02-13 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-11 | 77922 | TB4LED-16' | 11 | 1 | Priority | 2019-02-13 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-2 | 77922 | TB4LED-12' | 2 | 1 | Priority | 2019-02-13 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-3 | 77922 | TB4LED-18' | 3 | 1 | Priority | 2019-02-13 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-4 | 77922 | TB4LED-20' | 4 | 1 | Priority | 2019-02-13 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-5 | 77922 | TB4LED-22' | 5 | 1 | Priority | 2019-02-13 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-6 | 77922 | TB4LED-24' | 6 | 1 | Priority | 2019-02-13 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-7 | 77922 | TB4LED-28' | 7 | 1 | Priority | 2019-02-13 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-8 | 77922 | TB2LED-4' | 8 | 1 | Priority | 2019-02-13 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77922-9 | 77922 | PERFKT-CCH | 9 | 1 | Priority | 2019-02-13 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
77926-1 | 77926 | SKFLED-22 | 1 | 1 | Regular | 2019-02-11 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
77932-1 | 77932 | PERFKT-CCWH | 1 | 1 | Regular | 2019-02-19 | 1900-01-20 | 0 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
77938-1 | 77938 | STENCL-16' | 1 | 1 | Regular | 2019-02-07 | 1900-01-03 | 7 | Machine Shop Started | Missing parts in BOM | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 39 | 2019-02-05 | 2v1-b | ToDo |  | NO
77939-3 | 77939 | STSFR | 3 | 1 | Regular | 2019-01-31 | 1900-01-05 | 7 | Machine Shop Finished | Others | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2S2-B |  |  | NO |  | +Cartridge | +Cartridge
77939-4 | 77939 | STNCLS-STSFR | 4 | 1 | Regular | 2019-01-31 | 1900-01-05 | 7 | Machine Shop Finished | Shortage | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2S2-B |  |  | NO |  | +Cartridge | +Cartridge
77943-1 | 77943 | SCULPT-4X4 | 1 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 7 | Machine Shop Started | Shortage | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77943-2 | 77943 | SCULPT-2X2 | 2 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77943-3 | 77943 | SCULPT-16' 6" | 3 | 1 | High Priority | 2019-02-21 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77943-4 | 77943 | SCULPT-7' 4" | 4 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77943-5 | 77943 | SCULPT-5' 6" | 5 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77943-6 | 77943 | SCULPT-3' 10" | 6 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77943-7 | 77943 | SCULPT-4' 10" | 7 | 1 | High Priority | 2019-02-21 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
77945-1 | 77945 | B2SLED-6 | 1 | 1 | High Priority | 2019-01-22 | 1899-12-31 | 4 | Machine Shop Finished | Mechanical issue | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-29 11:53 |  | 2019-01-23 | 2s3-b |  |  | NO |  | +Cartridge | +Cartridge
77945-2 | 77945 | B2SLED-32 | 2 | 1 | High Priority | 2019-01-22 | 1900-01-02 | 4 | Machine Shop Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-23 16:17 |  |  | 2s3-b |  |  | NO |  | +Cartridge | +Cartridge
77945-3 | 77945 | B2SLED-18 | 3 | 1 | High Priority | 2019-01-22 | 1900-01-01 | 4 | Machine Shop Finished | Shortage | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-23 16:18 |  |  | 2s3-b |  |  | NO |  | +Cartridge | +Cartridge
77947-1 | 77947 | B2SLED-34 | 1 | 1 | High Priority | 2019-01-22 | 1900-01-02 | 4 | Machine Shop Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-23 16:21 |  |  | 2s3-b |  |  | NO |  | +Cartridge | +Cartridge
77947-15 | 77947 | B2SLED-37' 5" | 15 | 1 | High Priority | 2019-01-22 | 1900-01-03 | 4 | Machine Shop Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-23 16:21 | 54 | 2019-01-21 | 2s3-b |  |  | NO
77947-2 | 77947 | B2SLED-24 | 2 | 1 | High Priority | 2019-01-22 | 1900-01-01 | 4 | Machine Shop Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-23 16:21 |  |  | 2s3-b |  |  | NO |  | +Cartridge | +Cartridge
78001-3 | 78001 | PERFKT-CCH | 3 | 1 | High Priority | 2019-02-14 | 1900-01-13 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78001-4 | 78001 | PERFKT-CCH | 4 | 1 | High Priority | 2019-02-14 | 1900-01-11 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78001-5 | 78001 | PERFKT-CCH | 5 | 1 | High Priority | 2019-02-14 | 1900-01-11 | 4 | Machine Shop Started | Missing info. In SD | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78001-6 | 78001 | PERFKT-CCH | 6 | 1 | High Priority | 2019-02-14 | 1900-01-13 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78001-7 | 78001 | PERFKT-CCH | 7 | 1 | High Priority | 2019-02-14 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78001-8 | 78001 | PERFKT-CCH | 8 | 1 | High Priority | 2019-02-14 | 1900-01-15 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78001-9 | 78001 | PERFKT-CCH | 9 | 1 | High Priority | 2019-02-14 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78009-1 | 78009 | STNCLS-STSFF | 1 | 1 | Regular | 2019-02-19 | 1900-01-05 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78009-2 | 78009 | SKETCH-AL(7'10 1/4") | 2 | 1 | Regular | 2019-02-19 | 1900-01-03 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78014-1 | 78014 | B6LED-32' | 1 | 1 | Regular | 2019-02-25 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78014-2 | 78014 | B6LED-40' | 2 | 1 | Regular | 2019-02-25 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78030-1 | 78030 | GRAZE-12'0" | 1 | 1 | Regular | 2019-02-22 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | Yes | [6 empty] | NA | FALSE | FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78047-1 | 78047 | B4LED-4' | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 13:24 | 54 | 2019-02-03 | 2w1-b |  |  | NO
78047-2 | 78047 | B4LED-8' | 2 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 13:24 | 54 | 2019-02-03 | 2w1-b |  |  | NO
78047-3 | 78047 | AIRLED-2' | 3 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 13:24 | 54 | 2019-02-03 | 2w1-b |  |  | NO
78047-4 | 78047 | B4LED-4' | 4 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 | 54 | 2019-02-03 | 2w1-b |  |  | NO
78047-5 | 78047 | B4LED-4' | 5 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | Done |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 | 54 | 2019-02-03 | 2w1-b |  |  | NO
78050-1 | 78050 | AIRLED-4' | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Machine Shop Finished | Wrong part in BOM | TRUE | Yes | Yes |  |  |  |  | Yes | Yes | TRUE | FALSE | 2019-02-03 10:26 |  |  | 2T1-A |  |  | NO |  | +Cartridge | +Cartridge
78053-2 | 78053 | SKETCH-AL#23' 6 3/4" | 2 | 1 | High Priority | 2019-02-14 | 1900-01-07 | 1 | Scheduled/Released |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-B |  |  | NO |  | +Cartridge | +Cartridge
78085-1 | 78085 | STENCL-S75' | 1 | 1 | Regular | 2019-04-30 | 1900-01-09 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78098-10 | 78098 | B4PLED-8 | 10 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 | 2V1-A |  |  | NO
78098-1 | 78098 | TB3LED-8 | 1 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Started | PM wrong/missing info | TRUE |  | Yes |  | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 14 | 2019-02-03 | 2V1-A |  |  | NO
78098-2 | 78098 | TB3LED-12 | 2 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Started | PM wrong/missing info | TRUE |  | Yes |  | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 14 | 2019-02-03 | 2V1-A |  |  | NO
78098-3 | 78098 | TB3LED-12 | 3 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes |  | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 14 | 2019-02-03 | 2V1-A |  |  | NO
78098-4 | 78098 | TB3LED-16 | 4 | 1 | High Priority | 2019-02-07 | 1900-01-01 | 18 | Machine Shop Started |  | FALSE |  | Yes |  | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 14 | 2019-02-03 | 2V1-A |  |  | NO
78098-5 | 78098 | TB3LED-16 | 5 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  | Yes |  | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 14 | 2019-02-03 | 2V1-A |  |  | NO
78098-6 | 78098 | B4PLED-3 | 6 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 | 2V1-A |  |  | NO
78098-7 | 78098 | B4PLED-5 | 7 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 | 2V1-A |  |  | NO
78098-8 | 78098 | B4PLED-6 | 8 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 | 2V1-A |  |  | NO
78098-9 | 78098 | B4PLED-6 | 9 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 18 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 | 2V1-A |  |  | NO
78105-1 | 78105 | TB3LED-24' | 1 | 1 | Priority | 2019-02-19 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-2 | 78105 | TB3LED-8' | 2 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-3 | 78105 | TB3LED-32' | 3 | 1 | Priority | 2019-02-19 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-4 | 78105 | TB3LED-20' | 4 | 1 | Priority | 2019-02-19 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-5 | 78105 | TB3LED-28' | 5 | 1 | Priority | 2019-02-19 | 1900-01-02 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-6 | 78105 | TB3LED-8' | 6 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-7 | 78105 | TB3LED-6' | 7 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78105-8 | 78105 | WWPRFK-8' | 8 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78106-1 | 78106 | B4LED-4' | 1 | 1 | Regular | 2019-02-11 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78106-2 | 78106 | B4PLED-6' 9" | 2 | 1 | Regular | 2019-02-11 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78106-3 | 78106 | B4PLED-10' 10" | 3 | 1 | Regular | 2019-02-11 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78106-4 | 78106 | B4PLED-16' | 4 | 1 | Regular | 2019-02-11 | 1900-01-02 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78110-1 | 78110 | B3LED-8' | 1 | 1 | Regular | 2019-02-11 | 1899-12-31 | 12 | Machine Shop Started | Wrong info. In SD | TRUE |  | Yes | Done |  | Done |  | Yes | Yes | FALSE | FALSE |  | 12 | 2019-01-24 | 2T1-A |  |  | NO
78110-2 | 78110 | B3LED-8' | 2 | 1 | Regular | 2019-02-11 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Done |  | Yes | Yes | FALSE | FALSE |  | 12 | 2019-01-24 | 2T1-A |  |  | NO
78110-3 | 78110 | B3LED-8' | 3 | 1 | Regular | 2019-02-11 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78124-1 | 78124 | TB2LED-4 | 1 | 1 | Priority | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-10 | 78126 | TB3LED-16' | 10 | 1 | Regular | 2019-02-18 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-1 | 78126 | TB3LED-4' | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-11 | 78126 | TB3LED-24' | 11 | 1 | Regular | 2019-02-18 | 1900-01-01 | 4 | Machine Shop Started | Others | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-12 | 78126 | TB3LED-28' | 12 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started | Others | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-13 | 78126 | TB3LED-28' | 13 | 1 | Regular | 2019-02-18 | 1900-01-02 | 4 | Machine Shop Started | Others | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-14 | 78126 | TB3LED-6' | 14 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-2 | 78126 | TB3LED-4' | 2 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-3 | 78126 | TB3LED-6' | 3 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-4 | 78126 | TB3LED-8' | 4 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-5 | 78126 | TB3LED-16' | 5 | 1 | Regular | 2019-02-18 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-6 | 78126 | TB3LED-4' | 6 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-7 | 78126 | TB3LED-4' | 7 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-8 | 78126 | TB3LED-6' | 8 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78126-9 | 78126 | TB3LED-8' | 9 | 1 | Regular | 2019-02-18 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78142-1 | 78142 | B3LED-10'0" | 1 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78142-2 | 78142 | B3LED-5'0" | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78142-3 | 78142 | ZEN-11'0" | 3 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78142-4 | 78142 | B3LED-20'0" | 4 | 1 | Regular | 2019-02-21 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78150-1 | 78150 | STNCLS-8' | 1 | 1 | Regular | 2019-02-01 | 1899-12-31 | 7 | Machine Shop Finished | Others | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2S2-A |  |  | NO |  | +Cartridge | +Cartridge
78150-2 | 78150 | STNCLS-12' | 2 | 1 | Regular | 2019-02-01 | 1899-12-31 | 7 | Machine Shop Finished | Shortage | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2S2-A |  |  | NO |  | +Cartridge | +Cartridge
78150-3 | 78150 | STNCLS-9' | 3 | 1 | Regular | 2019-02-01 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2S2-A |  |  | NO |  | +Cartridge | +Cartridge
78165-1 | 78165 | B2LED-34 | 1 | 1 | Regular | 2019-02-12 | 1900-01-08 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78165-2 | 78165 | B2LED-32 | 2 | 1 | Regular | 2019-02-12 | 1900-01-08 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78165-3 | 78165 | SKFLED-22 | 3 | 1 | Regular | 2019-02-12 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-04 |  |  |  | NO | Material |  | Material
78165-4 | 78165 | SKFLED-22 | 4 | 1 | Regular | 2019-02-12 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-04 |  |  |  | NO | Material |  | Material
78165-5 | 78165 | SKFLED-22 | 5 | 1 | Regular | 2019-02-12 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-04 |  |  |  | NO | Material |  | Material
78165-6 | 78165 | SKFLED-22 | 6 | 1 | Regular | 2019-02-12 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-04 |  |  |  | NO | Material |  | Material
78165-7 | 78165 | B6LED-8 | 7 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78170-1 | 78170 | SCULPT-58' | 1 | 1 | Regular | 2019-02-06 | 1900-01-09 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78170-2 | 78170 | SCULPT-29' | 2 | 1 | Regular | 2019-02-06 | 1900-01-04 | 4 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE |  |  |  | 2s1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78171-1 | 78171 | WWPRFK-4'0" | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:25 |  |  | 2q1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78174-10 | 78174 | STENCL-4 | 10 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-1 | 78174 | STFC | 1 | 1 | Regular | 2019-02-20 | 1900-01-07 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-11 | 78174 | STENCL-4 | 11 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-12 | 78174 | STENCL-8 | 12 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-13 | 78174 | SCULPT-4 | 13 | 1 | Regular | 2019-02-20 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-14 | 78174 | STNCLS-STSFF | 14 | 1 | Regular | 2019-02-20 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-15 | 78174 | STNCLS-STSFF | 15 | 1 | Regular | 2019-02-20 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-16 | 78174 | STNCLS-STSFF | 16 | 1 | Regular | 2019-02-20 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-17 | 78174 | STNCLS-STSFF | 17 | 1 | Regular | 2019-02-20 | 1900-01-03 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-18 | 78174 | SCULPT-10 | 18 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-19 | 78174 | SCULPT-50' | 19 | 1 | Regular | 2019-02-20 | 1900-01-05 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-20 | 78174 | PERFKT-CCL | 20 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-2 | 78174 | AULED-22 | 2 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-21 | 78174 | PERFKT-CCL | 21 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-22 | 78174 | PERFKT-CCL | 22 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-23 | 78174 | STENCL-4' | 23 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-24 | 78174 | STENCL-6' | 24 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-25 | 78174 | AULED-22 | 25 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-26 | 78174 | AULED-22 | 26 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-27 | 78174 | SCULPT-10 | 27 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-29 | 78174 | ACCENT-4 | 29 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78174-3 | 78174 | SCULPT-6' 8" | 3 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-4 | 78174 | SCULPT-5 | 4 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-5 | 78174 | SCULPT-4 | 5 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-6 | 78174 | SCULPT-17 | 6 | 1 | Regular | 2019-02-20 | 1900-01-01 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78174-7 | 78174 | SCULPT-5 | 7 | 1 | Regular | 2019-02-20 | 1899-12-31 | 7 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78177-1 | 78177 | B2LED-7'0" | 1 | 1 | High Priority | 2019-02-14 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78177-2 | 78177 | B2LED-8'0" | 2 | 1 | High Priority | 2019-02-14 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78177-3 | 78177 | B2LED-9'0" | 3 | 1 | High Priority | 2019-02-14 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-10 | 78220 | WWPRFK-2 | 10 | 1 | High Priority | 2019-02-12 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-1 | 78220 | TB2LED-16 | 1 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-11 | 78220 | B4PLED-26' 6" | 11 | 1 | High Priority | 2019-02-12 | 1900-01-03 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-12 | 78220 | B4PLED-92' 11" | 12 | 1 | High Priority | 2019-02-12 | 1900-01-11 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-13 | 78220 | B4PLED-39' 5" | 13 | 1 | High Priority | 2019-02-12 | 1900-01-04 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-14 | 78220 | B4PLED-19' 5" | 14 | 1 | High Priority | 2019-02-12 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-15 | 78220 | B4PLED-26' 5" | 15 | 1 | High Priority | 2019-02-12 | 1900-01-03 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-2 | 78220 | TB2LED-14 | 2 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-3 | 78220 | TB2LED-12 | 3 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-4 | 78220 | TB2LED-10 | 4 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-5 | 78220 | TB2LED-8 | 5 | 1 | High Priority | 2019-02-12 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-6 | 78220 | TB2LED-6 | 6 | 1 | High Priority | 2019-02-12 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-7 | 78220 | WWPRFK-13 | 7 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-8 | 78220 | WWPRFK-10 | 8 | 1 | High Priority | 2019-02-12 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78220-9 | 78220 | WWPRFK-6 | 9 | 1 | High Priority | 2019-02-12 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-10 | 78221 | B4PLED-23' 8" | 10 | 1 | Regular | 2019-02-11 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-1 | 78221 | TB2LED-22 | 1 | 1 | Regular | 2019-02-11 | 1900-01-02 | 4 | Machine Shop Started | PM wrong/missing info | TRUE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-11 | 78221 | B4PLED-76' 2" | 11 | 1 | Regular | 2019-02-11 | 1900-01-09 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-12 | 78221 | B4PLED-18' 9" | 12 | 1 | Regular | 2019-02-11 | 1900-01-03 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-13 | 78221 | B4PLED-11' 5" | 13 | 1 | Regular | 2019-02-11 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-14 | 78221 | B4PLED-17' 11" | 14 | 1 | Regular | 2019-02-11 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-15 | 78221 | B4PLED-18' 3" | 15 | 1 | Regular | 2019-02-11 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-16 | 78221 | B4PLED-75' 9" | 16 | 1 | Regular | 2019-02-11 | 1900-01-10 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-2 | 78221 | TB2LED-14 | 2 | 1 | Regular | 2019-02-11 | 1900-01-01 | 4 | Machine Shop Started | Shortage | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-3 | 78221 | TB2LED-12 | 3 | 1 | Regular | 2019-02-11 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-4 | 78221 | TB2LED-8 | 4 | 1 | Regular | 2019-02-11 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-5 | 78221 | WWPRFK-2 | 5 | 1 | Regular | 2019-02-11 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-6 | 78221 | WWPRFK-10 | 6 | 1 | Regular | 2019-02-11 | 1900-01-01 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-7 | 78221 | WWPRFK-6 | 7 | 1 | Regular | 2019-02-11 | 1899-12-31 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-8 | 78221 | B4PLED-97' | 8 | 1 | Regular | 2019-02-11 | 1900-01-12 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78221-9 | 78221 | B4PLED-18' 8" | 9 | 1 | Regular | 2019-02-11 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78225-10 | 78225 | B4PLED-97' 3" | 10 | 1 | High Priority | 2019-02-08 | 1900-01-12 | 7 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-1 | 78225 | TB2LED-22 | 1 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-11 | 78225 | B4PLED-18' 10" | 11 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-12 | 78225 | B4PLED-18' 6" | 12 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-13 | 78225 | B4PLED-38' 1" | 13 | 1 | High Priority | 2019-02-08 | 1900-01-04 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-14 | 78225 | B4PLED-55' 9" | 14 | 1 | High Priority | 2019-02-08 | 1900-01-06 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-2 | 78225 | TB2LED-16 | 2 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-3 | 78225 | TB2LED-14 | 3 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-4 | 78225 | TB2LED-8 | 4 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-5 | 78225 | TB2LED-6 | 5 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-6 | 78225 | WWPRFK-2 | 6 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-7 | 78225 | WWPRFK-13 | 7 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-8 | 78225 | WWPRFK-14 | 8 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78225-9 | 78225 | B4PLED-18' 9" | 9 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-1 | 78226 | TB2LED-16 | 1 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-2 | 78226 | TB2LED-14 | 2 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 4 | Machine Shop Started | Shortage | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-3 | 78226 | TB2LED-12 | 3 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-4 | 78226 | WWPRFK-2 | 4 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 4 | Machine Shop Started | Shortage | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-5 | 78226 | B4PLED-28' 6" | 5 | 1 | High Priority | 2019-02-08 | 1900-01-03 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-6 | 78226 | B4PLED-90' 6" | 6 | 1 | High Priority | 2019-02-08 | 1900-01-11 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-7 | 78226 | B4PLED-18' 11" | 7 | 1 | High Priority | 2019-02-08 | 1900-01-02 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-8 | 78226 | B4PLED-73' 5" | 8 | 1 | High Priority | 2019-02-08 | 1900-01-09 | 4 | Machine Shop Started | Others | TRUE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78226-9 | 78226 | B4PLED-28' | 9 | 1 | High Priority | 2019-02-08 | 1900-01-03 | 4 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78240-1 | 78240 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78240-2 | 78240 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78240-3 | 78240 | STENCL-STFC | 3 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78240-4 | 78240 | STENCL-STFC | 4 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78240-5 | 78240 | STENCL-STFC | 5 | 1 | Regular | 2019-02-14 | 1900-01-03 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78272-1 | 78272 | TEKLED-4 | 1 | 1 | Regular | 2019-01-31 | 1899-12-31 | 12 | Machine Shop Finished | Shortage | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 40 | 2019-01-24 | 2x1-a |  |  | NO
78272-2 | 78272 | TEKLED-4 | 2 | 1 | Regular | 2019-01-31 | 1899-12-31 | 12 | Machine Shop Started | Shortage | TRUE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | 40 | 2019-01-24 | 2x1-a |  |  | NO
78279-1 | 78279 | B4LED-8 | 1 | 1 | Regular | 2019-02-12 | 1899-12-31 | 18 | Machine Shop Started | Shortage | FALSE |  |  |  | Done |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78279-2 | 78279 | B3LED-4 | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 18 | Machine Shop Started |  | FALSE |  |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78290-1 | 78290 | ZEN-12 | 1 | 1 | Regular | 2019-02-04 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-02-04 11:48 |  | 2019-01-25 |  |  |  | OK
78302-2 | 78302 | BEAM2-40 | 2 | 1 | High Priority | 2019-02-14 | 1900-01-03 | 12 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78306-1 | 78306 | ACCENT-6'0" | 1 | 1 | Regular | 2019-02-06 | 1899-12-31 | 12 | Machine Shop Started | Shortage | FALSE | Yes |  |  |  | Done |  | Yes | No | FALSE | FALSE |  | #2 | 2019-01-28 |  |  |  | NO | Material |  | Material
78311-1 | 78311 | B2LED-8' | 1 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78311-2 | 78311 | B2LED-7' | 2 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78311-3 | 78311 | SCULPT-8' | 3 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78311-5 | 78311 | SCULPT-12' | 5 | 1 | Regular | 2019-02-25 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-10 | 78328 | B4SLED-12 | 10 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-1 | 78328 | B4SLED-12 | 1 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-11 | 78328 | B4SLED-12 | 11 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started | Shortage | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-12 | 78328 | B4SLED-18 | 12 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-13 | 78328 | B4SLED-18 | 13 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-14 | 78328 | B4SLED-18 | 14 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-15 | 78328 | B4SLED-18 | 15 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-16 | 78328 | B4SLED-18 | 16 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-17 | 78328 | B4SLED-18 | 17 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-18 | 78328 | B4SLED-24 | 18 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-2 | 78328 | B4SLED-12 | 2 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-3 | 78328 | B4SLED-24 | 3 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-4 | 78328 | B4SLED-24 | 4 | 1 | Regular | 2019-02-13 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-5 | 78328 | B4SLED-8 | 5 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-6 | 78328 | B2LED-12 | 6 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-7 | 78328 | B2LED-12 | 7 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-8 | 78328 | B2LED-6 | 8 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78328-9 | 78328 | B2LED-6 | 9 | 1 | Regular | 2019-02-13 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78346-1 | 78346 | AULED-14 | 1 | 1 | Regular | 2019-02-15 | 1899-12-31 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-1 | 78355 | DIALED-22 | 1 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-2 | 78355 | AULED-22 | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-3 | 78355 | SKFLED-22 | 3 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-4 | 78355 | SKFLED-22 | 4 | 1 | Regular | 2019-02-21 | 1899-12-31 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-5 | 78355 | CLICK-8 | 5 | 1 | Regular | 2019-02-21 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-6 | 78355 | PERFKT-CCH | 6 | 1 | Regular | 2019-02-21 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78355-7 | 78355 | PERFKT-CCWH | 7 | 1 | Regular | 2019-02-21 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78360-1 | 78360 | GRAZE-23 | 1 | 1 | High Priority | 2019-02-22 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78381-1 | 78381 | ZEN-12 | 1 | 1 | Regular | 2019-03-01 | 1899-12-31 | 0 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78381-2 | 78381 | B4LED-11' | 2 | 1 | Regular | 2019-02-14 | 1900-01-02 | 18 | Machine Shop Started | Others | TRUE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78381-3 | 78381 | ZEN-12 | 3 | 1 | Regular | 2019-03-01 | 1899-12-31 | 0 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78386-1 | 78386 | B2LED-5 | 1 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Given to Shipping |  | FALSE |  | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 09:28 | 35 | 2019-01-31 |  |  |  | NO
78386-2 | 78386 | B2LED-6 | 2 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Given to Shipping |  | FALSE |  | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 09:28 | 35 | 2019-01-31 |  |  |  | NO
78386-3 | 78386 | B2LED-4 | 3 | 1 | Regular | 2019-02-04 | 1899-12-31 | 18 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 09:28 | 35 | 2019-01-31 |  |  |  | NO
78388-1 | 78388 | STNCLS-6 | 1 | 1 | High Priority | 2019-02-01 | 1899-12-31 | 12 | Machine Shop Finished | Others | FALSE | Yes |  | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:21 |  |  | 2T2-A |  |  | NO | Material | +Cartridge | Material+Cartridge
78394-1 | 78394 | B4LED-8 | 1 | 1 | Priority | 2019-03-14 | 1899-12-31 | 15 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78395-1 | 78395 | TB2LED-4 | 1 | 1 | High Priority | 2019-02-25 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78395-2 | 78395 | TB2LED-8 | 2 | 1 | High Priority | 2019-02-25 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78395-3 | 78395 | TB2LED-8 | 3 | 1 | High Priority | 2019-02-25 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78395-4 | 78395 | SCULPT-8 | 4 | 1 | High Priority | 2019-02-25 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78401-1 | 78401 | B4LED-24 | 1 | 1 | High Priority | 2019-02-08 | 1900-01-01 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:29 | 9 | 2019-02-03 | 2w1-a |  |  | NO
78401-2 | 78401 | B4LED-8 | 2 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | No | TRUE | FALSE | 2019-02-04 14:29 | 9 | 2019-02-03 |  |  |  | NO
78408-1 | 78408 | B3LED-4 | 1 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78408-2 | 78408 | B3LED-8 | 2 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78408-3 | 78408 | B3LED-12 | 3 | 1 | Regular | 2019-02-18 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78410-1 | 78410 | STNCLS-8' | 1 | 1 | Regular | 2019-02-25 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78410-2 | 78410 | STNCLS-12' | 2 | 1 | Regular | 2019-02-25 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78413-1 | 78413 | B4LED-4 | 1 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78413-2 | 78413 | B4LED-6 | 2 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78413-3 | 78413 | B4LED-2 | 3 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78413-4 | 78413 | B4LED-10 | 4 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78413-5 | 78413 | B6PLED-4 | 5 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78413-6 | 78413 | B6PLED-10 | 6 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78423-10 | 78423 | SCULPT-6' 3" | 10 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78423-11 | 78423 | SCULPT-6' 3" | 11 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78423-12 | 78423 | SCULPT-5' 6" | 12 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78423-13 | 78423 | SCULPT-6' 3" | 13 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | No | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78423-14 | 78423 | SCULPT-6' 3" | 14 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | No | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78423-8 | 78423 | SCULPT-5' 4" | 8 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78423-9 | 78423 | SCULPT-5' 4" | 9 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2r2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78436-10 | 78436 | STENCL-STCO | 10 | 1 | High Priority | 2019-02-15 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-1 | 78436 | STENCL-STCO | 1 | 1 | High Priority | 2019-02-15 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-11 | 78436 | STENCL-STCO | 11 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-2 | 78436 | STENCL-STCO | 2 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-3 | 78436 | STENCL-STCO | 3 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-4 | 78436 | STENCL-STCO | 4 | 1 | High Priority | 2019-02-15 | 1900-01-06 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-6 | 78436 | STENCL-STCO | 6 | 1 | High Priority | 2019-02-15 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-7 | 78436 | STENCL-STCO | 7 | 1 | High Priority | 2019-02-15 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-8 | 78436 | STENCL-STCO | 8 | 1 | High Priority | 2019-02-15 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78436-9 | 78436 | STENCL-STCO | 9 | 1 | High Priority | 2019-02-15 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78442-1 | 78442 | TB2LED-6' | 1 | 1 | Regular | 2019-02-04 | 1899-12-31 | 12 | Machine Shop Finished | Shortage | FALSE | Yes |  | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 4 | 2019-02-04 |  |  |  | NO | Material |  | Material
78448-10 | 78448 | SCULPT-1'0" | 10 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-1 | 78448 | SCULPT-1'3" | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-11 | 78448 | SCULPT-2'0" | 11 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-12 | 78448 | SCULPT-3'0" | 12 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-13 | 78448 | SCULPT-5'0" | 13 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-14 | 78448 | ZENSQ-8' | 14 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started | Shortage | FALSE | Yes |  |  |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2s2-a |  |  | NO | Material |  | Material
78448-15 | 78448 | ZENSQ-8' | 15 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started | Missing parts in BOM | TRUE | Yes | Yes |  |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-31 | 2s2-a |  |  | NO
78448-16 | 78448 | SCULPT-53'10 6/8" | 16 | 1 | Regular | 2019-02-08 | 1900-01-07 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-17 | 78448 | SCULPT-3'0" | 17 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-18 | 78448 | SCULPT-2'0" | 18 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-19 | 78448 | SCULPT-10'2" | 19 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-20 | 78448 | SCULPT-1'3" | 20 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-2 | 78448 | SCULPT-10'2" | 2 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | NA | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-3 | 78448 | SCULPT-6'10" | 3 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-4 | 78448 | SCULPT-10'7 3/4" | 4 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-5 | 78448 | SCULPT-16'8 1/2" | 5 | 1 | Regular | 2019-02-08 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-6 | 78448 | SCULPT-10'7 3/4" | 6 | 1 | Regular | 2019-02-08 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-7 | 78448 | SCULPT-16'8 1/2" | 7 | 1 | Regular | 2019-02-08 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-8 | 78448 | SCULPT-55'4" | 8 | 1 | Regular | 2019-02-08 | 1900-01-07 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78448-9 | 78448 | SCULPT-48'0" | 9 | 1 | Regular | 2019-02-08 | 1900-01-07 | 1 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2s2-a |  |  | NO |  | +Cartridge | +Cartridge
78469-1 | 78469 | B3LED-7'4" | 1 | 1 | Regular | 2019-02-12 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78469-2 | 78469 | B3LED-8' | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78471-1 | 78471 | B4LED-29' | 1 | 1 | Regular | 2019-02-27 | 1899-12-31 | 12 | Scheduled/Released | PM wrong/missing info | TRUE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78471-2 | 78471 | B4LED-11' | 2 | 1 | Regular | 2019-02-27 | 1899-12-31 | 12 | Scheduled/Released | PM wrong/missing info | TRUE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78471-3 | 78471 | B4LED-20' | 3 | 1 | Regular | 2019-02-27 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78471-4 | 78471 | B4LED-18' | 4 | 1 | Regular | 2019-02-27 | 1900-01-01 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78476-1 | 78476 | PERFKT-CCL | 1 | 1 | Regular | 2019-02-14 | 1900-01-01 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78476-2 | 78476 | PERFKT-CCL | 2 | 1 | Regular | 2019-02-14 | 1900-01-06 | 7 | Machine Shop Started | PM wrong/missing info | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78476-3 | 78476 | PERFKT-CCL | 3 | 1 | Regular | 2019-02-14 | 1900-01-03 | 7 | Machine Shop Started | PM wrong/missing info | TRUE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78476-4 | 78476 | PERFKT-CCL | 4 | 1 | Regular | 2019-02-14 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78476-5 | 78476 | PERFKT-CCL | 5 | 1 | Regular | 2019-02-14 | 1900-01-02 | 7 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78491-1 | 78491 | B2LED-4' | 1 | 1 | Regular | 2019-02-06 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE |  | 1 | 2019-02-05 | 2V2-A |  |  | NO
78498-1 | 78498 | B3LED-2 | 1 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-2 | 78498 | B3LED-2 | 2 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-3 | 78498 | B3LED-6 | 3 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-4 | 78498 | B3LED-8 | 4 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-5 | 78498 | B3LED-14 | 5 | 1 | Regular | 2019-02-15 | 1900-01-01 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-6 | 78498 | B3LED-2 | 6 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-7 | 78498 | B3LED-6 | 7 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78498-8 | 78498 | B3LED-2 | 8 | 1 | Regular | 2019-02-15 | 1899-12-31 | 1 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-10 | 78500 | SCULPT-12' | 10 | 1 | Priority | 2019-02-19 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-1 | 78500 | SCULPT-8 | 1 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-11 | 78500 | B3LED-12' | 11 | 1 | Priority | 2019-02-19 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-12 | 78500 | MINLED-6' | 12 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-2 | 78500 | SCULPT-10' | 2 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-3 | 78500 | SCULPT-18' | 3 | 1 | Priority | 2019-02-19 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-4 | 78500 | SCULPT-20' | 4 | 1 | Priority | 2019-02-19 | 1900-01-01 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-5 | 78500 | MINLED-6 | 5 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-6 | 78500 | SCULPT-6' | 6 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-7 | 78500 | SCULPT-8' | 7 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-8 | 78500 | SCULPT-9' | 8 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78500-9 | 78500 | SCULPT-10' | 9 | 1 | Priority | 2019-02-19 | 1899-12-31 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78503-1 | 78503 | B3LED-6' | 1 | 1 | High Priority | 2019-03-04 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78503-2 | 78503 | B3LED-6' | 2 | 1 | High Priority | 2019-03-04 | 1899-12-31 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78506-1 | 78506 | STENCL-8' | 1 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO
78506-2 | 78506 | STENCL-4' | 2 | 1 | High Priority | 2019-02-08 | 1899-12-31 | 7 | Machine Shop Started | Missing parts in BOM | TRUE | Yes | Yes |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO
78506-3 | 78506 | STENCL-STFC | 3 | 1 | High Priority | 2019-02-08 | 1900-01-03 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78506-4 | 78506 | STENCL-STFC | 4 | 1 | High Priority | 2019-02-08 | 1900-01-03 | 7 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78511-1 | 78511 | PERFKT-CCL | 1 | 1 | Regular | 2019-02-06 | 1900-01-15 | 4 | Machine Shop Finished | Shortage | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-25 |  |  |  | OK
78511-2 | 78511 | PERFKT-CCL | 2 | 1 | Regular | 2019-02-06 | 1900-01-03 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-25 |  |  |  | OK
78515-1 | 78515 | B2LED-6 | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 12 | Given to Shipping |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 10:27 | 33 | 2019-02-01 |  |  |  | NO
78517-1 | 78517 | PERFKT-CCWL | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes |  |  |  | NA |  | Yes | NA | TRUE | FALSE | 2019-02-04 14:27 |  | 2019-01-31 | 2R1-A |  |  | NO | Material |  | Material
78517-2 | 78517 | WWPRFK-3 | 2 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Finished |  | FALSE | Yes | [5 empty] | Yes | NA | TRUE | FALSE | 2019-02-04 14:27 |  |  | 2R1-A |  |  | NO | Material | +Cartridge | Material+Cartridge
78521-1 | 78521 | WWPRFK-2 | 1 | 1 | Regular | 2019-02-05 | 1899-12-31 | 12 | Wiring Started | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-01-31 11:33 | 39 | 2019-02-03 | 2T2-B |  |  | NO
78522-25 | 78522 | B3LED-13' 6" | 25 | 1 | Regular | 2019-02-21 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-26 | 78522 | B3LED-4' 6" | 26 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-27 | 78522 | B3LED-10' | 27 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-28 | 78522 | B3LED-5' 6" | 28 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-29 | 78522 | B3LED-13' 6" | 29 | 1 | Regular | 2019-02-21 | 1900-01-01 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-30 | 78522 | B3LED-4' 6" | 30 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-31 | 78522 | B3LED-10' | 31 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-32 | 78522 | B3LED-6' | 32 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-33 | 78522 | B3LED-26' 4" | 33 | 1 | Regular | 2019-02-21 | 1900-01-02 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-34 | 78522 | B3LED-10' | 34 | 1 | Regular | 2019-02-21 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78522-35 | 78522 | B4PLED-39' 8" | 35 | 1 | Regular | 2019-02-21 | 1900-01-03 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78525-1 | 78525 | SCULPT-K(2X6) | 1 | 1 | Regular | 2019-02-08 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | Yes | [6 empty] | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78529-1 | 78529 | B4LED-12' | 1 | 1 | Regular | 2019-02-07 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE |  | 23 | 2019-02-04 | 2s1-a |  |  | NO
78529-2 | 78529 | B4LED-20' | 2 | 1 | Regular | 2019-02-07 | 1900-01-01 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 23 | 2019-02-04 | 2s1-a |  |  | NO
78529-3 | 78529 | B4LED-4' | 3 | 1 | Regular | 2019-02-07 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 23 | 2019-02-04 | 2s1-a |  |  | NO
78529-4 | 78529 | B4LED-8' | 4 | 1 | Regular | 2019-02-07 | 1899-12-31 | 15 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | FALSE | FALSE |  | 23 | 2019-02-04 | 2s1-a |  |  | NO
78530-1 | 78530 | B3LED-4 | 1 | 1 | Regular | 2019-02-15 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78530-2 | 78530 | B3LED-8 | 2 | 1 | Regular | 2019-02-15 | 1899-12-31 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78533-1 | 78533 | SKETCH-90 | 1 | 1 | Regular | 2019-02-28 | 1900-01-03 | 0 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78534-1 | 78534 | B4LED-4' | 1 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78534-2 | 78534 | B4LED-2' | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 15 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78535-1 | 78535 | B3LED-4' | 1 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78535-2 | 78535 | B3LED-2' | 2 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78535-3 | 78535 | B3LED-2' | 3 | 1 | Regular | 2019-02-12 | 1899-12-31 | 7 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78535-4 | 78535 | B3LED-10' | 4 | 1 | Regular | 2019-02-12 | 1900-01-02 | 7 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78538-4 | 78538 | BEAM4-8' | 4 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | Yes |  |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
78538-5 | 78538 | BEAM4-6' | 5 | 1 | High Priority | 2019-02-07 | 1899-12-31 | 7 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | Yes |  |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
78538-6 | 78538 | BEAM4-16' | 6 | 1 | High Priority | 2019-02-07 | 2 | 7 | Machine Shop Started | Wrong info. In SD | TRUE | Yes | Yes |  |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO
78542-1 | 78542 | B2SLED-6' | 1 | 1 | High Priority | 2019-02-20 | 1 | 15 | Machine Shop Finished | Missing info. In SD | TRUE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78542-2 | 78542 | B2SLED-9' | 2 | 1 | High Priority | 2019-02-20 | 1 | 15 | Machine Shop Finished |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78542-3 | 78542 | B2SLED-4' | 3 | 1 | High Priority | 2019-02-20 | 1 | 15 | Machine Shop Finished | Others | TRUE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78542-4 | 78542 | B2SLED-4' | 4 | 1 | High Priority | 2019-02-20 | 1 | 15 | Machine Shop Finished |  | FALSE | [7 empty] | No | FALSE | FALSE |  |  |  | 2v1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78545-1 | 78545 | ACCENT-4' | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
78559-10 | 78559 | MINLED-4' | 10 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Finished |  | FALSE | [6 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78559-1 | 78559 | DIALED-22 | 1 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78559-2 | 78559 | DIALED-22 | 2 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78559-3 | 78559 | DIALED-24 | 3 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78559-4 | 78559 | MINLED-4' | 4 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Finished |  | FALSE | [6 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78559-5 | 78559 | AULED-22 | 5 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78559-6 | 78559 | DIALED-22 | 6 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78559-7 | 78559 | DIALED-22 | 7 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78559-8 | 78559 | MINLED-4' | 8 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Finished |  | FALSE | [6 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78559-9 | 78559 | AULED-22 | 9 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78563-1 | 78563 | PERFKT-CCL | 1 | 1 | High Priority | 2019-02-19 | 2 | 0 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78563-2 | 78563 | PERFKT-CCL | 2 | 1 | High Priority | 2019-02-19 | 2 | 0 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78563-3 | 78563 | PERFKT-CCL | 3 | 1 | High Priority | 2019-02-19 | 1 | 0 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78565-1 | 78565 | AULED-14 | 1 | 1 | High Priority | 2019-02-21 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78565-2 | 78565 | B4LED-8' | 2 | 1 | High Priority | 2019-02-21 | 1 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78565-3 | 78565 | B4LED-16' | 3 | 1 | High Priority | 2019-02-21 | 2 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78569-1 | 78569 | WB4LED-5 | 1 | 1 | High Priority | 2019-02-08 | 1 | 18 | Machine Shop Finished | Shortage | FALSE |  |  | Done | Done | Done |  | Yes | Yes | FALSE | FALSE |  | 54 | 2019-02-03 | 2V1-B |  |  | NO | Material |  | Material
78581-100 | 78581 | B3LED-16' | 100 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-10 | 78581 | B3PLED-12' | 10 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-101 | 78581 | B3LED-10' | 101 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-102 | 78581 | B3LED-10' | 102 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-103 | 78581 | B3LED-10' | 103 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-104 | 78581 | B3LED-4' | 104 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-105 | 78581 | B3LED-14' | 105 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-106 | 78581 | B3LED-22' | 106 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-107 | 78581 | B3LED-18' | 107 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-108 | 78581 | B3LED-18' | 108 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-109 | 78581 | B3LED-18' | 109 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-1 | 78581 | B3LED-14' | 1 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-110 | 78581 | B3LED-18' | 110 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-11 | 78581 | B3PLED-12' | 11 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-111 | 78581 | B3LED-18' | 111 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-112 | 78581 | B3LED-18' | 112 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-113 | 78581 | B3LED-18' | 113 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-114 | 78581 | B3LED-18' | 114 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-115 | 78581 | B3LED-18' | 115 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-116 | 78581 | B3LED-18' | 116 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-117 | 78581 | B3LED-18' | 117 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-118 | 78581 | B3LED-18' | 118 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-119 | 78581 | B3LED-18' | 119 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-120 | 78581 | B3LED-18' | 120 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-12 | 78581 | B3PLED-12' | 12 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-121 | 78581 | B3LED-18' | 121 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-122 | 78581 | B3LED-18' | 122 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-123 | 78581 | B3LED-20' | 123 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-124 | 78581 | B3LED-4' | 124 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-125 | 78581 | B3LED-4' | 125 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-126 | 78581 | B3LED-4' | 126 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-127 | 78581 | B3LED-4' | 127 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-128 | 78581 | B3LED-8' | 128 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-13 | 78581 | B3PLED-13' | 13 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-14 | 78581 | B3PLED-14' 10" | 14 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-15 | 78581 | B3PLED-14' 4" | 15 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-16 | 78581 | B3PLED-15' 3" | 16 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-17 | 78581 | B3PLED-15' 6" | 17 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-18 | 78581 | B3PLED-16' 1" | 18 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-19 | 78581 | B3PLED-16' 2" | 19 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-20 | 78581 | B3PLED-16' 9" | 20 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-2 | 78581 | B3LED-22' | 2 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-21 | 78581 | B3PLED-16' | 21 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-22 | 78581 | B3PLED-16' | 22 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-23 | 78581 | B3PLED-17' | 23 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-24 | 78581 | B3PLED-19' 11" | 24 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-25 | 78581 | B3PLED-21' 4" | 25 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-26 | 78581 | B3PLED-21' 5" | 26 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-27 | 78581 | B3PLED-21' 6" | 27 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-28 | 78581 | B3PLED-21' | 28 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-29 | 78581 | B3PLED-22' 2" | 29 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-30 | 78581 | B3PLED-22' 2" | 30 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-3 | 78581 | B3LED-8' | 3 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-31 | 78581 | B3PLED-22' 9" | 31 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-32 | 78581 | B3PLED-22' | 32 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-33 | 78581 | B3PLED-24' 3" | 33 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-34 | 78581 | B3PLED-27' 11" | 34 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-35 | 78581 | B3PLED-27' 3" | 35 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-36 | 78581 | B3PLED-3' 5" | 36 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-37 | 78581 | B3PLED-3' 5" | 37 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-38 | 78581 | B3PLED-4' 10" | 38 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-39 | 78581 | B3PLED-5' 1" | 39 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-40 | 78581 | B3PLED-5' 2" | 40 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-4 | 78581 | B3LED-24' | 4 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-41 | 78581 | B3PLED-7' 10" | 41 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-42 | 78581 | B3PLED-7' 10" | 42 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-43 | 78581 | B3PLED-7' 2" | 43 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-44 | 78581 | B3PLED-7' 5" | 44 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-45 | 78581 | B3PLED-7' 5" | 45 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-46 | 78581 | B3PLED-7' 6" | 46 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-47 | 78581 | B3PLED-7' 6" | 47 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-48 | 78581 | B3PLED-7' | 48 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-49 | 78581 | B3PLED-8' 10" | 49 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-50 | 78581 | B3PLED-8' 10" | 50 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-5 | 78581 | B3PLED-10' 3" | 5 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-51 | 78581 | B3PLED-8' | 51 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-52 | 78581 | B3PLED-8' | 52 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-53 | 78581 | B3PLED-8' | 53 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-54 | 78581 | B3PLED-8' | 54 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-55 | 78581 | B3PLED-8' | 55 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-56 | 78581 | B3PLED-8' | 56 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-57 | 78581 | B3PLED-8' | 57 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-58 | 78581 | B3PLED-8' | 58 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-59 | 78581 | B3PLED-8' | 59 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-60 | 78581 | B3PLED-8' | 60 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-6 | 78581 | B3PLED-10' 6" | 6 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-61 | 78581 | B3PLED-9' 4" | 61 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-62 | 78581 | B3PLED-9' 8" | 62 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-63 | 78581 | B3PLED-9' | 63 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-64 | 78581 | B3LED-20' | 64 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-65 | 78581 | B6LED-2' | 65 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-66 | 78581 | B6LED-2' | 66 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-67 | 78581 | B3LED-4 | 67 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-68 | 78581 | B3LED-4' | 68 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-69 | 78581 | B3LED-4' | 69 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-70 | 78581 | B3LED-14' | 70 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-7 | 78581 | B3PLED-10' 7" | 7 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-71 | 78581 | B4PLED-31' 1" | 71 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-72 | 78581 | B4PLED-12' 10" | 72 | 1 | Priority | 2019-02-20 | 2 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-73 | 78581 | B4PLED-27' | 73 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-74 | 78581 | B4PLED-28' 9" | 74 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-75 | 78581 | B4PLED-30' | 75 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-76 | 78581 | B4PLED- 31' 1" | 76 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-77 | 78581 | B4PLED-31' 2" | 77 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-78 | 78581 | B4PLED-31' 2" | 78 | 1 | Priority | 2019-02-20 | 3 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-79 | 78581 | B4PLED-39' 6" | 79 | 1 | Priority | 2019-02-20 | 4 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-80 | 78581 | B4PLED-4' 10" | 80 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-8 | 78581 | B3PLED-11' 10" | 8 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-81 | 78581 | B4PLED-40' 2" | 81 | 1 | Priority | 2019-02-20 | 4 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-82 | 78581 | B2LED-21' 10"X25' | 82 | 1 | Priority | 2019-02-21 | 5 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-83 | 78581 | B3LED-16' | 83 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-84 | 78581 | B3LED-16' | 84 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-85 | 78581 | B3LED-16' | 85 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-86 | 78581 | B3LED-16' | 86 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-87 | 78581 | B3LED-16' | 87 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-88 | 78581 | B3LED-10' | 88 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-89 | 78581 | B3LED-10' | 89 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-90 | 78581 | B3LED-10' | 90 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-9 | 78581 | B3PLED-11' 10" | 9 | 1 | Priority | 2019-02-20 | 1 | 1 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78581-91 | 78581 | B3LED-10' | 91 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-92 | 78581 | B3LED-10' | 92 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-93 | 78581 | B3LED-10' | 93 | 1 | Priority | 2019-02-21 | 1 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-94 | 78581 | B3LED-16' | 94 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-95 | 78581 | B3LED-16' | 95 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-96 | 78581 | B3LED-16' | 96 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-97 | 78581 | B3LED-16' | 97 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-98 | 78581 | B3LED-16' | 98 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78581-99 | 78581 | B3LED-16' | 99 | 1 | Priority | 2019-02-21 | 2 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78588-1 | 78588 | SCULPT-26 | 1 | 1 | High Priority | 2019-02-13 | 4 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78588-2 | 78588 | SCULPT-26 | 2 | 1 | High Priority | 2019-02-13 | 4 | 12 | Scheduled/Released |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78590-1 | 78590 | STNCLS-12' | 1 | 1 | Regular | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE |  |  |  |  | ToDo |  | NO | Material | +Cartridge | Material+Cartridge
78593-1 | 78593 | SL2LED-4 | 1 | 1 | High Priority | 2019-02-01 | 1 | 4 | Wiring Started | PM wrong/missing info | TRUE |  | Yes | Done | Done | NA |  | Yes | No | TRUE | FALSE | 2019-02-05 10:41 |  | 2019-01-29 | 2s1-a |  |  | OK
78593-2 | 78593 | SL2LED-4 | 2 | 1 | High Priority | 2019-02-01 | 1 | 4 | Wiring Started |  | FALSE |  | Yes | Done | Done | NA |  | Yes | No | TRUE | FALSE | 2019-02-05 10:41 |  | 2019-01-29 | 2s1-a |  |  | OK
78593-3 | 78593 | SCULPT-6 | 3 | 1 | High Priority | 2019-02-01 | 1 | 4 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:41 | #9 | 2019-01-29 | 2s1-a |  |  | NO
78593-4 | 78593 | SCULPT-20 | 4 | 1 | High Priority | 2019-02-01 | 2 | 4 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | No | TRUE | FALSE | 2019-02-05 10:41 | #9 | 2019-01-29 | 2s1-a |  |  | NO
78594-1 | 78594 | B3LED-44' | 1 | 1 | Regular | 2019-02-28 | 8 | 1 | Scheduled/Released |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78594-2 | 78594 | CLICK-6' | 2 | 1 | Regular | 2019-02-28 | 1 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78594-3 | 78594 | CLICK-6' | 3 | 1 | Regular | 2019-02-28 | 1 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78594-4 | 78594 | CLICK-8' | 4 | 1 | Regular | 2019-02-28 | 1 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78594-5 | 78594 | CLICK-8' | 5 | 1 | Regular | 2019-02-28 | 1 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78594-6 | 78594 | CLICK-4' | 6 | 1 | Regular | 2019-02-28 | 1 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78594-7 | 78594 | CLICK-4' | 7 | 1 | Regular | 2019-02-28 | 1 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78594-8 | 78594 | CLICK-16' | 8 | 1 | Regular | 2019-02-28 | 2 | 1 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78596-1 | 78596 | SCULPT-10' | 1 | 1 | High Priority | 2019-02-15 | 1 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78596-2 | 78596 | SLMLED-8' | 2 | 1 | High Priority | 2019-02-15 | 1 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78596-3 | 78596 | SLMLED-8' | 3 | 1 | High Priority | 2019-02-15 | 1 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | No | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78596-4 | 78596 | SCULPT-8' | 4 | 1 | High Priority | 2019-02-15 | 1 | 4 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78603-1 | 78603 | STENCL-6' | 1 | 1 | Regular | 2019-02-12 | 1 | 1 | Machine Shop Started | Shortage | FALSE | Yes |  |  | Done |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78603-2 | 78603 | STENCL-5' | 2 | 1 | Regular | 2019-02-12 | 1 | 1 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78606-1 | 78606 | CLICK-4' | 1 | 1 | High Priority | 2019-02-15 | 1 | 0 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78606-2 | 78606 | CLICK-4' | 2 | 1 | High Priority | 2019-02-15 | 1 | 0 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78606-3 | 78606 | SCULPT-28' | 3 | 1 | High Priority | 2019-02-15 | 4 | 0 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78607-1 | 78607 | STENCL-STFC | 1 | 1 | Regular | 2019-02-11 | 2 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78607-2 | 78607 | STENCL-STFC | 2 | 1 | Regular | 2019-02-11 | 2 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78607-3 | 78607 | STENCL-STFC | 3 | 1 | Regular | 2019-02-11 | 2 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78607-4 | 78607 | STENCL-STFC | 4 | 1 | Regular | 2019-02-11 | 2 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78614-1 | 78614 | WDILED-2 | 1 | 1 | High Priority | 2019-02-07 | 1 | 7 | Machine Shop Started | Shortage | FALSE | Yes |  | Done | Done |  |  | Yes | No | FALSE | FALSE |  |  |  | 2S2-B(BOARD) |  |  | NO | Material | +Cartridge | Material+Cartridge
78616-1 | 78616 | B4LED-8 | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started | Shortage | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | FALSE | FALSE |  | 4 | 2019-02-04 | 2V1-B |  |  | NO
78617-1 | 78617 | GRAZE-16'0" | 1 | 1 | High Priority | 2019-02-22 | 2 | 12 | Scheduled/Released |  | FALSE | Yes | [6 empty] | NA | FALSE | FALSE |  |  |  | 2r2-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78624-1 | 78624 | SKFLED-22 | 1 | 1 | Regular | 2019-03-05 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78624-2 | 78624 | SKFLED-22 | 2 | 1 | Regular | 2019-03-05 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78624-3 | 78624 | SKFLED-22 | 3 | 1 | Regular | 2019-03-05 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78624-4 | 78624 | SKFLED-22 | 4 | 1 | Regular | 2019-02-08 | 1 | 10 | Scheduled/Released |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78624-4 | 78624 | SKFLED-22 | 4 | 2 | Regular | 2019-03-05 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78637-1 | 78637 | CUBLED-8' | 1 | 1 | Regular | 2019-02-05 | 1 | 12 | Packaging Finished | Others | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:11 | 4 | 2019-02-04 | 2v1-a |  |  | NO
78637-2 | 78637 | CUBLED-4' | 2 | 1 | Regular | 2019-02-05 | 1 | 12 | Packaging Finished | Others | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:11 | 4 | 2019-02-04 | 2v1-a |  |  | NO
78640-1 | 78640 | B2LED-4 | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-B |  |  | NO | Material | +Cartridge | Material+Cartridge
78640-3 | 78640 | B2LED-32' | 3 | 1 | Regular | 2019-02-07 | 3 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2T1-B |  |  | NO | Material | +Cartridge | Material+Cartridge
78642-10 | 78642 | B6LED-8 | 10 | 1 | Regular | 2019-04-15 | 1 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-1 | 78642 | B6LED-4 | 1 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released | Wrong info. In SD | TRUE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-11 | 78642 | B6LED-4 | 11 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-2 | 78642 | B6LED-8 | 2 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-3 | 78642 | B2LED-8' | 3 | 1 | Regular | 2019-04-15 | 1 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-4 | 78642 | B6LED-8 | 4 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-5 | 78642 | B6LED-8 | 5 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-6 | 78642 | B6LED-4 | 6 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-7 | 78642 | B6LED-6 | 7 | 1 | Regular | 2019-04-15 | 1 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-8 | 78642 | B6LED-4 | 8 | 1 | Regular | 2019-03-01 | 1 | 4 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78642-9 | 78642 | B6LED-8 | 9 | 1 | Regular | 2019-04-15 | 1 | 18 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78643-5 | 78643 | TB2LED-8' | 5 | 1 | Regular | 2019-02-06 | 1 | 15 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | No | FALSE | FALSE |  | 33 | 2019-01-31 |  |  |  | NO | Material |  | Material
78645-1 | 78645 | TB2LED-6 | 1 | 1 | High Priority | 2019-02-01 | 1 | 12 | Packaging Finished | Mechanical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 11:22 | 19 | 2019-01-28 |  |  |  | NO
78645-2 | 78645 | TB2LED-6 | 2 | 1 | High Priority | 2019-02-01 | 1 | 12 | Packaging Finished | Electrical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-29 11:22 | 19 | 2019-01-28 |  |  |  | NO
78650-1 | 78650 | B4LED-8' | 1 | 1 | High Priority | 2019-02-04 | 1 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 16:02 | 15 | 2019-01-29 |  |  |  | NO
78650-2 | 78650 | B4LED-4' | 2 | 1 | High Priority | 2019-02-04 | 1 | 15 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 16:02 | 15 | 2019-01-29 |  |  |  | NO
78651-1 | 78651 | SLMLED-6 | 1 | 1 | Regular | 2019-02-05 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:20 |  | 2019-01-25 |  |  |  | OK
78651-2 | 78651 | SLMLED-8 | 2 | 1 | Regular | 2019-02-05 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:20 |  | 2019-01-25 |  |  |  | OK
78651-3 | 78651 | SLMLED-12 | 3 | 1 | Regular | 2019-02-05 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-02-04 14:20 |  | 2019-01-25 |  |  |  | OK
78658-1 | 78658 | B3PLED-20'6" | 1 | 1 | Regular | 2019-02-19 | 2 | 12 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78658-2 | 78658 | SCULPT-3 | 2 | 1 | Regular | 2019-02-19 | 1 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78659-1 | 78659 | SCULPT-2X2 | 1 | 1 | Regular | 2019-02-18 | 1 | 18 | Machine Shop Started |  | FALSE |  | Yes | [5 empty] | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78659-2 | 78659 | SCULPT-2X2 | 2 | 1 | Regular | 2019-02-18 | 1 | 18 | Machine Shop Started | Shortage | FALSE |  | Yes | [5 empty] | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78661-1 | 78661 | WWPRFK-8 | 1 | 1 | High Priority | 2019-02-01 | 1 | 12 | Wiring Started | Mechanical issue | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 13:31 | 37 | 2019-02-03 | 2w1-a |  |  | NO | Material |  | Material
78661-2 | 78661 | B4LED-4 | 2 | 1 | High Priority | 2019-02-01 | 1 | 12 | Wiring Started |  | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 13:31 | 37 | 2019-02-03 | 2w1-a |  |  | NO | Material |  | Material
78663-1 | 78663 | SCULPT-8 | 1 | 1 | Regular | 2019-02-05 | 1 | 12 | Machine Shop Started |  | FALSE |  |  | Done | Done | Done |  | Yes | No | FALSE | FALSE |  | #1 | 2019-02-04 | 2v1-a |  |  | NO | Material |  | Material
78664-1 | 78664 | STENCL-12' | 1 | 1 | Regular | 2019-02-12 | 2 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78664-2 | 78664 | STENCL-15' | 2 | 1 | Regular | 2019-02-12 | 3 | 7 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78664-3 | 78664 | STENCL-25' | 3 | 1 | Regular | 2019-02-12 | 4 | 7 | Machine Shop Started | Shortage | FALSE | Yes | [5 empty] | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78667-1 | 78667 | B3LED-16' | 1 | 1 | Regular | 2019-02-06 | 2 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:30 | 4 | 2019-02-04 | 2V2-A |  |  | NO | Material |  | Material
78680-1 | 78680 | TWGLED-4' | 1 | 1 | High Priority | 2019-02-08 | 1 | 18 | Machine Shop Started |  | FALSE |  | Yes |  |  | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-02-01 |  |  |  | NO
78686-1 | 78686 | SCULPT-8 | 1 | 1 | Priority | 2019-01-31 | 1 | 12 | Packaging Finished | Others | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-28 11:14 | #1 | 2019-01-28 | 2s1-b |  |  | NO
78686-2 | 78686 | SCULPT-8 | 2 | 1 | Priority | 2019-01-31 | 1 | 12 | Packaging Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-01-28 11:14 | #1 | 2019-01-28 | 2s1-b |  |  | NO
78687-1 | 78687 | B4LED-4' | 1 | 1 | Regular | 2019-02-18 | 1 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78687-2 | 78687 | WWPRFK-2' | 2 | 1 | Regular | 2019-02-18 | 1 | 12 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78694-1 | 78694 | B4LED-16 | 1 | 1 | Regular | 2019-02-12 | 2 | 1 | Machine Shop Finished |  | FALSE | Yes | [5 empty] | Yes | No | TRUE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78694-2 | 78694 | B4LED-8 | 2 | 1 | Regular | 2019-02-12 | 1 | 1 | Machine Shop Started |  | FALSE | Yes | [5 empty] | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78694-3 | 78694 | B4LED-16 | 3 | 1 | Regular | 2019-02-12 | 2 | 1 | Machine Shop Finished |  | FALSE | Yes | [5 empty] | Yes | No | TRUE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78699-1 | 78699 | B3LED-26' | 1 | 1 | Regular | 2019-02-11 | 3 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
78699-2 | 78699 | B3LED-24' | 2 | 1 | Regular | 2019-02-11 | 2 | 12 | Machine Shop Started | Others | TRUE | Yes | Yes | Done |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
78699-3 | 78699 | B3LED-16' | 3 | 1 | Regular | 2019-02-11 | 2 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
78699-4 | 78699 | B3LED-8' | 4 | 1 | Regular | 2019-02-11 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
78699-5 | 78699 | B3LED-9' | 5 | 1 | Regular | 2019-02-11 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  |  |  | Yes | Yes | FALSE | FALSE |  |  |  | 2w1-b |  |  | NO |  | +Cartridge | +Cartridge
78699-6 | 78699 | B3LED-20' | 6 | 1 | Regular | 2019-02-11 | 2 | 12 | Machine Shop Started |  | FALSE |  | Yes | [5 empty] | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78703-1 | 78703 | SCULPT-4' | 1 | 1 | Regular | 2019-02-11 | 1 | 12 | Machine Shop Started | Missing parts in BOM | TRUE |  |  | Done |  |  |  | Yes | No | FALSE | FALSE |  |  |  | 2v2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78706-1 | 78706 | SCULPT-8' | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Finished | Mechanical issue | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 11:49 | #4 | 2019-02-04 | 2q1-b |  |  | NO
78706-2 | 78706 | SCULPT-8 | 2 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 11:49 | #4 | 2019-02-04 | 2q1-b |  |  | NO
78707-1 | 78707 | SCULPT-K(4X4) | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | FALSE | FALSE |  | #3 | 2019-02-04 | 2v2-b |  |  | NO
78708-1 | 78708 | CUBLED-4' | 1 | 1 | High Priority | 2019-02-25 | 1 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78708-2 | 78708 | CUBLED-6 | 2 | 1 | High Priority | 2019-02-25 | 1 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78708-3 | 78708 | CUBLED-24 | 3 | 1 | High Priority | 2019-02-25 | 2 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78708-4 | 78708 | CUBLED-4' | 4 | 1 | High Priority | 2019-02-25 | 1 | 7 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78710-1 | 78710 | SCULPT-2X6 | 1 | 1 | Regular | 2019-02-06 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Done |  | Yes | Yes | FALSE | FALSE |  | #4 | 2019-02-01 | 2w1-a |  |  | NO
78710-2 | 78710 | SCULPT-6 | 2 | 1 | Regular | 2019-02-06 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | FALSE | FALSE |  | #4 | 2019-02-01 | 2w1-a |  |  | NO
78710-3 | 78710 | SCULPT-4X4 | 3 | 1 | Regular | 2019-02-06 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes | Done |  | Done |  | Yes | Yes | FALSE | FALSE |  | #4 | 2019-02-01 | 2w1-a |  |  | NO
78711-1 | 78711 | B4LED-2' | 1 | 1 | Regular | 2019-02-06 | 1 | 12 | Machine Shop Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:03 | 4 | 2019-02-04 | 2w1-b |  |  | NO | Material |  | Material
78715-1 | 78715 | ZENSQ-16 | 1 | 1 | Regular | 2019-02-07 | 2 | 12 | Machine Shop Finished | Shortage | FALSE | Yes |  | Done | Done | NA |  | Yes | No | TRUE | FALSE | 2019-02-04 14:21 |  | 2019-01-30 |  |  |  | NO | Material |  | Material
78720-1 | 78720 | SKLPTP-52 | 1 | 1 | High Priority | 2019-02-07 | 8 | 7 | Machine Shop Started | Missing info. In SD | TRUE |  | Yes | [5 empty] | NA | FALSE | FALSE |  |  |  | 2t1-a |  |  | NO |  | +Cartridge | +Cartridge
78726-1 | 78726 | B3SLED-16' | 1 | 1 | Regular | 2019-02-19 | 2 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78726-2 | 78726 | B3SLED-4' | 2 | 1 | Regular | 2019-02-19 | 1 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78726-3 | 78726 | SKETCH-AL(7' 10 1/4") | 3 | 1 | Regular | 2019-02-19 | 4 | 1 | Machine Shop Started |  | FALSE | [7 empty] | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78727-1 | 78727 | B4PLED-30' | 1 | 1 | Regular | 2019-02-12 | 3 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78729-1 | 78729 | WB4LED-2' | 1 | 1 | High Priority | 2019-02-07 | 1 | 18 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-04 07:31 | 35 | 2019-02-01 | 2w1-a |  |  | NO
78730-1 | 78730 | PERFKT-CCH | 1 | 1 | High Priority | 2019-02-25 | 10 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78730-2 | 78730 | PERFKT-CCH | 2 | 1 | High Priority | 2019-02-25 | 3 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78730-3 | 78730 | PERFKT-CCH | 3 | 1 | High Priority | 2019-02-25 | 2 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78730-4 | 78730 | PERFKT-CCH | 4 | 1 | High Priority | 2019-02-25 | 3 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78730-5 | 78730 | PERFKT-CCH | 5 | 1 | High Priority | 2019-02-25 | 6 | 4 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78731-1 | 78731 | DIALED-14 | 1 | 1 | Regular | 2019-02-06 | 1 | 10 | Packaging Finished |  | FALSE |  |  |  |  | NA |  |  | NA | FALSE | FALSE | [6 empty] | NO | Material |  | Material
78744-1 | 78744 | SCULPT-4' | 1 | 1 | Regular | 2019-02-05 | 1 | 15 | Machine Shop Finished |  | FALSE |  | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE |  | #1 | 2019-01-28 | 2v2-a |  |  | NO
78759-1 | 78759 | B2LED-10' | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 14:28 | 54 | 2019-02-03 | 2w1-b |  |  | NO | Material |  | Material
78759-2 | 78759 | B2LED-8' | 2 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 14:28 | 54 | 2019-02-03 | 2w1-b |  |  | NO | Material |  | Material
78776-1 | 78776 | STENCL-6 | 1 | 1 | Regular | 2019-03-11 | 1 | 12 | Scheduled/Released |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78778-1 | 78778 | PERFKT-CCWH | 1 | 1 | Regular | 2019-02-07 | 4 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | NA |  | Yes | NA | TRUE | FALSE | 2019-02-01 09:57 |  | 2019-01-30 |  |  |  | OK
78778-2 | 78778 | PERFKT-CCWH | 2 | 1 | Regular | 2019-02-07 | 3 | 4 | Machine Shop Finished | Shortage | FALSE | Yes |  | Yes | Yes | NA |  | Yes | NA | TRUE | FALSE | 2019-02-01 09:57 |  | 2019-01-30 |  |  |  | NO | Material |  | Material
78789-1 | 78789 | WWPRFK-10' | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-03 13:24 |  |  | 2R1-A |  |  | NO |  | +Cartridge | +Cartridge
78796-1 | 78796 | DIALED-22 | 1 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78796-2 | 78796 | DIALED-22 | 2 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78796-3 | 78796 | DIALED-22 | 3 | 1 | Regular | 2019-02-13 | 1 | 10 | Machine Shop Started |  | FALSE |  |  |  |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78798-1 | 78798 | CLICK-4' | 1 | 1 | Regular | 2019-02-12 | 1 | 1 | Machine Shop Started |  | FALSE | Yes |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
78798-2 | 78798 | CLICK-4' | 2 | 1 | Regular | 2019-02-12 | 1 | 1 | Machine Shop Started |  | FALSE | Yes |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
78806-1 | 78806 | B4LED-4' | 1 | 1 | High Priority | 2019-02-05 | 1 | 10 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 12:50 | 4 | 2019-02-04 |  |  |  | NO
78806-2 | 78806 | SCULPT-8' | 2 | 1 | High Priority | 2019-02-05 | 1 | 10 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 12:50 | #5 | 2019-01-30 |  |  |  | NO
78806-3 | 78806 | SCULPT-6' | 3 | 1 | High Priority | 2019-02-05 | 1 | 10 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | No | TRUE | FALSE | 2019-02-05 12:50 | #5 | 2019-01-30 |  |  |  | NO
78812-1 | 78812 | DIALED-24 | 1 | 1 | Regular | 2019-02-06 | 1 | 10 | Packaging Finished |  | FALSE |  |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO | Material |  | Material
78812-2 | 78812 | DIALED-22 | 2 | 1 | Regular | 2019-02-06 | 1 | 10 | Packaging Finished |  | FALSE |  |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO | Material |  | Material
78812-3 | 78812 | DIALED-22 | 3 | 1 | Regular | 2019-02-06 | 1 | 10 | Packaging Finished |  | FALSE |  |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO | Material |  | Material
78812-4 | 78812 | LTLED-4' | 4 | 1 | Regular | 2019-02-06 | 1 | 12 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:02 | 43 | 2019-02-05 | 2v1-a |  |  | NO
78812-5 | 78812 | LTLED-4' | 5 | 1 | Regular | 2019-02-06 | 1 | 12 | Wiring Started | Mechanical issue | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:02 | 43 | 2019-02-05 | 2v1-a |  |  | NO
78812-6 | 78812 | LTLED-4' | 6 | 1 | Regular | 2019-02-06 | 1 | 12 | Wiring Started | Mechanical issue | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:02 | 43 | 2019-02-05 | 2v1-a |  |  | NO
78812-7 | 78812 | LTLED-8' | 7 | 1 | Regular | 2019-02-06 | 1 | 12 | Wiring Started | Others | TRUE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-01 11:02 | 43 | 2019-02-05 | 2v1-a |  |  | NO
78819-1 | 78819 | B2LED-8' | 1 | 1 | Regular | 2019-02-15 | 1 | 12 | Machine Shop Started |  | FALSE | [7 empty] | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78820-1 | 78820 | DIALED-22 | 1 | 1 | Regular | 2019-02-07 | 1 | 10 | Machine Shop Started | Shortage | FALSE |  |  |  |  | NA | Yes | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
78820-2 | 78820 | TB2LED-4' | 2 | 1 | Regular | 2019-02-07 | 1 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done | Yes | Yes | Yes | TRUE | FALSE |  | 20 | 2019-01-30 | 2V1-A |  |  | NO
78820-3 | 78820 | TB2LED-8' | 3 | 1 | Regular | 2019-02-07 | 1 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done | Yes | Yes | Yes | TRUE | FALSE |  | 20 | 2019-01-30 | 2V1-A |  |  | NO
78820-4 | 78820 | TB2LED-4' | 4 | 1 | Regular | 2019-02-07 | 1 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done | Yes | Yes | Yes | TRUE | FALSE |  | 20 | 2019-01-30 | 2V1-A |  |  | NO
78820-5 | 78820 | TB2LED-8' | 5 | 1 | Regular | 2019-02-07 | 1 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done | Yes | Yes | Yes | TRUE | FALSE |  | 20 | 2019-01-30 | 2V1-A |  |  | NO
78822-1 | 78822 | B3LED-4' | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Yes |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:29 |  | 2019-02-05 | 2T2-A |  |  | OK
78822-2 | 78822 | B3LED-6' | 2 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Yes |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:29 |  | 2019-02-05 | 2T2-A |  |  | OK
78822-3 | 78822 | PERFKT-CCL | 3 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:29 |  | 2019-01-31 | 2T2-A |  |  | OK
78822-4 | 78822 | PERFKT-CCL | 4 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:29 |  | 2019-01-31 | 2T2-A |  |  | OK
78825-1 | 78825 | WB4LED-4' | 1 | 1 | High Priority | 2019-02-12 | 1 | 15 | Machine Shop Finished |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78825-2 | 78825 | WB4LED-4' | 2 | 1 | High Priority | 2019-02-12 | 1 | 15 | Machine Shop Finished |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78844-1 | 78844 | B4LED-6' | 1 | 1 | Regular | 2019-02-15 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78854-1 | 78854 | B3LED-4' | 1 | 1 | Regular | 2019-02-06 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes |  |  |  | Done |  | Yes | NA | TRUE | FALSE | 2019-02-01 11:03 | 33 | 2019-01-31 |  |  |  | NO | Material |  | Material
78861-1 | 78861 | DIALED-22 | 1 | 1 | Regular | 2019-02-06 | 1 | 10 | Wiring Started |  | FALSE |  |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO | Material |  | Material
78861-2 | 78861 | DIALED-22 | 2 | 1 | Regular | 2019-02-06 | 1 | 10 | Wiring Started |  | FALSE |  |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO | Material |  | Material
78864-1 | 78864 | ZENSQ-8 | 1 | 1 | Regular | 2019-02-04 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-01-30 14:51 |  | 2019-01-25 |  |  |  | OK
78864-2 | 78864 | ZENSQ-4 | 2 | 1 | Regular | 2019-02-04 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | NA |  | Yes | Yes | TRUE | FALSE | 2019-01-30 14:51 |  | 2019-01-25 |  |  |  | OK
78866-1 | 78866 | B4PLED-4' | 1 | 1 | High Priority | 2019-02-07 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:30 | [5 empty] | NO |  | +Cartridge | +Cartridge
78866-2 | 78866 | B4PLED-8' | 2 | 1 | High Priority | 2019-02-07 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:30 | [5 empty] | NO |  | +Cartridge | +Cartridge
78875-1 | 78875 | STENCL-STFC | 1 | 1 | High Priority | 2019-02-11 | 4 | 4 | Scheduled/Released |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
78887-1 | 78887 | SCULPT-8' | 1 | 1 | Regular | 2019-02-14 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2w1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
78889-1 | 78889 | PERFKT-CCH | 1 | 1 | Regular | 2019-02-08 | 2 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | NA |  | Yes | NA | TRUE | FALSE | 2019-02-01 09:57 |  | 2019-01-31 |  |  |  | OK
78889-2 | 78889 | PERFKT-CCH | 2 | 1 | Regular | 2019-02-08 | 1 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | NA |  | Yes | NA | TRUE | FALSE | 2019-02-01 09:57 |  | 2019-01-31 |  |  |  | OK
78889-3 | 78889 | PERFKT-CCH | 3 | 1 | Regular | 2019-02-08 | 2 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | NA |  | Yes | NA | TRUE | FALSE | 2019-02-01 09:57 |  | 2019-01-31 |  |  |  | OK
78889-4 | 78889 | PERFKT-CCH | 4 | 1 | Regular | 2019-02-08 | 2 | 4 | Machine Shop Finished |  | FALSE | Yes | Yes | Yes | Yes | NA |  | Yes | NA | TRUE | FALSE | 2019-02-01 09:58 |  | 2019-01-31 |  |  |  | OK
78890-1 | 78890 | B4LED-4 | 1 | 1 | High Priority | 2019-02-15 | 1 | 12 | Machine Shop Finished |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78893-1 | 78893 | B2LED-3 | 1 | 1 | High Priority | 2019-02-21 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78908-1 | 78908 | AULED-24 | 1 | 1 | Regular | 2019-02-15 | 1 | 10 | Scheduled/Released | Others | FALSE FALSE FALSE FALSE: TRUE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
78908-2 | 78908 | AULED-14 | 2 | 1 | Regular | 2019-02-15 | 1 | 10 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
78908-3 | 78908 | AULED-22 | 3 | 1 | Regular | 2019-02-15 | 1 | 10 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
78908-4 | 78908 | B4LED-4' | 4 | 1 | Regular | 2019-02-15 | 1 | 15 | Scheduled/Released | PM wrong/missing info | FALSE FALSE FALSE FALSE: TRUE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78908-5 | 78908 | B3LED-4' | 5 | 1 | Regular | 2019-02-15 | 1 | 15 | Scheduled/Released | PM wrong/missing info | FALSE FALSE FALSE FALSE: TRUE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78908-6 | 78908 | AIRLED-2' | 6 | 1 | Regular | 2019-02-15 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78911-1 | 78911 | B6LED-6 | 1 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78911-2 | 78911 | B6LED-6 | 2 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78914-1 | 78914 | B3LED-5' | 1 | 1 | Regular | 2019-02-15 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78914-2 | 78914 | B3LED-6' | 2 | 1 | Regular | 2019-02-15 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78916-1 | 78916 | B4LED-4' | 1 | 1 | Regular | 2019-02-14 | 1 | 18 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78916-2 | 78916 | B4LED-4' | 2 | 1 | Regular | 2019-02-14 | 1 | 18 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78926-1 | 78926 | B4PLED-148 3/4" | 1 | 1 | Regular | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78927-1 | 78927 | DIALED-DIALED | 1 | 1 | High Priority | 2019-02-06 | 1 | 10 | Wiring Started | Others | FALSE FALSE FALSE FALSE: TRUE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-01-29 | 2t2-b |  |  | NO | Material |  | Material
78927-2 | 78927 | DIALED-DIALED | 2 | 1 | High Priority | 2019-02-06 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-01-29 | 2t2-b |  |  | NO | Material |  | Material
78927-3 | 78927 | DIALED-DIALED | 3 | 1 | High Priority | 2019-02-06 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-01-29 | 2t2-b |  |  | NO | Material |  | Material
78927-4 | 78927 | SCULPT-4' | 4 | 1 | High Priority | 2019-02-06 | 1 | 7 | Machine Shop Finished | Others | TRUE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-30 16:03 | [5 empty] | NO |  | +Cartridge | +Cartridge
78927-5 | 78927 | SCULPT-16' | 5 | 1 | High Priority | 2019-02-06 | 2 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-30 16:03 | [5 empty] | NO |  | +Cartridge | +Cartridge
78927-6 | 78927 | SCULPT-16' | 6 | 1 | High Priority | 2019-02-06 | 2 | 7 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-30 16:03 | [5 empty] | NO |  | +Cartridge | +Cartridge
78930-1 | 78930 | B3LED-16'7 1/2" | 1 | 1 | High Priority | 2019-02-07 | 3 | 12 | Machine Shop Started | PM wrong/missing info | FALSE FALSE FALSE FALSE: TRUE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78933-1 | 78933 | DIALED-22 | 1 | 1 | Regular | 2019-02-07 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
78934-1 | 78934 | DIALED-22 | 1 | 1 | Regular | 2019-03-06 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
78936-1 | 78936 | B4LED-8' | 1 | 1 | Regular | 2019-02-05 | 1 | 12 | Wiring Started | Mechanical issue | TRUE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 10:35 | 9 | 2019-02-03 |  |  |  | NO
78943-1 | 78943 | SCULPT-8' | 1 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: Done; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2t1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
78949-1 | 78949 | B4LED-12' | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: TRUE; FALSE FALSE FALSE FALSE: FALSE | 2019-02-03 13:23 |  |  | 2V2-A |  |  | NO | Material | +Cartridge | Material+Cartridge
78964-1 | 78964 | PERFKT-CCH | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes |  | Done | Done | NA |  | Yes | NA | TRUE | FALSE | 2019-02-04 14:28 |  | 2019-01-31 |  |  |  | NO | Material |  | Material
78967-10 | 78967 | B2LED-3' | 10 | 1 | Regular | 2019-02-22 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-1 | 78967 | B2LED-6' | 1 | 1 | Regular | 2019-02-22 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-2 | 78967 | B2LED-18' | 2 | 1 | Regular | 2019-02-22 | 2 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-3 | 78967 | B2LED-32' | 3 | 1 | Regular | 2019-02-22 | 3 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-4 | 78967 | B2LED-4' | 4 | 1 | Regular | 2019-02-22 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-5 | 78967 | B2LED-27' | 5 | 1 | Regular | 2019-02-22 | 3 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-6 | 78967 | B2LED-10' | 6 | 1 | Regular | 2019-02-22 | 3 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-7 | 78967 | B2LED-12' | 7 | 1 | Regular | 2019-02-22 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-8 | 78967 | B2LED-12' | 8 | 1 | Regular | 2019-02-22 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78967-9 | 78967 | B2LED-2' | 9 | 1 | Regular | 2019-02-22 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78968-1 | 78968 | B2LED-4' | 1 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Finished |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78970-1 | 78970 | CLICK-4' | 1 | 1 | Regular | 2019-02-18 | 1 | 18 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
78970-2 | 78970 | CLICK-8' | 2 | 1 | Regular | 2019-02-18 | 1 | 18 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
78971-1 | 78971 | B3LED-4' | 1 | 1 | Regular | 2019-02-05 | 1 | 12 | Machine Shop Finished |  | FALSE |  | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 10:27 | 4 | 2019-02-04 | 2T1-B |  |  | NO
78974-1 | 78974 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 2 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78975-1 | 78975 | B3LED-8 | 1 | 1 | Regular | 2019-02-28 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78982-1 | 78982 | B4LED-6' | 1 | 1 | Regular | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78983-1 | 78983 | SCULPT-66' | 1 | 1 | Regular | 2019-02-20 | 9 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78983-2 | 78983 | SCULPT-66' | 2 | 1 | Regular | 2019-02-20 | 9 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78983-3 | 78983 | SCULPT-66' | 3 | 1 | Regular | 2019-02-20 | 9 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78984-1 | 78984 | STNCLS-8'0" | 1 | 1 | High Priority | 2019-02-14 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78986-1 | 78986 | B4LED-6' | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE |  | 1 | 2019-02-05 | 2T1-B |  |  | NO
78988-1 | 78988 | BEAM4-8' | 1 | 1 | High Priority | 2019-02-12 | 1 | 12 | Machine Shop Started | Shortage | FALSE | Yes |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
78988-2 | 78988 | BEAM4-4 | 2 | 1 | High Priority | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
78989-1 | 78989 | SCULPT-10 | 1 | 1 | Regular | 2019-02-28 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78989-2 | 78989 | TB2LED-19' 4 3/4" | 2 | 1 | Regular | 2019-02-28 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
78994-1 | 78994 | SCULPT-6 | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started | Wrong part in BOM | TRUE | Yes | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 10:27 | #4 | 2019-02-04 | 2s2-a |  |  | NO
78994-2 | 78994 | SCULPT-8 | 2 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  |  | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 10:27 | #4 | 2019-02-04 | 2s2-a |  |  | NO
78995-1 | 78995 | STENCL-9 | 1 | 1 | High Priority | 2019-03-11 | 2 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79005-1 | 79005 | AURA-AULED | 1 | 1 | Regular | 2019-02-05 | 1 | 10 | Packaging Finished |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-01-28 |  |  |  | NO | Material |  | Material
79008-1 | 79008 | B3LED-12 | 1 | 1 | High Priority | 2019-03-04 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79008-2 | 79008 | B3LED-12 | 2 | 1 | High Priority | 2019-03-04 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79008-3 | 79008 | B3LED-16 | 3 | 1 | High Priority | 2019-03-04 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79008-4 | 79008 | B3LED-16 | 4 | 1 | High Priority | 2019-03-04 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79010-1 | 79010 | AIRLED-4' | 1 | 1 | Regular | 2019-02-01 | 1 | 12 | Machine Shop Started | Others | FALSE FALSE FALSE FALSE: TRUE; Done Done Done Done: Done; Done Done Done Done: Done; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  | 4 | 2019-02-04 |  |  |  | NO | Material |  | Material
79011-2 | 79011 | SKYPOL-SKPLED | 2 | 1 | Regular | 2019-02-01 | 1 | 12 | Wiring Started | Others | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 11:47 | #9 | 2019-01-29 | 2v1-a |  |  | NO | Material |  | Material
79011-3 | 79011 | SKYPOL-SKPLED | 3 | 1 | Regular | 2019-02-01 | 1 | 12 | Wiring Started | Others | FALSE |  |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 11:47 | #9 | 2019-01-29 | 2v1-a |  |  | NO | Material |  | Material
79012-1 | 79012 | B2LED-8' | 1 | 1 | Regular | 2019-05-02 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79014-1 | 79014 | B2LED-4' | 1 | 1 | Regular | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: Done; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79015-1 | 79015 | B3LED-16' | 1 | 1 | Regular | 2019-02-14 | 2 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79015-2 | 79015 | B3LED-16' | 2 | 1 | Regular | 2019-02-14 | 2 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79015-3 | 79015 | B3LED-16' | 3 | 1 | Regular | 2019-02-14 | 2 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79017-1 | 79017 | SCULPT-8' 11" | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 14:22 | #3 | 2019-02-04 | 2w1-b |  |  | NO
79019-1 | 79019 | SCULPT-TR60X4 | 1 | 1 | High Priority | 2019-02-05 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | Done |  | Yes | NA | FALSE | FALSE |  | #8 | 2019-01-30 | 2v1-b |  |  | NO
79020-1 | 79020 | SCULPT-20' | 1 | 1 | Regular | 2019-03-05 | 4 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79020-2 | 79020 | SCULPT-5 | 2 | 1 | Regular | 2019-03-05 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79020-3 | 79020 | SCULPT-16' | 3 | 1 | Regular | 2019-03-05 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79024-1 | 79024 | B6LED-5 | 1 | 1 | Regular | 2019-02-05 | 1 | 12 | Order UnShipped |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 14:21 | 4 | 2019-02-04 | 2T1-A |  |  | NO
79034-1 | 79034 | ZENSQ-44 | 1 | 1 | High Priority | 2019-02-04 | 4 | 4 | Machine Shop Finished | Shortage | TRUE | Yes |  | Done | Done | NA |  | Yes | Yes | FALSE | FALSE |  |  | 2019-01-25 |  |  |  | NO | Material |  | Material
79035-1 | 79035 | SCULPT-10' | 1 | 1 | Regular | 2019-02-11 | 2 | 12 | Machine Shop Started | Others | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2w1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
79041-1 | 79041 | SCULPT-4' | 1 | 1 | Regular | 2019-02-18 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79042-13 | 79042 | DAYFLED-22 | 13 | 1 | Regular | 2019-02-22 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79042-14 | 79042 | DAYFLED-22 | 14 | 1 | Regular | 2019-02-22 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79043-1 | 79043 | DIALED-22 | 1 | 1 | Regular | 2019-02-05 | 1 | 10 | Packaging Finished |  | FALSE |  |  | Done | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-28 |  |  |  | NO | Material |  | Material
79048-1 | 79048 | CLICK-4' | 1 | 1 | Regular | 2019-02-08 | 1 | 1 | Machine Shop Started |  | FALSE |  | Yes |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-01 |  |  |  | OK
79049-1 | 79049 | B2LED-8' | 1 | 1 | Regular | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79049-2 | 79049 | B2LED-5' | 2 | 1 | Regular | 2019-02-12 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79074-1 | 79074 | B2LED-8 | 1 | 1 | Regular | 2019-02-28 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79074-2 | 79074 | B2LED-14 | 2 | 1 | Regular | 2019-02-28 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79074-3 | 79074 | B2LED-17 | 3 | 1 | Regular | 2019-02-28 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79076-1 | 79076 | B4LED-BBWDILED | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Finished |  | FALSE | Yes | Yes | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-02-04 11:49 |  |  | 2T1-B |  |  | NO |  | +Cartridge | +Cartridge
79078-1 | 79078 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 5 | 7 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79078-2 | 79078 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 5 | 7 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79080-1 | 79080 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 9 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79080-2 | 79080 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 9 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79080-3 | 79080 | STENCL-STFC | 3 | 1 | Regular | 2019-02-14 | 6 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79082-1 | 79082 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 3 | 7 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79082-2 | 79082 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 6 | 7 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79083-1 | 79083 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 4 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79083-2 | 79083 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 2 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79083-3 | 79083 | STENCL-STFC | 3 | 1 | Regular | 2019-02-14 | 4 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79084-1 | 79084 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 9 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79084-2 | 79084 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 8 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79084-3 | 79084 | STENCL-STFC | 3 | 1 | Regular | 2019-02-14 | 8 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79084-4 | 79084 | STENCL-STFC | 4 | 1 | Regular | 2019-02-14 | 10 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79085-1 | 79085 | B4LED-2 | 1 | 1 | Regular | 2019-02-05 | 1 | 10 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 09:58 | 4 | 2019-02-03 | 2T1-A |  |  | NO
79086-1 | 79086 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 8 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79086-2 | 79086 | STENCL-STFC | 2 | 1 | Regular | 2019-02-14 | 2 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79086-3 | 79086 | STENCL-STFC | 3 | 1 | Regular | 2019-02-14 | 4 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79089-1 | 79089 | STENCL-STFC | 1 | 1 | Regular | 2019-02-14 | 8 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79098-1 | 79098 | WB4LED-4' | 1 | 1 | Regular | 2019-02-11 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: Done; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
79101-1 | 79101 | SLMLED-32 | 1 | 1 | Regular | 2019-02-19 | 3 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79104-1 | 79104 | AULED-22 | 1 | 1 | Regular | 2019-02-20 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79104-2 | 79104 | B3LED-2' | 2 | 1 | Regular | 2019-02-20 | 1 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79104-3 | 79104 | B3LED-2' | 3 | 1 | Regular | 2019-02-20 | 1 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79104-4 | 79104 | B3LED-4' | 4 | 1 | Regular | 2019-02-20 | 1 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79104-5 | 79104 | B3LED-4' | 5 | 1 | Regular | 2019-02-20 | 1 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79106-1 | 79106 | B4LED-6' | 1 | 1 | Priority | 2019-02-07 | 1 | 12 | Packaging Finished | Others | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 07:36 | 9 | 2019-02-03 | 2V1-B |  |  | NO | Material |  | Material
79106-2 | 79106 | B4LED-6' | 2 | 1 | Priority | 2019-02-07 | 1 | 12 | Packaging Finished | Others | FALSE | Yes |  | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-05 07:36 | 9 | 2019-02-03 | 2V1-B |  |  | NO | Material |  | Material
79110-1 | 79110 | POLED-22 | 1 | 1 | High Priority | 2019-02-11 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
79116-1 | 79116 | BEAM6-4 | 1 | 1 | Priority | 2019-02-11 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | OK
79121-1 | 79121 | STNCLS-8' | 1 | 1 | Regular | 2019-02-12 | 1 | 4 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2w2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
79124-1 | 79124 | CLICK-12' | 1 | 1 | Regular | 2019-02-11 | 2 | 18 | Machine Shop Started |  | FALSE |  |  |  | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-02-03 |  |  |  | NO | Material |  | Material
79125-1 | 79125 | WB4LED-5' | 1 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79133-1 | 79133 | SCULPT-5' 6" | 1 | 1 | High Priority | 2019-02-07 | 1 | 12 | Machine Shop Finished | Wrong info. In SD | TRUE | Yes | Yes | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-05 10:30 | #3 | 2019-02-04 | 2w2-a |  |  | NO
79135-1 | 79135 | WB4LED-5' | 1 | 1 | High Priority | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  | Done |  |  |  | Yes | No | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79139-1 | 79139 | SCULPT-68" | 1 | 1 | Regular | 2019-02-25 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79149-1 | 79149 | SCULPT-4 | 1 | 1 | Regular | 2019-02-14 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2w2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
79151-1 | 79151 | B4LED-205 1/2" | 1 | 1 | Regular | 2019-02-25 | 5 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79157-1 | 79157 | B3LED-6' | 1 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79157-2 | 79157 | B3LED-8' | 2 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79157-3 | 79157 | B3LED-8' | 3 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79163-1 | 79163 | SCULPT-4' | 1 | 1 | High Priority | 2019-02-21 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 | 2w1-a |  |  | NO
79163-2 | 79163 | SCULPT-4' | 2 | 1 | High Priority | 2019-02-21 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: Yes; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 | 2w1-a |  |  | NO
79163-3 | 79163 | SCULPT-6' | 3 | 1 | High Priority | 2019-02-21 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: Yes; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 | 2w1-a |  |  | NO
79164-1 | 79164 | B2LED-8' | 1 | 1 | Regular | 2019-02-11 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
79168-1 | 79168 | B6LED-4' | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
79169-1 | 79169 | B4LED-10' | 1 | 1 | Regular | 2019-02-15 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79170-1 | 79170 | MK-R-DW-1X1-1 | 1 | 1 | Regular | 2019-02-01 | 0 | 10 | Order UnShipped |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79183-1 | 79183 | SCULPT-PN60X2 | 1 | 1 | Regular | 2019-02-27 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79183-2 | 79183 | SCULPT-PP60X2 | 2 | 1 | Regular | 2019-02-27 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79186-1 | 79186 | B4LED-28 | 1 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Started | Shortage | FALSE | Yes | Yes |  | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2R1-A |  |  | NO |  | +Cartridge | +Cartridge
79187-1 | 79187 | ZENSQ-48 | 1 | 1 | Regular | 2019-02-14 | 4 | 1 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79187-2 | 79187 | ZENSQ-32 | 2 | 1 | Regular | 2019-02-14 | 4 | 1 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79187-3 | 79187 | ZENSQ-61 | 3 | 1 | Regular | 2019-02-14 | 7 | 1 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79189-1 | 79189 | B4LED-4'7" | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2v1-a |  |  | NO | Material | +Cartridge | Material+Cartridge
79194-1 | 79194 | CLICK-4 | 1 | 1 | High Priority | 2019-02-15 | 1 | 1 | Machine Shop Started | Shortage | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79194-2 | 79194 | CLICK-8 | 2 | 1 | High Priority | 2019-02-15 | 1 | 1 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79194-3 | 79194 | SCULPT-TR60X2 | 3 | 1 | High Priority | 2019-02-15 | 1 | 1 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79198-1 | 79198 | SCULPT-14' | 1 | 1 | High Priority | 2019-02-05 | 2 | 12 | Given to Shipping |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 11:49 | #4 | 2019-02-04 | 2w2-a |  |  | NO
79201-1 | 79201 | CUBIC-24 | 1 | 1 | Regular | 2019-02-13 | 2 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 |  |  |  | NO | Material |  | Material
79210-1 | 79210 | B2LED-40 | 1 | 1 | Regular | 2019-03-01 | 4 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79210-2 | 79210 | B2LED-4' | 2 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79210-3 | 79210 | B2LED-6' | 3 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79210-4 | 79210 | B2LED-8' | 4 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79217-1 | 79217 | SCULPT-8 | 1 | 1 | High Priority | 2019-02-21 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79220-1 | 79220 | POLED-22 | 1 | 1 | Regular | 2019-02-07 | 1 | 10 | Machine Shop Started |  | FALSE |  |  | Done | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-30 |  |  |  | NO | Material |  | Material
79225-1 | 79225 | SCULPT-6 | 1 | 1 | Regular | 2019-02-14 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2s2-a |  |  | NO | Material | +Cartridge | Material+Cartridge
79234-1 | 79234 | B3LED-12' | 1 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Started |  | FALSE | Yes |  |  | Done |  |  | Yes | NA | FALSE | FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79240-1 | 79240 | DIALED-22 | 1 | 1 | Regular | 2019-02-06 | 1 | 10 | Machine Shop Started |  | FALSE |  |  | Done | Done | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-29 |  |  |  | NO | Material |  | Material
79240-2 | 79240 | DIALED-22 | 2 | 1 | Regular | 2019-02-06 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79245-1 | 79245 | PLNLED-POLED | 1 | 1 | Regular | 2019-02-21 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79245-2 | 79245 | PLNLED-POLED | 2 | 1 | Regular | 2019-02-21 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79248-1 | 79248 | SLMLED-8 | 1 | 1 | Regular | 2019-02-21 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79259-1 | 79259 | B3PLED-24' | 1 | 1 | Regular | 2019-02-14 | 2 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79259-2 | 79259 | SCULPT-98 11/16" | 2 | 1 | Regular | 2019-02-14 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79264-1 | 79264 | B4LED-4 | 1 | 1 | Regular | 2019-02-13 | 1 | 12 | Machine Shop Finished |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-10 | 79279 | B4PLED-9' 3/4" | 10 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-1 | 79279 | B4PLED-14' | 1 | 1 | Regular | 2019-03-01 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-11 | 79279 | B4PLED-9' 3/4" | 11 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-12 | 79279 | B4PLED-9' 3/4" | 12 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-13 | 79279 | B4PLED-9' 3/4" | 13 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-14 | 79279 | B4PLED-9' 3/4" | 14 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-15 | 79279 | B4PLED-9' 3/4" | 15 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-2 | 79279 | B4PLED-18'5 3/4" | 2 | 1 | Regular | 2019-03-01 | 2 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-3 | 79279 | B4PLED-9' 3/4" | 3 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-4 | 79279 | B4PLED-9' 3/4" | 4 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-5 | 79279 | B4PLED-9' 3/4" | 5 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-6 | 79279 | B4PLED-9' 3/4" | 6 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-7 | 79279 | B4PLED-9' 3/4" | 7 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-8 | 79279 | B4PLED-9' 3/4" | 8 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79279-9 | 79279 | B4PLED-9' 3/4" | 9 | 1 | Regular | 2019-03-01 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79282-1 | 79282 | DIALED-22 | 1 | 1 | Regular | 2019-02-21 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79284-1 | 79284 | B2SLED-2 | 1 | 1 | High Priority | 2019-02-01 | 1 | 12 | Packaging Finished | Others | TRUE |  |  | Done | Done |  |  | Yes | Yes | TRUE | FALSE | 2019-01-31 17:07 |  | 2019-02-04 | 2r1-a |  | Done | NO | Material | +Cartridge | Material+Cartridge
79285-1 | 79285 | B2LED-11 | 1 | 1 | Regular | 2019-02-11 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
79303-1 | 79303 | LTLED-4' | 1 | 1 | Regular | 2019-02-28 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79303-2 | 79303 | B2LED-4' | 2 | 1 | Regular | 2019-02-28 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79303-3 | 79303 | B2LED-4' | 3 | 1 | Regular | 2019-02-28 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79303-4 | 79303 | B2LED-4' | 4 | 1 | Regular | 2019-02-28 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79303-5 | 79303 | B2LED-4' | 5 | 1 | Regular | 2019-02-28 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79303-6 | 79303 | B2LED-4' | 6 | 1 | Regular | 2019-02-28 | 1 | 15 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79304-1 | 79304 | B4LED-8' | 1 | 1 | Regular | 2019-03-04 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79304-2 | 79304 | B4LED-4' | 2 | 1 | Regular | 2019-03-04 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79304-3 | 79304 | B4LED-16' | 3 | 1 | Regular | 2019-03-04 | 2 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79304-4 | 79304 | B4LED-8' | 4 | 1 | Regular | 2019-03-04 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79304-5 | 79304 | B3PLED-3' | 5 | 1 | Regular | 2019-03-04 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79304-6 | 79304 | B3PLED-6' | 6 | 1 | Regular | 2019-03-04 | 1 | 7 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79307-5 | 79307 | SCULPT-K(L4X4) | 5 | 1 | Regular | 2019-02-08 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | NA | FALSE | FALSE |  |  |  | 2t3-b |  |  | NO |  | +Cartridge | +Cartridge
79309-1 | 79309 | DAY-DAYF | 1 | 1 | Regular | 2019-02-18 | 1 | 10 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79311-1 | 79311 | PERFKT-CCH | 1 | 1 | Regular | 2019-02-07 | 1 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
79311-2 | 79311 | PERFKT-CCH | 2 | 1 | Regular | 2019-02-07 | 1 | 4 | Machine Shop Started |  | FALSE | Yes |  | Done |  | NA |  | Yes | NA | FALSE | FALSE |  |  | 2019-01-31 |  |  |  | NO | Material |  | Material
79314-1 | 79314 | B4LED-11' | 1 | 1 | Regular | 2019-02-28 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79314-2 | 79314 | B4LED-5' | 2 | 1 | Regular | 2019-02-28 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79316-1 | 79316 | B4LED-4 | 1 | 1 | Regular | 2019-02-21 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79320-1 | 79320 | B2LED-32' | 1 | 1 | High Priority | 2019-02-04 | 4 | 12 | Packaging Finished |  | FALSE |  |  | Done | Done | Done |  | Yes | Yes | TRUE | FALSE | 2019-02-03 10:27 | 4 | 2019-02-04 | 2w2-a |  |  | NO | Material |  | Material
79322-1 | 79322 | GRAZE-24 3/4" | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  |  | 2q1-b |  |  | NO | Material | +Cartridge | Material+Cartridge
79342-1 | 79342 | AULED-24 | 1 | 1 | Regular | 2019-02-07 | 1 | 10 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79346-1 | 79346 | B4LED-4 | 1 | 1 | High Priority | 2019-02-19 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79347-1 | 79347 | B2SLED-110 1/2" | 1 | 1 | Regular | 2019-02-07 | 1 | 12 | Machine Shop Started |  | FALSE | Yes | Yes |  |  |  |  | Yes | Yes | FALSE | FALSE | [6 empty] | NO |  | +Cartridge | +Cartridge
79351-1 | 79351 | B3LED-4' | 1 | 1 | Regular | 2019-02-15 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79370-1 | 79370 | DIALED-22 | 1 | 1 | High Priority | 2019-02-11 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79372-1 | 79372 | SCULPT-5' | 1 | 1 | Regular | 2019-02-15 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79372-2 | 79372 | SCULPT-5' | 2 | 1 | Regular | 2019-02-15 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79372-3 | 79372 | SCULPT-5' | 3 | 1 | Regular | 2019-02-15 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79372-4 | 79372 | SCULPT-5' | 4 | 1 | Regular | 2019-02-15 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79373-1 | 79373 | SCULPT-4' | 1 | 1 | High Priority | 2019-02-21 | 1 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79373-2 | 79373 | SCULPT-6' | 2 | 1 | High Priority | 2019-02-21 | 1 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79373-3 | 79373 | SCULPT-24' | 3 | 1 | High Priority | 2019-02-21 | 2 | 15 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79375-1 | 79375 | SKETCH-AL 1' 11 9/16" | 1 | 1 | High Priority | 2019-02-01 | 1 | 1 | Wiring Started |  | FALSE |  | Yes | Done | Done | Done |  | Yes | NA | TRUE | FALSE | 2019-02-04 10:27 | 4 | 2019-02-04 | 2s1-a |  |  | NO
79379-1 | 79379 | B4LED-4' | 1 | 1 | Priority | 2019-02-14 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79411-1 | 79411 | DAYFLED-22 | 1 | 1 | High Priority | 2019-02-07 | 1 | 10 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material |  | Material
79418-1 | 79418 | ZEN-4 | 1 | 1 | High Priority | 2019-02-05 | 1 | 4 | Machine Shop Started | Shortage | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 | 2q2-b |  |  | NO
79418-2 | 79418 | ZEN-4 | 2 | 1 | High Priority | 2019-02-05 | 1 | 4 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 | 2q2-b |  |  | NO
79418-3 | 79418 | ZENSQ-4 | 3 | 1 | High Priority | 2019-02-05 | 1 | 4 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 |  |  |  | NO
79418-4 | 79418 | ZENSQ-4 | 4 | 1 | High Priority | 2019-02-05 | 1 | 4 | Machine Shop Started | Shortage | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 |  |  |  | NO
79425-1 | 79425 | TB2LED-19 1/4" | 1 | 1 | High Priority | 2019-02-18 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79431-1 | 79431 | AULED-22 | 1 | 1 | High Priority | 2019-02-12 | 1 | 10 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Done Done Done Done: NA; Yes Yes Yes Yes: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-04 |  |  |  | NO | Material |  | Material
79453-1 | 79453 | B4LED-7 | 1 | 1 | Regular | 2019-02-18 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79483-1 | 79483 | B3LED-4 | 1 | 1 | Priority | 2019-02-14 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79488-1 | 79488 | STNCLS-STSFF | 1 | 1 | High Priority | 2019-02-19 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79488-2 | 79488 | STNCLS-4 | 2 | 1 | High Priority | 2019-02-19 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79488-3 | 79488 | STNCLS-4 | 3 | 1 | High Priority | 2019-02-19 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: No; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79488-4 | 79488 | SCULPT-4 | 4 | 1 | High Priority | 2019-02-19 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79488-5 | 79488 | SCULPT-4 | 5 | 1 | High Priority | 2019-02-19 | 1 | 0 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge
79502-1 | 79502 | B3LED-2 | 1 | 1 | High Priority | 2019-02-06 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 |  |  |  | NO
79502-2 | 79502 | B3LED-2 | 2 | 1 | High Priority | 2019-02-06 | 1 | 12 | Machine Shop Started |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: Yes; Done Done Done Done: Yes; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE |  |  | 2019-02-05 |  |  |  | NO
79537-1 | 79537 | SKLPTP-7' 11 1/2" | 1 | 1 | Regular | 2019-02-18 | 1 | 12 | Scheduled/Released |  | FALSE FALSE FALSE FALSE: FALSE; Yes Yes Yes Yes: NA; TRUE TRUE TRUE TRUE: FALSE; FALSE FALSE FALSE FALSE: FALSE | [6 empty] | NO | Material | +Cartridge | Material+Cartridge

## MS Dashboard
job-no | Order | Line | Rel | Category | Part | Part Description | Non Conformance Reason | Status | MS Date | MS Time | Machine Shop Due Date | Scheduled Ship Date | Open Qty | Total Sections | PM | Pick Status | Sched Date Priority | Production Comment | Fixture Type | Assembly Line | SD vs BOM | Material (Stores) | Type Labels | Extrusion cut double saw | Cut Flanges | CNC Holes | Asymmetric (CNC) | CNC Controls | CNC Cartridge | Milling MFG | End Plates Joiners | Punch Holes | Welding Corners | SAW Cartridge | Body Assembly | LED Sub Assembly | MSLens | DeliveredChk | DeliveredDate | RequestDate | Material Kit | Issue Resolved
58763-1 | 58763 | 1 | 1 | Regular | PRMLED-S | SP16237(1)-PWWLED-B3-MF-800-80-50-S-4-W-277-DP-1-OS(1)-C(5000K) | Shortage | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 111 | 111 | Gagandeep Singh |  | Regular |  | FS | 15 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
59584-10 | 59584 | 10 | 1 | Regular | SCULPT-61'11" | SCRPAT-OPR-90(1)-300-80-35-FL-61'11"-NL-W-UNV-DP-1+E(3)-D |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 7 | Gagandeep Singh | Picked - Complete | High Priority |  | F4-16'2"X45'9"'-L SHAPE | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
59584-12 | 59584 | 12 | 1 | Regular | SCULPT-226'3/8" | SCRPAT-OPR-90(2)-300-80-35-FL-226'3/8"-NL-W-UNV-DP-1+E(2)-D | Missing parts in BOM | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 21 | Gagandeep Singh | Picked - Complete | High Priority |  | F4-12'10"X67'4-5/8"X145'9 3/4" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | TRUE
59584-66 | 59584 | 66 | 1 | Regular | SCULPT-35'5" | SCRPAT-OPR-90(1)-300-80-35-FL-34'9"-NL-W-UNV-DP-1+E(2)-D |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 5 | Gagandeep Singh | Picked - Complete | High Priority |  | F4-16'2"X18'7"-L SHAPE | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
59584-67 | 59584 | 67 | 1 | Regular | SCULPT-211'11 1/4 | SCRPAT-OPR-90(4)-300-80-35-FL-211'11 1/4-NL-W-UNV-DP-1+E(7)-D |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 22 | Gagandeep Singh | Picked - Complete | High Priority |  | F4-57'6-3/4"X31'4"X29'1"X65'2"X28'9-1/2 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
63435-2 | 63435 | 2 | 1 | Regular | SCULPT-K(4X2) | SCS-500-80-30-FL-K(4X2)-W-UNV-DP-1-SC-OS(1)-C(L SHAPE/POWER AT 2FT END)) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 10 | 10 | Christina Torok |  | Regular |  | S5-A | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
63435-7 | 63435 | 7 | 1 | Regular | SCULPT-K(4X2) | SCS-500-80-30-FL-K(4X2)-W-UNV-DP-1-SC-OS(1)-C(L SHAPE/POWER AT 4FT END) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Christina Torok |  | Regular |  | S5-B | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-8 | 64752 | 8 | 1 | Regular | B3LED-16 | BMRLED-500-80-35-ASO-16-W-UNV-O(DEXAL)-1-TB15 |  | Machine Shop Finished | 2019-02-03 | 20:36:57 | 2019-01-31 | 2019-02-05 | 12 | 24 | Gagandeep Singh |  | Regular |  | B-16' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
64752-9 | 64752 | 9 | 1 | Regular | B3LED-20 | BMRLED-500-80-35-ASO-20-W-UNV-O(DEXAL)-1-TB15 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 27 | 54 | Gagandeep Singh |  | Regular |  | B1-20' | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-10 | 64752 | 10 | 1 | Regular | B3LED-30 | BMRLED-500-80-35-FL-30-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:07 | 2019-01-31 | 2019-02-05 | 9 | 27 | Gagandeep Singh |  | Regular |  | C10-30' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-11 | 64752 | 11 | 1 | Regular | B3LED-36 | BMRLED-500-80-35-FL-36-W-UNV-O(DEXAL)-1-TG15 |  | Machine Shop Finished | 2019-02-03 | 20:37:08 | 2019-01-31 | 2019-02-05 | 5 | 15 | Gagandeep Singh |  | Regular |  | C11-36' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-12 | 64752 | 12 | 1 | Regular | B3LED-46 | BMRLED-500-80-35-FL-46-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:10 | 2019-01-31 | 2019-02-05 | 1 | 4 | Gagandeep Singh |  | Regular |  | C13-46' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-13 | 64752 | 13 | 1 | Regular | B3LED-60 | BMRLED-500-80-35-FL-60-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:22 | 2019-01-31 | 2019-02-05 | 1 | 5 | Gagandeep Singh |  | Regular |  | C14-60' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:39 |  | TRUE | FALSE
64752-14 | 64752 | 14 | 1 | Regular | B3LED-6 | BMRLED-500-80-35-FL-6-W-UNV-O(DEXAL)-1-TG9 | Shortage | Machine Shop Finished | 2019-02-03 | 20:37:23 | 2019-01-31 | 2019-02-05 | 116 | 116 | Gagandeep Singh |  | Regular |  | C2-6'-TG9 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
64752-15 | 64752 | 15 | 1 | Regular | B3LED-8 | BMRLED-500-80-35-FL-8-W-UNV-O(DEXAL)-1-TG15 | Wrong info. In SD | Machine Shop Finished | 2019-02-03 | 20:37:25 | 2019-01-31 | 2019-02-05 | 32 | 32 | Gagandeep Singh |  | Regular |  | C3-8'-TG15 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:39 |  | TRUE | TRUE
64752-16 | 64752 | 16 | 1 | Regular | B3LED-10 | BMRLED-500-80-35-FL-10-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:26 | 2019-01-31 | 2019-02-05 | 1 | 1 | Gagandeep Singh |  | Regular |  | C4-10' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-17 | 64752 | 17 | 1 | Regular | B3LED-14 | BMRLED-500-80-35-FL-14-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:28 | 2019-01-31 | 2019-02-05 | 1 | 2 | Gagandeep Singh |  | Regular |  | C6-14' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-18 | 64752 | 18 | 1 | Regular | B3LED-16 | BMRLED-500-80-35-FL-16-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:30 | 2019-01-31 | 2019-02-05 | 1 | 2 | Gagandeep Singh |  | Regular |  | C7-16' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-19 | 64752 | 19 | 1 | Regular | B3LED-18 | BMRLED-500-80-35-FL-18-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:31 | 2019-01-31 | 2019-02-05 | 2 | 4 | Gagandeep Singh |  | Regular |  | C8-18' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-20 | 64752 | 20 | 1 | Regular | B3LED-20 | BMRLED-500-80-35-FL-20-W-UNV-O(DEXAL)-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:39 | 2019-01-31 | 2019-02-05 | 9 | 18 | Gagandeep Singh |  | Regular |  | C9-20' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-22 | 64752 | 22 | 1 | Regular | PRMLED-10 | PRWLED-500-80-35-S-10-W-277-DP-1 | Wrong part in BOM | Machine Shop Finished | 2019-02-04 | 08:32:05 | 2019-01-29 | 2019-02-05 | 1 | 1 | Gagandeep Singh |  | Regular |  | D-10' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 11:39 |  | TRUE | TRUE
64752-23 | 64752 | 23 | 1 | Regular | PRMLED-16 | PRWLED-500-80-35-S-16-W-277-DP-1 | Shortage | Machine Shop Finished | 2019-02-04 | 08:32:07 | 2019-01-29 | 2019-02-05 | 8 | 16 | Gagandeep Singh |  | Regular |  | D1-16' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 11:39 |  | TRUE | FALSE
64752-24 | 64752 | 24 | 1 | Regular | PRMLED-28 | PRWLED-500-80-35-S-28-W-277-DP-1 |  | Machine Shop Finished | 2019-02-04 | 08:32:10 | 2019-01-29 | 2019-02-05 | 1 | 4 | Gagandeep Singh |  | Regular |  | D2-28' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 11:39 |  | TRUE | FALSE
64752-25 | 64752 | 25 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-O(DEXAL)-1-TB15 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 40 | 40 | Gagandeep Singh |  | Regular |  | EE | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-26 | 64752 | 26 | 1 | Regular | DIALED-24 | DIALED-24-4500-80-35-VL-W-UNV-O(DEXAL)-1-TB15 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 95 | 95 | Gagandeep Singh |  | Regular |  | FF | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-30 | 64752 | 30 | 1 | Regular | B4LED-5 | BBWDILED-640-400-80-35-SO-5-W-UNV-DP-1-D |  | Machine Shop Finished | 2019-02-03 | 22:04:11 | 2019-01-29 | 2019-02-05 | 26 | 26 | Gagandeep Singh |  | Regular |  | TT-5' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-31 | 64752 | 31 | 1 | Regular | B3LED-6 | BMRLED-500-80-35-FL-6-W-UNV-O(DEXAL)-1-DF |  | Machine Shop Finished | 2019-02-03 | 20:37:40 | 2019-01-31 | 2019-02-05 | 2 | 2 | Gagandeep Singh |  | Regular |  | C2-6'-DF | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-32 | 64752 | 32 | 1 | Regular | DIALED-24 | DIALED-24-4500-80-35-VL-W-UNV-O(DEXAL)-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 3 | Gagandeep Singh |  | Regular |  | FF-DF | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-33 | 64752 | 33 | 1 | Regular | DIALED-24 | DIALED-24-4500-80-35-VL-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 110 | 110 | Gagandeep Singh |  | Regular |  | FF-DP | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-37 | 64752 | 37 | 1 | Regular | B3LED-4 | BMRLED-500-80-35-FL-4-W-UNV-O(DEXAL)-1-TG15 |  | Machine Shop Finished | 2019-02-03 | 20:37:42 | 2019-01-31 | 2019-02-05 | 12 | 12 | Gagandeep Singh |  | Regular |  | C1-4' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 11:40 |  | TRUE | FALSE
64752-38 | 64752 | 38 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Gagandeep Singh |  | Regular |  | EE-DP | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-39 | 64752 | 39 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-O(DEXAL)-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Gagandeep Singh |  | Regular |  | EE-DF | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
64752-40 | 64752 | 40 | 1 | Regular | B3LED-6 | BMRLED-500-80-35-FL-6-W-UNV-DP-1-TG9 |  | Machine Shop Finished | 2019-02-03 | 20:37:49 | 2019-01-31 | 2019-02-05 | 10 | 10 | Gagandeep Singh |  | Regular |  | C2-DP | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
66961-1 | 66961 | 1 | 1 | Regular | B4LED-42' 1/2" | SP000-BBWDILEDPAT-REC-90(4)-400-640-80-50-SO-42' 1/2"-EX-W-UNV-DP-2 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 12 | 96 | Stan Buyansky |  | Regular |  | LDB-42' | 4 | TRUE | FALSE | FALSE | FALSE | [5 empty] | ToDo |  |  | ToDo |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
66961-2 | 66961 | 2 | 1 | Regular | B4LED-350' 1/4" | SP000-BBRLEDPAT-SQ-90(4)-1000-80-50-SO-FL-350' 1/4"-NL-W-UNV-DP-4-DF |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 34 | Stan Buyansky |  | Regular |  | LDC | 4 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | ToDo |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
66961-3 | 66961 | 3 | 1 | Regular | B4LED-40' | SP000-BBWDILEDPAT-REC-90(4)-400-640-80-50-SO-40'-EX-W-UNV-DP-2 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 16 | Stan Buyansky |  | Regular |  | LDB-40' | 4 | TRUE | FALSE | FALSE | FALSE | [5 empty] | ToDo |  |  | ToDo |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
66961-4 | 66961 | 4 | 1 | Regular | B4LED-39' 11 3/4" | SP000-BBWDILEDPAT-REC-90(4)-400-640-80-50-SO-39' 11 3/4"-EX-W-UNV-DP-2 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Stan Buyansky |  | Regular |  | LDB-39' | 4 | TRUE | FALSE | FALSE | FALSE | [5 empty] | ToDo |  |  | ToDo |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
66961-5 | 66961 | 5 | 1 | Regular | B4LED-40' 10 3/4" | SP000-BBWDILEDPAT-REC-90(4)-400-640-80-50-SO-40' 10 3/4"-EX-W-UNV-DP-2 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Stan Buyansky |  | Regular |  | LDB-41' | 4 | TRUE | FALSE | FALSE | FALSE | [5 empty] | ToDo |  |  | ToDo |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-41 | 67150 | 41 | 1 | Regular | B6LED-15 | B6RLED-400-80-30-FL-15-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 10 | 20 | Gagandeep Singh | Picked - Complete | Regular |  | LT-02D-15'-BASEMNT FL | 15 | TRUE | TRUE | FALSE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-42 | 67150 | 42 | 1 | Regular | B6LED-15 | B6RLED-400-80-30-FL-15-W-120-DP-E(1)-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | LT-02D-15'EM-BASEMNT FL | 15 | TRUE | TRUE | FALSE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-43 | 67150 | 43 | 1 | Regular | B6LED-10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:20 | 2019-02-06 | 2019-02-11 | 5 | 5 | Gagandeep Singh |  | Regular |  | LT-02B-10'-1ST FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-44 | 67150 | 44 | 1 | Regular | B6LED-15 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:37 | 2019-02-06 | 2019-02-11 | 4 | 8 | Gagandeep Singh |  | Regular |  | LT-02B-15'-1ST FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-45 | 67150 | 45 | 1 | Regular | B6LED-5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:40 | 2019-02-06 | 2019-02-11 | 4 | 4 | Gagandeep Singh |  | Regular |  | LT-02C-5'-1ST FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-46 | 67150 | 46 | 1 | Regular | B6LED-10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:47:29 | 2019-02-06 | 2019-02-11 | 3 | 3 | Gagandeep Singh |  | Regular |  | LT-02B-10'-2ND FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-47 | 67150 | 47 | 1 | Regular | B6LED-15 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 4 | 8 | Gagandeep Singh | Picked - Complete | Regular |  | LT-02B-15'-2ND FL | 15 | TRUE | TRUE | FALSE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-48 | 67150 | 48 | 1 | Regular | B6LED-5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:43 | 2019-02-06 | 2019-02-11 | 5 | 5 | Gagandeep Singh |  | Regular |  | LT-02C-5'-2ND FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-49 | 67150 | 49 | 1 | Regular | B6LED-10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:26 | 2019-02-06 | 2019-02-11 | 12 | 12 | Gagandeep Singh |  | Regular |  | LT-02B-10'-3RD FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-50 | 67150 | 50 | 1 | Regular | B6LED-15 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:57 | 2019-02-06 | 2019-02-11 | 5 | 10 | Gagandeep Singh |  | Regular |  | LT-02B-15'-3RD FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-51 | 67150 | 51 | 1 | Regular | B6LED-5 | B6RLED-1000-80-30-FL-5-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:48 | 2019-02-06 | 2019-02-11 | 5 | 5 | Gagandeep Singh |  | Regular |  | LT-02C-5'-3RD FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-52 | 67150 | 52 | 1 | Regular | B6LED-10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 14 | 14 | Gagandeep Singh | Picked - Complete | Regular |  | LT-02B-10'-4TH FL | 15 | TRUE | TRUE | FALSE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-53 | 67150 | 53 | 1 | Regular | B6LED-15 | B6RLED-750-80-30-FL-15-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 9 | 18 | Gagandeep Singh | Picked - Complete | Regular |  | LT-02B-15'-4TH FL | 15 | TRUE | TRUE | FALSE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-55 | 67150 | 55 | 1 | Regular | B6LED-4 | B6RLED-750-80-30-FL-4-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:47:12 | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | LT-02B-4'-5TH FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-56 | 67150 | 56 | 1 | Regular | B6LED-5 | B6RLED-750-80-30-FL-5-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:54 | 2019-02-06 | 2019-02-11 | 3 | 3 | Gagandeep Singh |  | Regular |  | LT-02B-5'-5TH FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-57 | 67150 | 57 | 1 | Regular | B6LED-10 | B6RLED-750-80-30-FL-10-W-120-DP-1-ST-FW(6) |  | Machine Shop Finished | 2019-02-03 | 14:46:30 | 2019-02-06 | 2019-02-11 | 10 | 10 | Gagandeep Singh |  | Regular |  | LT-02B-10'-5TH FL | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
67150-58 | 67150 | 58 | 1 | Regular | B2LED-14 | BRLED-500-80-30-FL-13-W-120-DP-1-D |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | LT-63D-13'-BASEMNT | 15 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-59 | 67150 | 59 | 1 | Regular | B2LED-18 | BRLED-500-80-30-FL-18-W-120-DP-1-D |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 6 | 12 | Gagandeep Singh | Picked - Complete | Regular |  | LT-63D-18'-BASEMNT | 15 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-60 | 67150 | 60 | 1 | Regular | B2LED-17 | BRLED-500-80-30-FL-17-W-120-DP-E(1)-D |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | LT-63D-17'EM-BASEMNT | 15 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67150-61 | 67150 | 61 | 1 | Regular | B2LED-18 | BRLED-500-80-30-FL-18-W-120-DP-E(1)-D |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 6 | 12 | Gagandeep Singh | Picked - Complete | Regular |  | LT-63D-18'EM-BASEMNT | 15 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
67875-1 | 67875 | 1 | 1 | Regular | CCL | CCL-SL-300-80-30-CP(83' 6")-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 14 | Gagandeep Singh |  | Regular |  | LF15-8'5"X33'4" | 12 | TRUE | TRUE | TRUE | TRUE | [8 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
69215-1 | 69215 | 1 | 1 | Regular | SKETCH-AL(15'8 1/2") | SKPE-10005-SL 60/40-CIR-AL(15'8 1/2")-550-80-35-SO-W-UNV-D-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Joshua Zimet |  | Regular |  | F11A-15'8 1/2" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69215-2 | 69215 | 2 | 1 | Regular | SKETCH-AL(23'6 3/4") | SKPE-10008-SL 60/40-CIR-AL(23'6 3/4")-550-80-35-SO-W-UNV-D-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Joshua Zimet |  | Regular |  | F11B-23'6 3/4" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69215-3 | 69215 | 3 | 1 | Regular | SCULPT-20 | SCD-500-80-35-FL-20-W-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Joshua Zimet |  | Regular |  | F10-20' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69215-4 | 69215 | 4 | 1 | Regular | SCULPT-28 | SCD-500-80-35-FL-28-W-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Joshua Zimet |  | Regular |  | F10-28' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69215-5 | 69215 | 5 | 1 | Regular | SCULPT-48 | SCD-500-80-35-FL-48-W-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Joshua Zimet |  | Regular |  | F10-48' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69215-6 | 69215 | 6 | 1 | Regular | SCULPT-48 | SCD-500-80-35-FL-48-W-UNV-DP-1+E(1)-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Joshua Zimet |  | Regular |  | F10-48' EM | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69215-7 | 69215 | 7 | 1 | Regular | SCULPT-70 | SCD-500-80-35-FL-70-W-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 6 | Joshua Zimet |  | Regular |  | F10-70' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69363-1 | 69363 | 1 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(184-400)-80-35-AH(19)+AY(18)-AP-UNV-MD-1+E(12)-CA(36)-RC | Shortage | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 46 | Christina Torok |  | Regular |  | F37 | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
69773-1 | 69773 | 1 | 1 | Regular | B3LED-4 | BMRLED-1000-80-35-FL-4-W-277-DP-1-D |  | Machine Shop Started |  |  | 2019-02-26 | 2019-03-01 | 14 | 14 | George Bacalla |  | Regular |  | F7 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69773-2 | 69773 | 2 | 1 | Regular | B3LED-8 | BMRLED-1000-80-35-FL-8-W-277-DP-1-D |  | Machine Shop Started |  |  | 2019-02-26 | 2019-03-01 | 5 | 5 | George Bacalla |  | Regular |  | F8 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-1 | 69828 | 1 | 1 | Regular | B4LED-8' | BBRLED-400-80-35-FL-8'-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | AL4-8' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-2 | 69828 | 2 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | AL7-8' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-3 | 69828 | 3 | 1 | Regular | B6LED-8 | B6RLED-1000-80-35-FL-8-W-277-DP-1+E(1)-TG15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 46 | 46 | Jessica Pasternyk |  | Regular |  | AL11-8' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-4 | 69828 | 4 | 1 | Regular | SCULPT-12' | SCR-500-80-35-FL-12'-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | AL13/16 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-5 | 69828 | 5 | 1 | Regular | SCULPT-11' | SCR-500-80-35-FL-11'-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 8 | 8 | Jessica Pasternyk |  | Regular |  | AL15/16 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-6 | 69828 | 6 | 1 | Regular | SCULPT-3' | SCR-300-80-35-FL-3'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | AL18-3' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-7 | 69828 | 7 | 1 | Regular | SCULPT-4' | SCR-300-80-35-FL-4'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | AL18-4' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-8 | 69828 | 8 | 1 | Regular | SCULPT-6' | SCR-300-80-35-FL-6'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | AL18-6' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-9 | 69828 | 9 | 1 | Regular | SCULPT-8' | SCR-300-80-35-FL-8'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | AL18-8' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-10 | 69828 | 10 | 1 | Regular | SCULPT-32' | SCR-500-80-35-FL-32'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 3 | Jessica Pasternyk |  | Regular |  | AL21-32' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-11 | 69828 | 11 | 1 | Regular | B6LED-4' | B6DLED-500-80-35-SO-4'-W-UNV-DP-1+E(1)-CA(36) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | JL1-4' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-12 | 69828 | 12 | 1 | Regular | B6LED-36' | B6DLED-500-80-35-SO-36'-W-UNV-DP-1+E(1)-CA(36) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 7 | 21 | Jessica Pasternyk |  | Regular |  | JL1-36' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-13 | 69828 | 13 | 1 | Regular | B6LED-48' | B6DLED-500-80-35-SO-48'-W-UNV-DP-1+E(1)-CA(36) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 13 | 52 | Jessica Pasternyk |  | Regular |  | JL1-48' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-14 | 69828 | 14 | 1 | Regular | B3LED-8' | BMDLED-500-80-35-SO-8'-BLK-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | JL8 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-15 | 69828 | 15 | 1 | Regular | SCULPT-7' | SCR-300-80-35-FL-7'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | AL18-7' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-16 | 69828 | 16 | 1 | Regular | SCULPT-12'6" | SCR-300-80-35-FL-12'6"-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 4 | Jessica Pasternyk |  | Regular |  | AL18-12'6" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-17 | 69828 | 17 | 1 | Regular | SCULPT-14'6" | SCR-300-80-35-FL-14'6"-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 4 | Jessica Pasternyk |  | Regular |  | AL18-14'6" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69828-18 | 69828 | 18 | 1 | Regular | SCULPT-31'6" | SCR-300-80-35-FL-31'6"-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 6 | Jessica Pasternyk |  | Regular |  | AL18-31'6" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69855-1 | 69855 | 1 | 1 | Regular | SLMLED-33 | SLWLED-SL 100/0-800-80-35-NO-33-W-UNV-O(SR)-1-C(10' 18/2AWG CORDS) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 3 | Gagandeep Singh |  | Regular |  | A-33' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69855-2 | 69855 | 2 | 1 | Regular | SLMLED-32 | SLWLED-SL 100/0-800-80-35-NO-32-W-UNV-O(SR)-1-C(10' 18/2AWG CORDS) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 3 | Gagandeep Singh |  | Regular |  | A-32' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69855-5 | 69855 | 5 | 1 | Regular | SLMLED-21 | SLWLED-SL 100/0-800-80-35-NO-21-W-UNV-O(SR)-1-C(10' 18/2AWG CORDS) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 3 | Gagandeep Singh |  | Regular |  | A1-21' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69855-6 | 69855 | 6 | 1 | Regular | SLMLED-36 | SLWLED-SL 100/0-800-80-35-NO-36-W-UNV-O(SR)-1-C(10' 18/2AWG CORDS) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 3 | Gagandeep Singh |  | Regular |  | A-36' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69983-15 | 69983 | 15 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(18' 11")-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rohan Srivastava |  | Regular |  | F9A-BO-18'-11" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69983-29 | 69983 | 29 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(4' 4"')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rohan Srivastava |  | Regular |  | F9A-CD-4'-4" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
69983-35 | 69983 | 35 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(5' 2")-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rohan Srivastava |  | Regular |  | F9A-CD2-5'-2" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70162-7 | 70162 | 7 | 1 | Regular | B4LED-8' | BBDILED-625-375-80-35-SO-8'-W-UNV-DP-2-CT15(36) |  | Machine Shop Finished | 2019-02-01 | 15:14:18 | 2019-02-11 | 2019-02-14 | 27 | 27 | Rohan Srivastava |  | Regular |  | AP01A-8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
70328-6 | 70328 | 6 | 1 | Regular | B3LED-11'2 5/8" | BMWDLED-400-80-35-SO-11'2 5/8"-W-UNV-DP-1-C(JOINERS EACH SIDE) | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-G-SECT 2 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
70328-7 | 70328 | 7 | 1 | Regular | B3LED-1'8" | BMWDLED-400-80-35-SO-1'8"-W-UNV-DP-1-C(JOINERS EACH SIDE) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-G-SECT 4 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70328-8 | 70328 | 8 | 1 | Regular | B3LED-35 5/32" | BMWDLED-400-80-35-SO-35 5/32"-W-UNV-DP-1-C(JOINER ON ONE SIDE) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-G-SECT 6 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70328-9 | 70328 | 9 | 1 | Regular | B3LED-11'2 5/8" | BMWDLED-400-80-35-SO-11'2 5/8"-W-UNV-DP-1-C(JOINERS EACH SIDE) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-D-SECT 2 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70328-10 | 70328 | 10 | 1 | Regular | B3LED-1'8" | BMWDLED-400-80-35-SO-1'8"-W-UNV-DP-1-C(JOINERS EACH SIDE) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-D-SECT 4 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70328-11 | 70328 | 11 | 1 | Regular | B3LED-35 5/32" | BMWDLED-400-80-35-SO-35 5/32"-W-UNV-DP-1-C(JOINER ON ONE SIDE) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-D-SECT 6 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70328-12 | 70328 | 12 | 1 | Regular | B3LED-2'6 11/32" | BMWDLEDPAT-OPR-150-400-80-35-SO-2'6 11/32"-EX-W-UNV-DP-1-C(JOINER ON ONE END, 23 11/32" + 7" @ 150 DEGREES) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-G-SECT 1 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70328-13 | 70328 | 13 | 1 | Regular | B3LED-2'6 11/32" | BMWDLEDPAT-OPR-150-400-80-35-SO-2'6 11/32"-EX-W-UNV-DP-1-C(JOINER ON ONE END, 23 11/32" + 7" @ 150 DEGREES) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Sacha Lempka |  | Priority |  | LQ-D-SECT 1 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70411-2 | 70411 | 2 | 3 | Regular | SCULPT-4' | SCDM-4'-(4)-800-90-TW2750-D55-BLK-C(HS512W1186)-UNV-O(DALIDT6)-1-CA(72)-LBC-C(120" POWER CORD) |  | Machine Shop Started |  |  | 2019-03-05 | 2019-03-08 | 815 | 815 | Gagandeep Singh |  | Regular |  | L-01.1-4' | 7 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70411-2 | 70411 | 2 | 4 | Regular | SCULPT-4' | SCDM-4'-(4)-800-90-TW2750-D55-BLK-C(HS512W1186)-UNV-O(DALIDT6)-1-CA(72)-LBC-C(120" POWER CORD) |  | Machine Shop Started |  |  | 2019-03-12 | 2019-03-15 | 733 | 733 | Gagandeep Singh |  | Regular |  | L-01.1-4' | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70411-5 | 70411 | 5 | 2 | Regular | SCULPT-3' | SCDM-3'-(3)-1000-90-TW2750-D55-BLK-C(HS512W1186)-UNV-O(DALIDT6)-1-CA(72)-LBC-C(120" POWER CORD) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 729 | 729 | Gagandeep Singh | Picked - Complete | Regular |  | L-01.4-3' | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70411-33 | 70411 | 33 | 2 | Regular | SCULPT-4 | SCDM-4'-(4)-800-90-TW2750-D55-BLK-C(HS512W1186)-UNV-0(DALIDT6)-CA(72)-LBC-C(120" POWER CORD) |  | Machine Shop Started |  |  | 2019-02-19 | 2019-02-22 | 353 | 353 | Gagandeep Singh |  | Regular |  | L-11-4' | 7 | TRUE | TRUE | TRUE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70411-33 | 70411 | 33 | 3 | Regular | SCULPT-4 | SCDM-4'-(4)-800-90-TW2750-D55-BLK-C(HS512W1186)-UNV-0(DALIDT6)-CA(72)-LBC-C(120" POWER CORD) |  | Machine Shop Started |  |  | 2019-02-26 | 2019-03-01 | 345 | 345 | Gagandeep Singh |  | Regular |  | L-11-4' | 7 | TRUE | TRUE | TRUE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
70411-37 | 70411 | 37 | 2 | Regular | SCULPT-3 | SCRM-3'-(3)-1000-90-TW2750-D55-BLK-C(HS512W1186)-UNV-O(DALIDT6)-1-TB15-LBC-C(PENDANT HANGERS 120" WITH CORD) | Others | Machine Shop Finished | 2019-01-27 | 07:37:59 | 2019-03-05 | 2019-02-08 | 281 | 281 | Gagandeep Singh |  | Regular |  | L-01.11-3' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
70426-1 | 70426 | 1 | 1 | Regular | PERFKT-CCH | CCH-SL-700-80-27-CL(5'2 1/2")-W-120-DP-1-C |  | Machine Shop Finished | 2019-02-04 | 09:31:09 | 2019-01-30 | 2019-02-04 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT-31-5'2 1/2" | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
70428-1 | 70428 | 1 | 1 | Regular | SKLPTP-5' 2" | SCPLED-750-80-30-FL-5' 2"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:37 | 2019-02-14 | 2019-02-19 | 1 | 1 | Gagandeep Singh |  | Regular |  | TH-5' 2" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-2 | 70428 | 2 | 1 | Regular | SKLPTP-5'11 1/2" | SCPLED-750-80-30-FL-4'11 1/2"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:38 | 2019-02-14 | 2019-02-19 | 1 | 1 | Gagandeep Singh |  | Regular |  | TH-4'11 1/2" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-3 | 70428 | 3 | 1 | Regular | SKLPTP-9' 1/4" | SCPLED-750-80-30-FL-9' 1/4"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:38 | 2019-02-14 | 2019-02-19 | 1 | 1 | Gagandeep Singh |  | Regular |  | TH-9' 1/4" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-4 | 70428 | 4 | 1 | Regular | SKLPTP-17'5 3/4" | SCPLED-750-80-30-FL-17'5 3/4"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:38 | 2019-02-14 | 2019-02-19 | 1 | 2 | Gagandeep Singh |  | Regular |  | TH-17'5 3/4" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-5 | 70428 | 5 | 1 | Regular | SKLPTP-9'1 3/4" | SCPLED-750-80-30-FL-9'1 3/4"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:38 | 2019-02-14 | 2019-02-19 | 1 | 1 | Gagandeep Singh |  | Regular |  | TH-9'1 3/4" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-6 | 70428 | 6 | 1 | Regular | SKLPTP-13' 3/4" | SCPLED-750-80-30-FL-13' 3/4"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:38 | 2019-02-14 | 2019-02-19 | 1 | 2 | Gagandeep Singh |  | Regular |  | TH-13' 3/4" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-7 | 70428 | 7 | 1 | Regular | SKLPTP-18' 2" | SCPLED-750-80-30-FL-18' 2"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:39 | 2019-02-14 | 2019-02-19 | 1 | 2 | Gagandeep Singh |  | Regular |  | TH-18' 2" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70428-9 | 70428 | 9 | 1 | Regular | SKLPTP-13' 9" | SCPLED-750-80-30-FL-13' 9"-W-277-DP-1-TB9-FW(6') |  | Machine Shop Started | 2019-01-29 | 13:26:39 | 2019-02-14 | 2019-02-19 | 2 | 4 | Gagandeep Singh |  | Regular |  | TH-13' 9" | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
70634-1 | 70634 | 1 | 1 | Regular | PERFKT-CCH | SP18083-CCH-SL-1100-80-2740-CP(110)-W-120-O(DMX)-2-C |  | Machine Shop Finished | 2019-02-01 | 12:27:22 | 2019-01-29 | 2019-02-01 | 1 | 41 | Gagandeep Singh | Picked - Complete | High Priority |  | LF05-110' INSIDE | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 14:52 |  | TRUE | FALSE
70634-2 | 70634 | 2 | 1 | Regular | PERFKT-CCH | SP18083-CCH-SL-1100-80-2740-CP(116)-W-120-O(DMX)-2-C | Wrong part in BOM | Machine Shop Finished | 2019-01-31 | 12:27:22 | 2019-01-29 | 2019-02-01 | 1 | 56 | Gagandeep Singh | Picked - Complete | High Priority |  | LF05-116' INSIDE | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 14:52 |  | TRUE | TRUE
70634-3 | 70634 | 3 | 1 | Regular | PERFKT-CCH | SP18083-CCH-SL-1100-80-2740-CP(110)-W-120-O(DMX)-2-C | Wrong part in BOM | Machine Shop Finished | 2019-01-31 | 12:27:22 | 2019-01-29 | 2019-02-01 | 1 | 41 | Gagandeep Singh | Picked - Complete | High Priority |  | LF05-110' OUTSIDE | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 14:52 |  | TRUE | TRUE
70634-4 | 70634 | 4 | 1 | Regular | PERFKT-CCH | SP18083-CCH-SL-1100-80-2740-CP(116)-W-120-O(DMX)-3-C | Wrong info. In SD | Machine Shop Finished | 2019-01-31 | 12:27:22 | 2019-01-29 | 2019-02-01 | 1 | 56 | Gagandeep Singh | Picked - Complete | High Priority |  | LF05-116' OUTSIDE | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 14:52 |  | TRUE | TRUE
70875-1 | 70875 | 1 | 1 | Regular | STFD | STFD-DSO(12)-300-90-35-AY(1)-AP-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 4 | 12 | Stan Buyansky | Picked - Complete | Regular |  | H15 | 12 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71407-5 | 71407 | 5 | 2 | Regular | AIRLED-4 | ARWLED-1000-80-30-S-4-W-UNV-BI-1-B1(BSL10LST)-OS(1) |  | Wiring Started | 2019-01-30 | 14:28:02 | 2019-02-04 | 2019-02-07 | 13 | 13 | Rohan Srivastava |  | Regular |  | BE-2E-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:25 |  | TRUE | FALSE
71407-10 | 71407 | 10 | 2 | Regular | AIRLED-4 | ARLED-1000-80-30-S-4-W-120-DP-1-CA(36)-B1(BSL10LST)-OS(FS-205) |  | Wiring Started | 2019-01-30 | 14:28:05 | 2019-02-04 | 2019-02-07 | 3 | 3 | Rohan Srivastava |  | Regular |  | PE-8E-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:25 |  | TRUE | FALSE
71700-1 | 71700 | 1 | 1 | Regular | B3LED-28 | BMDLED-1000-80-40-SO-28-W-277-DP-1-CT15(36) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Jessica Pasternyk |  | Regular |  | G | 15 | TRUE | FALSE | FALSE | TRUE |  | Ready |  | ToDo | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
71700-2 | 71700 | 2 | 1 | Regular | B6LED-4 | B6RLED-1000-80-40-FL-4-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 12 | 12 | Jessica Pasternyk |  | Regular |  | L-4' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-3 | 71700 | 3 | 1 | Regular | B6LED-16 | B6RLED-1000-80-40-FL-16-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 3 | 6 | Jessica Pasternyk |  | Regular |  | L-16' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-4 | 71700 | 4 | 1 | Regular | B6LED-20 | B6RLED-1000-80-40-FL-20-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 12 | 24 | Jessica Pasternyk |  | Regular |  | L-20' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-5 | 71700 | 5 | 1 | Regular | B6LED-28 | B6RLED-1000-80-40-FL-28-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 6 | Jessica Pasternyk |  | Regular |  | L-28' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-6 | 71700 | 6 | 1 | Regular | B6LED-16 | B6RLED-1000-80-40-FL-16-W-UNV-DP-1+E(1)-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 3 | 6 | Jessica Pasternyk |  | Regular |  | L1-16' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-9 | 71700 | 9 | 1 | Regular | B3LED-28 | BMDLED-1000-80-40-SO-28-W-277-DP-1+E(1)-CT15(36) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Jessica Pasternyk |  | Regular |  | G-EM | 15 | TRUE | FALSE | FALSE | TRUE |  |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-10 | 71700 | 10 | 1 | Regular | B6LED-28 | B6RLED-1000-80-40-FL-28-W-UNV-DP-1+E(1)-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Jessica Pasternyk |  | Regular |  | L1-28'E | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-11 | 71700 | 11 | 1 | Regular | B6LED-12 | B6RLED-1000-80-40-FL-12-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Jessica Pasternyk |  | Regular |  | L-12 | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-12 | 71700 | 12 | 1 | Regular | B6LED-12 | B6RLED-1000-80-40-FL-12-W-UNV-DP-1+E(1)-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Jessica Pasternyk |  | Regular |  | L1-12E | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-13 | 71700 | 13 | 1 | Regular | B6LED-20 | B6RLED-1000-80-40-FL-20-W-UNV-DP-1+E(1)-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 6 | 12 | Jessica Pasternyk |  | Regular |  | L1-20E | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71700-14 | 71700 | 14 | 1 | Regular | B6LED-20 | B6RLED-1000-80-40-FL-20-W-UNV-DP-1+E(2)-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 3 | 6 | Jessica Pasternyk |  | Regular |  | L2-20E | 15 | TRUE | FALSE | FALSE | TRUE | ToDo |  |  | ToDo | [6 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-1 | 71803 | 1 | 1 | Regular | B3LED-7 | BMRLED-750-80-40-1.25M-7-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | H1-7' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-2 | 71803 | 2 | 1 | Regular | B3LED-8 | BMRLED-750-80-40-1.25M-8-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 35 | 35 | Jessica Pasternyk |  | Regular |  | H2-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-3 | 71803 | 3 | 1 | Regular | B4LED-5 | BBRLED-600-80-40-FL-5-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 23 | 23 | Jessica Pasternyk |  | Regular |  | H3-5' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-4 | 71803 | 4 | 1 | Regular | B3LED-5 | BMRLED-750-80-40-1.25M-5-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 38 | 38 | Jessica Pasternyk |  | Regular |  | H3A-5' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-5 | 71803 | 5 | 1 | Regular | B3LED-10 | BMRLED-750-80-40-1.25M-10-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | H4-10' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-6 | 71803 | 6 | 1 | Regular | B3LED-12 | BMRLED-750-80-40-1.25M-12-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Jessica Pasternyk |  | Regular |  | H5-12' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-7 | 71803 | 7 | 1 | Regular | B4LED-4 | BBRLED-600-80-40-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 16 | 16 | Jessica Pasternyk |  | Regular |  | H6-4' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-8 | 71803 | 8 | 1 | Regular | B3LED-8 | BMRLED-750-80-40-FL-8-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 1 | Jessica Pasternyk |  | Regular |  | H7-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-9 | 71803 | 9 | 1 | Regular | B3LED-4 | BMRLED-750-80-40-1.25M-4-BLK-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | H9-4' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-10 | 71803 | 10 | 1 | Regular | ZEN-8 | ZELED-SL 65/35-1100-80-40-MAL-8-AP-UNV-MD-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 1 | Jessica Pasternyk |  | Regular |  | P6-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-11 | 71803 | 11 | 1 | Regular | STFI | STFI-I(18-350)-80-40-AH(6)-AP-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 5 | Jessica Pasternyk |  | Regular |  | S1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-12 | 71803 | 12 | 1 | Regular | STFI | STFI-I(12-700)-80-40-AY(1)-AP-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 3 | Jessica Pasternyk |  | Regular |  | S2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-14 | 71803 | 14 | 1 | Regular | WB4LED-8' | SP19024(1)-WBRLED-500-80-50-S-8'-BLK-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 15 | 15 | Jessica Pasternyk |  | Regular |  | KK-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-15 | 71803 | 15 | 1 | Regular | WB4LED-6' | SP19024(1)-WBRLED-500-80-50-S-6'-BLK-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 5 | 15 | Jessica Pasternyk |  | Regular |  | MM-6' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-16 | 71803 | 16 | 1 | Regular | WB4LED-30' | SP19024(1)-WBRLED-500-80-50-S-30'-BLK-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 3 | Jessica Pasternyk |  | Regular |  | AA-30' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-17 | 71803 | 17 | 1 | Regular | WB4LED-20' | SP19024(1)-WBRLED-500-80-50-S-20'-BLK-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 2 | Jessica Pasternyk |  | Regular |  | AA-20' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
71803-18 | 71803 | 18 | 1 | Regular | WB4LED-10' | SP19024(1)-WBRLED-500-80-50-S-10'-BLK-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | AA-10' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72049-3 | 72049 | 3 | 1 | Regular | SKETCH-AL(28' 1 1/4") | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(28' 1 1/4")-550-80-35-SO-C(RAL5017)-UNV-DP-1-CT15(36)-B2(BSL10LST) | Shortage | Machine Shop Started |  |  | 2019-01-24 | 2019-01-29 | 2 | 8 | Joshua Zimet |  | Regular |  | DL | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
72049-4 | 72049 | 4 | 1 | Regular | SKETCH-AL(19' 9 1/4") | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(19' 9 1/4")-550-80-35-SO-C(RAL5017)-UNV-DP-1-CT15(36) | Shortage | Wiring Started | 2019-01-28 | 15:05:02 | 2018-12-13 | 2019-01-29 | 2 | 4 | Joshua Zimet |  | Regular |  | DS | 1 | TRUE | TRUE | TRUE | TRUE | [9 empty] | ToDo | TRUE |  | Done | TRUE | 2019-02-04 12:37 |  | TRUE | TRUE
72049-15 | 72049 | 15 | 1 | Regular | SKETCH-AL(28' 1 1/4") | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(28' 1 1/4")-550-80-35-SO-C(RAL6017)-UNV-DP-1-CT15(36)-B2(BSL10LST) | Shortage | Machine Shop Started |  |  | 2019-01-24 | 2019-01-29 | 2 | 8 | Joshua Zimet |  | Regular |  | DL | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
72049-16 | 72049 | 16 | 1 | Regular | SKETCH-AL(19' 9 1/4") | SP17629(2)-SKPE-17051-SL 60/40-ASO-AL(19' 9 1/4")-550-80-35-SO-C(RAL6017)-UNV-DP-1-CT15(36) |  | Wiring Started | 2019-02-03 | 11:43:08 | 2018-12-13 | 2019-01-29 | 2 | 4 | Joshua Zimet |  | Regular |  | DS | 1 | TRUE | TRUE | TRUE | TRUE | [9 empty] | ToDo | TRUE |  | Done | TRUE | 2019-02-04 12:37 |  | TRUE | FALSE
72070-1 | 72070 | 1 | 1 | Regular | B4LED-ASO | SP18147(4)-BBRLED-600-80-(27-50)-ASO-4-M16LED(2)-W-277-O(DALI)-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 3 | Zahra Vatani |  | High Priority |  | ZC4 | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
72070-2 | 72070 | 2 | 1 | Regular | B4LED-ASO | SP18147(4)-BBRLED-600-80-(27-50)-ASO-2-M16LED(2)-W-277-O(DALI)-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Zahra Vatani |  | High Priority |  | ZC2 | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72070-3 | 72070 | 3 | 1 | Regular | B4LED-ASO | SP18147(4)-BBRLED-600-80-(27-50)-ASO-3-M16LED(2)-W-277-O(DALI)-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 33 | 33 | Zahra Vatani |  | High Priority |  | ZC3 | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
72070-6 | 72070 | 6 | 1 | Regular | B4LED-ASO | SP18147(4)-BBRLED-600-80-(27-50)-ASO-7-M16LED(2)-W-277-O(DALI)-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Zahra Vatani |  | High Priority |  | ZC7 | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-1 | 72089 | 1 | 1 | Regular | SCULPT-K(3X3) | SCS-650-80-30-FL-K(3X3)-AP-UNV-DP-1-SB9-C(MODIFIED MOUNTING HOLES & LOCATIONS) |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 128 | 128 | Rohan Srivastava |  | Regular |  | FH-3'X3' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-2 | 72089 | 2 | 1 | Regular | AULED-22 | AULED-22-4000-80-30-SO-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-04-01 | 2019-04-03 | 79 | 79 | Rohan Srivastava |  | Regular |  | FE | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-3 | 72089 | 3 | 1 | Regular | SCULPT-20 | SCR-500-80-30-FL-20-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 3 | 6 | Rohan Srivastava |  | Regular |  | FQ-20' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-4 | 72089 | 4 | 1 | Regular | SCULPT-22 | SCR-500-80-30-FL-22-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 4 | 8 | Rohan Srivastava |  | Regular |  | FQ-22' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-5 | 72089 | 5 | 1 | Regular | SCULPT-24 | SCR-500-80-30-FL-24-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 2 | 4 | Rohan Srivastava |  | Regular |  | FQ-24' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-6 | 72089 | 6 | 1 | Regular | SCULPT-25 | SCR-500-80-30-FL-25-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 1 | 3 | Rohan Srivastava |  | Regular |  | FQ-25' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-7 | 72089 | 7 | 1 | Regular | SCULPT-26 | SCR-500-80-30-FL-26-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 2 | 6 | Rohan Srivastava |  | Regular |  | FQ-26' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72089-8 | 72089 | 8 | 1 | Regular | SCULPT-30 | SCR-500-80-30-FL-30-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-03-29 | 2019-04-03 | 2 | 6 | Rohan Srivastava |  | Regular |  | FQ-30' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72101-1 | 72101 | 1 | 1 | Regular | STENCL-STFD | STFD-DSO(12'-400)-80-40-AH(6)-W-UNV-MD-1-CA(120)-RC |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 38 | 228 | Christina Torok |  | Regular |  | 10 | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72221-1 | 72221 | 1 | 1 | Regular | B2LED-4 | BDLED-1000-80-35-SO-4-W-UNV-DP-1-CTS(36) |  | Machine Shop Finished | 2019-01-30 | 13:32:07 | 2019-02-04 | 2019-02-07 | 13 | 13 | Jessica Pasternyk |  | Regular |  | L13 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
72221-2 | 72221 | 2 | 1 | Regular | B2LED-6 | BDLED-1000-80-35-SO-6-W-UNV-DP-1-CTS(36) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 14 | 14 | Jessica Pasternyk |  | Regular |  | L13-6' | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | TRUE | FALSE
72221-3 | 72221 | 3 | 1 | Regular | B2LED-8 | BDLED-1000-80-35-SO-8-W-UNV-DP-1-CTS(36) |  | Machine Shop Finished | 2019-01-30 | 13:32:28 | 2019-02-04 | 2019-02-07 | 12 | 12 | Jessica Pasternyk |  | Regular |  | L13-8 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
72221-4 | 72221 | 4 | 1 | Regular | B2LED-8 | BSLED-750-80-35-SO-8-W-UNV-DP-1-SC |  | Machine Shop Finished | 2019-01-30 | 13:36:28 | 2019-02-04 | 2019-02-07 | 13 | 13 | Jessica Pasternyk |  | Regular |  | L14 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
72722-1 | 72722 | 1 | 1 | Regular | AIRLED-2 | ARWLED-500-80-35-S-2-W-120-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 4 | 4 | Sacha Lempka |  | Regular |  | L10 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-2 | 72722 | 2 | 1 | Regular | AIRLED-4 | ARWLED-500-80-35-S-4-W-120-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 3 | 3 | Sacha Lempka |  | Regular |  | L10A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-3 | 72722 | 3 | 1 | Regular | AIRLED-8 | ARWLED-500-80-35-S-8-W-120-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Sacha Lempka |  | Regular |  | L10B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-4 | 72722 | 4 | 1 | Regular | B4LED-8 | BBDLED-1000-80-35-SO-8-AP-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 16 | 16 | Sacha Lempka |  | Regular |  | L12 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-5 | 72722 | 5 | 1 | Regular | STFD | STFD-DML(32-225)-80-35-AL(4)-AP-120-MD-1-CA(48)-RC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 4 | Sacha Lempka |  | Regular |  | L15 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-6 | 72722 | 6 | 1 | Regular | STENCL-STFD | STFD-DML(52-450)-80-35-AH(10)+AY(2)-AP-120-MD-1-CA(72)-RC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 13 | Sacha Lempka |  | Regular |  | L18 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-7 | 72722 | 7 | 1 | Regular | STENCL-STFD | STFD-DML(56-450)-80-35-AH(10)+AY(2)+AI(1)-AP-120-MD-1-CA(72)-RC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 14 | Sacha Lempka |  | Regular |  | L18A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-8 | 72722 | 8 | 1 | Regular | STENCL-STFD | SP0000-STFD-DML(236-450)-80-35-AH(34)+AY(14)+AI(4)-AP-120-MD-3-CA(72)-RC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 59 | Sacha Lempka |  | Regular |  | L18B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-9 | 72722 | 9 | 1 | Regular | AIRLED-4 | ARWLED-500-80-35-S-4-AP-120-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Sacha Lempka |  | Regular |  | 4' WALL-M | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-10 | 72722 | 10 | 1 | Regular | STENCL-STFD | STFD-DML(56-450)-80-35-AH(10)+AY(2)+AI(1)-AP-120-MD-1-CA(72)-RC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 14 | Sacha Lempka |  | Regular |  | L18B1 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72722-11 | 72722 | 11 | 1 | Regular | STENCL-STFD | STFD-DML(56-450)-80-35-AH(10)+AY(2)+AI(1)-AP-120-MD-1-CA(72)-RC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 14 | Sacha Lempka |  | Regular |  | L18B2 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72844-1 | 72844 | 1 | 1 | Regular | B4LED-6 | BBRLED-750-80-27-FL-6-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 8 | 8 | Sacha Lempka |  | Regular |  | R20 | 12 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
72891-1 | 72891 | 1 | 1 | Regular | WB4LED-5 | WBRLED-500-80-35-S-5-AP-120-DP-1-D |  | Scheduled/Released |  |  | 2019-03-04 | 2019-03-07 | 19 | 19 | Sacha Lempka |  | Regular |  | V | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72891-2 | 72891 | 2 | 1 | Regular | WB4LED-2 | WBRLED-500-80-35-S-2-AP-120-DP-1-D |  | Scheduled/Released |  |  | 2019-03-04 | 2019-03-07 | 1 | 1 | Sacha Lempka |  | Regular |  | V1 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72891-3 | 72891 | 3 | 1 | Regular | MINLED-4 | SP18347(1)-MBWVLED-500-80-35-S-4-AP-120-DP-1-EF |  | Scheduled/Released |  |  | 2019-03-04 | 2019-03-07 | 4 | 4 | Sacha Lempka |  | Regular |  | S1 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72891-4 | 72891 | 4 | 1 | Regular | MINLED-8 | SP18347(1)-MBWVLED-500-80-35-S-8-AP-120-DP-1-EF |  | Scheduled/Released |  |  | 2019-03-04 | 2019-03-07 | 3 | 3 | Sacha Lempka |  | Regular |  | S2 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
72906-2 | 72906 | 2 | 1 | Regular | B2LED-4 | BRLED-1000-90-35-FL-4-W-120-DP-1-DS |  | Machine Shop Finished | 2019-01-30 | 15:50:34 | 2019-02-04 | 2019-02-07 | 1 | 1 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | N1 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
72906-3 | 72906 | 3 | 1 | Regular | B2LED-10 | BRLED-1000-90-35-FL-10-W-120-DP-1-DS |  | Machine Shop Finished | 2019-01-30 | 15:50:39 | 2019-02-04 | 2019-02-07 | 2 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | N2 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
72906-4 | 72906 | 4 | 1 | Regular | B2LED-6 | BRLED-1000-90-35-FL-6-W-120-DP-1-DS |  | Machine Shop Finished | 2019-01-30 | 15:52:24 | 2019-02-04 | 2019-02-07 | 1 | 1 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | N3 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
72906-5 | 72906 | 5 | 1 | Regular | B2SLED-50 | B2SQDLED-1000-90-35-SO-50-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-31 | 11:02:54 | 2019-02-04 | 2019-02-07 | 2 | 10 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K50 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
72906-6 | 72906 | 6 | 1 | Regular | B2SLED-22 | B2SQDLED-1000-90-35-SO-22-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-31 | 11:02:56 | 2019-02-04 | 2019-02-07 | 1 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K22 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
72906-7 | 72906 | 7 | 1 | Regular | B2SLED-21 | B2SQDLED-1000-90-35-SO-21-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-31 | 11:02:58 | 2019-02-04 | 2019-02-07 | 1 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K21 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
72906-8 | 72906 | 8 | 1 | Regular | B2SLED-20 | B2SQDLED-1000-90-35-SO-20-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-31 | 11:03:49 | 2019-02-04 | 2019-02-07 | 1 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K20 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:58 |  | TRUE | FALSE
73065-1 | 73065 | 1 | 1 | Regular | BEAM4-2 | BBR-WW-NO-2-NL-T5-1-W-120-ERS-1-TB9 |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 7 | 7 | Joshua Zimet | Picked - Complete | Regular |  | P2 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73065-2 | 73065 | 2 | 1 | Regular | BEAM4-4 | BBR-WW-NO-4-NL-T5-1-W-120-ERS-1-TB9 | Wrong info. In SD | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 36 | 36 | Joshua Zimet | Picked - Complete | Regular |  | P4 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
73251-1 | 73251 | 1 | 1 | Regular | B3PLED-4'5" | BMPRLED-750-90-35-FL-4'5"-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F1-4'5" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-2 | 73251 | 2 | 1 | Regular | B3PLED-8'2 5/8" | BMPRLED-750-90-35-FL-8'2 5/8"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F1-8'2-5/8" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-4 | 73251 | 4 | 1 | Regular | B3LED-28'8 1/2" | BMRLED-750-90-35-FL-28'8 1/2"-W-UNV-DP-1+E(2)-TG9 |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F1-28'8-1/2" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-5 | 73251 | 5 | 1 | Regular | B3LED-73'2 7/8" | BMRLED-750-90-35-FL-73'2 7/8"-W-UNV-DP-1+E(3)-TG9 |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 4 | Gagandeep Singh |  | High Priority |  | F1-73'2-7/8" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-6 | 73251 | 6 | 1 | Regular | B3LED-95'6" | BMRLED-750-90-35-FL-95'6"-W-UNV-DP-1+E(5)-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 8 | Gagandeep Singh |  | High Priority |  | F1-95'6" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-7 | 73251 | 7 | 1 | Regular | B3LED-2 | BMRLED-750-90-35-FL-2-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 8 | 8 | Gagandeep Singh |  | High Priority |  | F1B-2' - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-9 | 73251 | 9 | 1 | Regular | B3LED-4 | BMRLED-750-90-35-FL-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 8 | 8 | Gagandeep Singh |  | High Priority |  | F1D/GY-4' - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-10 | 73251 | 10 | 1 | Regular | B3PLED-22'9 7/8" | BMPRLED-OPRO(1)-750-90-35-FL-22'9 7/8"-W-UNV-DP-1+E(2)-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 4 | Gagandeep Singh |  | High Priority |  | F1W-45 7/8"X18'11" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-11 | 73251 | 11 | 1 | Regular | B3PLED-36'11 3/4" | BMPRLED-OPRO(1)-750-90-35-FL-36'11 3/4"-W-UNV-DP-1+E(2)-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 5 | Gagandeep Singh |  | High Priority |  | F1W-18'10-3/4"X18'1" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-15 | 73251 | 15 | 1 | Regular | SKLPTP-28' 3/4" | SCPLED-OPRI(2)-300-90-35-RG2-28' 3/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 5 | Gagandeep Singh |  | High Priority |  | F24-8'10"X10'4-3/4"X8'10" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-16 | 73251 | 16 | 1 | Regular | SKLPTP-32'8" | SCPLED-OPRI(2)-300-90-35-RG2-32'8"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 10 | Gagandeep Singh |  | High Priority |  | F24-11'1-1/4"X10'5-1/2"X11'1-1/4" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-17 | 73251 | 17 | 1 | Regular | B3PLED-3'7" | BMPRLED-750-90-35-FL-3'7"-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F1-3'7" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-18 | 73251 | 18 | 1 | Regular | B3LED-111'8" | BMRLED-750-90-35-FL-111'8"-W-UNV-DP-1+E(7)-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 10 | Gagandeep Singh |  | High Priority |  | F1-111'8" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-19 | 73251 | 19 | 1 | Regular | B3PLED-25'10" | BMPRLED-750-90-35-FL-25'10"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F1-25'10" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-20 | 73251 | 20 | 1 | Regular | B3LED-2 | BMRLED-750-90-35-FL-2-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 5 | 5 | Gagandeep Singh |  | High Priority |  | F1B-2' - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-21 | 73251 | 21 | 1 | Regular | B3LED-56" | BMRLED-750-90-35-FL-56"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F1C-56" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-22 | 73251 | 22 | 1 | Regular | B3PLED-37'1" | BMPRLED-OPRO(1)-750-90-35-FL-37'1"-W-UNV-DP-1+E(2)-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 5 | Gagandeep Singh |  | High Priority |  | F1W-18'11-3/8"X18'1-5/8" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-23 | 73251 | 23 | 1 | Regular | B3PLED-40'7 3/4" | BMPRLED-OPRO(1)-750-90-35-FL-40'7 3/4"-W-UNV-DP-1+E(2)-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 5 | Gagandeep Singh |  | High Priority |  | F1W-21'8-1/2"X18'11-1/4" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-27 | 73251 | 27 | 1 | Regular | B3LED-27'1 1/4" | BMRVLED-750-80-35-SO-27'1 1/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F7-27'1-1/4" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-28 | 73251 | 28 | 1 | Regular | B3LED-83'7 1/8" | BMRLED-750-90-35-FL-83'7 1/8"-W-UNV-DP-1+E(6)-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 7 | Gagandeep Singh | Picked - Complete | High Priority |  | F1-83'7-1/8" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-29 | 73251 | 29 | 1 | Regular | B3LED-97" | BMRLED-750-90-35-FL-97"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Gagandeep Singh | Picked - Complete | High Priority |  | F1A-97" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-30 | 73251 | 30 | 1 | Regular | B3LED-2 | BMRLED-750-90-35-FL-2-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 3 | 3 | Gagandeep Singh | Picked - Complete | High Priority |  | F1B-2' - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-31 | 73251 | 31 | 1 | Regular | B3LED-57 1/2" | BMRLED-750-90-35-FL-57 1/2"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Gagandeep Singh | Picked - Complete | High Priority |  | F1C-57-1/2" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-32 | 73251 | 32 | 1 | Regular | B3PLED-32'3 7/8" | BMPRLED-OPRO(1)-750-90-35-FL-32'3 7/8"-W-UNV-DP-1+E(1)-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 4 | Gagandeep Singh | Picked - Complete | High Priority |  | F1W-20'3-7/8"X12' - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-33 | 73251 | 33 | 1 | Regular | B3PLED-42'1/4" | BMPRLED-OPRO(1)-750-90-35-FL-42'1/4"-W-UNV-DP-1+E(4)-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 4 | Gagandeep Singh | Picked - Complete | High Priority |  | F1W-21'7 3/4"X20'4-1/2" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-36 | 73251 | 36 | 1 | Regular | B3LED-13'5 5/8" | BMRLEDPAT-OPI-90-750-80-35-SO-13'5 5/8"-EX-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 3 | Gagandeep Singh | Picked - Complete | High Priority |  | F7-5'3-1/4"X8'2-3/8" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-37 | 73251 | 37 | 1 | Regular | B3LED-31'1" | BMRLEDPAT-OPI-90-750-80-35-SO-31'1"-EX-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 4 | Gagandeep Singh | Picked - Complete | High Priority |  | F7-9'11-5/8"X22'-3/8" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-38 | 73251 | 38 | 1 | Regular | SKLPTP-28'1 1/4" | SCPLED-OPRI(2)-300-90-35-RG2-28'1 1/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 5 | Gagandeep Singh |  | High Priority |  | F24-8'10"X10'5-1/2"X8'10" - 6TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-39 | 73251 | 39 | 1 | Regular | B3PLED-34'9" | BMPRLED-750-90-35-FL-34'9"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F1W-34'9" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-40 | 73251 | 40 | 1 | Regular | B3LED-23'1 5/8" | BMRVLED-750-80-35-SO-23'1 5/8"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Gagandeep Singh |  | High Priority |  | F7-23'1-5/8" - 7TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-41 | 73251 | 41 | 1 | Regular | B3LED-96 3/4" | BMRLED-750-90-35-FL-96 3/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Gagandeep Singh | Picked - Complete | High Priority |  | F1A-96-3/4" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-42 | 73251 | 42 | 1 | Regular | B3LED-57 3/4" | BMRLED-750-90-35-FL-57 3/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Gagandeep Singh | Picked - Complete | High Priority |  | F1C-57-3/4" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73251-43 | 73251 | 43 | 1 | Regular | B3PLED-28'7 1/4" | BMPRLED-750-90-35-FL-28'7 1/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 3 | Gagandeep Singh | Picked - Complete | High Priority |  | F1W-28'7-1/4" - 22ND FL | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-20 | 73699 | 20 | 1 | Regular | B2SLED-30 | B2SQWDLED-400-80-35-SO-30-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Joshua Zimet |  | Regular |  | F11-30' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-21 | 73699 | 21 | 1 | Regular | B2SLED-35 | B2SQWDLED-400-80-35-SO-35-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 3 | Joshua Zimet |  | Regular |  | F11-35' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-22 | 73699 | 22 | 1 | Regular | B4LED-3 | BBDILED-400-400-80-35-SO-3-BLK-UNV-DP-2-CT15(60) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 4 | 4 | Joshua Zimet |  | Regular |  | F16-3' | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-28 | 73699 | 28 | 1 | Regular | TB2LED-49' 1 1/2" | TB2DILEDPAT-REC-90(4)-400-400-80-35-SO-SO-49' 1 1/2"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-49' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-29 | 73699 | 29 | 1 | Regular | TB2LED-32' 10 1/4" | TB2DILEDPAT-ASO-90(2)+85-400-400-80-35-SO-SO-32' 10 1/4"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 7 | Joshua Zimet |  | Regular |  | F31-32' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-30 | 73699 | 30 | 1 | Regular | TB2LED-53' 5 1/2" | TB2DILEDPAT-REC-90(4)-400-400-80-35-SO-SO-53' 5 1/2"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-53' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-31 | 73699 | 31 | 1 | Regular | TB2LED-38' 5 1/4" | TB2DILEDPAT-ASO-90(2)+95+85-400-400-80-35-SO-SO-38' 5 1/4"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-38' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-32 | 73699 | 32 | 1 | Regular | TB2LED-42' 4 5/8" | TB2DILEDPAT-ASO-90(2)+94.5+85.5-400-400-80-35-SO-SO-42' 4 5/8"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-42' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-33 | 73699 | 33 | 1 | Regular | TB2LED-41' 2 1/4" | TB2DILEDPAT-ASO-90(2)+94.5+85.5-400-400-80-35-SO-SO-41' 2 1/4"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-41' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-34 | 73699 | 34 | 1 | Regular | TB2LED-34' 4 1/8" | TB2DILEDPAT-ASO-90(2)+94.5+85.5-400-400-80-35-SO-SO-34' 4 1/8"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-34' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-35 | 73699 | 35 | 1 | Regular | TB2LED-28' 1 1/2" | TB2DILEDPAT-ASO-90(2)+94.5+85.5-400-400-80-35-SO-SO-28' 1 1/2"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-28' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73699-36 | 73699 | 36 | 1 | Regular | TB2LED-28' 10 7/8" | TB2DILEDPAT-ASO-90(2)+94.5+85.5-400-400-80-35-SO-SO-28' 10 7/8"-EX-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 8 | Joshua Zimet |  | Regular |  | F31-28.9' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73799-1 | 73799 | 1 | 1 | Regular | WALED-11 | WALED-11-1600-80-30-VL-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 287 | 287 | Jessica Pasternyk |  | Regular |  | A2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73799-2 | 73799 | 2 | 1 | Regular | WALED-14 | WALED-14-6500-80-30-VL-W-UNV-DP-1-SM |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 263 | 263 | Jessica Pasternyk |  | Regular |  | A4 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
73799-3 | 73799 | 3 | 1 | Regular | WALED-14 | WALED-14-7700-80-30-VL-W-UNV-DP-1-SM |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 21 | 21 | Jessica Pasternyk |  | Regular |  | A5 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-4 | 73799 | 4 | 1 | Regular | SCULPT-4 | SCR-500-90-40-FL-4-W-UNV-DP-1-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 17 | 17 | Jessica Pasternyk |  | Regular |  | K1-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-5 | 73799 | 5 | 1 | Regular | SCULPT-4 | SCR-500-90-40-FL-4-W-UNV-DP-E(1)-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 13 | 13 | Jessica Pasternyk |  | Regular |  | K1E-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-6 | 73799 | 6 | 1 | Regular | SCULPT-8 | SCR-500-90-40-FL-8-W-UNV-DP-1+E(1)-MFTG9-C(4' FL LENS+4' 0.5M STEP LENS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 3 | 3 | Jessica Pasternyk |  | Regular |  | K1E/K2-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-7 | 73799 | 7 | 1 | Regular | SCULPT-8 | SCR-500-90-40-FL-8-W-UNV-DP-1+E(1)-MFTG9-C(4' 0.5M STEP LENS+4' FL LENS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Pasternyk |  | Regular |  | K2E/K1-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-8 | 73799 | 8 | 1 | Regular | SCULPT-8 | SCR-500-90-40-FL-8-W-UNV-DP-1-MFTG9-C(4' FL LENS+4' 2M STEP LENS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Jessica Pasternyk |  | Regular |  | K1/K3-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-9 | 73799 | 9 | 1 | Regular | SCULPT-2 | SCR-500-90-40-FL-2-W-UNV-DP-1-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Jessica Pasternyk |  | Regular |  | K1 2 | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-10 | 73799 | 10 | 1 | Regular | SCULPT-8 | SCR-500-90-40-FL-8-W-UNV-DP-1-MFTG9-C(4' FL LENS+4' 0.5M STEP LENS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Jessica Pasternyk |  | Regular |  | K1/K2-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-11 | 73799 | 11 | 1 | Regular | SCULPT-4 | SCR-500-90-40-0.5M-4-W-UNV-DP-1-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 11 | 11 | Jessica Pasternyk |  | Regular |  | K2-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-12 | 73799 | 12 | 1 | Regular | SCULPT-4 | SCR-500-90-40-0.5M-4-W-UNV-DP-E(1)-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 9 | 9 | Jessica Pasternyk |  | Regular |  | K2E-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-13 | 73799 | 13 | 1 | Regular | SCULPT-3 | SCR-500-90-40-0.5M-3-W-UNV-DP-1-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Jessica Pasternyk |  | Regular |  | K2 3 | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-14 | 73799 | 14 | 1 | Regular | SCULPT-8' | SCR-500-90-40-0.5M-8'-W-UNV-DP-1-MFTG9-C(4' 0.5M+4' 2M STEP LENS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 5 | 5 | Jessica Pasternyk |  | Regular |  | K2/K3-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-15 | 73799 | 15 | 1 | Regular | SCULPT-8' | SCR-500-90-40-0.5M-8'-W-UNV-DP-1+E(1)-MFTG9-C(4' 0.5M+4' 2M STEP LENS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Pasternyk |  | Regular |  | K2/K3E-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-16 | 73799 | 16 | 1 | Regular | SCULPT-8' | SCR-500-90-40-0.5M-8'-W-UNV-DP-1+E(1)-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Pasternyk |  | Regular |  | K2, K2E-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-17 | 73799 | 17 | 1 | Regular | SCULPT-4 | SCR-500-90-40-2M-4-W-UNV-DP-1-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 20 | 20 | Jessica Pasternyk |  | Regular |  | K3-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-18 | 73799 | 18 | 1 | Regular | SCULPT-4 | SCR-500-90-40-2M-4-W-UNV-DP-E(1)-MFTG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Jessica Pasternyk |  | Regular |  | K3E-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-19 | 73799 | 19 | 1 | Regular | B3SLED-4' | B3RLED-SL-750-90-40-FL-4'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 9 | 9 | Jessica Pasternyk |  | Regular |  | Z-4' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-20 | 73799 | 20 | 1 | Regular | B3LED-168' | SP18274-BMRLED-400-80-40-ASO-168'-W-UNV-DP-1+E(9)-TB9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 5 | 70 | Jessica Pasternyk |  | Regular |  | L-168' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-21 | 73799 | 21 | 1 | Regular | B3LED-132' | SP18274-BMRLED-400-80-40-ASO-132'-W-UNV-DP-1+E(8)-TB9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 11 | Jessica Pasternyk |  | Regular |  | L-132' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73799-22 | 73799 | 22 | 1 | Regular | B3LED-148' | SP18274-BMRLED-400-80-40-ASO-148'-W-UNV-DP-1+E(8)-TB9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 5 | 65 | Jessica Pasternyk |  | Regular |  | L-148' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
73827-1 | 73827 | 1 | 1 | Regular | B3LED-4 | BMRLED-400-80-35-FL-4-W-120-DP-1-DF |  | Machine Shop Finished | 2019-01-31 | 11:22:42 | 2019-03-06 | 2019-03-11 | 3 | 3 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
73829-1 | 73829 | 1 | 1 | Regular | CUBLED-36 | CUBLED-SL 75/25-1000-90-35-PL-36-W-UNV-DP-1-CT9(120) |  | Wiring Started | 2019-01-30 | 10:58:50 | 2019-02-01 | 2019-02-06 | 8 | 24 | George Bacalla | Picked - Complete | High Priority |  | A1 | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-2 | 73829 | 2 | 1 | Regular | CUBLED-28 | CUBLED-SL 75/25-1000-90-35-PL-28-W-UNV-DP-1-CT9(120) |  | Wiring Started | 2019-01-30 | 10:58:51 | 2019-02-01 | 2019-02-06 | 9 | 27 | George Bacalla | Picked - Complete | High Priority |  | A2 | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-3 | 73829 | 3 | 1 | Regular | CUBLED-24 | CUBLED-SL 75/25-1000-90-35-PL-24-W-UNV-DP-1-CT9(120) |  | Wiring Started | 2019-01-30 | 10:58:52 | 2019-02-01 | 2019-02-06 | 1 | 2 | George Bacalla | Picked - Complete | High Priority |  | A3 | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-4 | 73829 | 4 | 1 | Regular | SCULPT-216 | SCR-500-90-35-FL-16-W-UNV-DP-1-DF |  | Wiring Started | 2019-01-29 | 23:38:57 | 2019-02-01 | 2019-02-06 | 2 | 4 | George Bacalla | Picked - Complete | High Priority |  | G | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-5 | 73829 | 5 | 1 | Regular | B6LED-36 | B6RLED-500-90-35-FL-36-W-UNV-DP-1-TB9 |  | Wiring Started | 2019-01-29 | 23:38:59 | 2019-02-01 | 2019-02-06 | 1 | 3 | George Bacalla | Picked - Complete | High Priority |  | H | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-6 | 73829 | 6 | 1 | Regular | B4LED-8 | BBRLED-1000-90-35-FL-8-W-UNV-DP-1-DF |  | Wiring Started | 2019-01-29 | 23:39:02 | 2019-02-01 | 2019-02-06 | 1 | 1 | George Bacalla | Picked - Complete | High Priority |  | L | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-7 | 73829 | 7 | 1 | Regular | B3LED-12 | BMRLED-1000-90-35-FL-12-W-UNV-DP-1-DF |  | Wiring Started | 2019-01-29 | 23:39:04 | 2019-02-01 | 2019-02-06 | 1 | 1 | George Bacalla | Picked - Complete | High Priority |  | M | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | FALSE
73829-8 | 73829 | 8 | 1 | Regular | TB2LED-10 | TBDILED-650-400-90-35-SO-10-W-UNV-DP-1-CT9(36) | Wrong part in BOM | Wiring Started | 2019-01-29 | 23:39:06 | 2019-02-01 | 2019-02-06 | 1 | 1 | George Bacalla | Picked - Complete | High Priority |  | N | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 07:59 |  | TRUE | TRUE
73887-15 | 73887 | 15 | 1 | Regular | STENCL-STFD | STFD-DSO(16-400)-80-35-AH(6)-BLK-UNV-MD-1-CA(36)-RC | Others | Machine Shop Finished | 2019-02-04 | 07:35:58 | 2019-01-31 | 2019-02-05 | 2 | 14 | Christina Torok |  | Regular |  | Q4 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:24 |  | TRUE | FALSE
74123-1 | 74123 | 1 | 1 | Regular | MINI-3 | MBWV-S-3-T5-1-W-120-ERS-1 |  | Scheduled/Released |  |  | 2019-03-04 | 2019-03-07 | 30 | 30 | Sacha Lempka |  | High Priority |  | D | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74123-1 | 74123 | 1 | 2 | Regular | MINI-3 | MBWV-S-3-T5-1-W-120-ERS-1 |  | Scheduled/Released |  |  | 2019-04-01 | 2019-04-04 | 35 | 35 | Sacha Lempka |  | High Priority |  | D | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74124-22 | 74124 | 22 | 1 | Regular | B4LED-8 | BBDILED-640-400-80-35-SO-8-W-UNV-DP-1-CA(36) |  | Wiring Started | 2019-01-29 | 23:29:55 | 2019-02-07 | 2019-02-12 | 4 | 4 | Joshua Zimet | Picked - Complete | Regular |  | F4-8' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74124-23 | 74124 | 23 | 1 | Regular | B4LED-16 | BBDILED-640-400-80-35-SO-16-W-UNV-DP-1-CA(36) |  | Wiring Started | 2019-01-29 | 23:29:56 | 2019-02-07 | 2019-02-12 | 10 | 20 | Joshua Zimet | Picked - Complete | Regular |  | F4-16' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74124-24 | 74124 | 24 | 1 | Regular | B4LED-24 | BBDILED-640-400-80-35-SO-24-W-UNV-DP-2-CA(36) |  | Wiring Started | 2019-01-29 | 23:29:57 | 2019-02-07 | 2019-02-12 | 8 | 16 | Joshua Zimet | Picked - Complete | Regular |  | F4-24' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74276-1 | 74276 | 1 | 2 | Regular | BEAM4-4 | BBS-PL-4-NL-T8-1-W-347-E-1-SC-F-C(STM / 1 FUSE HOLDER GEC-ALSTHOM ) | Shortage | Machine Shop Started |  |  | 2019-02-21 | 2019-02-26 | 100 | 100 | Sacha Lempka | Picked - Complete | High Priority |  | A1 | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
74276-1 | 74276 | 1 | 3 | Regular | BEAM4-4 | BBS-PL-4-NL-T8-1-W-347-E-1-SC-F-C(STM / 1 FUSE HOLDER GEC-ALSTHOM ) |  | Scheduled/Released |  |  | 2019-05-24 | 2019-05-29 | 100 | 100 | Sacha Lempka |  | High Priority |  | A1 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74276-1 | 74276 | 1 | 4 | Regular | BEAM4-4 | BBS-PL-4-NL-T8-1-W-347-E-1-SC-F-C(STM / 1 FUSE HOLDER GEC-ALSTHOM ) |  | Scheduled/Released |  |  | 2019-08-23 | 2019-08-28 | 100 | 100 | Sacha Lempka |  | High Priority |  | A1 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74276-1 | 74276 | 1 | 5 | Regular | BEAM4-4 | BBS-PL-4-NL-T8-1-W-347-E-1-SC-F-C(STM / 1 FUSE HOLDER GEC-ALSTHOM ) |  | Scheduled/Released |  |  | 2019-12-27 | 2020-01-01 | 100 | 100 | Sacha Lempka |  | High Priority |  | A1 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74276-1 | 74276 | 1 | 6 | Regular | BEAM4-4 | BBS-PL-4-NL-T8-1-W-347-E-1-SC-F-C(STM / 1 FUSE HOLDER GEC-ALSTHOM ) |  | Scheduled/Released |  |  | 2020-03-24 | 2020-03-27 | 78 | 78 | Sacha Lempka |  | High Priority |  | A1 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74276-2 | 74276 | 2 | 2 | Regular | BEAM4-4 | BBS-PL-4-NL-T8-1-W-347-E-E(1)-SC-F-C(STM / B50-CAN BATT PACK / 2 FUSE HOLDERS GEC-ALSTHOM) |  | Machine Shop Started |  |  | 2019-02-21 | 2019-02-26 | 28 | 28 | Sacha Lempka | Picked - Complete | High Priority |  | AA1 | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
74294-4 | 74294 | 4 | 1 | Regular | PERFKT-CCH | CCH-SL-700-90-TC1680-CP(26)-W-UNV-DMX-1-C | Shortage | Machine Shop Finished | 2019-01-23 | 18:20:14 | 2019-01-03 | 2019-01-08 | 4 | 32 | Joshua Zimet | Picked - Complete | Regular |  | L20A | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-17 09:35 |  | TRUE | FALSE
74540-1 | 74540 | 1 | 1 | Regular | TB2LED-8 | TB2DILED-1110-500-80-30-SO-SO-8-W-347-DP-1-CT15(36) |  | Scheduled/Released |  |  | 2019-04-29 | 2019-05-02 | 1 | 1 | Sacha Lempka |  | High Priority |  | P1 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74540-2 | 74540 | 2 | 1 | Regular | TB2LED-12 | TB2DILED-1110-500-80-30-SO-SO-12-W-347-DP-1-CT15(36) |  | Scheduled/Released |  |  | 2019-04-29 | 2019-05-02 | 2 | 2 | Sacha Lempka |  | High Priority |  | P2 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74695-1 | 74695 | 1 | 1 | Regular | DIALED-22 | DIALED-22-2500-80-35-VL-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 28 | 28 | George Bacalla |  | Regular |  | AR8 | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74695-2 | 74695 | 2 | 1 | Regular | DIALED-11 | DIALED-11-1600-80-35-VL-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 14 | 14 | George Bacalla |  | Regular |  | AS3 | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74695-3 | 74695 | 3 | 1 | Regular | DIALED-11 | DIALED-11-1600-80-35-VL-W-UNV-DP-E(1)-DF-B1 |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 8 | 8 | George Bacalla |  | Regular |  | AS3E | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74695-4 | 74695 | 4 | 1 | Regular | DIALED-14 | DIALED-14-4000-80-30-VL-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 3 | 3 | George Bacalla |  | Regular |  | AS5 | 10 | TRUE | TRUE | FALSE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74695-5 | 74695 | 5 | 1 | Regular | B3LED-4' | BMDLED-750-80-35-SO-4'-BLK-UNV-DP-1-CT9(36) |  | Machine Shop Finished | 2019-01-31 | 20:18:18 | 2019-02-04 | 2019-02-07 | 3 | 3 | George Bacalla | Picked - Complete | Regular |  | L1-4' | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
74740-1 | 74740 | 1 | 1 | Regular | PRMLED-6 | PWWLED-500-80-35-S-6-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 2 | 2 | Jessica Kennedy |  | Regular |  | DL1 @ 6'-GROUND FLOOR | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-2 | 74740 | 2 | 1 | Regular | PRMLED-2 | PWWLED-500-80-35-S-2-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 2 | 2 | Jessica Kennedy |  | Regular |  | DL1A @ 2'-GROUND FLOOR | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-3 | 74740 | 3 | 1 | Regular | B4LED-12 | BBRLED-500-80-35-RG-12-CB20934(3)-W-120-DP-2-TG9 |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 2 | 2 | Jessica Kennedy |  | Regular |  | AL5 @ 12'- FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-4 | 74740 | 4 | 1 | Regular | SL2LED-6 | SL2HLED-2XSL-1000-1000-80-35-VL-6-AP-UNV-DP-1-CA(108)-C(9' CABLE & 20' POWER CORD) |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 37 | 37 | Jessica Kennedy |  | Regular |  | BL1 @ 6' - FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-5 | 74740 | 5 | 1 | Regular | SL2LED-8 | SL2LLED-2XSL-1000-500-80-35-VL-8-W-UNV-DP-1-CT9(36) |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 10 | 10 | Jessica Kennedy |  | Regular |  | BL2 @ 8' - FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-6 | 74740 | 6 | 1 | Regular | SL2LED-8 | SL2LLED-2XSL-1000-500-80-35-VL-8-W-UNV-DP-1+E(1)-CT9(36) |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 2 | 2 | Jessica Kennedy |  | Regular |  | BL2 @ 8' EM - FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-7 | 74740 | 7 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(26)-W-UNV-DP-1+E(2)-AC |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 1 | 8 | Jessica Kennedy |  | Regular |  | CL1 & 8.5'X17' - FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-8 | 74740 | 8 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(37)-W-UNV-DP-1+E(2)-AC |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 1 | 12 | Jessica Kennedy |  | Regular |  | CL1 @ 20'X17' - FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74740-9 | 74740 | 9 | 1 | Regular | PRMLED-6 | PWWLED-500-80-35-S-6-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-03-08 | 2019-03-13 | 2 | 2 | Jessica Kennedy |  | Regular |  | DL1 @ 6' - FLOOR 1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-1 | 74964 | 1 | 1 | Regular | GRAZE-35'5" | GPRLED-FC2W-500-90-35-RG2-35'5"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 6 | Jessica Pasternyk |  | High Priority |  | C1-(10800MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-2 | 74964 | 2 | 1 | Regular | GRAZE-16 | GPRLED-EX2W-500-90-35-RG2-16-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 13 | 26 | Jessica Pasternyk |  | High Priority |  | C1-(4890MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-3 | 74964 | 3 | 1 | Regular | GRAZE-34'8" | GPRLED-FC2W-500-90-35-RG2-34'8"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 4 | 12 | Jessica Pasternyk |  | High Priority |  | C1-(10560MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-4 | 74964 | 4 | 1 | Regular | GRAZE-36'7" | GPRLED-FC2W-500-90-35-RG2-36'7"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 8 | Jessica Pasternyk |  | High Priority |  | C1-(11156MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-5 | 74964 | 5 | 1 | Regular | GRAZE-37'1" | GPRLED-FC2W-500-90-35-RG2-37'1"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 8 | Jessica Pasternyk |  | High Priority |  | C1-(11300MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-6 | 74964 | 6 | 1 | Regular | GRAZE-35'4" | GPRLED-FC2W-500-90-35-RG2-35'4"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1-(10761MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-7 | 74964 | 7 | 1 | Regular | GRAZE-33'2" | GPRLED-FC2W-500-90-35-RG2-33'2"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 5 | 15 | Jessica Pasternyk |  | High Priority |  | C1-(10113MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-8 | 74964 | 8 | 1 | Regular | GRAZE-33'7" | GPRLED-FC2W-500-90-35-RG2-33'7"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 7 | 21 | Jessica Pasternyk |  | High Priority |  | C1-(10226MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-9 | 74964 | 9 | 1 | Regular | GRAZE-35'6" | GPRLED-FC2W-500-90-35-RG2-35'6"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1-(10830MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-10 | 74964 | 10 | 1 | Regular | GRAZE-36'9" | GPRLED-FC2W-500-90-35-RG2-36'9"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 8 | Jessica Pasternyk |  | High Priority |  | C1-(11198MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-11 | 74964 | 11 | 1 | Regular | GRAZE-34'6" | GPRLED-FC2W-500-90-35-RG2-34'6"-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 6 | Jessica Pasternyk |  | High Priority |  | C1-(10524MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-12 | 74964 | 12 | 1 | Regular | GRAZE-12' | GPRLED-EX2W-500-90-35-RG2-12'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Jessica Pasternyk |  | High Priority |  | C1-(3670MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-13 | 74964 | 13 | 1 | Regular | GRAZE-27' | GPRLED-FC2W-500-90-35-RG2-27'-W-120-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1-(8229MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-14 | 74964 | 14 | 1 | Regular | GRAZE-27'10" | GPRLED-FC2W-500-90-35-RG2-27'10"-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1A-(8490MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-15 | 74964 | 15 | 1 | Regular | GRAZE-34' | GPRLED-FC2W-500-90-35-RG2-34'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1A-(9747MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-16 | 74964 | 16 | 1 | Regular | GRAZE-27'9" | GPRLED-FC2W-500-90-35-RG2-27'9"-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1A-(8447MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-17 | 74964 | 17 | 1 | Regular | CLICK-12 | CLKLED-750-90-35-SO-12-W-120-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-08 | 9 | 18 | Jessica Pasternyk | Picked - Complete | High Priority |  | LS1-12FT | 1 | TRUE | TRUE | FALSE | TRUE |  | Ready | [7 empty] | ToDo | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-18 | 74964 | 18 | 1 | Regular | CLICK-16 | CLKLED-750-90-35-SO-16-W-120-DP-1-ST | Shortage | Machine Shop Started |  |  | 2019-02-08 | 2019-02-08 | 55 | 110 | Jessica Pasternyk | Picked - Complete | High Priority |  | LS1-16FT | 1 | TRUE | TRUE | FALSE | TRUE |  | InProg | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-19 | 74964 | 19 | 1 | Regular | ARCLED-8 | SP18407-ARCLED-SL 23/77-800-80-35-SO-8-W-120-DP-1-CTS(36) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-08 | 5 | 5 | Jessica Pasternyk | Picked - Complete | High Priority |  | SL1-8FT | 1 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-20 | 74964 | 20 | 1 | Regular | ARCLED-4 | SP18407-ARCLED-SL 23/77-800-80-35-SO-4-W-120-DP-1-CTS(36) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-08 | 3 | 3 | Jessica Pasternyk | Picked - Complete | High Priority |  | SL3 | 1 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-21 | 74964 | 21 | 1 | Regular | ARCLED-8 | SP18407-ARCWLED-SL 23/77-800-80-35-SO-8-W-120-DP-1 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-08 | 1 | 1 | Jessica Pasternyk | Picked - Complete | High Priority |  | W1-8FT | 1 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-22 | 74964 | 22 | 1 | Regular | ARCLED-18 | SP18407-ARCWLED-SL 23/77-800-80-35-SO-18-W-120-DP-1 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-08 | 1 | 3 | Jessica Pasternyk | Picked - Complete | High Priority |  | W1-18FT | 1 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74964-23 | 74964 | 23 | 1 | Regular | GRAZE-27' 11 1/2" | GPRLED-EXNW-500-90-35-RG2-27' 11 1/2"-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Jessica Pasternyk |  | High Priority |  | C1A-(8528MM) | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74968-1 | 74968 | 1 | 1 | Regular | SKETCH-AL(#23' 9 1/4") | SKPE-18075-SL 60/40-ASO-AL(#23' 9 1/4")-1000-80-40-SO-C(RAL5012)-UNV-D-1-CA(36) | Others | Machine Shop Started |  |  | 2019-01-24 | 2019-01-29 | 1 | 4 | Rohan Srivastava | Picked - Complete | High Priority |  | A-23 '9-1/4" | 1 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
74968-2 | 74968 | 2 | 1 | Regular | SKETCH-AL(#14' 10 | SKPE-18075-SL 60/40-ASO-AL(#14' 10-1/4")-1000-80-40-SO-C(RAL6038)-UNV-D-1-CA(36) | Others | Machine Shop Started |  |  | 2019-01-24 | 2019-01-29 | 1 | 3 | Rohan Srivastava | Picked - Complete | High Priority |  | B-14' 10-1/4" | 1 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
74968-3 | 74968 | 3 | 1 | Regular | SKETCH-AL(# 16' 10 | SKPE-18075-SL 60/40-ASO-AL(# 16' 10-1/4")-1000-80-40-SO-C(RAL2007)-UNV-D-1-CA(36) | Shortage | Machine Shop Started |  |  | 2019-01-24 | 2019-01-29 | 1 | 3 | Rohan Srivastava | Picked - Complete | High Priority |  | C-16' 10-1/4"` | 1 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
74971-1 | 74971 | 1 | 1 | Regular | B4LED-16 | BBRLED-1000-90-30-FL-16-W-277-DP-1+E(1)-DS-C(10% DIMMING) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Stan Buyansky |  | Regular |  | F9A-16-EM | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74971-2 | 74971 | 2 | 1 | Regular | B4LED-22 | BBRLED-1000-90-30-FL-22-W-277-DP-1+E(1)-DS-C(10% DIMMING) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 7 | 14 | Stan Buyansky |  | Regular |  | F9-22-EM | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74971-3 | 74971 | 3 | 1 | Regular | B4LED-12 | BBRLED-750-90-30-FL-12-W-277-DP-1+E(1)-DS-C(10% DIMMING) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 8 | 8 | Stan Buyansky |  | Regular |  | F2-12-EM | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
74971-4 | 74971 | 4 | 1 | Regular | B4LED-30 | BBRLED-750-90-30-FL-30-W-277-DP-1+E(2)-DS-C(10% DIMMING) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Stan Buyansky |  | Regular |  | F2-30-EM | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75090-1 | 75090 | 1 | 1 | Regular | TBEAM2-10 | TB-S-10-NL-T5HO-2-W-UNV-D(MARK7)-1-CA(36) |  | Machine Shop Finished | 2019-02-04 | 07:32:17 | 2019-02-06 | 2019-02-11 | 1 | 1 | Rohan Srivastava |  | Regular |  | L6-10' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75090-2 | 75090 | 2 | 1 | Regular | ZENSQ-15 | ZESQDI-SL 50/50-1200-80-35-SO-15-AP-UNV-MD-1-CA(36) |  | Machine Shop Finished | 2019-02-04 | 07:32:19 | 2019-02-06 | 2019-02-11 | 2 | 4 | Rohan Srivastava |  | Regular |  | L7-15' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75090-3 | 75090 | 3 | 1 | Regular | SKETCH-AL(7'10 1/4") | SKPE-10005-SL 60/40-CIR-AL(7'10 1/4")-1000-80-35-SO-W-277-D-1-CTS(36) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 12 | Rohan Srivastava |  | Regular |  | L9-7'10 1/2" | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75090-4 | 75090 | 4 | 1 | Regular | ZENSQ-20 | ZESQDI-SL 50/50-1200-80-35-SO-20-AP-UNV-MD-1-CA(36) |  | Machine Shop Finished | 2019-02-04 | 07:33:47 | 2019-02-06 | 2019-02-11 | 2 | 4 | Rohan Srivastava |  | Regular |  | L7-20' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-3 | 75103 | 3 | 1 | Regular | TWGLED-4 | TWRWLED-SL 90/10-1000-80-35-SO-4-W-120-DP-1 |  | Machine Shop Finished | 2019-02-01 | 09:47:13 | 2019-02-01 | 2019-02-06 | 6 | 6 | Sacha Lempka |  | Priority |  | B4-NIV5 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-4 | 75103 | 4 | 1 | Regular | TWGLED-6 | TWRWLED-SL 90/10-1000-80-35-SO-6-W-120-DP-1 |  | Machine Shop Finished | 2019-02-01 | 09:47:10 | 2019-02-01 | 2019-02-06 | 5 | 5 | Sacha Lempka |  | Priority |  | B6-NIV5 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-5 | 75103 | 5 | 1 | Regular | TWGLED-8 | TWRWLED-SL 90/10-1000-80-35-SO-8-W-120-DP-1 |  | Machine Shop Finished | 2019-02-01 | 09:47:07 | 2019-02-01 | 2019-02-06 | 12 | 12 | Sacha Lempka |  | Priority |  | B8-NIV5 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-6 | 75103 | 6 | 1 | Regular | TWGLED-4 | TWRLED-SL 90/10-1250-80-35-SO-4-W-120-DP-1-CTS(36) |  | Machine Shop Finished | 2019-02-01 | 09:47:06 | 2019-02-01 | 2019-02-06 | 7 | 7 | Sacha Lempka |  | Priority |  | M4-NIV5 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-7 | 75103 | 7 | 1 | Regular | TWGLED-6 | TWRLED-SL 90/10-1250-80-35-SO-6-W-120-DP-1-CTS(36) |  | Machine Shop Finished | 2019-02-01 | 09:47:04 | 2019-02-01 | 2019-02-06 | 3 | 3 | Sacha Lempka |  | Priority |  | M6-NIV5 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-10 | 75103 | 10 | 1 | Regular | TWGLED-4 | TWRWLED-SL 90/10-1000-80-35-SO-4-W-120-DP-1 |  | Machine Shop Finished | 2019-02-01 | 09:47:02 | 2019-02-01 | 2019-02-06 | 1 | 1 | Sacha Lempka |  | Priority |  | B4-NIV6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-11 | 75103 | 11 | 1 | Regular | TWGLED-6 | TWRWLED-SL 90/10-1000-80-35-SO-6-W-120-DP-1 |  | Machine Shop Finished | 2019-02-01 | 09:47:01 | 2019-02-01 | 2019-02-06 | 4 | 4 | Sacha Lempka |  | Priority |  | B6-NIV6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-12 | 75103 | 12 | 1 | Regular | TWGLED-8 | TWRWLED-SL 90/10-1000-80-35-SO-8-W-120-DP-1 |  | Machine Shop Finished | 2019-02-01 | 09:46:59 | 2019-02-01 | 2019-02-06 | 1 | 1 | Sacha Lempka |  | Priority |  | B8-NIV6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-13 | 75103 | 13 | 1 | Regular | TWGLED-4 | TWRLED-SL 90/10-1250-80-35-SO-4-W-120-DP-1-CTS(36) |  | Machine Shop Finished | 2019-02-01 | 09:46:57 | 2019-02-01 | 2019-02-06 | 1 | 1 | Sacha Lempka |  | Priority |  | M4-NIV6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-14 | 75103 | 14 | 1 | Regular | TWGLED-6 | TWRLED-SL 90/10-1250-80-35-SO-6-W-120-DP-1-CTS(36) |  | Machine Shop Finished | 2019-02-01 | 09:46:56 | 2019-02-01 | 2019-02-06 | 1 | 1 | Sacha Lempka |  | Priority |  | M6-NIV6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75103-15 | 75103 | 15 | 1 | Regular | TWGLED-8 | TWRLED-SL 90/10-1250-80-35-SO-8-W-120-DP-1-CTS(36) |  | Machine Shop Finished | 2019-02-01 | 09:46:53 | 2019-02-01 | 2019-02-06 | 1 | 1 | Sacha Lempka |  | Priority |  | M8-NIV6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75164-1 | 75164 | 1 | 1 | Regular | SLMLED-30 | SLLED-SL 0/100-800-80-35-PL-30-W-347-DP-1-CA(36)+SM | Wrong info. In SD | Wiring Started | 2019-01-27 | 13:26:43 | 2019-01-29 | 2019-02-01 | 3 | 9 | George Bacalla |  | High Priority |  | L1-30' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-29 11:23 |  | TRUE | TRUE
75164-2 | 75164 | 2 | 1 | Regular | B3LED-4 | BMWDLED-400-80-35-SO-4-W-UNV-DP-1 | Others | Wiring Started | 2019-01-29 | 07:58:18 | 2019-01-29 | 2019-02-01 | 2 | 2 | George Bacalla |  | High Priority |  | L2 4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 11:23 |  | TRUE | TRUE
75164-3 | 75164 | 3 | 1 | Regular | B3LED-12 | BMWDLED-400-80-35-SO-12-W-UNV-DP-1 | Others | Wiring Started | 2019-01-29 | 07:58:22 | 2019-01-29 | 2019-02-01 | 1 | 1 | George Bacalla |  | High Priority |  | L2 12' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 11:23 |  | TRUE | TRUE
75212-22 | 75212 | 22 | 1 | Regular | B2LED-16 | BRLEDPAT-SQ-90(4)-500-80-30-SO-FL-16-NL-W-UNV-DP-1-TG9-C(4' X 4' SQUARE WITH LIT CORNERS) |  | Given to Shipping | 2019-01-30 | 07:43:01 | 2019-01-29 | 2019-02-01 | 33 | 33 | Philip Halsey |  | Regular |  | R8 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-30 07:44 |  | TRUE | FALSE
75212-23 | 75212 | 23 | 1 | Regular | B2LED-3 | BRLED-500-80-30-FL-3-W-UNV-DP-1-D |  | Given to Shipping | 2019-01-29 | 01:18:52 | 2019-01-29 | 2019-02-01 | 1 | 1 | Philip Halsey |  | Regular |  | R9, 3' | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-24 | 75212 | 24 | 1 | Regular | B2LED-4 | BRLED-500-80-30-FL-4-W-UNV-DP-1-TG9 | Missing parts in BOM | Given to Shipping | 2019-01-29 | 01:19:03 | 2019-01-29 | 2019-02-01 | 6 | 6 | Philip Halsey |  | Regular |  | R9, 4' | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | TRUE
75212-25 | 75212 | 25 | 1 | Regular | B2LED-8 | BRLED-500-80-30-FL-8-W-UNV-DP-1-TG9 |  | Given to Shipping | 2019-01-29 | 01:19:10 | 2019-01-29 | 2019-02-01 | 30 | 30 | Philip Halsey |  | Regular |  | R9, 8' | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-26 | 75212 | 26 | 1 | Regular | B2LED-8 | BRLED-500-80-30-FL-8-W-UNV-DP-1+E(1)-TG9 |  | Given to Shipping | 2019-01-29 | 01:19:16 | 2019-01-29 | 2019-02-01 | 17 | 17 | Philip Halsey |  | Regular |  | R9, 8' EM | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-27 | 75212 | 27 | 1 | Regular | B2LED-12 | BRLED-500-80-30-FL-12-W-UNV-DP-1-TG9 |  | Given to Shipping | 2019-01-29 | 01:19:23 | 2019-01-29 | 2019-02-01 | 5 | 5 | Philip Halsey |  | Regular |  | R9, 12' | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-28 | 75212 | 28 | 1 | Regular | B2LED-12 | BRLED-500-80-30-FL-12-W-UNV-DP-1+E(1)-TG9 |  | Given to Shipping | 2019-01-29 | 01:19:32 | 2019-01-29 | 2019-02-01 | 2 | 2 | Philip Halsey |  | Regular |  | R9, 12' EM | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-29 | 75212 | 29 | 1 | Regular | B2LED-24 | BRLED-500-80-30-FL-24-W-UNV-DP-1-D |  | Given to Shipping | 2019-01-29 | 01:19:46 | 2019-01-29 | 2019-02-01 | 2 | 4 | Philip Halsey |  | Regular |  | R9, 24' | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-30 | 75212 | 30 | 1 | Regular | B3LED-4' | BMRLED-1000-80-30-ASO-4'-W-UNV-DP-1-D | Shortage | Machine Shop Started |  |  | 2019-01-29 | 2019-02-01 | 14 | 14 | Philip Halsey |  | Regular |  | R10, 4' | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | TRUE | 2019-02-04 08:38 |  | TRUE | FALSE
75212-36 | 75212 | 36 | 1 | Regular | B2LED-12 | BRLED-500-80-30-FL-12-W-UNV-DP-1-D |  | Given to Shipping | 2019-01-29 | 01:19:56 | 2019-01-29 | 2019-02-01 | 1 | 1 | Philip Halsey |  | Regular |  | R9, 12' (D) | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-37 | 75212 | 37 | 1 | Regular | B2LED-15 | BRLED-500-80-30-FL-15-W-UNV-DP-1-D |  | Given to Shipping | 2019-01-29 | 01:20:09 | 2019-01-29 | 2019-02-01 | 1 | 2 | Philip Halsey |  | Regular |  | R9, 15' | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-29 07:44 |  | TRUE | FALSE
75212-38 | 75212 | 38 | 1 | Regular | B3LED-24' | BMRLED-1000-80-30-ASO-24'-W-UNV-DP-1+E(1)-TB15 |  | Machine Shop Started |  |  | 2019-01-29 | 2019-02-12 | 4 | 8 | Philip Halsey |  | Regular |  | R10, 24' EM | 18 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-1 | 75218 | 1 | 1 | Regular | B3LED-16 | BMRLED-750-80-35-1.25M-16-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 2 | 4 | Joshua Zimet |  | Regular |  | F6-16' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-2 | 75218 | 2 | 1 | Regular | B3LED-28 | BMRLED-750-80-35-1.25M-28-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 3 | Joshua Zimet |  | Regular |  | F6-28' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-3 | 75218 | 3 | 1 | Regular | B3LED-36 | BMRLED-750-80-35-1.25M-36-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 3 | Joshua Zimet |  | Regular |  | F6-36' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-4 | 75218 | 4 | 1 | Regular | B3LED-40 | BMRLED-750-80-35-1.25M-40-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 4 | Joshua Zimet |  | Regular |  | F6-40' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-5 | 75218 | 5 | 1 | Regular | B3LED-42 | BMRLED-750-80-35-1.25M-42-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 4 | Joshua Zimet |  | Regular |  | F6-42' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-6 | 75218 | 6 | 1 | Regular | B3LED-44 | BMRLED-750-80-35-1.25M-44-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 1 | 4 | Joshua Zimet |  | Regular |  | F6-44' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-7 | 75218 | 7 | 1 | Regular | SL2LED-24 | SP19015(1)-SL2LLED-2XSL-200-700-80-35-SM-24-W-UNV-DP-1-CA(144) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 5 | 10 | Joshua Zimet |  | Regular |  | F7-24' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75218-8 | 75218 | 8 | 1 | Regular | SCULPT-K(4X4) | SCD-600-80-35-2M-K(4X4)-W-UNV-DP-1-CT15(36) |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 4 | 4 | Joshua Zimet |  | Regular |  | F11 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75368-1 | 75368 | 1 | 1 | Regular | B4LED-14 | BBRLED-500-80-35-RG-14-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Jessica Kennedy |  | Regular |  | R4(14') | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75368-2 | 75368 | 2 | 1 | Regular | B4LED-24 | BBRLED-500-80-35-RG-24-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Jessica Kennedy |  | Regular |  | R4(24') | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75392-1 | 75392 | 1 | 1 | Regular | PERFKT-CCWH | CCWH-SL-1100-80-27-CP(30')-W-120-DP-1-C |  | Machine Shop Finished | 2019-02-04 | 01:51:46 | 2019-01-31 | 2019-02-05 | 1 | 6 | Gagandeep Singh |  | Regular |  | LT19D-2'10"X25'7"X1'7" | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:11 |  | TRUE | FALSE
75398-1 | 75398 | 1 | 1 | Regular | B2SLED-4 | SP000-B2SQILED-1100-80-TW2750-SL-4-BLK-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Missing parts in BOM | Wiring Started | 2019-01-11 | 00:55:52 | 2019-01-11 | 2019-01-16 | 3 | 3 | Stan Buyansky | Picked - Complete | High Priority |  | L01A - 4 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:46 |  | TRUE | FALSE
75398-2 | 75398 | 2 | 1 | Regular | B2SLED-26 | SP000-B2SQILED-1100-80-TW2750-SLA-26-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Missing info. In SD | Wiring Started | 2019-01-13 | 17:12:26 | 2019-01-11 | 2019-01-16 | 43 | 129 | Stan Buyansky | Picked - Complete | High Priority |  | L01B - 26 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:46 |  | TRUE | TRUE
75398-3 | 75398 | 3 | 1 | Regular | B2SLED-4' 6 1/2" | SP000-B2SQILED-1100-80-TW2750-SLA-4' 6 1/2"-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Others | Wiring Started | 2019-01-11 | 00:56:06 | 2019-01-11 | 2019-01-16 | 1 | 1 | Stan Buyansky | Picked - Complete | High Priority |  | L01B - 4.5 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:46 |  | TRUE | TRUE
75462-4 | 75462 | 4 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Gagandeep Singh |  | High Priority |  | F05-10'-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-5 | 75462 | 5 | 1 | Regular | WWPRFK-11'8" | SP18369-WWR-SL-750-80-35-L-11'8"-C(ROCKFON723)-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F05-11'8"-PATH-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-6 | 75462 | 6 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Gagandeep Singh |  | High Priority |  | F05-8'-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-7 | 75462 | 7 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F05A-6'-TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-8 | 75462 | 8 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-c(ROCKFON723)-UNV-DP-1-DS-C(1 LONG SIDE D) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F05B-10'-PATH-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75462-9 | 75462 | 9 | 1 | Regular | WWPRFK-18' | SP18369-WWR-SL-750-80-35-L-18'-C(ROCKFON723)-UNV-DP-1-DS-C(1 LONG SIDE D) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 2 | Gagandeep Singh |  | High Priority |  | F05B-18'-PATH-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-10 | 75462 | 10 | 1 | Regular | WWPRFK-14' | SP18369-WWR-SL-750-80-35-L-14'-C(ROCKFON723)-UNV-DP-1-DS-C(1 LONG SIDE D) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 2 | Gagandeep Singh |  | High Priority |  | F05B-14'-PATH-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-11 | 75462 | 11 | 1 | Regular | WWPRFK-4' | SP18369-WWR-SL-750-80-35-L-4'-C(ROCKFON723)-UNV-DP-1-DS-C(1 LONG SIDE D) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | High Priority |  | F05B-4'-PATH-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75462-14 | 75462 | 14 | 1 | Regular | SCULPT-339 | SP18276-SCRPAT-OPR-131°+49°+71°+109°+91°+89°+87°+101°-350-80-35-FL-339-EX-W-UNV-DP-6-DS-C(ANGLED ENDS) | Missing info. In SD | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 24 | Gagandeep Singh | Picked - Complete | High Priority |  | F10-339'-5TH FL | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75462-15 | 75462 | 15 | 1 | Regular | SCULPT-46'5" | SP18276-SCR-350-80-35-FL-46'5"-W-UNV-DP-1-DS-C(ANGLED ENDS) | Missing info. In SD | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F10-46'5"-5TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75467-6 | 75467 | 6 | 1 | NPI | NPI-N18003-04 | NPI-N18003-GPDLED-1000-80-TW2750-RG2-14-W-O(DALIDT6)-1-CA(72)-LBC | Others | Wiring Started | 2018-12-19 | 16:23:14 | 2018-11-26 | 2018-11-29 | 3 | 6 | Stan Buyansky |  | Regular |  | L-04-14' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2018-12-04 16:05 |  | TRUE | FALSE
75475-5 | 75475 | 5 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-10'-6TH FL | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-6 | 75475 | 6 | 1 | Regular | WWPRFK-8 | SP18369-WWR-SL-750-80-35-L-8-C(ROCKFON723)-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-8'-PATH 6TH FL | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-7 | 75475 | 7 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 4 | 4 | Gagandeep Singh |  | Regular |  | F05-8'-6TH FL | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-8 | 75475 | 8 | 1 | Regular | WWPRFK-4' | SP18369-WWR-SL-750-80-35-L-4'-C(PS541A1391)-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05A-4'-PATH-6TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-9 | 75475 | 9 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-10'PATH-6TH FL | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-10 | 75475 | 10 | 1 | Regular | WWPRFK-20' | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS-C(1 LONG SIDE D) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 2 | Gagandeep Singh |  | Regular |  | F05B-20'-6TH FL | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-27 | 75475 | 27 | 1 | Regular | SCULPT-46'2" | SP18276-SCR-350-80-35-FL-46'2"-W-UNV-DP-1-DS-C(ANGLED ENDS) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 3 | Gagandeep Singh |  | Regular |  | F10-46'2"-ELEVATORS-6TH FL | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75475-28 | 75475 | 28 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Gagandeep Singh |  | Regular |  | F05-6'-06-30T | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75556-1 | 75556 | 1 | 1 | Regular | TB2LED-8 | TB2DILED-400-400-80-35-SO-SO-8-W-UNV-DP-1-CT15(36) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 44 | 44 | Christina Torok |  | High Priority |  | F3-CT15 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75556-2 | 75556 | 2 | 1 | Regular | TB2LED-8' | TB2DILED-400-400-80-35-SO-SO-8'-W-UNV-DP-1-CT15(36)-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 13 | 13 | Christina Torok |  | High Priority |  | F3E-CT15 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75556-3 | 75556 | 3 | 1 | Regular | TB2LED-8 | TB2DILED-400-400-80-35-SO-SO-8-W-UNV-DP-1-CT9(36) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 16 | 16 | Christina Torok |  | High Priority |  | F3-CT9 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75556-4 | 75556 | 4 | 1 | Regular | TB2LED-8' | TB2DILED-400-400-80-35-SO-SO-8'-W-UNV-DP-1-CT9(36)-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Christina Torok |  | High Priority |  | F3E-CT9 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75675-1 | 75675 | 1 | 1 | Regular | STENCL-STFC | STFC-NO-DML(9'-450)-80-35-AY(1)-W-120-MD-1-CT9(180")-RC |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Jessica Pasternyk |  | Regular |  | L02 | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75675-2 | 75675 | 2 | 1 | Regular | STENCL-STCO | STCO-NO-DSO(30'-400)-80-35-W-120-MD-1-CT9(180")-RC | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 5 | Jessica Pasternyk |  | Regular |  | L03 | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
75692-10 | 75692 | 10 | 1 | Regular | WWPRFK-14' | SP18369-WWR-SL-750-80-35-L-14'-W-UNV-DP-1-TG9 | Mechanical issue | Wiring Started | 2019-01-25 | 09:10:32 | 2019-01-21 | 2019-01-24 | 2 | 4 | Gagandeep Singh |  | High Priority |  | F05-14'-3RD FL | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-28 10:32 |  | TRUE | FALSE
75692-11 | 75692 | 11 | 1 | Regular | B3PLED-40'2 1/8" | SP18435(2)-BMPRLED-OPRO(158°)-750-80-35-RG3-40'2 1/8"-C(BLK)-UNV-DP-1-DS-TS(2)-C(127° ANGLED END) | Shortage | Wiring Started | 2019-01-28 | 15:36:08 | 2019-01-11 | 2019-01-16 | 1 | 5 | Gagandeep Singh | Picked - Complete | High Priority |  | F04A-26'10-11/16"X13'3-7/16"-3RD FL | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 16:05 |  | TRUE | FALSE
75693-4 | 75693 | 4 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 | Others | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 2 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | F05-8'-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-5 | 75693 | 5 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 2 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | F05-10'-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-6 | 75693 | 6 | 1 | Regular | WWPRFK-12' | SP18369-WWR-SL-750-80-35-L-12'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F05-12'-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-7 | 75693 | 7 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F05A-6'-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-8 | 75693 | 8 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-C(PS541A1391)-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F05A-6'-PATH-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-12 | 75693 | 12 | 1 | Regular | B3PLED-22'11 3/4" | SP18435(2)-BMPRLED-OPRI(79°)-750-80-35-RG3-22'11 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(102° ANGLED END) | Wrong info. In SD | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-13'5-7/16"X9'6-5/16"-07-15H | 7 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75693-13 | 75693 | 13 | 1 | Regular | B3PLED-19'10 5/16" | SP18435(2)-BMPRLED-OPRI(79°)-750-80-35-RG3-19'10 5/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(102° ANGLED END) | Wrong info. In SD | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'9-3/16"X8'11-1/8"-07-15K | 7 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-14 | 75693 | 14 | 1 | Regular | B3PLED-17'1 5/8" | SP18435(2)-BMPRLED-OPRI(102°)-750-80-35-RG3-17'1 5/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(79°ANGLED END) | Wrong info. In SD | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'2-7/16"X6'11-3/16"-07-15L | 7 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-17 | 75693 | 17 | 1 | Regular | B3PLED-18'8 1/2" | SP18435(2)-BMPRLED-OPRI(1)-750-80-35-RG3-18'8 1/2"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(74° ANGLED END) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-6'7-13/16"X12'-11/16"-07-17T | 7 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-18 | 75693 | 18 | 1 | Regular | B3PLED-10'3 3/16" | SP18435(2)-BMPRLED-750-80-35-RG3-10'3 3/16"-W-UNV-DP-1-TG9-TS(1)-C(74° & 107° ANGLED END) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'3-3/16"-07-19T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-19 | 75693 | 19 | 1 | Regular | B3PLED-9'10 1/6" | BMPRLED-750-80-35-RG3-9'10 1/6"-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-9'10-1/16"-07-20T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-20 | 75693 | 20 | 1 | Regular | B3PLED-10'4 1/8" | BMPRLED-750-80-35-RG3-10'4 1/8"-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'4-1/8"-07-22T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-21 | 75693 | 21 | 1 | Regular | B3PLED-10'4 1/8" | BMPRLED-750-80-35-RG3-10'4 1/8"-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'4-1/8"-07-24T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-22 | 75693 | 22 | 1 | Regular | B3PLED-21'3 3/16" | SP18435(2)-BMPRLED-OPRI(107°)-750-80-35-RG3-21'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2)-C(72.5°ANGLED END) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'10-5/16"X10'4-7/8"-07-17W | 7 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-23 | 75693 | 23 | 1 | Regular | B3PLED-9'7 3/8" | BMPRLED-750-80-35-RG3-9'7 3/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-9'7-3/8"-07-19W | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-24 | 75693 | 24 | 1 | Regular | B3PLED-9'5 1/4" | BMPRLED-750-80-35-RG3-9'5 1/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) | Missing parts in BOM | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-9'5-1/4"-07-21W | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75693-25 | 75693 | 25 | 1 | Regular | B3PLED-9'3 3/16" | BMPRLED-750-80-35-RG3-9'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-9'3-3/16"-07-23W | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-26 | 75693 | 26 | 1 | Regular | B3PLED-9'3 3/16" | BMPRLED-750-80-35-RG3-9'3 3/16"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-9'3-3/16"-07-26W | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-27 | 75693 | 27 | 1 | Regular | B3PLED-8'10" | BMPRLED-750-80-35-RG3-8'10"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-8'10"-07-28W | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-28 | 75693 | 28 | 1 | Regular | B3PLED-8'4 7/8" | BMPRLED-750-80-35-RG3-8'4 7/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-8'4 7/8"-07-30W | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-29 | 75693 | 29 | 1 | Regular | B3PLED-22'6 5/8" | SP18435(2)-BMPRLED-750-80-35-RG3-22'6 5/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1)-C(98° & 82° ANGLED END) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | F04-22'6-5/8"-07-34T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-30 | 75693 | 30 | 1 | Regular | B3PLED-24'11 1/8" | SP18435(2)-BMPRLED-750-80-35-RG3-24'11 1/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1)-C(98° & 75° ANGLED END) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-24'11-1/8"-07-39T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-31 | 75693 | 31 | 1 | Regular | B3PLED-34'7 1/2" | SP18435(2)-BMPRLED-750-80-35-RG3-34'7 1/2"-W-UNV-DP-1-TG9-TS(1)-C(64° & 105° ANGLED END) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F04-34'7-1/2"-07-41F | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-32 | 75693 | 32 | 1 | Regular | B3PLED-48'6" 3/8" | SP18435(2)-BMPRLED-OPRI(113°)+OPRO(113°+67°)-750-80-35-RG3-48'6" 3/8"-W-UNV-DP-1-TG9-TS(4)-C(79°&67°ANGLED END) | Missing info. In SD | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 8 | Gagandeep Singh | Picked - Complete | Regular |  | F04-13'5"X8'4"X8'4"X18'3"-04-44M | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75693-33 | 75693 | 33 | 1 | Regular | B3PLED-7'10 3/8" | BMPRLED-750-80-35-RG3-7'10 3/8"-W-UNV-DP-1-DS-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04A-7'10-3/8"-07-22F | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-36 | 75693 | 36 | 1 | Regular | SCULPT-45'5" | SP18276-SCR-350-80-35-FL-45'5"-W-UNV-DP-1-DS-C(85°&46° ANGLED ENDS) | Others | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Gagandeep Singh | Picked - Complete | Regular |  | F10-46'5"-ELEC LOBBY-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-40 | 75693 | 40 | 1 | Regular | B3PLED-10' | BMPRLED-750-80-35-RG3-10'-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-10'-07-19T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-41 | 75693 | 41 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-35-RG3-8'-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-8'-07-20T & 22T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-42 | 75693 | 42 | 1 | Regular | B3PLED-7'8" | BMPRLED-750-80-35-RG3-7'8"-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-7'8"-07-24T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-43 | 75693 | 43 | 1 | Regular | B3PLED-17'8" | BMPRLED-750-80-35-RG3-17'8"-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 2 | Gagandeep Singh | Picked - Complete | Regular |  | F04-17'8"-07-24T | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-44 | 75693 | 44 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-C(ROCKFON723)-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F05-6'-PATH-7TH FL | 7 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75693-45 | 75693 | 45 | 1 | Regular | B3PLED-12'2" | BMPRLED-750-80-35-RG3-12'2"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | F04-12'2"-07-15D | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75697-1 | 75697 | 1 | 1 | Regular | PRMLED-4 | PRWLED-800-80-40-S-4-W-UNV-BI-1-OS(1) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 7 | 7 | Jessica Kennedy |  | Regular |  | F5-4' | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75697-2 | 75697 | 2 | 1 | Regular | PRMLED-4 | PRWLED-800-80-40-S-4-W-UNV-BI-1-OS(1) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 35 | 35 | Jessica Kennedy |  | Regular |  | F5-4' E | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75697-3 | 75697 | 3 | 1 | Regular | PRMLED-8 | PRWLED-800-80-40-S-8-W-UNV-BI-1-OS(1) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 26 | 26 | Jessica Kennedy |  | Regular |  | F5-8' E | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75697-4 | 75697 | 4 | 1 | Regular | PRMLED-12 | PRWLED-800-80-40-S-12-W-UNV-BI-1-OS(1) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Jessica Kennedy |  | Regular |  | F5-12' E | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75728-1 | 75728 | 1 | 1 | Regular | SCULPT-4 | SCR-500-80-30-FL-4-W-120-DP-1-TG9 |  | Machine Shop Finished | 2019-01-25 | 10:53:53 | 2019-02-05 | 2019-02-08 | 4 | 4 | Sacha Lempka | Picked - Complete | High Priority |  | A-4 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75728-2 | 75728 | 2 | 1 | Regular | SCULPT-8 | SCR-500-80-30-FL-8-W-120-DP-1-TG9 |  | Machine Shop Finished | 2019-01-25 | 10:53:54 | 2019-02-05 | 2019-02-08 | 1 | 1 | Sacha Lempka | Picked - Complete | High Priority |  | A-8 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75728-3 | 75728 | 3 | 1 | Regular | SCULPT-8 | SCR-300-80-30-FL-8-W-120-DP-1-TG9 |  | Machine Shop Finished | 2019-01-25 | 10:53:55 | 2019-02-05 | 2019-02-08 | 1 | 1 | Sacha Lempka | Picked - Complete | High Priority |  | AA-8 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75728-4 | 75728 | 4 | 1 | Regular | SCULPT-36 | SCR-500-80-30-FL-36-W-120-DP-1-TG9 |  | Machine Shop Finished | 2019-01-25 | 10:53:57 | 2019-02-05 | 2019-02-08 | 1 | 3 | Sacha Lempka | Picked - Complete | High Priority |  | A-36 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75728-5 | 75728 | 5 | 1 | Regular | SCULPT-16 | SCR-500-80-30-FL-16-W-120-DP-1-TG9 |  | Machine Shop Finished | 2019-02-01 | 07:25:31 | 2019-02-05 | 2019-02-08 | 2 | 4 | Sacha Lempka | Picked - Complete | High Priority |  | A-16 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75728-9 | 75728 | 9 | 1 | Regular | SCULPT-159' | SCRPAT-OPR-90(2)-300-80-30-FL-159'-EX-W-120-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 16 | Sacha Lempka | Picked - Complete | High Priority |  | AA-98X51X10 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75738-1 | 75738 | 1 | 2 | Regular | B3LED-4 | BMRLED-500-80-35-ASO-4-W-120-DP-1-D | Wrong info. In SD | Wiring Started | 2019-02-01 | 10:46:30 | 2019-01-30 | 2019-02-04 | 9 | 9 | George Bacalla |  | Regular |  | LI04-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-30 12:55 |  | TRUE | TRUE
75738-2 | 75738 | 2 | 2 | Regular | B3LED-2 | BMRLED-500-80-35-ASO-2-W-120-DP-1-D | Wrong info. In SD | Wiring Started | 2019-02-01 | 11:38:03 | 2019-01-30 | 2019-02-04 | 9 | 9 | George Bacalla |  | Regular |  | LI05-2' | 12 | TRUE | TRUE | TRUE | TRUE | [6 empty] | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-01-30 12:55 |  | TRUE | TRUE
75745-5 | 75745 | 5 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 4 | 4 | Gagandeep Singh |  | Regular |  | F05-8'-8TH FL | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75745-6 | 75745 | 6 | 1 | Regular | WWPRFK-16' | SP18369-WWR-SL-750-80-35-L-16'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Gagandeep Singh |  | Regular |  | F05-16'-8TH FL | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75745-7 | 75745 | 7 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-C(ROCKFON723)-UNV-DP-1-TG9 | Wrong part in BOM | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-8'-PATH-8TH FL | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
75745-8 | 75745 | 8 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-10'PATH -8TH FL | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75745-9 | 75745 | 9 | 1 | Regular | WWPRFK-20' | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS-C(1 LONG SIDE D) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Gagandeep Singh |  | Regular |  | F05B-20'-8TH FL | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
75745-13 | 75745 | 13 | 1 | Regular | B3PLED-36'6" | SP18435(2)-BMPRLED-OPRI(119°)-750-80-35-RG3-36'6"-W-UNV-DP-1-TG9-TS(2)-C(140.6° ANGLED END) | Shortage | Wiring Started | 2019-01-29 | 14:00:22 | 2019-01-23 | 2019-01-28 | 1 | 5 | Gagandeep Singh | Picked - Complete | Regular |  | F04-6'4-11/16"X30'1-15/16"-08-39Q | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready | Ready |  | TRUE |  | Done | TRUE | 2019-01-31 15:52 |  | TRUE | FALSE
75745-21 | 75745 | 21 | 1 | Regular | SCULPT-46'5" | SP18276-SCR-350-80-35-FL-46'5"-W-UNV-DP-1-DS-C(133° & 85° ANGLED ENDS) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Gagandeep Singh |  | Regular |  | F10-46'5"-ELEV LOBBY-8TH FL | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
75746-5 | 75746 | 5 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-6'-10TH FL | 1 | TRUE | TRUE | FALSE | TRUE | ToDo | ToDo | [7 empty] | ToDo | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-6 | 75746 | 6 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-8'-10TH FL | 1 | TRUE | TRUE | FALSE | TRUE | ToDo | ToDo | [7 empty] | ToDo | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-7 | 75746 | 7 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-10'-10TH FL | 1 | TRUE | TRUE | FALSE | TRUE | ToDo | ToDo | [7 empty] | ToDo | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-8 | 75746 | 8 | 1 | Regular | WWPRFK-20' | SP18369-WWR-SL-750-80-35-L-20'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Gagandeep Singh |  | Regular |  | F05A-6'-10TH FL | 1 | TRUE | TRUE | FALSE | TRUE | ToDo | ToDo | [7 empty] | ToDo | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-22 | 75746 | 22 | 1 | Regular | B3PLED-9'8 1/8" | BMPRLED-750-80-35-RG3-9'8 1/8"-C(ROCKFON723)-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F04-9'8-1/8"-10-33X | 1 | TRUE | TRUE | FALSE | FALSE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-24 | 75746 | 24 | 1 | Regular | B3PLED-17'6" | BMPRLED-OPRI(1)-750-80-35-RG3-17'6"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Gagandeep Singh |  | Regular |  | F04-8'7-1/8"X8'10-7/8"-10-29T | 1 | TRUE | TRUE | FALSE | FALSE | ToDo | [7 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-25 | 75746 | 25 | 1 | Regular | B3PLED-19'6 3/4" | BMPRLED-OPRI(1)-750-80-35-RG3-19'6 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Gagandeep Singh |  | Regular |  | F04-8'7-1/8"X9'3-16/16"-10-32T | 1 | TRUE | TRUE | FALSE | FALSE | ToDo | [7 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-26 | 75746 | 26 | 1 | Regular | B3PLED-38' | BMPRLED-750-80-35-RG3-38'-W-UNV-DP-1-TG9-TS(1) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 4 | Gagandeep Singh |  | Regular |  | F04-38'-10-41L | 1 | TRUE | TRUE | FALSE | FALSE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-29 | 75746 | 29 | 1 | Regular | SCULPT-46'1" | SP18276-SCR-350-80-35-FL-46'1"-W-UNV-DP-1-DS-C(32° & 85° ANGLED ENDS) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Gagandeep Singh |  | Regular |  | F10-46'1"-ELEV LOBBY-10TH FL | 1 | TRUE | TRUE | FALSE | FALSE |  | ToDo |  |  | ToDo | [5 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75746-31 | 75746 | 31 | 1 | Regular | B3PLED-19'6 3/4" | BMPRLED-OPRI(1)-750-80-35-RG3-19'6 3/4"-C(ROCKFON723)-UNV-DP-1-TG9-TS(2) | Missing info. In SD | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Gagandeep Singh |  | Regular |  | F04-9'6 7/8"X9'11-15/16"-10-34T | 1 | TRUE | TRUE | FALSE | FALSE | ToDo | [7 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75746-34 | 75746 | 34 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-C(ROCKFON723)-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-8'PATH-10TH FL | 1 | TRUE | TRUE | FALSE | TRUE | ToDo | ToDo | [7 empty] | ToDo | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-1 | 75801 | 1 | 1 | Regular | CLICK-5 | CLKLED-700-80-30-SO-7' 6"-W-UNV-DP-1-AC-FW(6) | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/7' 6"-22ND | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75801-2 | 75801 | 2 | 1 | Regular | CLICK-13 | CLKLED-700-80-30-SO-15' 6"-W-UNV-DP-1-AC-FW(6) | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/15' 6"-22ND | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75801-3 | 75801 | 3 | 1 | Regular | CLICK-14 | CLKLED-700-80-30-SO-13' 6"-W-UNV-DP-1-AC-FW(6) | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Rohan Srivastava |  | Regular |  | LT05/13' 6"-22ND | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75801-4 | 75801 | 4 | 1 | Regular | CLICK-15 | CLKLED-700-80-30-SO-14'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/14'-22ND | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-5 | 75801 | 5 | 1 | Regular | CLICK-19 | CLKLED-700-80-30-SO-18' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT05/18' 6"-22ND | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-8 | 75801 | 8 | 1 | Regular | CLICK-8 | CLKLED-700-80-30-SO-6'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/6'-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-9 | 75801 | 9 | 1 | Regular | CLICK-12 | CLKLED-700-80-30-SO-9'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/9'-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-10 | 75801 | 10 | 1 | Regular | CLICK-14 | CLKLED-700-80-30-SO-13' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Rohan Srivastava |  | Regular |  | LT05/13' 6"-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-11 | 75801 | 11 | 1 | Regular | CLICK-15 | CLKLED-700-80-30-SO-13'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Rohan Srivastava |  | Regular |  | LT05/13'-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-12 | 75801 | 12 | 1 | Regular | CLICK-16 | CLKLED-700-80-30-SO-14'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/14'-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-13 | 75801 | 13 | 1 | Regular | CLICK-18 | CLKLED-700-80-30-SO-17' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 3 | Rohan Srivastava |  | Regular |  | LT05/17' 6"-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-14 | 75801 | 14 | 1 | Regular | CLICK-19 | CLKLED-700-80-30-SO-18' 6"-W-UNV-DP-1-AC-FW(6) | Shortage | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT05/18' 6"-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-18 | 75801 | 18 | 1 | Regular | CLICK-4 | CLKLED-700-80-30-SO-2'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/2'-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-19 | 75801 | 19 | 1 | Regular | CLICK-5 | CLKLED-700-80-30-SO-6'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/6'-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-20 | 75801 | 20 | 1 | Regular | CLICK-14 | CLKLED-700-80-30-SO-13' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Rohan Srivastava |  | Regular |  | LT05/13' 6"-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-21 | 75801 | 21 | 1 | Regular | CLICK-15 | CLKLED-700-80-30-SO-14'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/14'-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-23 | 75801 | 23 | 1 | Regular | CLICK-18 | CLKLED-700-80-30-SO-17' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 3 | Rohan Srivastava |  | Regular |  | LT05/17' 6"-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-24 | 75801 | 24 | 1 | Regular | CLICK-19 | CLKLED-700-80-30-SO-18' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT05/18' 6"-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-26 | 75801 | 26 | 1 | Regular | B2LED-8 | BDLEDPAT-OPR-90(1)-400-80-30-SO-8-EX-W-120-DP-1-CA(48) | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT36, L 4'X4'-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
75801-27 | 75801 | 27 | 1 | Regular | B2LED-12 | BDLEDPAT-OPR-90(2)-400-80-30-SO-12-EX-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT36, U 4'X4'X4'-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-30 | 75801 | 30 | 1 | Regular | CLICK-6 | CLKLED-700-80-30-SO-7'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/7'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-31 | 75801 | 31 | 1 | Regular | CLICK-8 | CLKLED-700-80-30-SO-7' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/7' 6"-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-32 | 75801 | 32 | 1 | Regular | CLICK-9 | CLKLED-700-80-30-SO-8' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/8' 6"-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-33 | 75801 | 33 | 1 | Regular | CLICK-14 | CLKLED-700-80-30-SO-13'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Rohan Srivastava |  | Regular |  | LT05/13'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-34 | 75801 | 34 | 1 | Regular | CLICK-15 | CLKLED-700-80-30-SO-14' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/14' 6"-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-35 | 75801 | 35 | 1 | Regular | CLICK-19 | CLKLED-700-80-30-SO-18' 6'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT05/18' 6'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-43 | 75801 | 43 | 1 | Regular | B2LED-8 | BDLEDPAT-OPR-90(1)-400-80-30-SO-8-EX-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT36, L 4'X4'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-44 | 75801 | 44 | 1 | Regular | B2LED-12 | BDLEDPAT-OPR-90(2)-400-80-30-SO-12-EX-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT36, U 4'X4'X4'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-45 | 75801 | 45 | 1 | Regular | CLICK-5 | CLKLED-700-80-30-SO-4'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/4'-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-46 | 75801 | 46 | 1 | Regular | CLICK-14 | CLKLED-700-80-30-SO-13' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Rohan Srivastava |  | Regular |  | LT05/13' 6"-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-47 | 75801 | 47 | 1 | Regular | CLICK-15 | CLKLED-700-80-30-SO-14' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/14' 6"-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-48 | 75801 | 48 | 1 | Regular | CLICK-18 | CLKLED-700-80-30-SO-17' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 3 | Rohan Srivastava |  | Regular |  | LT05/17' 6"-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-51 | 75801 | 51 | 1 | Regular | B2LED-8 | BDLEDPAT-OPR-90(1)-400-80-30-SO-8-EX-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT36, L 4'X4'-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-52 | 75801 | 52 | 1 | Regular | B2LED-12 | BDLEDPAT-OPR-90(2)-400-80-30-SO-12-EX-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT36, U 4'X4'X4'-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-53 | 75801 | 53 | 1 | Regular | CLICK-19' | CLKLED-700-80-30-SO-18' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Rohan Srivastava |  | Regular |  | LT05/18' 6"-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-56 | 75801 | 56 | 1 | Regular | CLICK-8' | CLKLED-700-80-30-SO-8'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/8'-23RD | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-57 | 75801 | 57 | 1 | Regular | CLICK-12' | CLKLED-700-80-30-SO-12'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/12'-24TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-58 | 75801 | 58 | 1 | Regular | CLICK-4' | CLKLED-700-80-30-SO-4'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Rohan Srivastava |  | Regular |  | LT05/4'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-59 | 75801 | 59 | 1 | Regular | CLICK-5' | CLKLED-700-80-30-SO-5'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Rohan Srivastava |  | Regular |  | LT05/5'-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-61 | 75801 | 61 | 1 | Regular | CLICK-9' 10" | CLKLED-700-80-30-SO-9' 6"-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/9' 6"-25TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75801-62 | 75801 | 62 | 1 | Regular | CLICK-13' | CLKLED-700-80-30-SO-13'-W-UNV-DP-1-AC-FW(6) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Rohan Srivastava |  | Regular |  | LT05/13'-26TH | 1 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75811-1 | 75811 | 1 | 1 | Regular | STENCL-20 | STD-SO-300-80-35-20-AP-UNV-MD-1-CA(36)-RC | Others | Machine Shop Finished | 2019-02-04 | 07:58:42 | 2019-01-29 | 2019-02-01 | 4 | 12 | Stan Buyansky | Picked - Complete | Regular |  | L1-20' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75811-2 | 75811 | 2 | 1 | Regular | STENCL-20 | STD-SO-300-80-35-20-AP-UNV-MD-1+E(1)-CA(36)-RC | Shortage | Machine Shop Finished | 2019-02-04 | 07:58:46 | 2019-01-29 | 2019-02-01 | 3 | 9 | Stan Buyansky | Picked - Complete | Regular |  | L1-EMCKT-20' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75811-3 | 75811 | 3 | 1 | Regular | STENCL-20 | STD-SO-300-80-35-20-AP-UNV-MD-1+E(2)-CA(36)-RC |  | Machine Shop Finished | 2019-02-04 | 07:58:48 | 2019-01-29 | 2019-02-01 | 1 | 3 | Stan Buyansky | Picked - Complete | Regular |  | L1-EMCKT2 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
75841-1 | 75841 | 1 | 1 | Regular | STENCL-STFC | STFC-NO-DML(9-600)-90-30-AY(1)-W-120-MD-1-CT15(36)-RC |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Jessica Kennedy |  | Regular |  | LP-1A | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75859-4 | 75859 | 4 | 1 | Regular | TB2LED-52' | TB2DILEDPAT-REC-90(4)-400-500-80-35-SL-SO-52'-EX-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 10 | 80 | Gagandeep Singh |  | Regular |  | F1, 10'X16'/5TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-36 | 75859 | 36 | 1 | Regular | B2LED-12' | BRLED-500-80-35-FL-12'-W-UNV-DP-1-DS-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 1 | Gagandeep Singh |  | Regular |  | F2, 12/7TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-39 | 75859 | 39 | 1 | Regular | B2LED-12' | BRLED-500-80-35-FL-12'-W-UNV-DP-1+E(1)-DS-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 1 | Gagandeep Singh |  | Regular |  | F2EC, 12/7TH | 12 | FALSE | TRUE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-42 | 75859 | 42 | 1 | Regular | B2LED-16' | BRLED-500-80-35-FL-16'-W-UNV-DP-1-DS-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 2 | 4 | Gagandeep Singh |  | Regular |  | F2, 16/7TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-61 | 75859 | 61 | 1 | Regular | B2LED-8' | BRLED-500-80-35-FL-8'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 4 | 4 | Gagandeep Singh |  | Regular |  | F2A, 8/6TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-62 | 75859 | 62 | 1 | Regular | B2LED-8' | BRLED-500-80-35-FL-8'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 1 | 1 | Gagandeep Singh |  | Regular |  | F2A, 8/7TH | 7 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-64 | 75859 | 64 | 1 | Regular | B2LED-10' | BRLED-500-80-35-FL-10'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 1 | Gagandeep Singh |  | Regular |  | F2A, 10/9TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-66 | 75859 | 66 | 1 | Regular | B2LED-12' | BRLED-500-80-35-FL-12'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 1 | Gagandeep Singh |  | Regular |  | F2A, 12/6TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-67 | 75859 | 67 | 1 | Regular | B2LED-12' | BRLED-500-80-35-FL-12'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 1 | 1 | Gagandeep Singh |  | Regular |  | F2A, 12/7TH | 7 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-69 | 75859 | 69 | 1 | Regular | B2LED-14' | BRLED-500-80-35-FL-14'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 2 | Gagandeep Singh |  | Regular |  | F2A, 14/6TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-70 | 75859 | 70 | 1 | Regular | B2LED-14' | BRLED-500-80-35-FL-14'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 1 | 2 | Gagandeep Singh |  | Regular |  | F2A, 14/7TH | 7 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-71 | 75859 | 71 | 1 | Regular | B2LED-14' | BRLED-500-80-35-FL-14'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 2 | Gagandeep Singh |  | Regular |  | F2A, 14/9TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-73 | 75859 | 73 | 1 | Regular | B2LED-18' | BRLED-500-80-35-FL-18'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 3 | 6 | Gagandeep Singh |  | Regular |  | F2A, 18/6TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-74 | 75859 | 74 | 1 | Regular | B2LED-18' | BRLED-500-80-35-FL-18'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 8 | 16 | Gagandeep Singh |  | Regular |  | F2A, 18/7TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-79 | 75859 | 79 | 1 | Regular | B2LED-42' | BRLED-500-80-35-FL-42'-W-UNV-DP-1+E(3)-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 4 | Gagandeep Singh |  | Regular |  | F2A,EC 42/6TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-81 | 75859 | 81 | 1 | Regular | B2LED-42' | BRLED-500-80-35-FL-42'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 4 | Gagandeep Singh |  | Regular |  | F2A, 42/9TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-82 | 75859 | 82 | 1 | Regular | B2LED-42' | BRLED-500-80-35-FL-42'-W-UNV-DP-1+E(3)-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 4 | Gagandeep Singh |  | Regular |  | F2AEC, 42/9TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-91 | 75859 | 91 | 1 | Regular | B3LED-4 | BMRLED-600-80-35-ASO-4-W-UNV-DP-1-DS-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 2 | 2 | Gagandeep Singh |  | Regular |  | F25, 4/9TH | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-97 | 75859 | 97 | 1 | Regular | B3LED-4 | BMRLED-600-80-35-ASO-4-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 4 | 4 | Gagandeep Singh |  | Regular |  | F25A, 4/6TH | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-98 | 75859 | 98 | 1 | Regular | B3LED-4 | BMRLED-600-80-35-ASO-4-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 4 | 4 | Gagandeep Singh |  | Regular |  | F25A, 4/7TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-100 | 75859 | 100 | 1 | Regular | B3LED-4 | BMRLED-600-80-35-ASO-4-W-UNV-DP-E(1)-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 6 | 6 | Gagandeep Singh |  | Regular |  | F25AEC, 4/6TH | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-104 | 75859 | 104 | 1 | Regular | TB2LED-140' | TB2ILED-886-80-35-SL-140'-W-UNV-DP-1+E(6)-CA(36) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 1 | 12 | Gagandeep Singh |  | Regular |  | F40EC 140/5TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-105 | 75859 | 105 | 1 | Regular | TB2LED-66' | TB2ILED-886-80-35-SL-66'-W-UNV-DP-1+E(3)-CA(36) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 1 | 9 | Gagandeep Singh |  | Regular |  | F40EC 66/5TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-106 | 75859 | 106 | 1 | Regular | TB2LED-66' | TB2ILED-886-80-35-SL-58'-W-UNV-DP-1+E(3)-CA(36) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 1 | 5 | Gagandeep Singh |  | Regular |  | F40EC 58/8TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75859-115 | 75859 | 115 | 1 | Regular | B2LED-42' | BRLED-500-80-35-FL-42'-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 1 | 4 | Gagandeep Singh |  | Regular |  | F2A, 42/6TH | 12 | FALSE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-1 | 75954 | 1 | 1 | Regular | B2LED-8 | BRLED-625-80-30-FL-8-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Joshua Zimet |  | Regular |  | G2-8' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-2 | 75954 | 2 | 1 | Regular | B2LED-10 | BRLED-625-80-30-FL-10-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 3 | Joshua Zimet |  | Regular |  | G2-10' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-4 | 75954 | 4 | 1 | Regular | B2LED-12 | BRLED-625-80-30-FL-12-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 4 | 4 | Joshua Zimet |  | Regular |  | G2-12' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-5 | 75954 | 5 | 1 | Regular | B2LED-14 | BRLED-625-80-30-FL-14-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 8 | 16 | Joshua Zimet |  | Regular |  | G2-14' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-6 | 75954 | 6 | 1 | Regular | B2LED-16 | BRLED-625-80-30-FL-16-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 4 | 8 | Joshua Zimet |  | Regular |  | G2-16' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-7 | 75954 | 7 | 1 | Regular | B2LED-20 | BRLED-625-80-30-FL-20-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 7 | 14 | Joshua Zimet |  | Regular |  | G2-20' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-8 | 75954 | 8 | 1 | Regular | B2LED-5 | BDLED-625-80-30-SO-5-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Joshua Zimet |  | Regular |  | G4-5' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-9 | 75954 | 9 | 1 | Regular | B2LED-6 | BDLED-625-80-30-SO-6-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Joshua Zimet |  | Regular |  | G4-6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-10 | 75954 | 10 | 1 | Regular | B2LED-16 | BDLED-625-80-30-SO-16-BLK-UNV-DP-2-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 12 | 24 | Joshua Zimet |  | Regular |  | G4-16' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-11 | 75954 | 11 | 1 | Regular | B2LED-18 | BDLED-625-80-30-SO-18-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 5 | 10 | Joshua Zimet |  | Regular |  | G4-18' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-12 | 75954 | 12 | 1 | Regular | B2LED-20 | BDLED-625-80-30-SO-20-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 11 | 22 | Joshua Zimet |  | Regular |  | G4-20' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-15 | 75954 | 15 | 1 | Regular | B2LED-23 | BDLED-625-80-30-SO-23-W-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Joshua Zimet |  | Regular |  | G4-23' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-16 | 75954 | 16 | 1 | Regular | SCULPT-18 | SCD-375-80-30-0.5M-18-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 4 | 8 | Joshua Zimet |  | Regular |  | G6-18' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-17 | 75954 | 17 | 1 | Regular | B2LED-4 | BDLED-625-80-30-SO-4-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 55 | 55 | Joshua Zimet |  | Regular |  | G14-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-18 | 75954 | 18 | 1 | Regular | B2LED-5 | BDLED-625-80-30-SO-5-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 42 | 42 | Joshua Zimet |  | Regular |  | G14-5' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-19 | 75954 | 19 | 1 | Regular | B2LED-6 | BDLED-625-80-30-SO-6-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 42 | 42 | Joshua Zimet |  | Regular |  | G14-6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-20 | 75954 | 20 | 1 | Regular | B2LED-16 | BDLED-625-80-30-SO-16-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Joshua Zimet |  | Regular |  | G14-16' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-21 | 75954 | 21 | 1 | Regular | B2LED-18 | BDLED-625-80-30-SO-18-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 6 | 12 | Joshua Zimet |  | Regular |  | G14-18' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-23 | 75954 | 23 | 1 | Regular | B3PLED-8'5" | BMPRLED-375-80-30-RG3-8'5"-W-UNV-DP-1-DS-TS(2)-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-8'5" | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-24 | 75954 | 24 | 1 | Regular | B3PLED-8'7" | BMPRLED-375-80-30-RG3-8'7"-W-UNV-DP-1-DS-TS(2)-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-8'7" | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-25 | 75954 | 25 | 1 | Regular | B3PLED-12' | BMPRLED-375-80-30-RG3-12'-W-UNV-DP-1-DS-TS(2)-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-12' | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-26 | 75954 | 26 | 1 | Regular | B3PLED-142" | BMPRLED-375-80-30-RG3-142"-W-UNV-DP-1-DS-TS(2)-CP |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-142" | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-27 | 75954 | 27 | 1 | Regular | B3PLED-150 3/4" | BMPRLED-375-80-30-RG3-150 3/4"-W-UNV-DP-1-DS-TS(2)-CP |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-150 3/4" | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75954-28 | 75954 | 28 | 1 | Regular | B3PLED-23' | BMPRLED-375-80-30-RG3-23'-W-UNV-DP-1-DS-TS(2)-CP |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 2 | 4 | Joshua Zimet | Picked - Complete | Regular |  | G17-23' | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75954-29 | 75954 | 29 | 1 | Regular | B3PLED-134" | BMPRLED-375-80-30-RG3-134"-W-UNV-DP-1-DS-TS(2)-CP |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-134" | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75954-32 | 75954 | 32 | 1 | Regular | B2LED-56 | BDLED-1000-80-30-SO-56-BLK-UNV-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 6 | 30 | Joshua Zimet |  | Regular |  | G35-56' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-34 | 75954 | 34 | 1 | Regular | B2LED-0' 245" | BSLED-375-80-30-SO-0' 245"-W-UNV-DP-1-S-C(OVERALL LENGTH) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 6 | 12 | Joshua Zimet |  | Regular |  | G54-245" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-35 | 75954 | 35 | 1 | Regular | B2LED-0' 317" | BSLED-375-80-30-SO-0' 317"-W-UNV-DP-1-S-C(OVERALL LENGTH) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 6 | Joshua Zimet |  | Regular |  | G54-317" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-36 | 75954 | 36 | 1 | Regular | SCULPT-8 | SCS-625-80-30-2M-8-AP-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 22 | 22 | Joshua Zimet |  | Regular |  | G58-8' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-37 | 75954 | 37 | 1 | Regular | B2LED-0' 244" | BSLED-375-80-30-SO-0' 244"-W-UNV-DP-1-S-C(OVERALL LENGTH) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Joshua Zimet |  | Regular |  | G54-244" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
75954-41 | 75954 | 41 | 1 | Regular | B3PLED-144" | BMPRLED-375-80-30-RG3-144"-W-UNV-DP-1-DS-TS(2)-CP |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | G17-144" | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75954-42 | 75954 | 42 | 1 | Regular | B3PLED-168" | BMPRLED-375-80-30-RG3-168"-W-UNV-DP-1-DS-TS(2)-CP |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 2 | Joshua Zimet | Picked - Complete | Regular |  | G17-168" | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
75966-8 | 75966 | 8 | 1 | Regular | SKVLED-14 | SKVLED-14-2400-80-40-2XVL-RE-W-277-DP-1-TB15-C(NLIGHT POWER PACK - NPP16-D) | Shortage | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 520 | 520 | Joshua Zimet |  | Regular |  | N27 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76021-1 | 76021 | 1 | 1 | Regular | WB4LED-2 | WBRLED-500-80-40-S-2-W-UNV-DP-1-DF-EF |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 10 | 10 | Jessica Pasternyk |  | Regular |  | K-2' | 18 | TRUE | TRUE | TRUE | TRUE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76028-32 | 76028 | 32 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(56)-W-UNV-DP-1-C |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 10 | George Bacalla |  | High Priority |  | L02-56' | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76028-44 | 76028 | 44 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(80)-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 1 | 9 | George Bacalla |  | High Priority |  | L02-80' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76076-1 | 76076 | 1 | 1 | Regular | B2LED-6' | BRVLED-500-90-27-SO-6'-W-277-DP-1-D |  | Machine Shop Finished | 2019-01-30 | 15:45:44 | 2019-02-05 | 2019-02-08 | 4 | 4 | Jessica Kennedy | Picked - Complete | Regular |  | L13-6' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
76076-2 | 76076 | 2 | 1 | Regular | B2LED-4' | BRVLED-500-90-27-SO-4'-W-277-DP-1-D |  | Machine Shop Finished | 2019-01-30 | 15:45:47 | 2019-02-05 | 2019-02-08 | 1 | 1 | Jessica Kennedy | Picked - Complete | Regular |  | L14-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
76076-3 | 76076 | 3 | 1 | Regular | B2LED-5' | BRVLED-500-90-27-SO-5'-W-277-DP-1-D |  | Machine Shop Finished | 2019-01-30 | 15:45:53 | 2019-02-05 | 2019-02-08 | 2 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | L15-5' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
76076-4 | 76076 | 4 | 1 | Regular | B2LED-8' | BRVLED-500-90-27-SO-8'-W-277-DP-1-D |  | Machine Shop Finished | 2019-01-30 | 15:46:04 | 2019-02-05 | 2019-02-08 | 3 | 3 | Jessica Kennedy | Picked - Complete | Regular |  | L16-8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
76093-2 | 76093 | 2 | 1 | Regular | WWPRFK-4 | WWR-SL-400-90-40-L-4-W-UNV-DP-1-DS |  | Machine Shop Finished | 2019-02-04 | 07:44:21 | 2019-02-07 | 2019-02-12 | 5 | 5 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | Y | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
76134-1 | 76134 | 1 | 1 | Regular | SCULPT-36 | SCDPAT-ASO-60-400-80-35-FL-36-EX-W-UNV-DP-1-CTS(36) |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 6 | George Bacalla |  | Regular |  | 10A-3X60 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-2 | 76134 | 2 | 1 | Regular | SCULPT-30 | SCDPAT-ASO-60-400-80-35-FL-30-EX-W-UNV-DP-1-CTS(36) |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 3 | 18 | George Bacalla |  | Regular |  | 10B-3X60 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-3 | 76134 | 3 | 1 | Regular | SCULPT-48 | SCDPAT-ASO-60-400-80-35-FL-48-EX-W-UNV-DP-1-CTS(36) |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 6 | George Bacalla |  | Regular |  | 10C-3X60 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-4 | 76134 | 4 | 1 | Regular | SCULPT-34 | SCWDI-750-500-80-35-SO-FL-34-W-120-DP-2 |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 3 | George Bacalla |  | Regular |  | 11-34' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-5 | 76134 | 5 | 1 | Regular | B3LED-16 | BMRLED-500-80-35-ASO-16-AP-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 2 | George Bacalla |  | Regular |  | 12-16' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-6 | 76134 | 6 | 1 | Regular | B3LED-35 | BMRLED-500-80-35-ASO-35-AP-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 2 | 6 | George Bacalla |  | Regular |  | 12A-35' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-7 | 76134 | 7 | 1 | Regular | B3LED-52 | BMRLED-500-80-35-ASO-52-AP-120-DP-2-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 5 | George Bacalla |  | Regular |  | 12B-52' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-8 | 76134 | 8 | 1 | Regular | B3LED-8 | BMRLED-500-80-35-ASO-8-AP-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 3 | 3 | George Bacalla |  | Regular |  | 12C-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-9 | 76134 | 9 | 1 | Regular | B3LED-12 | BMRLED-500-80-35-ASO-12-AP-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 1 | George Bacalla |  | Regular |  | 12D-12' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-10 | 76134 | 10 | 1 | Regular | B3LED-60 | BMRLED-500-80-35-ASO-60-AP-120-DP-2-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 5 | George Bacalla |  | Regular |  | 13-60' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-11 | 76134 | 11 | 1 | Regular | B3LED-59 | BMRLED-500-80-35-ASO-59-AP-120-DP-2-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 5 | George Bacalla |  | Regular |  | 13A-59' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-12 | 76134 | 12 | 1 | Regular | B3LED-4 | BMDLED-1000-80-35-SO-4-W-120-DP-1-CTS(36) |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 21 | 21 | George Bacalla |  | Regular |  | 14-4' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-13 | 76134 | 13 | 1 | Regular | B3LED-8 | BMDLED-1000-80-35-SO-8-W-120-DP-1-CTS(36) |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 2 | 2 | George Bacalla |  | Regular |  | 14A-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-14 | 76134 | 14 | 1 | Regular | B3LED-20 | BMRLED-750-80-35-FL-20-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 2 | 4 | George Bacalla |  | Regular |  | 16-20' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76134-15 | 76134 | 15 | 1 | Regular | B3LED-16 | BMRLED-750-80-35-FL-16-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-19 | 2019-04-24 | 1 | 2 | George Bacalla |  | Regular |  | 16A-16' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-1 | 76155 | 1 | 1 | Regular | SLMLED-8 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-8-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 2 | Stan Buyansky |  | Regular |  | P8-OS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-2 | 76155 | 2 | 1 | Regular | SLMLED-8 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-8-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 4 | Stan Buyansky |  | Regular |  | P8-DS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-3 | 76155 | 3 | 1 | Regular | SLMLED-8 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-8-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 121 | 121 | Stan Buyansky |  | Regular |  | P8-F/OS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-4 | 76155 | 4 | 1 | Regular | SLMLED-8 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-8-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 16 | 16 | Stan Buyansky |  | Regular |  | P8-F/DS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-5 | 76155 | 5 | 1 | Regular | SLMLED-12 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-12-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 11 | 11 | Stan Buyansky |  | Regular |  | P12-OS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-6 | 76155 | 6 | 1 | Regular | SLMLED-12 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-12-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 14 | 14 | Stan Buyansky |  | Regular |  | P12-F/OS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76155-7 | 76155 | 7 | 1 | Regular | SLMLED-12 | SP18218(4)-SLLED-SL 80/20-800-90-30-PL-12-W-UNV-DP-1-SA(24 3/4")+SM |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 3 | Stan Buyansky |  | Regular |  | P12-F/DS-2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76181-1 | 76181 | 1 | 1 | Regular | STENCL-STFD | STFD-DSO(6-400)-80-40-BT(3)-W-120-MD-1-CA(144")-RC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 9 | Zahra Vatani |  | Regular |  | P-6' | 4 | TRUE | FALSE | FALSE | TRUE |  | ToDo |  |  | ToDo | [5 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76181-2 | 76181 | 2 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-40-CP(48')-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-02-03 | 22:30:16 | 2019-02-13 | 2019-02-18 | 1 | 18 | Zahra Vatani |  | Regular |  | Q-48' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
76181-3 | 76181 | 3 | 1 | Regular | STENCL-STFD | STFD-DSO(9-400)-80-40-BT(3)-W-120-MD-1-CA(144")-RC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 9 | Zahra Vatani |  | Regular |  | R-9' | 4 | TRUE | FALSE | FALSE | TRUE |  | ToDo |  |  | ToDo | [5 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76181-4 | 76181 | 4 | 1 | Regular | STENCL-STFD | STFD-DSO(12-400)-80-40-BT(3)-W-120-MD-1-CA(144")-RC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 9 | Zahra Vatani |  | Regular |  | S-12' | 4 | TRUE | FALSE | FALSE | FALSE |  | ToDo |  |  | ToDo | [5 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76191-1 | 76191 | 1 | 1 | Regular | ZEN-8 | ZESLED-SL 0/100-600-80-35-MSO-8-W-UNV-MD-1-S | Mechanical issue | Machine Shop Started | 2019-01-15 | 07:27:13 | 2019-01-14 | 2019-01-17 | 5 | 5 | Sacha Lempka | Picked - Complete | Regular |  | P2 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-17 10:47 |  | TRUE | FALSE
76192-1 | 76192 | 1 | 1 | Regular | GRAZE-7' | GPRLED-EX2W-750-80-35-RG2-7'-W-277-LT(L3D)-1-DF | Others | Machine Shop Started | 2019-01-31 | 10:18:21 | 2019-01-25 | 2019-01-30 | 2 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | FS-7' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  | ToDo |  |  |  |  | ToDo | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76192-2 | 76192 | 2 | 1 | Regular | GRAZE-9' | GPRLED-EX2W-750-80-35-RG2-9'-W-277-LT(L3D)-1-DF | Shortage | Machine Shop Started | 2019-01-31 | 10:18:25 | 2019-01-25 | 2019-01-30 | 2 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | FS-9' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  | ToDo |  |  |  |  | ToDo | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76192-3 | 76192 | 3 | 1 | Regular | GRAZE-12' | GPRLED-EX2W-750-80-35-RG2-12'-W-277-LT(L3D)-1-DF | Shortage | Machine Shop Started | 2019-01-31 | 10:18:26 | 2019-01-25 | 2019-01-30 | 2 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | FS-12' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  | ToDo |  |  |  |  | ToDo | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76192-4 | 76192 | 4 | 1 | Regular | GRAZE-13' | GPRLED-EX2W-750-80-35-RG2-13'-W-277-LT(L3D)-1-DF |  | Machine Shop Started | 2019-01-31 | 10:18:27 | 2019-01-25 | 2019-01-30 | 2 | 4 | Jessica Kennedy | Picked - Complete | Regular |  | FS-13' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  | ToDo |  |  |  |  | ToDo | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76192-5 | 76192 | 5 | 1 | Regular | GRAZE-14' | GPRLED-EX2W-750-80-35-RG2-14'-W-277-LT(L3D)-1-DF |  | Machine Shop Started | 2019-01-31 | 10:18:28 | 2019-01-25 | 2019-01-30 | 8 | 16 | Jessica Kennedy | Picked - Complete | Regular |  | FS-14' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  | ToDo |  |  |  |  | ToDo | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76192-6 | 76192 | 6 | 1 | Regular | GRAZE-19' | GPRLED-EX2W-750-80-35-RG2-19'-W-277-LT(L3D)-1-DF |  | Machine Shop Started | 2019-01-31 | 10:18:32 | 2019-01-25 | 2019-01-30 | 2 | 4 | Jessica Kennedy | Picked - Complete | Regular |  | FS-19' | 1 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  | ToDo |  |  |  |  | ToDo | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76203-28 | 76203 | 28 | 1 | Regular | WWPRFK-10' | SP18369-WWR-SL-750-80-35-L-10'-C(ROCKFON723)-UNV-DP-1-TG9 | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Gagandeep Singh |  | Regular |  | F05-10'PATH-9TH FL | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
76203-29 | 76203 | 29 | 1 | Regular | WWPRFK-18' | SP18369-WWR-SL-750-80-35-L-18'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 2 | Gagandeep Singh |  | Regular |  | F05-18'-9TH FL | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76203-30 | 76203 | 30 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Gagandeep Singh |  | Regular |  | F05-6'-9TH FL | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76203-31 | 76203 | 31 | 1 | Regular | WWPRFK-8' | SP18369-WWR-SL-750-80-35-L-8'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 4 | 4 | Gagandeep Singh |  | Regular |  | F05-8'-9TH FL | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76203-32 | 76203 | 32 | 1 | Regular | WWPRFK-6' | SP18369-WWR-SL-750-80-35-L-6'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Gagandeep Singh |  | Regular |  | F05A-6'-9TH FL | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76241-6 | 76241 | 6 | 1 | Regular | B4LED-12 | BBRLED-750-80-40-FL-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | George Bacalla |  | Regular |  | 202-12' | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76241-7 | 76241 | 7 | 1 | Regular | B4LED-16 | BBRLED-750-80-40-FL-16-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 4 | George Bacalla |  | Regular |  | 202-16' | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76241-8 | 76241 | 8 | 1 | Regular | B4LED-18'9" | BBRLED-750-80-40-FL-18'9"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | George Bacalla |  | Regular |  | 202-18'9" | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76241-9 | 76241 | 9 | 1 | Regular | B4LED-29 | BBRLED-750-80-40-FL-29-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | George Bacalla |  | Regular |  | 202-29' | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76241-10 | 76241 | 10 | 1 | Regular | B4LED-6 | BBRLED-750-80-40-FL-6-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | George Bacalla |  | Regular |  | 202-6' | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76285-2 | 76285 | 2 | 1 | Regular | B4LED-26 | BBRLED-750-80-40-FL-26-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | George Bacalla |  | Regular |  | 202-26' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76294-1 | 76294 | 1 | 1 | Regular | SKETCH-AL(32') | SKPE-18086-SL 0/100-ASO-AL(32')-550-80-30-SO-AP-UNV-D-1-CA(96) |  | Scheduled/Released |  |  | 2019-03-06 | 2019-03-11 | 8 | 48 | Jessica Kennedy |  | Regular |  | D-32' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76294-2 | 76294 | 2 | 1 | Regular | B3LED-4 | BMRLED-500-80-30-FL-4-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-03-06 | 2019-03-11 | 8 | 8 | Jessica Kennedy |  | Regular |  | L-4' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76294-3 | 76294 | 3 | 1 | Regular | B3LED-4 | BMRLED-500-80-30-FL-4-W-UNV-DP-1-ST-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-03-06 | 2019-03-11 | 4 | 4 | Jessica Kennedy |  | Regular |  | L-4' EM | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76370-1 | 76370 | 1 | 1 | Regular | B4LED-8' | BBSLED-750-90-35-SO-8'-W-UNV-DP-1-S-B1(BSL10LST)-DOS(1) | Others | Wiring Started | 2019-01-29 | 16:45:43 | 2019-01-29 | 2019-02-01 | 3 | 3 | Stan Buyansky |  | Regular |  | D | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | TRUE
76372-1 | 76372 | 1 | 1 | Regular | STENCL-STFD | STFD-DSO(132-400)-80-35-AL(9)+AT(14)+AI(5)+AX(1)-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 42 | Stan Buyansky |  | Regular |  | L-05 TYPE 1 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76372-2 | 76372 | 2 | 1 | Regular | STNCLS-STSFF | STSFF-SO(100-400)-80-35-AL(6)+AT(13)+AI(2)-BLK-UNV-MD-1-S |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 34 | Stan Buyansky |  | Regular |  | L-05 TYPE 2 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76372-3 | 76372 | 3 | 1 | Regular | STENCL-STFD | STFD-DSO(42-400)-80-35-AL(2)+AT(7)-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 15 | Stan Buyansky |  | Regular |  | L-05 TYPE 3 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-4 | 76465 | 4 | 1 | Regular | WDILED-2' | WBDIWLED-1000-1000-90-40-SO-SO-2'-C(RAL8019)-UNV-DP-1-BF |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 4 | 4 | George Bacalla |  | Regular |  | FO4-2' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-5 | 76465 | 5 | 1 | Regular | B2LED-20' | BRLEDPAT-REC-90(4)-1000-80-35-SO-FL-20'-NL-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 4 | George Bacalla |  | Regular |  | N3-SMALL-6'X4' REC | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-6 | 76465 | 6 | 1 | Regular | B2LED-52' | BRLEDPAT-REC-90(4)-1000-80-35-SO-FL-52'-NL-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 8 | George Bacalla |  | Regular |  | N3-LARGE-12'X14' REC | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-8 | 76465 | 8 | 1 | Regular | WDILED-4' | WBDIWLED-1000-1000-90-40-SO-SO-4'-C(RAL8019)-UNV-DP-1-BF |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 9 | 9 | George Bacalla |  | Regular |  | FO1-4' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-9 | 76465 | 9 | 1 | Regular | WDILED-4 | WBDIWLED-1000-1000-90-40-SO-SO-4-C(RAL8019)-UNV-DP-1-BF |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 8 | 8 | George Bacalla |  | Regular |  | FO1-4' E | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-10 | 76465 | 10 | 1 | Regular | WDILED-4 | WBIWLED-1000-90-40-SO-4-C(RAL8019)-UNV-DP-1-BF |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 8 | 8 | George Bacalla |  | Regular |  | FO2-4' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-11 | 76465 | 11 | 1 | Regular | WDILED-4 | WBDIWLED-500-500-90-40-SO-SO-4-C(RAL8019)-UNV-DP-1-BF |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 2 | 2 | George Bacalla |  | Regular |  | FO3-4' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76465-12 | 76465 | 12 | 1 | Regular | WDILED-4 | WBDIWLED-500-500-90-40-SO-SO-4-CRAL8019)-UNV-DP-1-BF |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | George Bacalla |  | Regular |  | FO3-4' E | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76472-1 | 76472 | 1 | 1 | Regular | B3LED-12 | BMRLED-700-80-40-FL-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-27 | 2019-04-01 | 1 | 1 | Gagandeep Singh |  | Regular |  | G @ 12' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76472-2 | 76472 | 2 | 1 | Regular | B3LED-4 | BMRLED-700-80-40-FL-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-27 | 2019-04-01 | 1 | 1 | Gagandeep Singh |  | Regular |  | G @ 4' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76528-1 | 76528 | 1 | 1 | Mockup/Samples | SCULPT-SCML | SCML-6-BW-700-MLB(6)-1000-BLK-80-35-BLK-UNV-DP-2-CA(36)-C(CORD, PLUG & DIMMER) | Others | Machine Shop Finished | 2019-01-28 | 11:05:53 | 2019-01-23 | 2019-01-28 | 1 | 1 | Christina Torok |  | Regular |  | A | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 09:43 |  | TRUE | FALSE
76550-1 | 76550 | 1 | 1 | Regular | TB4LED-6 | TB4DLED-1000-80-35-SO-6-W-277-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-03-20 | 2019-03-25 | 52 | 52 | Sacha Lempka |  | Priority |  | A-6' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-2 | 76550 | 2 | 1 | Regular | TB4LED-12 | TB4DLED-1000-80-35-SO-12-W-277-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-03-20 | 2019-03-25 | 8 | 8 | Sacha Lempka |  | Priority |  | A-12' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-3 | 76550 | 3 | 1 | Regular | TB4LED-56 | TB4DLED-1000-80-35-SO-56-W-277-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-03-20 | 2019-03-25 | 4 | 20 | Sacha Lempka |  | Priority |  | A-56' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-4 | 76550 | 4 | 1 | Regular | STENCL-STFC | STFC-I(24-500)-NO-90-40-AH(3)+AY(1)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 6 | Sacha Lempka |  | Priority |  | H1-A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-5 | 76550 | 5 | 1 | Regular | STENCL-STFC | STFC-I(56-500)-NO-90-40-AH(8)+AY(3)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 14 | Sacha Lempka |  | Priority |  | H1-B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-6 | 76550 | 6 | 1 | Regular | STENCL-STFC | STFC-I(44-500)-NO-90-40-AH(7)+AY(2)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 11 | Sacha Lempka |  | Priority |  | H1-C | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-7 | 76550 | 7 | 1 | Regular | STENCL-4 | STI-500-90-40-4-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Sacha Lempka |  | Priority |  | H1-C1 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-8 | 76550 | 8 | 1 | Regular | STENCL-STFC | STFC-I(56-500)-NO-90-40-AH(7)+AY(4)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 14 | Sacha Lempka |  | Priority |  | H1-D | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-9 | 76550 | 9 | 1 | Regular | STENCL-STFC | STFC-I(56-500)-NO-90-40-AH(4)+AY(5)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 14 | Sacha Lempka |  | Priority |  | H1-E | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-10 | 76550 | 10 | 1 | Regular | STENCL-STFC | STFC-I(28-500)-NO-90-40-AH(4)+AY(1)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 7 | Sacha Lempka |  | Priority |  | H1-F | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-11 | 76550 | 11 | 1 | Regular | STENCL-STFC | STFC-I(8-500)-NO-90-40-AL(1)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 8 | 16 | Sacha Lempka |  | Priority |  | H | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-12 | 76550 | 12 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(44-400)-90-40-AL(2)-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 6 | Sacha Lempka |  | Priority |  | V-1-44' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76550-13 | 76550 | 13 | 1 | Regular | STENCL-34 | STD-SO-400-90-40-34-W-277-MD-1-CT9(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 6 | 30 | Sacha Lempka |  | Priority |  | V-1-34' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76592-1 | 76592 | 1 | 1 | Regular | B3LED-40 | BMRLEDPAT-REC-90-1000-90-35-SO-RG-40-NL-W-277-DP-1-DS-FW(6) | Wrong part in BOM | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 8 | Rohan Srivastava | Picked - Complete | Regular |  | L6A-6'X14' | 7 | TRUE | TRUE | FALSE | FALSE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
76592-2 | 76592 | 2 | 1 | Regular | B3LED-35' | BMRLEDPAT-ASO-87+93+93+87-1000-90-35-SO-RG-35'-NL-W-277-DP-1-DS-FW(6) | Wrong part in BOM | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 8 | Rohan Srivastava | Picked - Complete | Regular |  | L6B-35' | 7 | TRUE | TRUE | FALSE | FALSE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
76592-19 | 76592 | 19 | 1 | Regular | B4PLED-5' 1"X5'5 1/2" | BBPRLED-OPRI(1)-750-90-35-RG2-5' 1"X5'5 1/2"-W-277-DP-1-DS-TS(1)-FW(6) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | L7-10'6 1/2"-48.75 | 7 | TRUE | TRUE | FALSE | FALSE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76592-22 | 76592 | 22 | 1 | Regular | B4PLED-5' 2"X11'11 1/2"X8' 4" | BBPRLED-OPRI(2)-750-90-35-RG2-5' 2"X11'11 1/2"X8' 4"-W-277-DP-1-DS-TS(1)-FW(6) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 5 | Rohan Srivastava | Picked - Complete | Regular |  | L7-25'5 1/2"-48.73 | 7 | TRUE | TRUE | FALSE | FALSE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76659-1 | 76659 | 1 | 1 | Regular | TB2LED-4 | TB2DILED-400-400-80-35-SO-SO-4-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 2 | 2 | Stan Buyansky |  | Regular |  | P1 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76659-2 | 76659 | 2 | 1 | Regular | B3LED-4 | BMRLED-400-80-35-FL-4-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 9 | 9 | Stan Buyansky |  | Regular |  | R3 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76659-3 | 76659 | 3 | 1 | Regular | B3LED-4 | BMRLED-400-80-35-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 2 | 2 | Stan Buyansky |  | Regular |  | R8 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76659-4 | 76659 | 4 | 1 | Regular | B3LED-4 | BMRVLED-400-80-35-SO-4-W-UNV-DP-1-DF | PM wrong/missing info | Scheduled/Released |  |  | 2019-03-25 | 2019-03-28 | 6 | 6 | Stan Buyansky |  | Regular |  | R3V | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
76687-1 | 76687 | 1 | 1 | Regular | DIALED-22 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Gagandeep Singh |  | Regular |  | A2 | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76687-2 | 76687 | 2 | 1 | Regular | LTLED-4 | LTLED-SL 80/20-800-90-30-SO-4-W-120-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 7 | 7 | Gagandeep Singh |  | Regular |  | B2-4' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-3 | 76687 | 3 | 1 | Regular | LTLED-8 | LTLED-SL 80/20-800-90-30-SO-8-W-120-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 13 | 13 | Gagandeep Singh |  | Regular |  | B3-8' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-4 | 76687 | 4 | 1 | Regular | LTLED-8 | LTLED-SL 80/20-800-90-30-SO-8-W-120-DP-1-CA(36)-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Gagandeep Singh |  | Regular |  | B3-8' EM | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-5 | 76687 | 5 | 1 | Regular | LTLED-8 | LTLED-SL 80/20-800-90-30-SO-8-W-120-DP-1-CA(36)-DS(1) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 33 | 33 | Gagandeep Singh |  | Regular |  | B4-8' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-6 | 76687 | 6 | 1 | Regular | LTLED-8 | LTLED-SL 80/20-800-90-30-SO-8-W-120-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 9 | 9 | Gagandeep Singh |  | Regular |  | B5-8' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-7 | 76687 | 7 | 1 | Regular | LTLED-12 | LTLED-SL 80/20-800-90-30-SO-12-W-120-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 7 | 14 | Gagandeep Singh |  | Regular |  | B6-12' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-8 | 76687 | 8 | 1 | Regular | LTLED-12 | LTLED-SL 80/20-800-90-30-SO-12-W-120-DP-1-CA(36)-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Gagandeep Singh |  | Regular |  | B6-12' EM | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-9 | 76687 | 9 | 1 | Regular | LTLED-12 | LTLED-SL 80/20-800-90-30-SO-12-W-120-DP-1-CA(36)-DS(1) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Gagandeep Singh |  | Regular |  | B7-12' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-10 | 76687 | 10 | 1 | Regular | LTLED-12 | LTLED-SL 80/20-800-90-30-SO-12-W-120-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Gagandeep Singh |  | Regular |  | B8-12' | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-11 | 76687 | 11 | 1 | Regular | CLICK-4 | CLKLED-750-90-30-SO-4-W-120-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 3 | Gagandeep Singh |  | Regular |  | D-4' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-12 | 76687 | 12 | 1 | Regular | CLICK-4 | CLKLED-750-90-30-SO-4-W-120-DP-1-ST-DS(1) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 9 | 9 | Gagandeep Singh |  | Regular |  | D1-4' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76687-13 | 76687 | 13 | 1 | Regular | CLICK-8 | CLKLED-750-90-30-SO-8-W-120-DP-1-ST-DS(1) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Gagandeep Singh |  | Regular |  | D2-8' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76692-1 | 76692 | 1 | 1 | Regular | B4LED-6 | BBRLED-750-80-40-FL-6-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 8 | 8 | Christina Torok |  | Regular |  | S1 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76692-2 | 76692 | 2 | 1 | Regular | B4LED-4 | BBRLED-750-80-40-FL-4-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 6 | 6 | Christina Torok |  | Regular |  | S2 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76692-3 | 76692 | 3 | 1 | Regular | B4LED-4 | BBRLED-750-80-40-FL-4-W-UNV-DP-1-TB15-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 3 | Christina Torok |  | Regular |  | S2EM | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76704-1 | 76704 | 1 | 1 | Regular | B2LED-12' 6" | BRLED-400-80-35-FL-12' 6"-W-277-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 2 | Rohan Srivastava |  | High Priority |  | F24-12' 6" | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76762-4 | 76762 | 4 | 1 | Regular | B3LED-48 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-48-EX-W-UNV-DP-1+E(2)-DS |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 16 | Rohan Srivastava |  | High Priority |  | F2-48'/1 | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76762-5 | 76762 | 5 | 1 | Regular | B3LED-48 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-48-EX-W-UNV-DP-1+E(2)-DS |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 16 | Rohan Srivastava |  | High Priority |  | F2-48'/2 | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76762-6 | 76762 | 6 | 1 | Regular | B3LED-28 | BMRLEDPAT-ASO-90-800-80-35-SO-FL-28-EX-W-UNV-DP-1+E(1)-DS |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 9 | Rohan Srivastava |  | High Priority |  | F2-28' | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76762-7 | 76762 | 7 | 1 | Regular | B3LED-12'X20' | SP18415(1)-BMRLEDPAT-REC-90-1200-80-35-SO-FL-12'X20'-EX-W-UNV-DP-1-ST | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 10 | Rohan Srivastava |  | High Priority |  | F3-64' REC | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
76762-8 | 76762 | 8 | 1 | Regular | B3LED-9'X25' | BMRLEDPAT-REC-90-400-80-35-SO-FL-9'X25'-EX-W-UNV-DP-1-DS | Wrong part in BOM | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 10 | Rohan Srivastava |  | High Priority |  | F3A-68' REC | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
76762-9 | 76762 | 9 | 1 | Regular | B3LED-4'X4' | BMRLEDPAT-SQ-90-400-80-35-SO-FL-4'X4'-EX-W-277-DP-1+E(1)-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Rohan Srivastava |  | High Priority |  | F3B-16' SQ/EM | 18 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76762-10 | 76762 | 10 | 1 | Regular | B3LED-4'X4' | BMRLEDPAT-SQ-90-400-80-35-SO-FL-4'X4'-EX-W-277-DP-1+NL(1)-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Rohan Srivastava |  | High Priority |  | F3B-16' SQ/NL | 18 | TRUE | FALSE | FALSE | TRUE | ToDo | [6 empty] | ToDo | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76817-1 | 76817 | 1 | 1 | Regular | SCULPT-4 | SCS-300-80-35-0.5M-4-AP-UNV-DP-1-S |  | Wiring Started | 2019-01-29 | 08:27:53 | 2019-01-30 | 2019-02-04 | 1 | 1 | Sacha Lempka | Picked - Complete | Regular |  | H-4' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-2 | 76817 | 2 | 1 | Regular | SCULPT-14 | SCS-300-80-35-0.5M-14-AP-UNV-DP-1-S-B1(BSL310LP) |  | Wiring Started | 2019-01-29 | 08:27:55 | 2019-01-30 | 2019-02-04 | 2 | 4 | Sacha Lempka | Picked - Complete | Regular |  | H/HE/H2-14' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-3 | 76817 | 3 | 1 | Regular | SCULPT-22 | SCS-300-80-35-0.5M-22-AP-UNV-DP-1-S-B2(BSL310LP) | Mechanical issue | Wiring Started | 2019-01-29 | 08:27:57 | 2019-01-30 | 2019-02-04 | 2 | 4 | Sacha Lempka | Picked - Complete | Regular |  | H/HE/H2-22' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | TRUE
76817-4 | 76817 | 4 | 1 | Regular | SCULPT-6 | SCS-300-80-35-0.5M-6-AP-UNV-DP-1-S-B1(BSL310LP) |  | Wiring Started | 2019-01-29 | 08:27:59 | 2019-01-30 | 2019-02-04 | 1 | 1 | Sacha Lempka | Picked - Complete | Regular |  | HE/H2-6' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-5 | 76817 | 5 | 1 | Regular | SCULPT-6 | SCS-300-80-35-0.5M-6-AP-UNV-DP-1-S |  | Wiring Started | 2019-01-29 | 08:28:01 | 2019-01-30 | 2019-02-04 | 2 | 2 | Sacha Lempka | Picked - Complete | Regular |  | H-6' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-6 | 76817 | 6 | 1 | Regular | SCULPT-8 | SCS-300-80-35-0.5M-8-AP-UNV-DP-1-S-B1(BSL310LP) |  | Wiring Started | 2019-01-29 | 08:28:03 | 2019-01-30 | 2019-02-04 | 2 | 2 | Sacha Lempka | Picked - Complete | Regular |  | H/HE-8' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-7 | 76817 | 7 | 1 | Regular | SCULPT-16 | SCS-400-80-35-0.5M-16-AP-UNV-DP-1-S-B1(BSL310LP) |  | Wiring Started | 2019-01-29 | 08:28:06 | 2019-01-30 | 2019-02-04 | 12 | 24 | Sacha Lempka | Picked - Complete | Regular |  | H3/H3E-16' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-8 | 76817 | 8 | 1 | Regular | SCULPT-16 | SCS-400-80-35-0.5M-16-AP-UNV-DP-1-S-B2(BSL310LP) |  | Machine Shop Finished | 2019-02-04 | 12:02:16 | 2019-01-30 | 2019-02-04 | 4 | 8 | Sacha Lempka | Picked - Complete | Regular |  | H3/H3E-16' B2 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-9 | 76817 | 9 | 1 | Regular | SCULPT-8 | SCDI-500-300-80-35-SO-FL-8-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) |  | Wiring Started | 2019-01-29 | 08:28:09 | 2019-01-30 | 2019-02-04 | 8 | 8 | Sacha Lempka | Picked - Complete | Regular |  | I-8' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-10 | 76817 | 10 | 1 | Regular | SCULPT-8 | SCDI-500-300-80-35-SO-FL-8-W-UNV-DP-2-CA(180)-B1(BSL310LP)-C(15FT POWER CORD & CABLES) | Wrong info. In SD | Wiring Started | 2019-01-29 | 08:28:10 | 2019-01-30 | 2019-02-04 | 2 | 2 | Sacha Lempka | Picked - Complete | Regular |  | I/IE-8' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | TRUE
76817-11 | 76817 | 11 | 1 | Regular | SCULPT-18 | SCDI-500-300-80-35-SO-FL-18-W-UNV-DP-2-CA(180)-B1(BSL310LP)-C(15FT POWER CORD & CABLES) |  | Wiring Started | 2019-01-29 | 08:28:12 | 2019-01-30 | 2019-02-04 | 2 | 4 | Sacha Lempka | Picked - Complete | Regular |  | I/IE/IE-18' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-12 | 76817 | 12 | 1 | Regular | SCULPT-18 | SCDI-500-300-80-35-SO-FL-18-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) |  | Wiring Started | 2019-01-29 | 08:28:13 | 2019-01-30 | 2019-02-04 | 2 | 4 | Sacha Lempka | Picked - Complete | Regular |  | I/I2-18' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-13 | 76817 | 13 | 1 | Regular | SCULPT-14 | SCDI-500-300-80-35-SO-FL-14-W-UNV-DP-2-CA(180)-C(15FT POWER CORD & CABLES) |  | Wiring Started | 2019-01-29 | 08:28:15 | 2019-01-30 | 2019-02-04 | 1 | 2 | Sacha Lempka | Picked - Complete | Regular |  | I/I2-14' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76817-14 | 76817 | 14 | 1 | Regular | SCULPT-8 | SCR-300-80-35-FL-8-W-UNV-DP-1-DS |  | Wiring Started | 2019-01-29 | 08:28:18 | 2019-01-30 | 2019-02-04 | 1 | 1 | Sacha Lempka | Picked - Complete | Regular |  | J-8' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:39 |  | TRUE | FALSE
76823-1 | 76823 | 1 | 1 | Regular | ZEN-4 | ZERLED-TR-400-80-35-4-W-UNV-DP-1-TG9 | Electrical issue | Machine Shop Finished | 2019-01-31 | 18:08:33 | 2019-01-30 | 2019-02-04 | 13 | 13 | Sacha Lempka | Picked - Complete | Priority |  | A4-4FT | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:23 |  | TRUE | TRUE
76823-3 | 76823 | 3 | 1 | Regular | ZEN-8 | ZERLED-TR-400-80-35-8-W-UNV-DP-1-TG9 | Shortage | Machine Shop Finished | 2019-01-31 | 18:08:36 | 2019-01-30 | 2019-02-04 | 20 | 20 | Sacha Lempka | Picked - Complete | Priority |  | A4-8FT | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:23 |  | TRUE | TRUE
76823-4 | 76823 | 4 | 1 | Regular | ZEN-12 | ZERLED-TR-400-80-35-12-W-UNV-DP-1-TG9 |  | Machine Shop Finished | 2019-01-31 | 18:08:40 | 2019-01-30 | 2019-02-04 | 9 | 9 | Sacha Lempka | Picked - Complete | Priority |  | A4-12FT | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:23 |  | TRUE | FALSE
76823-5 | 76823 | 5 | 1 | Regular | ZEN-16 | ZERLED-TR-400-80-35-16-W-UNV-DP-1-TG9 |  | Machine Shop Finished | 2019-01-31 | 18:08:42 | 2019-01-30 | 2019-02-04 | 1 | 2 | Sacha Lempka | Picked - Complete | Priority |  | A4-16FT | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:23 |  | TRUE | FALSE
76823-6 | 76823 | 6 | 1 | Regular | ZEN-20 | ZERLED-TR-400-80-35-20-W-UNV-DP-1-TG9 |  | Machine Shop Finished | 2019-01-31 | 18:09:11 | 2019-01-30 | 2019-02-04 | 2 | 4 | Sacha Lempka | Picked - Complete | Priority |  | A4-20FT | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 08:23 |  | TRUE | FALSE
76823-7 | 76823 | 7 | 1 | Regular | STENCL-STFD | STFD-DSO(16-400)-80-35-AL(3)-AP-120-MD-1-CA(72)-RC | Shortage | Wiring Started | 2019-01-30 | 10:46:39 | 2019-01-30 | 2019-02-04 | 6 | 24 | Sacha Lempka | Picked - Complete | Priority |  | C1-16FT | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:32 |  | TRUE | TRUE
76823-8 | 76823 | 8 | 1 | Regular | STENCL-STFD | STFD-DSO(20-400)-80-35-AL(4)-AP-120-MD-1-CA(72)-RC | Shortage | Wiring Started | 2019-01-30 | 10:46:48 | 2019-01-30 | 2019-02-04 | 3 | 15 | Sacha Lempka | Picked - Complete | Priority |  | C1-20FT | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:32 |  | TRUE | TRUE
76823-9 | 76823 | 9 | 1 | Regular | STENCL-16 | STD-SO-400-80-35-16-AP-120-MD-1-CA(72)-RC |  | Wiring Started | 2019-01-30 | 10:47:01 | 2019-01-30 | 2019-02-04 | 1 | 2 | Sacha Lempka | Picked - Complete | Priority |  | C2-16FT | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:33 |  | TRUE | FALSE
76823-10 | 76823 | 10 | 1 | Regular | STENCL-20 | STD-SO-400-80-35-20-AP-120-MD-1-CA(72)-RC |  | Wiring Started | 2019-01-30 | 10:47:10 | 2019-01-30 | 2019-02-04 | 1 | 3 | Sacha Lempka | Picked - Complete | Priority |  | C2-20FT | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:33 |  | TRUE | FALSE
76823-11 | 76823 | 11 | 1 | Regular | STENCL-STFD | STFD-DSO(36-400)-80-35-AH(4)+AY(2)-AP-120-MD-1-CA(72)-RC |  | Wiring Started | 2019-01-30 | 10:47:17 | 2019-01-30 | 2019-02-04 | 9 | 81 | Sacha Lempka | Picked - Complete | Priority |  | C3 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:33 |  | TRUE | FALSE
76823-12 | 76823 | 12 | 1 | Regular | STENCL-STFD | STFD-DSO(12-400)-80-35-AH(6)-AP-120-MD-1-CA(72)-RC |  | Wiring Started | 2019-01-30 | 10:47:26 | 2019-01-30 | 2019-02-04 | 4 | 24 | Sacha Lempka | Picked - Complete | Priority |  | C4 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:33 |  | TRUE | FALSE
76823-13 | 76823 | 13 | 1 | Regular | ZENSQ-12 | ZESQDI-SL-50/50-800-80-35-SO-12-AP-UNV-MD-1-CA(72) |  | Machine Shop Finished | 2019-01-30 | 10:47:38 | 2019-01-30 | 2019-02-04 | 10 | 10 | Sacha Lempka | Picked - Complete | Priority |  | D-12FT | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 12:38 |  | TRUE | FALSE
76853-1 | 76853 | 1 | 1 | Regular | TB4LED-6 | TB4DILED-750-500-80-35-SL-SO-6-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 30 | 30 | Philip Halsey |  | Regular |  | BL10-6FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-2 | 76853 | 2 | 1 | Regular | TB4LED-4 | TB4DILED-750-500-80-35-SL-SO-4-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 3 | Philip Halsey |  | Regular |  | BL10A-4FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-3 | 76853 | 3 | 1 | Regular | TB4LED-4 | TB4DILED-750-500-80-35-SL-SO-8-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 1 | Philip Halsey |  | Regular |  | BL10A-8FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-4 | 76853 | 4 | 1 | Regular | TB4LED-10 | TB4DILED-750-500-80-35-SL-SO-10-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 8 | 8 | Philip Halsey |  | Regular |  | BL10A-10FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-5 | 76853 | 5 | 1 | Regular | TB4LED-14 | TB4DILED-750-500-80-35-SL-SO-14-W-UNV-DP-2-CT9(48)-C(2 CIRCUIT SPLIT 8'-6' FEED ON EACH END - 5 CONDUCTOR CABLE EACH END) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 18 | 36 | Philip Halsey |  | Regular |  | BL10A-14FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-6 | 76853 | 6 | 1 | Regular | TB4LED-6 | TB4DILED-400-400-80-35-SL-SO-6-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 4 | Philip Halsey |  | Regular |  | BL11-6FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-7 | 76853 | 7 | 1 | Regular | TB4LED-8 | TB4DILED-400-400-80-35-SL-SO-8-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 7 | 7 | Philip Halsey |  | Regular |  | BL11-8FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-8 | 76853 | 8 | 1 | Regular | TB4LED-10 | TB4DILED-400-400-80-35-SL-SO-10-W-UNV-DP-2-CT9(48)-C(2 CIRCUIT SPLIT 6'-4' FEED ON EACH END - 5 CONDUCTOR CABLE EACH END) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 14 | 14 | Philip Halsey |  | Regular |  | BL11E-10FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-9 | 76853 | 9 | 1 | Regular | TB4LED-10 | TB4DILED-400-400-80-35-SL-SO-10-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 1 | Philip Halsey |  | Regular |  | BL11-10FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-10 | 76853 | 10 | 1 | Regular | TB4LED-12 | TB4DILED-400-400-80-35-SL-SO-12-W-UNV-DP-2-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 8 | 8 | Philip Halsey |  | Regular |  | BL11E-12FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-11 | 76853 | 11 | 1 | Regular | TB4LED-14 | TB4DILED-400-400-80-35-SL-SO-14-W-UNV-DP-2-CT9(48)-C(2 CIRCUIT SPLIT 8'-6' FEED ON EACH END - 5 CONDUCTOR CABLE EACH END) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 8 | Philip Halsey |  | Regular |  | BL11E-14FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-12 | 76853 | 12 | 1 | Regular | TB4LED-18 | TB4DILED-400-400-80-35-SL-SO-18-W-UNV-DP-2-CT9(48)-C(2 CIRCUIT SPLIT 2'-16' FEED ON EACH END - 5 CONDUCTOR CABLE EACH END) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 6 | Philip Halsey |  | Regular |  | BL11E-18FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-13 | 76853 | 13 | 1 | Regular | TB4LED-22 | TB4DILED-400-400-80-35-SL-SO-22-W-UNV-DP-2-CT9(48)-C(2 CIRCUIT SPLIT 8'-14' FEED ON EACH END - 5 CONDUCTOR CABLE EACH END) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 4 | Philip Halsey |  | Regular |  | BL11E-22FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-14 | 76853 | 14 | 1 | Regular | TB4LED-24 | TB4DILED-400-400-80-35-SL-SO-24-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 6 | Philip Halsey |  | Regular |  | BL11-24FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-15 | 76853 | 15 | 1 | Regular | TB4LED-28 | TB4DILED-400-400-80-35-SL-SO-28-W-UNV-DP-2-CT9(48)-C(2 CIRCUIT SPLIT 8'-20' FEED ON EACH END - 5 CONDUCTOR CABLE EACH END) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 12 | Philip Halsey |  | Regular |  | BL11E-28FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76853-16 | 76853 | 16 | 1 | Regular | TB4LED-6 | TB4DILED-400-400-80-35-SL-SO-6-W-UNV-DP-1-CT9(48) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 13 | 13 | Philip Halsey |  | Regular |  | BL11A-6FT | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76884-1 | 76884 | 1 | 1 | NPI | NPI-18008-01 | NPI-N18008-SKPE-10004-SL60/40-CIR-AL# 12' 6.75"-1000-80-35-SO-W-UNV-D-1-CA(36) | Mechanical issue | Wiring Started | 2019-01-27 | 10:02:50 | 2018-12-21 | 2019-02-06 | 2 | 4 | Stan Buyansky |  | Regular |  | A | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
76910-2 | 76910 | 2 | 1 | Regular | B3LED-3 | BMRLED-500-80-35-FL-3-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Philip Halsey |  | Priority |  | RL3-W | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-3 | 76910 | 3 | 1 | Regular | B3LED-4 | BMRLED-500-80-35-FL-4-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Philip Halsey |  | Priority |  | RL4 | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-5 | 76910 | 5 | 1 | Regular | B3LED-18 | BMRLED-500-80-35-FL-18-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Philip Halsey |  | Priority |  | RL6-18' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-6 | 76910 | 6 | 1 | Regular | CLICK-4 | CLKLED-500-80-35-SO-4-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RL4A | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-7 | 76910 | 7 | 1 | Regular | CLICK-4 | CLKLED-500-80-35-SO-4-W-UNV-DP-1-AC-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 3 | Philip Halsey |  | Priority |  | RL4AE | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-8 | 76910 | 8 | 1 | Regular | CLICK-6 | CLKLED-500-80-35-SO-6-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 7 | 7 | Philip Halsey |  | Priority |  | RL6A | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-9 | 76910 | 9 | 1 | Regular | CLICK-6 | CLKLED-500-80-35-SO-6-W-UNV-DP-1-AC-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 3 | Philip Halsey |  | Priority |  | RL6AE | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-10 | 76910 | 10 | 1 | Regular | CLICK-8 | CLKLED-500-80-35-SO-8-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RL8A | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-11 | 76910 | 11 | 1 | Regular | CLICK-8 | CLKLED-500-80-35-SO-8-W-UNV-DP-1-AC-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RL8AE | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-13 | 76910 | 13 | 1 | Regular | B3LED-3 | BMDLED-500-80-35-SO-3-AP-UNV-DP-1-CA(96)-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | PL3E | 1 | TRUE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76910-16 | 76910 | 16 | 1 | Regular | B3LED-6 | BMDLED-500-80-35-SO-6-AP-UNV-DP-1-CA(96) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | PL6 | 1 | TRUE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76910-17 | 76910 | 17 | 1 | Regular | B3LED-6 | BMDLED-500-80-35-SO-6-AP-UNV-DP-1-CA(96)-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Philip Halsey |  | Priority |  | PL6E | 1 | TRUE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76910-18 | 76910 | 18 | 1 | Regular | GRAZE-8'6" | GPRLED-NLNW-400-80-35-RG2-8'6"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Philip Halsey |  | Priority |  | WG13-8'6" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-19 | 76910 | 19 | 1 | Regular | GRAZE-10'6" | GPRLED-NLNW-400-80-35-RG2-10'6"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Philip Halsey |  | Priority |  | WG13-10'6" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-20 | 76910 | 20 | 1 | Regular | GRAZE-11'6" | GPRLED-NLNW-400-80-35-RG2-11'6"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Philip Halsey |  | Priority |  | WG13-11'6" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-21 | 76910 | 21 | 1 | Regular | B3LED-3 | BMDLED-500-80-35-SO-3-AP-UNV-DP-1-CA(96) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | PL3 | 1 | TRUE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
76910-22 | 76910 | 22 | 1 | Regular | B3LED-3 | BMRLED-500-80-35-FL-3-BLK-UNV-DP-1-DF-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RL3E | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-23 | 76910 | 23 | 1 | Regular | B3LED-4 | BMRLED-500-80-35-FL-4-BLK-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Philip Halsey |  | Priority |  | RL4E | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-24 | 76910 | 24 | 1 | Regular | SCULPT-3 | SCR-500-80-35-FL-3-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RM3 | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-25 | 76910 | 25 | 1 | Regular | SCULPT-4 | SCR-500-80-35-FL-4-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Philip Halsey |  | Priority |  | RM4 | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-26 | 76910 | 26 | 1 | Regular | SCULPT-5 | SCR-500-80-35-FL-5-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RM5 | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76910-28 | 76910 | 28 | 1 | Regular | B3LED-3 | BMRLED-500-80-35-FL-3-BLK-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Priority |  | RL3-BLK | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76914-1 | 76914 | 1 | 1 | Regular | B3LED-12 | BMRLED-700-80-40-FL-12-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-01 | 2019-03-20 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | G-12' | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76938-9 | 76938 | 9 | 1 | Regular | B4LED-4 | BBRLED-300-80-35-FL-4-CB20946(2)-W-UNV-DP-1+LDI-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 8 | 8 | Gagandeep Singh |  | Regular |  | F23/5-4' | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76938-10 | 76938 | 10 | 1 | Regular | B4LED-4 | BBRLED-300-80-35-FL-4-CB20946(2)-W-UNV-DP-E(1)+LDI-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 8 | 8 | Gagandeep Singh |  | Regular |  | F23/5-4' EM | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76939-2 | 76939 | 2 | 1 | Regular | B2LED-12 | BRLED-400-80-35-FL-12-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | George Bacalla |  | High Priority |  | F23 12' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76939-3 | 76939 | 3 | 1 | Regular | B2LED-16 | BRLED-400-80-35-FL-16-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 4 | George Bacalla |  | High Priority |  | F23 16' | 12 | TRUE | FALSE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76939-4 | 76939 | 4 | 1 | Regular | B2LED-34 | BRLED-400-80-35-FL-34-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 6 | George Bacalla |  | High Priority |  | F23 34' | 12 | TRUE | FALSE | FALSE | TRUE |  | InProg | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
76943-1 | 76943 | 1 | 1 | Regular | STENCL-8' | STLDI-SLI-350-DSO-400-8'-80-35-BLK-UNV-DP-1-CA(36")-RC-C(BLACK FIXTURES, CORDS AND CANOPIES) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 20 | 20 | Rajithan Sivapatharajahon |  | High Priority |  | E 4TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76943-2 | 76943 | 2 | 1 | Regular | STENCL-8' | STLDI-SLI-350-DML-450-8'-80-35-BLK-UNV-DP-1-CA(36")-RC-C(BLACK FIXTURE, CORDS AND CANOPY) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 11 | 11 | Rajithan Sivapatharajahon |  | High Priority |  | F 10TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-1 | 76963 | 1 | 1 | Regular | SCULPT-SCRML | SCRML-20'-FL(12')-500-80-35-MKL(6')-350-80-35-BLK-BL(24")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 6 | 12 | Gagandeep Singh |  | Regular |  | F32-20' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-2 | 76963 | 2 | 1 | Regular | SCULPT-SCRML | SCRML-12'-FL(8')-500-80-35-MKL(3')-350-80-35-BLK-BL(12")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 3 | Gagandeep Singh |  | Regular |  | F32A-12' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-3 | 76963 | 3 | 1 | Regular | SCULPT-SCRML | SCRML-6'-FL(4')-500-80-35-MKL(2')-350-80-35-BLK-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Gagandeep Singh |  | Regular |  | F32B-6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-4 | 76963 | 4 | 1 | Regular | SCULPT-SCRML | SCRML-48'-FL(40')-500-80-35-MKL(5'6")-350-80-35-BLK-BL(30")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 15 | Gagandeep Singh |  | Regular |  | F32-C-48' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-5 | 76963 | 5 | 1 | Regular | SCULPT-SCRML | SCRML-20'-FL(12')-500-80-35-MKL(6')-350-80-35-BLK-BL(24")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Gagandeep Singh |  | Regular |  | F32-D-20' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-6 | 76963 | 6 | 1 | Regular | SCULPT-SCRML | SCRML-24'-FL(16')-500-80-35-MKL(6')-350-80-35-BLK-BL(24")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Gagandeep Singh |  | Regular |  | F32-E-24' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-7 | 76963 | 7 | 1 | Regular | SCULPT-SCRML | SCRML-26'-FL(16')-500-80-35-MKL(7'6")-350-80-35-BLK-BL(30")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Gagandeep Singh |  | Regular |  | F32-F-26' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-8 | 76963 | 8 | 1 | Regular | SCULPT-SCRML | SCRML-34'-FL(26')-500-80-35-MKL(4')-350-80-35-BLK-BL(24")-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 5 | 15 | Gagandeep Singh |  | Regular |  | F32-G-34' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76963-9 | 76963 | 9 | 1 | Regular | SCULPT-SCRML | SCRML-4'-FL(2')-500-80-35-MKL(2')-350-80-35-BLK-BLK-UNV-DP-2-MFTG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Gagandeep Singh |  | Regular |  | F32-H-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76965-1 | 76965 | 1 | 1 | Regular | ARCLED-4 | ARCWLED-SL 80/20-1000-80-35-SO-4-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 16 | 16 | Rajithan Sivapatharajahon |  | Regular |  | F15 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
76983-1 | 76983 | 1 | 1 | Regular | WWPRFK-16' | WWS-SL-1000-90-35-16'-AP-UNV-DP-1-SC | Shortage | Machine Shop Finished | 2019-02-04 | 21:40:48 | 2019-01-28 | 2019-01-31 | 1 | 2 | Stan Buyansky |  | Regular |  | A | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 11:23 |  | TRUE | FALSE
77011-1 | 77011 | 1 | 1 | Regular | WB4LED-W | SP16169(2)-WBRLED-750-30-S-12'-W-UNV-DP-1-DS-TF | On Hold | Given to Shipping | 2019-01-16 | 14:58:21 | 2019-01-14 | 2019-01-17 | 13 | 13 | Stan Buyansky | Picked - Complete | High Priority |  | F10-12 | 18 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | TRUE |  | Done | TRUE | 2019-01-16 15:52 |  | TRUE | FALSE
77060-2 | 77060 | 2 | 1 | Regular | B3SLED-4 | B3RLED-SL-750-80-30-FL-4-W-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 12 | 12 | Philip Halsey |  | Regular |  | F5-R2 | 12 | TRUE | FALSE | FALSE | TRUE | Ready | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77142-1 | 77142 | 1 | 1 | Regular | ZEN-8 | ZELED-SL 50/50-1050-80-35-MSO-8-W-UNV-MD-2-CT15(48) |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Jessica Pasternyk |  | High Priority |  | LT4-8' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77142-2 | 77142 | 2 | 1 | Regular | STNCLS-6 | STSLF-SO-300-80-30-6-BLK-120-MD-1-SG15 |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 3 | 3 | Jessica Pasternyk |  | High Priority |  | LT6 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77149-1 | 77149 | 1 | 1 | Regular | CLICK-6' | CLKLED-400-80-30-SO-6'-W-UNV-DP-1-AC | Shortage | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 3 | 3 | Philip Halsey |  | Regular |  | LR20-S-6' | 18 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77149-2 | 77149 | 2 | 1 | Regular | CLICK-8' | CLKLED-400-80-30-SO-8'-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 1 | 1 | Philip Halsey |  | Regular |  | LR20-S-8' | 18 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77149-3 | 77149 | 3 | 1 | Regular | CLICK-14' | CLKLED-400-80-30-SO-14'-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 1 | 2 | Philip Halsey |  | Regular |  | LR20-S-14' | 18 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-17 | 77175 | 17 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 | Others | Machine Shop Finished | 2019-02-03 | 20:33:50 | 2019-01-30 | 2019-02-04 | 45 | 45 | Jessica Kennedy | Picked - Complete | Regular |  | A-14TH | 15 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-18 | 77175 | 18 | 1 | Regular | B3SLED-6 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 | Others | Machine Shop Finished | 2019-02-03 | 20:33:57 | 2019-01-30 | 2019-02-04 | 12 | 12 | Jessica Kennedy | Picked - Complete | Regular |  | A1-14TH | 15 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-19 | 77175 | 19 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-03 | 20:34:11 | 2019-01-30 | 2019-02-04 | 4 | 4 | Jessica Kennedy |  | Regular |  | A2-14TH | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-20 | 77175 | 20 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-03 | 20:34:15 | 2019-01-30 | 2019-02-04 | 2 | 2 | Jessica Kennedy |  | Regular |  | A3-DF-14TH | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-21 | 77175 | 21 | 1 | Regular | ACCENT-28 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Jessica Kennedy |  | Regular |  | A4-14TH | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-22 | 77175 | 22 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 2 | 4 | Jessica Kennedy |  | Regular |  | A4A-14TH | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-23 | 77175 | 23 | 1 | Regular | B3LED-12 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 3 | 3 | Jessica Kennedy | Picked - Complete | Regular |  | A9-DWF-14TH | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77175-24 | 77175 | 24 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 18 | 18 | Jessica Kennedy | Picked - Complete | Regular |  | P4-14TH | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77175-25 | 77175 | 25 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC |  | Machine Shop Finished | 2019-02-04 | 20:35:29 | 2019-01-30 | 2019-02-04 | 8 | 8 | Jessica Kennedy |  | Regular |  | P8-14TH | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-26 | 77175 | 26 | 1 | Regular | SCULPT-16 | SCS-750-80-35-0.5P-16-BLK-UNV-DP-1-SC-FW(6) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 4 | 8 | Jessica Kennedy | Picked - Complete | Regular |  | P16A-14TH | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77175-27 | 77175 | 27 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 | Others | Machine Shop Finished | 2019-02-03 | 20:34:00 | 2019-01-30 | 2019-02-04 | 49 | 49 | Jessica Kennedy | Picked - Complete | Regular |  | A-15TH | 15 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-28 | 77175 | 28 | 1 | Regular | B3SLED-6 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | Machine Shop Finished | 2019-02-03 | 20:34:09 | 2019-01-30 | 2019-02-04 | 18 | 18 | Jessica Kennedy | Picked - Complete | Regular |  | A1-15TH | 15 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-29 | 77175 | 29 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-03 | 20:34:18 | 2019-01-30 | 2019-02-04 | 5 | 5 | Jessica Kennedy |  | Regular |  | A2-15TH | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-30 | 77175 | 30 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-03 | 20:34:33 | 2019-01-30 | 2019-02-04 | 3 | 3 | Jessica Kennedy |  | Regular |  | A3-DF-15TH | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-31 | 77175 | 31 | 1 | Regular | ACCENT-28 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 3 | Jessica Kennedy |  | Regular |  | A4-15TH | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-32 | 77175 | 32 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 1 | 2 | Jessica Kennedy |  | Regular |  | A4A-15TH | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-33 | 77175 | 33 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 18 | 18 | Jessica Kennedy | Picked - Complete | Regular |  | P4-15TH | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77175-34 | 77175 | 34 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC | Others | Machine Shop Finished | 2019-02-03 | 20:35:36 | 2019-01-30 | 2019-02-04 | 4 | 4 | Jessica Kennedy |  | Regular |  | P8-15TH | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-35 | 77175 | 35 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 50 | 50 | Jessica Kennedy |  | Regular |  | A-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-36 | 77175 | 36 | 1 | Regular | B3SLED-6 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 13 | 13 | Jessica Kennedy |  | Regular |  | A1-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-37 | 77175 | 37 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 5 | 5 | Jessica Kennedy |  | Regular |  | A2-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-38 | 77175 | 38 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A3-DF-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-39 | 77175 | 39 | 1 | Regular | ACCENT-28 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Jessica Kennedy |  | Regular |  | A4-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-40 | 77175 | 40 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Jessica Kennedy |  | Regular |  | A4A-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-41 | 77175 | 41 | 1 | Regular | B3LED-12 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A9-DWF-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-42 | 77175 | 42 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 18 | 18 | Jessica Kennedy |  | Regular |  | P4-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-43 | 77175 | 43 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 4 | Jessica Kennedy |  | Regular |  | P8-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-45 | 77175 | 45 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 55 | 55 | Jessica Kennedy |  | Regular |  | A-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-46 | 77175 | 46 | 1 | Regular | B3SLED-6 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 38 | 38 | Jessica Kennedy |  | Regular |  | A1-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-47 | 77175 | 47 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A2-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-48 | 77175 | 48 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A3-DF-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-49 | 77175 | 49 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Jessica Kennedy |  | Regular |  | A4A-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-50 | 77175 | 50 | 1 | Regular | ACCENT-28 | SCRAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Jessica Kennedy |  | Regular |  | A4B-DWF-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-51 | 77175 | 51 | 1 | Regular | WWPRFK-20 | WWR-SL-400-80-35-L-20-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 6 | Jessica Kennedy |  | Regular |  | A11-GRID-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-52 | 77175 | 52 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 15 | 15 | Jessica Kennedy |  | Regular |  | P4-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-53 | 77175 | 53 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 4 | Jessica Kennedy |  | Regular |  | P8-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-54 | 77175 | 54 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 54 | 54 | Jessica Kennedy |  | Regular |  | A-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-55 | 77175 | 55 | 1 | Regular | B3SLED-6 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 12 | 12 | Jessica Kennedy |  | Regular |  | A1-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-56 | 77175 | 56 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 5 | 5 | Jessica Kennedy |  | Regular |  | A2-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-57 | 77175 | 57 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A3-DF-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-59 | 77175 | 59 | 1 | Regular | B3LED-12 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A9-DWF-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-60 | 77175 | 60 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 18 | 18 | Jessica Kennedy |  | Regular |  | P4-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-61 | 77175 | 61 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 4 | Jessica Kennedy |  | Regular |  | P8-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-62 | 77175 | 62 | 1 | Regular | SCULPT-16 | SCS-750-80-35-0.5P-16-BLK-UNV-DP-1-SC-FW(6) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 8 | Jessica Kennedy |  | Regular |  | P16A-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-63 | 77175 | 63 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 55 | 55 | Jessica Kennedy |  | Regular |  | A-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-64 | 77175 | 64 | 1 | Regular | B3SLED-6 | B3RLED-SL-1000-80-35-FL-6-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 19 | 19 | Jessica Kennedy |  | Regular |  | A1-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-65 | 77175 | 65 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 7 | 7 | Jessica Kennedy |  | Regular |  | A2-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-66 | 77175 | 66 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 3 | Jessica Kennedy |  | Regular |  | A3-DF-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-68 | 77175 | 68 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Jessica Kennedy |  | Regular |  | A4A-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-69 | 77175 | 69 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 18 | 18 | Jessica Kennedy |  | Regular |  | P4-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-70 | 77175 | 70 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 4 | Jessica Kennedy |  | Regular |  | P8-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-71 | 77175 | 71 | 1 | Regular | B3SLED-4 | B3RLED-SL-1000-80-35-FL-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 52 | 52 | Jessica Kennedy |  | Regular |  | A-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-72 | 77175 | 72 | 1 | Regular | WWPRFK-8 | WWR-SL-400-80-35-8-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Kennedy |  | Regular |  | A2-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-73 | 77175 | 73 | 1 | Regular | WWPRFK-12 | WWR-SL-400-80-35-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Jessica Kennedy |  | Regular |  | A2B-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-74 | 77175 | 74 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Kennedy |  | Regular |  | A3-DF-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-75 | 77175 | 75 | 1 | Regular | ACCENT-28 | SCSAC-AC(16)-D60-HX-D-CC-80-30-28-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Kennedy |  | Regular |  | A4-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-76 | 77175 | 76 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Jessica Kennedy |  | Regular |  | A4A-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-77 | 77175 | 77 | 1 | Regular | B3SLED-8 | B3RLED-SL-1000-80-35-FL-8-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 12 | 12 | Jessica Kennedy |  | Regular |  | A8-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-78 | 77175 | 78 | 1 | Regular | B3LED-12 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Kennedy |  | Regular |  | A9-DWF-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-79 | 77175 | 79 | 1 | Regular | WWPRFK-20 | WWR-SL-400-80-35-L-20-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Jessica Kennedy |  | Regular |  | A11-DWF-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-80 | 77175 | 80 | 1 | Regular | SCULPT-4 | SCS-500-80-35-0.5P-4-BLK-UNV-DP-1-SC-FW(6) |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 17 | 17 | Jessica Kennedy |  | Regular |  | P4-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-81 | 77175 | 81 | 1 | Regular | STENCL-BLK | SP18376A(1)-STD-DSO(7)-400-80-35-BLK-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Jessica Kennedy |  | Regular |  | P8-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-143 | 77175 | 143 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Machine Shop Finished | 2019-02-03 | 20:34:35 | 2019-01-30 | 2019-02-04 | 8 | 8 | Jessica Kennedy |  | Regular |  | A3-GRID-14TH | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-144 | 77175 | 144 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Machine Shop Finished | 2019-02-04 | 10:12:04 | 2019-01-30 | 2019-02-04 | 10 | 10 | Jessica Kennedy |  | Regular |  | A3-GRID-15TH | 18 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77175-145 | 77175 | 145 | 1 | Regular | B3LED-12 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 2 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | A9-DWF-15TH | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77175-146 | 77175 | 146 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 8 | 8 | Jessica Kennedy |  | Regular |  | A3-GRID-16TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-147 | 77175 | 147 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 4 | Jessica Kennedy |  | Regular |  | A3-GRID-17TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-148 | 77175 | 148 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 8 | 8 | Jessica Kennedy |  | Regular |  | A3-GRID-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-149 | 77175 | 149 | 1 | Regular | ACCENT-18 | SCSAC-AC(8)-D60-HX-D-CC-80-30-18-W-UNV-1-SC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Jessica Kennedy |  | Regular |  | A4A-18TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-150 | 77175 | 150 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 10 | 10 | Jessica Kennedy |  | Regular |  | A3-GRID-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-151 | 77175 | 151 | 1 | Regular | B3LED-12 | BMRLED-1000-80-35-1.25P-12-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Jessica Kennedy |  | Regular |  | A9-DWF-19TH | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-152 | 77175 | 152 | 1 | Regular | WWPRFK-4 | WWR-SL-400-80-35-4-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Jessica Kennedy |  | Regular |  | A3-GRID-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77175-153 | 77175 | 153 | 1 | Regular | B3LED-16 | BMRLED-1000-80-35-1.25P-16-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Jessica Kennedy |  | Regular |  | A10-DWF-20TH | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77180-1 | 77180 | 1 | 1 | Regular | SCULPT-4' | SCR-300-80-35-FL-4'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 6 | 6 | Sacha Lempka |  | Regular |  | D-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-2 | 77180 | 2 | 1 | Regular | SCULPT-8' | SCR-300-80-35-FL-8'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 6 | 6 | Sacha Lempka |  | Regular |  | D-8' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-3 | 77180 | 3 | 1 | Regular | SCULPT-8' | SCR-300-80-35-FL-8'-W-UNV-DP-1-DF-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Sacha Lempka |  | Regular |  | D-8' (1)EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-4 | 77180 | 4 | 1 | Regular | SCULPT-16' | SCR-300-80-35-FL-16'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 8 | Sacha Lempka |  | Regular |  | D-16' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-5 | 77180 | 5 | 1 | Regular | SCULPT-28' | SCR-300-80-35-FL-28'-W-UNV-DP-1-DF-B2(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 12 | Sacha Lempka |  | Regular |  | D-28' (2)EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-6 | 77180 | 6 | 1 | Regular | SCULPT-4' | SCR-300-80-35-FL-4'-C(BLK)-UNV-DP-1-DF | Shortage | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 4 | Sacha Lempka |  | Regular |  | F-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-7 | 77180 | 7 | 1 | Regular | SCULPT-8' | SCR-300-80-35-FL-8'-C(BLK)-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 5 | 5 | Sacha Lempka |  | Regular |  | F-8' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-8 | 77180 | 8 | 1 | Regular | SCULPT-8' | SCR-300-80-35-FL-8'-C(BLK)-UNV-DP-1-DF-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 5 | 5 | Sacha Lempka |  | Regular |  | F-8' EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-9 | 77180 | 9 | 1 | Regular | SCULPT-4' | SCR-300-80-40-FL-4'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 9 | 9 | Sacha Lempka |  | Regular |  | SC-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-10 | 77180 | 10 | 1 | Regular | SCULPT-4' | SCR-300-80-40-FL-4'-W-UNV-DP-1-DF-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Sacha Lempka |  | Regular |  | SC-4' (1)EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-11 | 77180 | 11 | 1 | Regular | SCULPT-8' | SCR-300-80-40-FL-8'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 3 | 3 | Sacha Lempka |  | Regular |  | SC-8' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77180-12 | 77180 | 12 | 1 | Regular | SCULPT-8' | SCR-300-80-40-FL-8'-W-UNV-DP-1-DF-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 3 | 3 | Sacha Lempka |  | Regular |  | SC-8' (1)EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | Ready | [6 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77187-1 | 77187 | 1 | 1 | Regular | SCULPT-40' | SCDIPAT-REC-90(4)-500-400-80-30-SO-FL-40'-NL-AP-UNV-DP-2-CA(36) | Missing info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 4 | Gagandeep Singh | Picked - Complete | Regular |  | F3B-14'X6' REC | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
77187-2 | 77187 | 2 | 1 | Regular | SCULPT-20' | SCDIPAT-REC-90(4)-500-400-80-30-SO-FL-20'-NL-AP-UNV-DP-2-CA(36) | Missing info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Gagandeep Singh | Picked - Complete | Regular |  | FB-8'X2' REC | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
77195-1 | 77195 | 1 | 1 | Regular | SKETCH-AL(15' 8 1/2") | SKPE-10005-SL 60/40-CIR-AL(15' 8 1/2")-1300-80-30-SO-AP-120-LT(LTE)-1-CA(144)+SM |  | Scheduled/Released |  |  | 2019-02-28 | 2019-03-05 | 4 | 16 | Stan Buyansky |  | Regular |  | LP2 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77207-1 | 77207 | 1 | 1 | Regular | TB2LED-16' | TB2DILED-1000-400-80-30-SL-SO-16'-W-277-DP-2-CA(36) |  | Machine Shop Finished | 2019-02-01 | 02:16:20 | 2019-02-01 | 2019-02-06 | 18 | 36 | Rohan Srivastava | Picked - Complete | Regular |  | D-16' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-2 | 77207 | 2 | 1 | Regular | TB2LED-30' | TB2DILED-1000-400-80-30-SL-SO-30'-W-277-DP-2-CA(36) | Wrong info. In SD | Machine Shop Finished | 2019-02-01 | 02:16:21 | 2019-02-01 | 2019-02-06 | 4 | 12 | Rohan Srivastava | Picked - Complete | Regular |  | D-30' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | TRUE
77207-3 | 77207 | 3 | 1 | Regular | B2SLED-2 | B2SQDLED-1000-80-30-SO-2-W-277-DP-1-CA(96) |  | Machine Shop Finished | 2019-02-01 | 02:16:23 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | E-2 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-4 | 77207 | 4 | 1 | Regular | B2SLED-4 | B2SQDLED-1000-80-30-SO-4-W-277-DP-1-CA(96) |  | Machine Shop Finished | 2019-02-01 | 02:16:24 | 2019-02-01 | 2019-02-06 | 5 | 5 | Rohan Srivastava | Picked - Complete | Regular |  | E-4 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-5 | 77207 | 5 | 1 | Regular | B2SLED-6 | B2SQDLED-1000-80-30-SO-6-W-277-DP-1-CA(96) |  | Machine Shop Finished | 2019-02-01 | 02:16:26 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | E-6 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-6 | 77207 | 6 | 1 | Regular | B2SLED-8 | B2SQDLED-1000-80-30-SO-8-W-277-DP-1-CA(96) |  | Machine Shop Finished | 2019-02-01 | 02:16:27 | 2019-02-01 | 2019-02-06 | 4 | 4 | Rohan Srivastava | Picked - Complete | Regular |  | E-8 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-7 | 77207 | 7 | 1 | Regular | B2SLED-8 | B2SQDLED-1000-80-30-SO-8-W-277-DP-1+E(1)-CA(96) |  | Machine Shop Finished | 2019-02-01 | 02:16:28 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | E-8E | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-8 | 77207 | 8 | 1 | Regular | B2LED-3 | BRLED-1000-80-30-FL-3-W-277-DP-1-DS-FW(6) |  | Machine Shop Finished | 2019-02-01 | 02:16:29 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | F-3 | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-9 | 77207 | 9 | 1 | Regular | B2LED-4 | BRLED-1000-80-30-FL-4-W-277-DP-1-DS-FW(6) |  | Machine Shop Finished | 2019-02-01 | 02:16:30 | 2019-02-01 | 2019-02-06 | 9 | 9 | Rohan Srivastava | Picked - Complete | Regular |  | F-4 | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-10 | 77207 | 10 | 1 | Regular | B2LED-6 | BRLED-1000-80-30-FL-6-W-277-DP-1-DS-FW(6) |  | Machine Shop Finished | 2019-02-01 | 02:16:34 | 2019-02-01 | 2019-02-06 | 5 | 5 | Rohan Srivastava | Picked - Complete | Regular |  | F-6 | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-11 | 77207 | 11 | 1 | Regular | B2LED-6 | BRLED-1000-80-30-FL-6-W-277-DP-1+E(1)-DS-FW(6) |  | Machine Shop Finished | 2019-02-01 | 02:16:32 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | F-6E | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-12 | 77207 | 12 | 1 | Regular | B2LED-8 | BRLED-1000-80-30-FL-8-W-277-DP-1-DS-FW(6) |  | Machine Shop Finished | 2019-02-01 | 02:16:39 | 2019-02-01 | 2019-02-06 | 6 | 6 | Rohan Srivastava | Picked - Complete | Regular |  | F-8 | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-13 | 77207 | 13 | 1 | Regular | B2LED-8 | BRLED-1000-80-30-FL-8-W-277-DP-1+E(1)-DS-FW(6) |  | Machine Shop Finished | 2019-02-01 | 02:16:41 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | F-8E | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-01 13:17 |  | TRUE | FALSE
77207-14 | 77207 | 14 | 1 | Regular | B3LED-6 | BMRLED-1000-80-30-FL-6-W-277-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 7 | 7 | Rohan Srivastava | Picked - Complete | Regular |  | H-6 | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77207-15 | 77207 | 15 | 1 | Regular | B3LED-8 | BMRLED-1000-80-30-FL-8-W-277-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | H-8 | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77207-16 | 77207 | 16 | 1 | Regular | B3LED-42' | BMRLEDPAT-REC-90(4)-1000-80-30-SO-FL-42'-EX-W-277-DP-1-DS-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 8 | Rohan Srivastava | Picked - Complete | Regular |  | H1-8'X13' REC | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77207-17 | 77207 | 17 | 1 | Regular | B3PLED-4' 8" | BMPRLED-1000-80-30-RG3-4' 8"-W-277-DP-1-DS-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | X-4' 8" | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77207-18 | 77207 | 18 | 1 | Regular | B3PLED-7' 4" | BMPRLED-1000-80-30-RG3-7' 4"-W-277-DP-1-DS-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | X-7' 4" | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77207-19 | 77207 | 19 | 1 | Regular | B3PLED-12' | BMPRLED-1000-80-30-RG3-14'-W-277-DP-1-DS-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | X-14' | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77207-20 | 77207 | 20 | 1 | Regular | B3PLED-20' | BMPRLED-1000-80-30-RG3-19' 9"-W-277-DP-1-DS-FW(6) | Others | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | X-19' 9" | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
77211-1 | 77211 | 1 | 1 | Regular | B4LED-8 | BBWDILED-640-400-80-40-SO-8-W-UNV-DP-1-D |  | Machine Shop Finished | 2019-01-24 | 13:52:56 | 2019-02-05 | 2019-02-08 | 12 | 12 | George Bacalla | Picked - Complete | Regular |  | F1-8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77211-2 | 77211 | 2 | 1 | Regular | B4LED-4 | BBWDILED-640-400-80-40-SO-4-W-UNV-DP-1-D |  | Machine Shop Finished | 2019-01-24 | 13:52:58 | 2019-02-05 | 2019-02-08 | 8 | 8 | George Bacalla | Picked - Complete | Regular |  | F2-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77249-1 | 77249 | 1 | 1 | Mockup/Samples | SCULPT-SCML | SCML-8-BW-400-MLB(16)-300-GR-80-35-AP-UNV-DP-1-CA(36)-EN(1) | Others | Machine Shop Finished | 2019-01-27 | 11:41:48 | 2019-01-15 | 2019-01-18 | 2 | 2 | Jatin Patel | Picked - Complete | High Priority |  | PRIVATE OFFICE - NEIL | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready |  | ToDo |  | ToDo |  |  |  |  | TRUE |  | Done | TRUE | 2019-01-28 09:44 |  | TRUE | FALSE
77249-2 | 77249 | 2 | 1 | Mockup/Samples | STNCLS-STSFF | STSFF-SO(16-400)-80-35-AL(2)+AT(2)-MKL(10)-80-35-W-BLK-BLK-UNV-MD-1-SBS-C(REMOTE ENLIGHTED INTEGRAL SENSOR) | Missing info. In SD | Machine Shop Finished | 2019-01-23 | 13:03:27 | 2019-01-07 | 2019-01-10 | 1 | 7 | Jatin Patel | Picked - Complete | High Priority |  | MEETING ROOM 4 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-01-11 10:01 |  | TRUE | FALSE
77249-3 | 77249 | 3 | 1 | Mockup/Samples | EDGE2-8 | ED2WD-1000-80-35-UB-8-W-W-UNV-DP-1-FL-C(REMOTE DRIVER AND ENLIGHTED INTEGRAL SENSOR) |  | Machine Shop Finished | 2019-01-24 | 14:45:44 | 2019-01-21 | 2019-01-24 | 1 | 1 | Jatin Patel |  | High Priority |  | MEETING ROOM 3 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77249-4 | 77249 | 4 | 1 | Mockup/Samples | SCULPT-6X8 | SCDIPAT-REC-90-500-300-80-35-BW-0.5M-6X8-NL-W-UNV-DP-1-CTS(12)-EN(1) | Wrong info. In SD | Machine Shop Finished | 2019-01-27 | 11:42:34 | 2019-01-15 | 2019-01-18 | 1 | 4 | Jatin Patel | Picked - Complete | High Priority |  | HR OFFICE | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 09:44 |  | TRUE | FALSE
77249-10 | 77249 | 10 | 1 | Mockup/Samples | EDGE2-6 | ED2-1000-80-35-UB-6-W-W-UNV-MD-1-90D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) | Mechanical issue | Machine Shop Started |  |  | 2019-01-21 | 2019-01-24 | 1 | 1 | Jatin Patel |  | High Priority |  | MICHAEL R | 4 | TRUE | TRUE | TRUE | TRUE |  | ToDo | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77249-11 | 77249 | 11 | 1 | Mockup/Samples | EDGE2-6 | ED2-1000-80-35-UB-6-W-W-UNV-MD-1-45D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) |  | Machine Shop Finished | 2019-01-24 | 14:45:46 | 2019-01-21 | 2019-01-24 | 1 | 1 | Jatin Patel |  | High Priority |  | LAZER | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77249-15 | 77249 | 15 | 1 | Mockup/Samples | EDGE2-4 | ED2-1000-80-35-UB-4-W-W-UNV-MD-1-45D-CA(36)-FL-C(REMOTE ENLIGHTED INTEGRAL SENSOR) |  | Machine Shop Finished | 2019-01-24 | 14:45:48 | 2019-01-21 | 2019-01-24 | 1 | 1 | Jatin Patel |  | High Priority |  | HR CORRIDOR | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77293-1 | 77293 | 1 | 1 | Regular | WB4LED-8 | WBSLED-500-80-35-S-8-BLK-UNV-DP-1-SC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 3 | Zahra Vatani |  | Regular |  | AA-8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-1 | 77314 | 1 | 1 | Regular | STENCL-STFD | STFD-DSO(6-200)-80-35-BT(3)-AP-UNV-MD-1-CA(36)-SC |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 6 | Christina Torok |  | Regular |  | L5 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-2 | 77314 | 2 | 1 | Regular | STENCL-STFD | STFD-DSO(15-200)-80-35-BT(3)-AP-UNV-MD-1-CA(36)-SC |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 12 | Christina Torok |  | Regular |  | L6 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-3 | 77314 | 3 | 1 | Regular | STENCL-STFD | STFD-DSO(24-200)-80-35-BT(3)-AP-UNV-MD-1-CA(36)-SC |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 9 | Christina Torok |  | Regular |  | L7 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-4 | 77314 | 4 | 1 | Regular | B2SLED-4 | B2SQWDLED-1000-80-35-L-4-AP-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 4 | Christina Torok |  | Regular |  | L9 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-5 | 77314 | 5 | 1 | Regular | SCULPT-4 | SCR-300-80-35-FL-4-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 3 | Christina Torok |  | Regular |  | L10 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-6 | 77314 | 6 | 1 | Regular | STENCL-STFD | STFD-DSO(24-200)-80-35-AL(4)-AP-UNV-MD-1-CA(36)-SC |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 4 | Christina Torok |  | Regular |  | L11 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77314-7 | 77314 | 7 | 1 | Regular | STENCL-5 | STD-SO-200-80-35-5-AP-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 2 | Christina Torok |  | Regular |  | L14 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77323-1 | 77323 | 1 | 1 | Regular | B4LED-10 | BBRLED-875-80-40-FL-10-W-UNV-DP-1-TX |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | LF23-10' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77323-2 | 77323 | 2 | 1 | Regular | B4LED-2 | BBRLED-1000-80-40-FL-2-W-UNV-DP-1-TX |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 4 | 4 | Rajithan Sivapatharajahon |  | Regular |  | LF23A-2' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77323-3 | 77323 | 3 | 1 | Regular | B4LED-12 | BBRLED-1000-80-40-FL-12-W-UNV-DP-1-TX |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 8 | 8 | Rajithan Sivapatharajahon |  | Regular |  | LF23A-12' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77351-1 | 77351 | 1 | 1 | Regular | B4LED-24' 0" | BBWDILED-400-750-80-35-SO-24' 0"-W-120-DP-1 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Jessica Pasternyk |  | Regular |  | L-04-24'-0" | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77356-1 | 77356 | 1 | 1 | Regular | B4LED-2' 0" | BBDLED-750-80-35-SO-2' 0"-W-UNV-DP-1-SA(120) |  | Machine Shop Finished | 2019-01-31 | 20:24:47 | 2019-02-06 | 2019-02-11 | 95 | 95 | Jessica Kennedy |  | Regular |  | L1-2' | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-2 | 77356 | 2 | 1 | Regular | B4LED-4' 0" | BBDLED-750-80-35-SO-4' 0"-W-UNV-DP-1-SA(120) |  | Machine Shop Finished | 2019-01-31 | 20:24:48 | 2019-02-06 | 2019-02-11 | 89 | 89 | Jessica Kennedy |  | Regular |  | L1-4' | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-3 | 77356 | 3 | 1 | Regular | B4LED-2' 0" | BBDLED-750-80-35-ASO-2' 0"-W-UNV-DP-1-SA(120) |  | Machine Shop Finished | 2019-01-31 | 20:24:49 | 2019-02-06 | 2019-02-11 | 5 | 5 | Jessica Kennedy |  | Regular |  | L1A | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-4 | 77356 | 4 | 1 | Regular | B4LED-8' 0" | BBDILED-400-640-80-35-SO-8' 0"-W-UNV-DP-2-CT15(36) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 3 | Jessica Kennedy |  | Regular |  | F3 | 18 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77356-5 | 77356 | 5 | 1 | Regular | WB4LED-4' 0" | WBRLED-750-80-35-S-4' 0"-AP-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 15 | 15 | Jessica Kennedy |  | Regular |  | F5A | 18 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77356-6 | 77356 | 6 | 1 | Regular | B4LED-4' 0" | BBRLED-400-80-35-FL-4' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 8 | 8 | Jessica Kennedy |  | Regular |  | F10-4' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-7 | 77356 | 7 | 1 | Regular | B4LED-5' 0" | BBRLED-400-80-35-FL-5' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 10 | 10 | Jessica Kennedy |  | Regular |  | F10-5' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-8 | 77356 | 8 | 1 | Regular | B4LED-6' 0" | BBRLED-400-80-35-FL-6' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 3 | Jessica Kennedy |  | Regular |  | F10-6' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-9 | 77356 | 9 | 1 | Regular | B4LED-7' 0" | BBRLED-400-80-35-FL-7' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 10 | 10 | Jessica Kennedy |  | Regular |  | F10-7' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-10 | 77356 | 10 | 1 | Regular | B4LED-8' 0" | BBRLED-400-80-35-FL-8' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Jessica Kennedy |  | Regular |  | F10-8' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-11 | 77356 | 11 | 1 | Regular | B4LED-9' 0" | BBRLED-400-80-35-FL-9' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Jessica Kennedy |  | Regular |  | F10-9' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-12 | 77356 | 12 | 1 | Regular | B4LED-10' 0" | BBRLED-400-80-35-FL-10' 0"-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Jessica Kennedy |  | Regular |  | F10-10' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-13 | 77356 | 13 | 1 | Regular | B4LED-11' 0" | BBRLED-400-80-35-FL-11' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 7 | 7 | Jessica Kennedy |  | Regular |  | F10-11' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-14 | 77356 | 14 | 1 | Regular | B4LED-12' 0" | BBRLED-400-80-35-FL-12' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Jessica Kennedy |  | Regular |  | F10-12' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-15 | 77356 | 15 | 1 | Regular | B4LED-13' 0" | BBRLED-400-80-35-FL-13' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 4 | Jessica Kennedy |  | Regular |  | F10-13' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-16 | 77356 | 16 | 1 | Regular | B4LED-14' 0" | BBRLED-400-80-35-FL-14' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Jessica Kennedy |  | Regular |  | F10-14' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-17 | 77356 | 17 | 1 | Regular | B4LED-13' 0" | BBRLED-400-80-35-FL-13' 0"-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Jessica Kennedy |  | Regular |  | F10-13' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-18 | 77356 | 18 | 1 | Regular | B4LED-15' 0" | BBRLED-400-80-35-FL-15' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 8 | 16 | Jessica Kennedy |  | Regular |  | F10-15' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-19 | 77356 | 19 | 1 | Regular | B4LED-15' 0" | BBRLED-400-80-35-FL-15' 0"-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Jessica Kennedy |  | Regular |  | F10-15' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-20 | 77356 | 20 | 1 | Regular | B4LED-24' 0" | BBRLED-400-80-35-FL-24' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Jessica Kennedy |  | Regular |  | F10-24' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-21 | 77356 | 21 | 1 | Regular | B4LED-28' 0" | BBRLED-400-80-35-FL-28' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Jessica Kennedy |  | Regular |  | F10-28' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-22 | 77356 | 22 | 1 | Regular | B4LED-33' 0" | BBRLED-400-80-35-FL-33' 0"-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Jessica Kennedy |  | Regular |  | F10-33' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-23 | 77356 | 23 | 1 | Regular | B4LED-52' 0" | BBRLED-400-80-35-FL-52' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 5 | Jessica Kennedy |  | Regular |  | F10-52' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77356-25 | 77356 | 25 | 1 | Regular | B4LED-10' 0" | BBRLED-400-80-35-FL-10' 0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Jessica Kennedy |  | Regular |  | F10-10' | 18 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77367-1 | 77367 | 1 | 1 | Regular | B4LED-4' | BBRLED-500-80-35-FL-4'-W-277-DP-1-TG15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 7 | 7 | Philip Halsey |  | Regular |  | LL1, 4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-2 | 77367 | 2 | 1 | Regular | B4LED-10' | BBRLED-500-80-35-FL-10'-W-277-DP-1-TG15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 9 | 9 | Philip Halsey |  | Regular |  | LL1, 10' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-3 | 77367 | 3 | 1 | Regular | B4LED-20' | BBRLED-500-80-35-FL-20'-W-277-DP-1-TG15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 2 | Philip Halsey |  | Regular |  | LL1, 20' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-4 | 77367 | 4 | 1 | Regular | B4LED-4' | BBRLED-500-80-35-FL-4'-W-277-DP-1-TG15-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 4 | 4 | Philip Halsey |  | Regular |  | LL1E, 4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-6 | 77367 | 6 | 1 | Regular | B4LED-10' | BBRLED-500-80-35-FL-10'-W-277-DP-1-TG15-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 5 | 5 | Philip Halsey |  | Regular |  | LL1E, 10' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-7 | 77367 | 7 | 1 | Regular | B4LED-12' | BBRLED-500-80-35-FL-12'-W-277-DP-1-TG15-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 2 | Philip Halsey |  | Regular |  | LL1E, 12' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-8 | 77367 | 8 | 1 | Regular | B4LED-6' | BBRLED-500-80-35-FL-6'-C(RAL8022)-277-DP-1-DF-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 2 | Philip Halsey |  | Regular |  | LL3E, 6' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-9 | 77367 | 9 | 1 | Regular | B4LED-8' | BBRLED-500-80-35-FL-8'-C(RAL8022)-277-DP-1-DF-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 2 | Philip Halsey |  | Regular |  | LL3E, 8' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-10 | 77367 | 10 | 1 | Regular | B4LED-6' | BBWDILED-500-500-80-35-SO-6'-AP-UNV-DP-2 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 1 | Philip Halsey |  | Regular |  | LW2 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-11 | 77367 | 11 | 1 | Regular | WB4LED-4' | WBSLED-500-80-35-S-4'-C(RAL8022)-UNV-DP-1-SC-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 4 | 4 | Philip Halsey |  | Regular |  | LX1E | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-12 | 77367 | 12 | 1 | Regular | B4LED-2' | BBRLED-500-80-35-FL-2'-W-277-DP-1-TG15-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 1 | Philip Halsey |  | Regular |  | LL1E-2' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77367-13 | 77367 | 13 | 1 | Regular | B4LED-2' | BBRLED-500-80-35-FL-2'-W-277-DP-1-TG15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 1 | Philip Halsey |  | Regular |  | LL1-2' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77370-1 | 77370 | 1 | 1 | Regular | WB4LED-8' 0" | WBSLED-750-80-40-S-8' 0"-AP-UNV-BI-1-SC-DOS(EL20985) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 3 | 3 | Zahra Vatani |  | High Priority |  | LS-8'-0" | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77370-2 | 77370 | 2 | 1 | Regular | WDILED-WBDIWLED | SP000-WBDIWLED-1000-1000-80-40-SO-SO-10' 0"-AP-UNV-BI-1-DOS(1)-C(EL20985) | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 4 | Zahra Vatani |  | High Priority |  | LW-10'-0" | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
77375-1 | 77375 | 1 | 1 | Regular | B3PLED-15'0" | BMPRLED-750-90-35-RG2-15'0"-W-UNV-DP-1-TB9-TS(1) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 4 | Philip Halsey |  | Regular |  | L04-15' | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77375-2 | 77375 | 2 | 1 | Regular | B3PLED-21'0" | BMPRLED-750-90-35-RG2-21'0"-W-UNV-DP-1-TB9-TS(1) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 4 | Philip Halsey |  | Regular |  | L04-21' | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77375-3 | 77375 | 3 | 1 | Regular | B3PLED-23'0" | BMPRLED-750-90-35-RG2-23'0"-W-UNV-DP-1-TB9-TS(1) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 2 | Philip Halsey |  | Regular |  | L04-23' | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77375-5 | 77375 | 5 | 1 | Regular | B3PLED-7' 5" | BMPRLED-750-90-35-RG2-7' 5"-W-UNV-DP-1-TB9-TS(1)-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Philip Halsey |  | Regular |  | L04E 7.5' | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77375-6 | 77375 | 6 | 1 | Regular | B2SLED-95'0" | B2SQILED-1000-90-35-SL-95'0"-W-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 8 | Philip Halsey |  | Regular |  | L07 | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77375-7 | 77375 | 7 | 1 | Regular | B2LED-105'0" | BDLED-750-90-35-SO-105'0"-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 9 | Philip Halsey |  | Regular |  | L08 | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77375-8 | 77375 | 8 | 1 | Regular | TB2LED-3'5" | TB2WDILED-1100-1000-80-35-SLA-SO-3'5"-W-UNV-DP-1-B1(BSL10LST)-OS(1) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 8 | 8 | Philip Halsey |  | Regular |  | L09E-3.5 | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77378-1 | 77378 | 1 | 1 | Regular | B3LED-58' 1/2" | BMWILEDPAT-REC-90(4)-750-90-30-C-58' 1/2"-NL-W-UNV-DP-1 | Mechanical issue | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 10 | Sacha Lempka |  | Priority |  | SL1-8'X10' RECT | 12 | TRUE | TRUE | FALSE | TRUE |  | Ready | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77393-1 | 77393 | 1 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(24' 0"-400)-80-35-AG(5)-BLK-UNV-MD-1-CA(96)-RC | Others | Machine Shop Finished | 2019-01-29 | 10:11:32 | 2019-01-24 | 2019-01-29 | 1 | 6 | George Bacalla | Picked - Complete | Regular |  | F12-24'-0" | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77417-1 | 77417 | 1 | 1 | Regular | B3LED-34 | BMRLED-1000-80-30-FL-34-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Jessica Kennedy |  | Regular |  | RLR/F-L2 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77417-2 | 77417 | 2 | 1 | Regular | B3LED-32 | BMRLED-1000-80-30-FL-32-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 3 | Jessica Kennedy |  | Regular |  | RLR/F-L2 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77432-1 | 77432 | 1 | 1 | Regular | B2LED-4 | BRLED-400-80-35-FL-4-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 20 | 20 | Gagandeep Singh | Picked - Complete | High Priority |  | F22-4'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77432-2 | 77432 | 2 | 1 | Regular | B2LED-6 | BRLED-400-80-35-FL-6-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 16 | 16 | Gagandeep Singh | Picked - Complete | High Priority |  | F22A-6'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77432-3 | 77432 | 3 | 1 | Regular | B2LED-24'6" | BDLED-400-80-35-SO-24'6"-W-UNV-DP-1-CA(60) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 14 | 42 | Gagandeep Singh | Picked - Complete | High Priority |  | F27-24'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | TRUE | FALSE
77432-4 | 77432 | 4 | 1 | Regular | B2LED-6 | BRLED-750-80-35-FL-6' 0"-DMLED(2)-C(RAL#7004)-UNV-DP-2-D | Shortage | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 8 | 8 | Gagandeep Singh | Picked - Complete | High Priority |  | F44-6'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77432-5 | 77432 | 5 | 1 | Regular | B2LED-6 | BRLED-1000-80-35-FL-6' 0"-DMLED(2)-C(RAL#7004)-UNV-DP-2-D |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 6 | 6 | Gagandeep Singh | Picked - Complete | High Priority |  | F45-6'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77432-6 | 77432 | 6 | 1 | Regular | B2LED-8 | BRLED-750-80-35-FL-8-C(RAL#7004)-UNV-DP-1-D |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 4 | 4 | Gagandeep Singh | Picked - Complete | High Priority |  | F45A-8'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77432-7 | 77432 | 7 | 1 | Regular | SLMLED-8 | SLWLED-SL 75/25-800-80-35-VL-8' 0"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-13 | 26 | 26 | Gagandeep Singh | Picked - Complete | High Priority |  | F50-8'-0" | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77440-1 | 77440 | 1 | 1 | Regular | STENCL-STFC | STFC-I(6-175)-DSO(12-400)-80-35-AH(6)-W-UNV-MD-1-CA(36)-RC | Wrong part in BOM | Wiring Started | 2019-01-29 | 16:37:31 | 2019-01-29 | 2019-02-01 | 2 | 12 | Sacha Lempka | Picked - Complete | Regular |  |  | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 09:39 |  | TRUE | TRUE
77441-1 | 77441 | 1 | 1 | Regular | SKVLED-22 | SKVLED-22-1800-80-35-2XVL-FL-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-05 | 2019-03-08 | 40 | 40 | Gagandeep Singh |  | Regular |  | F5/6 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77441-2 | 77441 | 2 | 1 | Regular | SKVLED-22 | SKVLED-22-1800-80-35-2XVL-FL-W-UNV-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-03-05 | 2019-03-08 | 20 | 20 | Gagandeep Singh |  | Regular |  | F5/7 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-1 | 77456 | 1 | 1 | Regular | B6LED-2' 0" | B6RLED-1000-90-35-FL-2' 0"-W-UNV-DP-1-DB | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Stan Buyansky |  | Regular |  | AF-2 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
77456-2 | 77456 | 2 | 1 | Regular | B6LED-10' 0" | B6RLED-1000-90-35-FL-10' 0"-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 1 | Stan Buyansky |  | Regular |  | A-10 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-3 | 77456 | 3 | 1 | Regular | B6LED-16' 0" | B6RLED-1000-90-35-FL-16' 0"-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 2 | Stan Buyansky |  | Regular |  | A-16 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-4 | 77456 | 4 | 1 | Regular | B6LED-4' 0" | B6RLED-1000-90-35-FL-4' 0"-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 10 | 10 | Stan Buyansky |  | Regular |  | A1-4 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-5 | 77456 | 5 | 1 | Regular | B6LED-4' 0" | B6RLED-1000-90-35-FL-4' 0"-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 2 | 2 | Stan Buyansky |  | Regular |  | A1F-4 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-6 | 77456 | 6 | 1 | Regular | B6LED-8' 0" | B6RLED-1000-90-35-FL-8' 0"-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Stan Buyansky |  | Regular |  | A2-8 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-7 | 77456 | 7 | 1 | Regular | B6LED-8' 0" | B6RLED-1000-90-35-FL-8' 0"-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Stan Buyansky |  | Regular |  | A2F-8 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-8 | 77456 | 8 | 1 | Regular | B6LED-8' 0" | B6RLED-1000-90-35-FL-8' 0"-W-UNV-DP-1+E(1)-DB |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 1 | Stan Buyansky |  | Regular |  | A2FE-8 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-12 | 77456 | 12 | 1 | Regular | B6LED-12' | B6RLED-1000-90-35-FL-12'-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 3 | 3 | Stan Buyansky |  | Regular |  | A3-12 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-13 | 77456 | 13 | 1 | Regular | B6LED-12' | B6RLED-1000-90-35-FL-12'-W-UNV-DP-1+E(1)-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 2 | 2 | Stan Buyansky |  | Regular |  | A3E-12 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77456-14 | 77456 | 14 | 1 | Regular | B6LED-12' | B6RLED-1000-90-35-FL-12'-W-UNV-DP-1-DB |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 2 | 2 | Stan Buyansky |  | Regular |  | A3F-12 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77458-1 | 77458 | 1 | 1 | Regular | B4LED-352' 0" | SP18482(1)-BBRLEDPAT-OPR-90(2)-400-80-40-ASO-352' 0"-NL-W-UNV-DP-1+E(13)-DF |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 34 | Joshua Zimet |  | Regular |  | F8-352'-0" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77479-1 | 77479 | 1 | 1 | Regular | B3LED-12' 0" | BMRLED-700-80-40-FL-12' 0"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-04-10 | 2019-04-15 | 1 | 1 | Gagandeep Singh |  | Regular |  | A-12'-0" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77497-11 | 77497 | 11 | 1 | Regular | SKLPTP-170" | SCPLED-OPRI(1)-300-90-35-RG2-170"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-28 | 2019-03-05 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F8-105"X65"-44-27 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77497-12 | 77497 | 12 | 1 | Regular | SKLPTP-168" | SCPLED-OPRI(1)-300-90-35-RG2-168"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-28 | 2019-03-05 | 1 | 3 | Gagandeep Singh |  | High Priority |  | F8-89"X79"-44-46 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-1 | 77526 | 1 | 1 | Regular | SCULPT-4' 0" | SCD-500-80-35-2P-4' 0"-W-UNV-DP-1-CA(60) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Sacha Lempka |  | High Priority |  | LP4-4'-0" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-2 | 77526 | 2 | 1 | Regular | SCULPT-8' 0" | SCD-500-80-35-2P-8' 0"-W-UNV-DP-1-CA(60) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 22 | 22 | Sacha Lempka |  | High Priority |  | LP8-8'-0" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-3 | 77526 | 3 | 1 | Regular | SCULPT-16' 0" | SCD-500-80-35-2P-16' 0"-W-UNV-DP-1-CA(60) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 8 | 16 | Sacha Lempka |  | High Priority |  | LP16-16'-0" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-4 | 77526 | 4 | 1 | Regular | SCULPT-16' 0" | SCD-500-80-35-2P-16' 0"-W-UNV-DP-1-CA(60)-DS(1) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 4 | 8 | Sacha Lempka |  | High Priority |  | LP16P-16'-0" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-5 | 77526 | 5 | 1 | Regular | B4LED-4' 0" | BBRLED-750-80-35-FL-4' 0"-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Sacha Lempka |  | High Priority |  | LR4-4'-0" | 4 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-6 | 77526 | 6 | 1 | Regular | B4LED-6' 0" | BBRLED-750-80-35-FL-6' 0"-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 40 | 40 | Sacha Lempka |  | High Priority |  | LR6-6'-0" | 4 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-7 | 77526 | 7 | 1 | Regular | B4LED-8' 0" | BBRLED-750-80-35-FL-8' 0"-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 3 | 3 | Sacha Lempka |  | High Priority |  | LR8-8'-0" | 4 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-8 | 77526 | 8 | 1 | Regular | B4LED-12' 0" | BBRLED-750-80-35-FL-12' 0"-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Sacha Lempka |  | High Priority |  | LR12-12'-0" | 4 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77526-9 | 77526 | 9 | 1 | Regular | TB2LED-4' 0" | TB2DLED-1000-80-35-SO-4' 0"-W-UNV-DP-1-CA(96) | Shortage | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 65 | 65 | Sacha Lempka |  | High Priority |  | PL4-4'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-10 | 77526 | 10 | 1 | Regular | TB2LED-4' 0" | TB2DLED-1000-80-35-SO-4' 0"-W-UNV-DP-1-CA(96)-DS(1) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 9 | 9 | Sacha Lempka |  | High Priority |  | PL4P-4'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-11 | 77526 | 11 | 1 | Regular | TB2LED-6' 0" | TB2DLED-1000-80-35-SO-6' 0"-W-UNV-DP-1-CA(96) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 10 | 10 | Sacha Lempka |  | High Priority |  | PL6-6'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-12 | 77526 | 12 | 1 | Regular | TB2LED-8' 0" | TB2DLED-1000-80-35-SO-8' 0"-W-UNV-DP-1-CA(96) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 24 | 24 | Sacha Lempka |  | High Priority |  | PL8-8'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-13 | 77526 | 13 | 1 | Regular | TB2LED-8' 0" | TB2DLED-1000-80-35-SO-8' 0"-W-UNV-DP-1-CA(96)-DS(1) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 11 | 11 | Sacha Lempka |  | High Priority |  | PL8P-8'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-14 | 77526 | 14 | 1 | Regular | TB2LED-16' 0" | TB2DLED-1000-80-35-SO-16' 0"-W-UNV-DP-1-CA(96) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 4 | Sacha Lempka |  | High Priority |  | PL16-16'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-15 | 77526 | 15 | 1 | Regular | TB2LED-16' 0" | TB2DLED-1000-80-35-SO-16' 0"-W-UNV-DP-1-CA(96)-DS(1) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Sacha Lempka |  | High Priority |  | PL16P-16'-0" | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77526-16 | 77526 | 16 | 1 | Regular | AIRLED-4' 0" | ARWLED-750-80-35-S-4' 0"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 9 | 9 | Sacha Lempka |  | High Priority |  | V4-4'-0" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77560-1 | 77560 | 1 | 1 | Regular | WB4LED-8' 0" | WBWLED-750-80-40-S-8' 0"-BLK-UNV-DP-1 | Others | Machine Shop Finished | 2019-01-23 | 21:02:39 | 2019-02-01 | 2019-02-06 | 12 | 12 | George Bacalla |  | Regular |  | W2-8'-0" | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-29 07:11 |  | TRUE | TRUE
77607-1 | 77607 | 1 | 1 | Regular | B2SLED-19 | B2SQDLED-750-90-35-SO-19-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-27 | 14:09:35 | 2019-02-05 | 2019-02-08 | 1 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K19 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77607-2 | 77607 | 2 | 1 | Regular | B2SLED-21 | B2SQDLED-750-90-35-SO-21-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-27 | 14:09:32 | 2019-02-05 | 2019-02-08 | 1 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K21 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77607-3 | 77607 | 3 | 1 | Regular | B2SLED-35 | B2SQDLED-750-90-35-SO-35-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-27 | 14:09:30 | 2019-02-05 | 2019-02-08 | 1 | 3 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K35 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77607-4 | 77607 | 4 | 1 | Regular | B2SLED-38 | B2SQDLED-750-90-35-SO-38-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-27 | 14:09:28 | 2019-02-05 | 2019-02-08 | 3 | 12 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | K38 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77607-5 | 77607 | 5 | 1 | Regular | B2LED-41 | BRLEDPAT-OPR-90(1)-1000-90-35-SO-FL-41-NL-W-120-DP-1-DS-C(L-SHAPE PATTERN, 15'H X 26'W) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 3 | 15 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | N1 | 4 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77607-6 | 77607 | 6 | 1 | Regular | B2SLED-4 | B2SQDLED-1000-90-35-SO-4-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-27 | 14:09:25 | 2019-02-05 | 2019-02-08 | 36 | 36 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | P | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77608-1 | 77608 | 1 | 1 | Regular | SCULPT-SCML | SCML-6-SO-300-SO-500-MLA(6)-500-W-80-35-W-UNV-DP-1-CA(36) | Others | Machine Shop Finished | 2019-01-29 | 14:55:59 | 2019-01-28 | 2019-01-31 | 3 | 3 | Zahra Vatani | Picked - Complete | High Priority |  |  | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77611-3 | 77611 | 3 | 1 | Regular | STENCL-12' | STFDI-I-500-DSO-400-12'-80-35-AH(6)-AP-UNV-DP-2-CA(48)-RC | Shortage | Wiring Started | 2019-01-24 | 10:03:58 | 2019-01-18 | 2019-01-23 | 2 | 12 | Stan Buyansky | Picked - Complete | High Priority |  | F6 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | [5 empty] | TRUE |  | Done | TRUE | 2019-01-25 10:28 |  | TRUE | TRUE
77615-1 | 77615 | 1 | 1 | Regular | TB2LED-12 | TB2DILED-600-500-80-35-SO-SO-12-W-277-DP-1-CT9(36) |  | Machine Shop Finished | 2019-01-31 | 09:54:09 | 2019-02-08 | 2019-02-07 | 5 | 5 | Jessica Kennedy | Picked - Complete | Regular |  | A1-12' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77615-2 | 77615 | 2 | 1 | Regular | TB2LED-16 | TB2DILED-600-500-80-35-SO-SO-16-W-277-DP-1-CT9(36) |  | Machine Shop Finished | 2019-01-31 | 09:54:11 | 2019-02-08 | 2019-02-07 | 8 | 16 | Jessica Kennedy | Picked - Complete | Regular |  | A1-16' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77615-3 | 77615 | 3 | 1 | Regular | TB2LED-20 | TB2DILED-600-500-80-35-SO-SO-20-W-277-DP-1-CT9(36) |  | Machine Shop Finished | 2019-01-31 | 12:36:37 | 2019-02-08 | 2019-02-07 | 6 | 12 | Jessica Kennedy | Picked - Complete | Regular |  | A1-20' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77615-4 | 77615 | 4 | 1 | Regular | CLICK-6 | CLKLED-500-80-35-SO-6-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 94 | 94 | Jessica Kennedy | Picked - Complete | Regular |  | B1-6' | 4 | TRUE | TRUE | TRUE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-5 | 77615 | 5 | 1 | Regular | B4LED-4 | BBRLED-500-80-35-FL-4-W-277-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 25 | 25 | Jessica Kennedy | Picked - Complete | Regular |  | B1-4' | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [6 empty] | ToDo |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-6 | 77615 | 6 | 1 | Regular | B4LED-8 | BBRLED-500-80-35-FL-8-W-277-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 7 | 7 | Jessica Kennedy | Picked - Complete | Regular |  | B1-8' | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [6 empty] | ToDo |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-7 | 77615 | 7 | 1 | Regular | B4LED-12 | BBRLED-500-80-35-FL-12-W-277-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 10 | 10 | Jessica Kennedy | Picked - Complete | Regular |  | B1-12' | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [6 empty] | ToDo |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-8 | 77615 | 8 | 1 | Regular | B4LED-16 | BBRLED-500-80-35-FL-16-W-277-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 3 | 6 | Jessica Kennedy | Picked - Complete | Regular |  | B1-16' | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [6 empty] | ToDo |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-9 | 77615 | 9 | 1 | Regular | B4LED-20 | BBRLED-500-80-35-FL-20-W-277-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 5 | 10 | Jessica Kennedy | Picked - Complete | Regular |  | B1-20' | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [6 empty] | ToDo |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-10 | 77615 | 10 | 1 | Regular | B4LED-24 | BBRLED-500-80-35-FL-24-W-277-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 1 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | B1-24' | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [6 empty] | ToDo |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77615-11 | 77615 | 11 | 1 | Regular | PRMLED-4 | PWWLED-800-90-35-S-4-W-277-DP-1 |  | Machine Shop Finished | 2019-01-31 | 09:51:23 | 2019-02-08 | 2019-02-07 | 17 | 17 | Jessica Kennedy | Picked - Complete | Regular |  | S1 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77615-12 | 77615 | 12 | 1 | Regular | PRMLED-4 | PWWLED-800-90-35-S-4-W-UNV-DP-1 |  | Machine Shop Finished | 2019-01-31 | 09:51:58 | 2019-02-08 | 2019-02-07 | 8 | 8 | Jessica Kennedy | Picked - Complete | Regular |  | S2 | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
77615-13 | 77615 | 13 | 1 | Regular | WB4LED-6 | WBRLED-500-80-35-S-6-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-07 | 12 | 12 | Jessica Kennedy | Picked - Complete | Regular |  | X4-6' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | TRUE | FALSE
77630-1 | 77630 | 1 | 1 | Regular | SCULPT-TR45X2 | SCR-300-80-35-FL-TR45X2-W-UNV-DP-1-MFTB15 |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 3 | 3 | George Bacalla | Picked - Complete | High Priority |  | L09 | 18 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77630-2 | 77630 | 2 | 1 | Regular | AIRLED-4 | ARLED-500-80-35-S-4-AP-UNV-DP-1-CTS(210) |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 3 | 3 | George Bacalla | Picked - Complete | High Priority |  | L08 | 18 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77630-3 | 77630 | 3 | 1 | Regular | AIRLED-4 | ARLED-500-80-35-S-4-AP-UNV-DP-1-CA(210) |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 3 | 3 | George Bacalla | Picked - Complete | High Priority |  | L08-DRY | 18 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-1 | 77636 | 1 | 1 | Regular | SCULPT-2' | SCR-500-80-30-FL-2'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 5 | 5 | Jessica Kennedy |  | Regular |  | T-RB8 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-2 | 77636 | 2 | 1 | Regular | SCULPT-4' | SCR-400-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 8 | 8 | Jessica Kennedy |  | Regular |  | T-RB18A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-3 | 77636 | 3 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 97 | 97 | Jessica Kennedy |  | Regular |  | T-RB22 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-4 | 77636 | 4 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 32 | 32 | Jessica Kennedy |  | Regular |  | T-RB22-TG | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-5 | 77636 | 5 | 1 | Regular | SCULPT-4' | SCR-500-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 7 | 7 | Jessica Kennedy |  | Regular |  | T-RB22A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-6 | 77636 | 6 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-C(RAL9006)-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 8 | 8 | Jessica Kennedy |  | Regular |  | T-RB22F | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-7 | 77636 | 7 | 1 | Regular | SCULPT-6' | SCR-400-80-30-FL-6'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | T-RB26 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-8 | 77636 | 8 | 1 | Regular | SCULPT-6' | SCR-400-80-30-0.5M-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 4 | 4 | Jessica Kennedy |  | Regular |  | T-RB26A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-9 | 77636 | 9 | 1 | Regular | SCULPT-6' | SCR-500-80-30-FL-6'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 24 | 24 | Jessica Kennedy |  | Regular |  | T-RB33 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-10 | 77636 | 10 | 1 | Regular | SCULPT-6' | SCR-500-80-30-FL-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 16 | 16 | Jessica Kennedy |  | Regular |  | T-RB33-TG | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-11 | 77636 | 11 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 1 | Jessica Kennedy |  | Regular |  | T-RB35 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-12 | 77636 | 12 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 5 | 5 | Jessica Kennedy |  | Regular |  | T-RB44 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-14 | 77636 | 14 | 1 | Regular | B4LED-6 | BBRLED-400-80-30-FL-6-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | T-RJ22 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-16 | 77636 | 16 | 1 | Regular | SCULPT-2' | SCR-500-80-30-FL-2'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 5 | 5 | Jessica Kennedy |  | Regular |  | P-RB8 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-17 | 77636 | 17 | 1 | Regular | SCULPT-4' | SCR-400-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 8 | 8 | Jessica Kennedy |  | Regular |  | P-RB18A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-18 | 77636 | 18 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 99 | 99 | Jessica Kennedy |  | Regular |  | P-RB22 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-19 | 77636 | 19 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 30 | 30 | Jessica Kennedy |  | Regular |  | P-RB22-TG | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-20 | 77636 | 20 | 1 | Regular | SCULPT-4' | SCR-500-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 1 | Jessica Kennedy |  | Regular |  | P-RB22A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-21 | 77636 | 21 | 1 | Regular | SCULPT-4' | SCR-500-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | P-RB22A-TG | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-22 | 77636 | 22 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-C(RAL9006)-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 8 | 8 | Jessica Kennedy |  | Regular |  | P-RB22F | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-23 | 77636 | 23 | 1 | Regular | SCULPT-6' | SCR-400-80-30-FL-6'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | P-RB26 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-24 | 77636 | 24 | 1 | Regular | SCULPT-6' | SCR-400-80-30-0.5M-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 4 | 4 | Jessica Kennedy |  | Regular |  | P-RB26A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-25 | 77636 | 25 | 1 | Regular | SCULPT-6' | SCR-500-80-30-FL-6'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 24 | 24 | Jessica Kennedy |  | Regular |  | P-RB33 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-26 | 77636 | 26 | 1 | Regular | SCULPT-6' | SCR-500-80-30-FL-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 16 | 16 | Jessica Kennedy |  | Regular |  | P-RB33-TG | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-27 | 77636 | 27 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 1 | Jessica Kennedy |  | Regular |  | P-RB35 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-28 | 77636 | 28 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 5 | 5 | Jessica Kennedy |  | Regular |  | P-RB44 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-30 | 77636 | 30 | 1 | Regular | B4LED-6 | BBRLED-400-80-30-FL-6-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | P-RJ22 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-32 | 77636 | 32 | 1 | Regular | SCULPT-2' | SCR-500-80-30-FL-2'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 5 | 5 | Jessica Kennedy |  | Regular |  | B-RB8 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-33 | 77636 | 33 | 1 | Regular | SCULPT-4' | SCR-400-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 8 | 8 | Jessica Kennedy |  | Regular |  | B-RB18A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-34 | 77636 | 34 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 97 | 97 | Jessica Kennedy |  | Regular |  | B-RB22 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-35 | 77636 | 35 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 32 | 32 | Jessica Kennedy |  | Regular |  | B-RB22-TG | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-36 | 77636 | 36 | 1 | Regular | SCULPT-4' | SCR-500-80-30-0.5M-4'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 7 | 7 | Jessica Kennedy |  | Regular |  | B-RB22A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-37 | 77636 | 37 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-C(RAL9006)-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-01 | 2019-03-06 | 8 | 8 | Jessica Kennedy |  | Regular |  | B-RB22F | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-38 | 77636 | 38 | 1 | Regular | SCULPT-6' | SCR-400-80-30-FL-6'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | B-RB26 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-39 | 77636 | 39 | 1 | Regular | SCULPT-6' | SCR-400-80-30-0.5M-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 2 | 2 | Jessica Kennedy |  | Regular |  | B-RB26A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-40 | 77636 | 40 | 1 | Regular | SCULPT-6' | SCR-400-80-30-0.5M-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 4 | 4 | Jessica Kennedy |  | Regular |  | B-RB26A-TG | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-41 | 77636 | 41 | 1 | Regular | SCULPT-6' | SCR-500-80-30-FL-6'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 25 | 25 | Jessica Kennedy |  | Regular |  | B-RB33 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-42 | 77636 | 42 | 1 | Regular | SCULPT-6' | SCR-500-80-30-FL-6'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 15 | 15 | Jessica Kennedy |  | Regular |  | B-RB33-TG | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-43 | 77636 | 43 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-120-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 1 | 1 | Jessica Kennedy |  | Regular |  | B-RB35 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-44 | 77636 | 44 | 1 | Regular | SCULPT-8' | SCR-500-80-30-FL-8'-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 5 | 5 | Jessica Kennedy |  | Regular |  | B-RB44 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77636-46 | 77636 | 46 | 1 | Regular | B4LED-6 | BBRLED-400-80-30-FL-6-W-120-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-21 | 2019-02-26 | 6 | 6 | Jessica Kennedy |  | Regular |  | B-RJ22 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77693-1 | 77693 | 1 | 1 | Regular | SCULPT-4'0" | SCD-500-80-40-FL-4'0"-BLK-UNV-DP-1-CA(12) |  | Machine Shop Finished | 2019-01-29 | 21:57:40 | 2019-01-31 | 2019-02-05 | 13 | 13 | Philip Halsey |  | Regular |  | LT2A | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-2 | 77693 | 2 | 1 | Regular | SCULPT-6'0" | SCD-500-80-40-FL-6'0"-BLK-UNV-DP-1-CA(12) |  | Machine Shop Finished | 2019-01-29 | 21:57:42 | 2019-01-31 | 2019-02-05 | 3 | 3 | Philip Halsey |  | Regular |  | LT2B | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-3 | 77693 | 3 | 1 | Regular | SCULPT-8'0" | SCD-500-80-40-FL-8'0"-BLK-UNV-DP-1-CA(12) |  | Machine Shop Finished | 2019-01-29 | 21:57:43 | 2019-01-31 | 2019-02-05 | 6 | 6 | Philip Halsey |  | Regular |  | LT2C | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-4 | 77693 | 4 | 1 | Regular | AIRLED-4'0" | ARLED-800-80-35-S-4'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-30 | 21:57:44 | 2019-01-31 | 2019-02-05 | 8 | 8 | Philip Halsey |  | Regular |  | LT3 | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-5 | 77693 | 5 | 1 | Regular | SCULPT-4'0" | SCDI-500-300-80-40-SO-0.5M-4'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-29 | 21:57:45 | 2019-01-31 | 2019-02-05 | 7 | 7 | Philip Halsey |  | Regular |  | LT11A | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-6 | 77693 | 6 | 1 | Regular | SCULPT-6'0" | SCDI-500-300-80-40-SO-0.5M-6'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-29 | 21:57:45 | 2019-01-31 | 2019-02-05 | 2 | 2 | Philip Halsey |  | Regular |  | LT11B | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-7 | 77693 | 7 | 1 | Regular | SCULPT-8'0" | SCDI-500-300-80-40-SO-0.5M-8'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-29 | 21:57:46 | 2019-01-31 | 2019-02-05 | 5 | 5 | Philip Halsey |  | Regular |  | LT11C | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-8 | 77693 | 8 | 1 | Regular | SCULPT-4'0" | SCDI-500-300-80-40-SO-FL-4'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-29 | 21:57:47 | 2019-01-31 | 2019-02-05 | 30 | 30 | Philip Halsey |  | Regular |  | LT12A | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-9 | 77693 | 9 | 1 | Regular | SCULPT-6'0" | SCDI-500-300-80-40-SO-FL-6'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-29 | 21:57:51 | 2019-01-31 | 2019-02-05 | 20 | 20 | Philip Halsey |  | Regular |  | LT12B | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-10 | 77693 | 10 | 1 | Regular | SCULPT-8'0" | SCDI-500-300-80-40-SO-FL-8'0"-BLK-UNV-DP-1-CA(48) |  | Machine Shop Finished | 2019-01-29 | 21:57:49 | 2019-01-31 | 2019-02-05 | 12 | 12 | Philip Halsey |  | Regular |  | LT12C | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77693-11 | 77693 | 11 | 1 | Regular | SCULPT-4'0" | SCD-500-80-40-FL-4'0"-BLK-UNV-DP-1-CA(12) |  | Machine Shop Finished | 2019-01-29 | 21:58:01 | 2019-01-31 | 2019-02-05 | 5 | 5 | Philip Halsey |  | Regular |  | LT12D | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 17:14 |  | TRUE | FALSE
77741-5 | 77741 | 5 | 1 | Regular | B3LED-4' | BMWDLED-750-80-30-ASO-4'-W-UNV-DP-1 |  | Machine Shop Finished | 2019-01-30 | 16:51:53 | 2019-01-31 | 2019-02-05 | 3 | 3 | Jessica Pasternyk |  | Regular |  | W5-4' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | Ready | [7 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-6 | 77741 | 6 | 1 | Regular | B3LED-5' | BMWDLED-750-80-30-ASO-5'-W-UNV-DP-1 |  | Machine Shop Finished | 2019-01-30 | 16:52:03 | 2019-01-31 | 2019-02-05 | 2 | 2 | Jessica Pasternyk |  | Regular |  | W5-5' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | Ready | [7 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-8 | 77741 | 8 | 1 | Regular | SCULPT-12' | SCSPAT-OPR-90(2)-500-80-30-FL-12'-NL-W-UNV-BI-1-SC |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Jessica Pasternyk |  | Regular |  | G1-4.5-4'X4'X4' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77741-9 | 77741 | 9 | 1 | Regular | SCULPT-12' | SCSPAT-OPR-90(1)-500-80-30-FL-12'-NL-W-UNV-BI-1-SC |  | Machine Shop Finished | 2019-02-04 | 02:38:12 | 2019-01-31 | 2019-02-05 | 1 | 3 | Jessica Pasternyk |  | Regular |  | G1-L-6'X6' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-10 | 77741 | 10 | 1 | Regular | SCULPT-16 | SCRPAT-OPR-90(2)-500-80-30-FL-15' 1-3/4-NL-W-UNV-BI-1-DS | Wrong info. In SD | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 2 | Jessica Pasternyk | Picked - Complete | Regular |  | G2-1.66 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | TRUE
77741-11 | 77741 | 11 | 1 | Regular | SCULPT-12 | SCRPAT-OPR-90(2)-500-80-30-FL-11' 2-1/2-NL-W-UNV-BI-1-DS |  | Machine Shop Finished | 2019-02-04 | 09:40:45 | 2019-01-31 | 2019-02-05 | 1 | 1 | Jessica Pasternyk | Picked - Complete | Regular |  | G2-2.33 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-12 | 77741 | 12 | 1 | Regular | SCULPT-12 | SCRPAT-OPR-90(2)-500-80-30-FL-10' 9-1/2-NL-W-UNV-BI-1-DS |  | Machine Shop Finished | 2019-02-04 | 09:40:51 | 2019-01-31 | 2019-02-05 | 1 | 1 | Jessica Pasternyk | Picked - Complete | Regular |  | G2-2.66 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-13 | 77741 | 13 | 1 | Regular | SCULPT-12 | SCRPAT-OPR-90(2)-500-80-30-FL-12'1-1/2-NL-W-UNV-BI-1-DS |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 2 | Jessica Pasternyk | Picked - Complete | Regular |  | G2-3.33 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77741-15 | 77741 | 15 | 1 | Regular | SCULPT-5 | SCR-500-80-30-FL-4'2"-W-UNV-BI-1-DS |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Jessica Pasternyk | Picked - Complete | Regular |  | G2-5' | 1 | TRUE | TRUE | TRUE | TRUE |  | ToDo | [6 empty] | Ready |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77741-17 | 77741 | 17 | 1 | Regular | SCULPT-30 | SCR-500-80-30-FL-30-W-UNV-BI-1-DS |  | Machine Shop Finished | 2019-01-25 | 13:31:15 | 2019-01-31 | 2019-02-05 | 1 | 3 | Jessica Pasternyk |  | Regular |  | G2-30' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-18 | 77741 | 18 | 1 | Regular | SCULPT-4' | SCS-500-80-30-FL-4'-W-UNV-BI-1-SC |  | Machine Shop Finished | 2019-01-25 | 14:40:50 | 2019-01-31 | 2019-02-05 | 5 | 5 | Jessica Pasternyk |  | Regular |  | G1-4' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77741-19 | 77741 | 19 | 1 | Regular | SCULPT-8' | SCS-500-80-30-FL-8'-W-UNV-BI-1-SC |  | Machine Shop Finished | 2019-01-24 | 14:41:06 | 2019-01-31 | 2019-02-05 | 2 | 2 | Jessica Pasternyk |  | Regular |  | G1-8' | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77765-1 | 77765 | 1 | 1 | Regular | SCULPT-9'0" | SCRPAT-OPI-90(1)-300-80-30-FL-9'0"-NL-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 8 | 16 | Philip Halsey | Picked - Complete | Regular |  | D | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77765-2 | 77765 | 2 | 1 | Regular | SCULPT-26'4" | SCRPAT-OPI-90(2)-500-80-30-FL-26'4"-NL-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 5 | Philip Halsey | Picked - Complete | Regular |  | D-10 | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77765-4 | 77765 | 4 | 1 | Regular | AULED-22 | AULED-22-3000-80-30-SO-W-UNV-DP-1-TB9-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Philip Halsey |  | Regular |  | EE | 10 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77765-5 | 77765 | 5 | 1 | Regular | SCULPT-6'10" | SCD-300-80-30-FL-6'10"-BLK-UNV-DP-1-CTS(48) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 4 | 4 | Philip Halsey | Picked - Complete | Regular |  | H-7 | 1 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77765-22 | 77765 | 22 | 1 | Regular | SCULPT-26'4" | SCRPAT-OPI-90(2)-500-80-30-FL-26'4"-NL-W-UNV-DP-1-DS | Missing info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 5 | Philip Halsey | Picked - Complete | Regular |  | D-10S | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | TRUE
77784-1 | 77784 | 1 | 1 | Regular | B3LED-12' | BMRLED-700-80-40-FL-12'-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-03-12 | 2019-03-15 | 1 | 1 | Gagandeep Singh |  | Regular |  | A-12' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-1 | 77790 | 1 | 1 | Regular | DIALED-22 | DIALED-22-4700-80-35-VL-W-277-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 180 | 180 | Stan Buyansky |  | Regular |  | LR1 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-2 | 77790 | 2 | 1 | Regular | WB4LED-4 | WBRLED-750-80-35-S-4-C(RAL#7037)-UNV-DP-1-DF-C(TF) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 15 | 15 | Stan Buyansky |  | Regular |  | LR5 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-3 | 77790 | 3 | 1 | Regular | B3LED-12' | BMRLED-1000-80-35-ASO-12'-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 2 | Stan Buyansky |  | Regular |  | LR7-12 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-4 | 77790 | 4 | 1 | Regular | B4LED-4 | BBRLED-1000-80-35-FL-4-W-277-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 4 | 4 | Stan Buyansky |  | Regular |  | LR8-4 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-5 | 77790 | 5 | 1 | Regular | B4LED-6 | BBRLED-1000-80-35-FL-6-W-277-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 2 | Stan Buyansky |  | Regular |  | LR8-6 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-6 | 77790 | 6 | 1 | Regular | B4LED-8 | BBRLED-1000-80-35-FL-8-W-277-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 10 | 10 | Stan Buyansky |  | Regular |  | LR8-8 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-7 | 77790 | 7 | 1 | Regular | B4LED-16 | BBRLED-1000-80-35-FL-16-W-277-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 3 | 6 | Stan Buyansky |  | Regular |  | LR4-16 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77790-8 | 77790 | 8 | 1 | Regular | B4LED-22 | BBRLED-1000-80-35-FL-22-W-277-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 2 | Stan Buyansky |  | Regular |  | LR4-22 | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-14 | 77793 | 14 | 1 | Regular | B4LED-27' 1" | BBRLED-750-90-40-1.5M-27' 1"-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 0 | Rajithan Sivapatharajahon |  | High Priority |  | R3-27'1" | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-22 | 77793 | 22 | 1 | Regular | B4LED-78' 2 3/8" | BBDILED-640-400-90-40-SO-78' 2 3/8"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 14 | Rajithan Sivapatharajahon |  | High Priority |  | L1-78' 2 3/8" | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-23 | 77793 | 23 | 1 | Regular | B4LED-78' 1.5" | BBDILED-640-400-90-40-SO-78' 1.5"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 14 | Rajithan Sivapatharajahon |  | High Priority |  | L1-78'1 1/2" | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-26 | 77793 | 26 | 1 | Regular | B4LED-96' 3/4" | BBDILED-640-400-90-40-SO-96' 3/4"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 17 | Rajithan Sivapatharajahon |  | High Priority |  | L1 96'-3/4" (11TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-30 | 77793 | 30 | 1 | Regular | B4LED-233' 8" | BBDILED-640-400-90-40-SO-233' 8"-W-UNV-DP-4-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 39 | Rajithan Sivapatharajahon |  | High Priority |  | L1 233'-8" (11TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-31 | 77793 | 31 | 1 | Regular | B4LED-234' 6 1/2" | BBDILED-640-400-90-40-SO-234' 6 1/2"-W-UNV-DP-4-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 40 | Rajithan Sivapatharajahon |  | High Priority |  | L1 234' 6-1/2" (10TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-33 | 77793 | 33 | 1 | Regular | B4LED-70' 4 1/2" | BBDILED-640-400-90-40-SO-70' 4 1/2"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 12 | Rajithan Sivapatharajahon |  | High Priority |  | L1 70' 4-1/2" (11TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-34 | 77793 | 34 | 1 | Regular | B4LED-70' 6" | BBDILED-640-400-90-40-SO-70' 6"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 12 | Rajithan Sivapatharajahon |  | High Priority |  | L1 70'-6" (11TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-35 | 77793 | 35 | 1 | Regular | B4LED-70' 2 1/2" | BBDILED-640-400-90-40-SO-70' 2 1/2"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 12 | Rajithan Sivapatharajahon |  | High Priority |  | L1 70' 2-1/2" (10TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-36 | 77793 | 36 | 1 | Regular | B4LED-68' 11 1/2" | BBDILED-640-400-90-40-SO-68' 11 1/2"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 12 | Rajithan Sivapatharajahon |  | High Priority |  | L1 68' 11-1/2" (10TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77793-37 | 77793 | 37 | 1 | Regular | B4LED-96' 8 7/8" | BBDILED-640-400-90-40-SO-96' 8 7/8"-W-UNV-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 17 | Rajithan Sivapatharajahon |  | High Priority |  | L1 96' 8-7/8" (10TH FLOOR) | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77806-1 | 77806 | 1 | 1 | Regular | STNCLS-5 | STSLF-SO-400-90-35-5-AP-120-MD-1-SB9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 3 | Sacha Lempka | Picked - Complete | Priority |  | B1 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77808-1 | 77808 | 1 | 1 | Regular | PRMLED-4 | PWSLED-1000-90-35-S-4-W-120-DP-1-SB15 |  | Wiring Started | 2019-01-30 | 07:58:09 | 2019-01-30 | 2019-02-04 | 15 | 15 | Sacha Lempka | Picked - Complete | Regular |  | L6-L6A | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 09:20 |  | TRUE | FALSE
77808-2 | 77808 | 2 | 1 | Regular | PRMLED-4 | PWSLED-1000-90-35-S-4-W-120-DP-1-S |  | Wiring Started | 2019-01-31 | 21:23:35 | 2019-01-30 | 2019-02-04 | 3 | 3 | Sacha Lempka | Picked - Complete | Regular |  | L6-S | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 09:20 |  | TRUE | FALSE
77833-1 | 77833 | 1 | 1 | Regular | WWPRFK-4 | WWR-SL-750-90-40-4-W-UNV-DP-1-TG15-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 4 | 4 | Christina Torok |  | Regular |  | R4 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77833-2 | 77833 | 2 | 1 | Regular | WWPRFK-8 | WWR-SL-750-90-40-8-W-UNV-DP-1-TG15-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 2 | Christina Torok |  | Regular |  | R5 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77848-1 | 77848 | 1 | 1 | Regular | SCULPT-94 1/4" | SP18276-SCRPAT-OPR-103°+77°-350-80-35-FL-94 1/4"-EX-W-UNV-DP-1-DS | Shortage | Given to Shipping | 2019-01-25 | 14:49:49 | 2019-01-22 | 2019-01-25 | 1 | 1 | Gagandeep Singh | Picked - Complete | High Priority |  | F10-#14-4TH FL | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 15:20 |  | FALSE | TRUE
77848-2 | 77848 | 2 | 1 | Regular | SCULPT-104 3/32" | SP18276-SCRPAT-OPR-99.60°+80.40°-350-80-35-FL-104 3/32"-EX-W-UNV-DP-1-DS | Others | Given to Shipping | 2019-01-27 | 13:13:17 | 2019-01-22 | 2019-01-25 | 1 | 1 | Gagandeep Singh | Picked - Complete | High Priority |  | F10-#6-4TH FL | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 15:20 |  | FALSE | TRUE
77848-3 | 77848 | 3 | 1 | Regular | SCULPT-154 1/4" | SP18276-SCRPAT-OPR-83°+97°-350-80-35-FL-154 1/4"-EX-W-UNV-DP-1-DS | Wrong info. In SD | Given to Shipping | 2019-01-27 | 13:13:18 | 2019-01-22 | 2019-01-25 | 1 | 2 | Gagandeep Singh | Picked - Complete | High Priority |  | F10-#21 &#22-4TH FL | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 15:20 |  | FALSE | TRUE
77848-4 | 77848 | 4 | 1 | Regular | SCULPT-239 7/16" | SP18276-SCRPAT-OPR-100°+70°-350-80-35-FL-239 7/16"-EX-W-UNV-DP-2-DS | Others | Given to Shipping | 2019-01-27 | 13:13:19 | 2019-01-22 | 2019-01-25 | 1 | 3 | Gagandeep Singh | Picked - Complete | High Priority |  | F10-#38-4TH FL | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 15:20 |  | FALSE | TRUE
77848-5 | 77848 | 5 | 1 | Regular | SCULPT-207 7/16" | SP18276-SCRPAT-OPR-93°+87°-350-80-35-FL-207 7/16"-EX-W-UNV-DP-1-DS |  | Given to Shipping | 2019-01-25 | 14:50:03 | 2019-01-22 | 2019-01-25 | 1 | 2 | Gagandeep Singh | Picked - Complete | High Priority |  | F10-#30, #29-4TH FL | 1 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | TRUE | 2019-01-28 15:20 |  | FALSE | FALSE
77853-1 | 77853 | 1 | 1 | Regular | SLMLED-4 | SP18426(1)-SLLED-SL 80/20-900-80-50-SM-4-W-UNV-DP-1-CT15(36'') |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 19 | 19 | Rajithan Sivapatharajahon |  | High Priority |  | D1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77853-2 | 77853 | 2 | 1 | Regular | SLMLED-8 | SP18426(1)-SLLED-SL 80/20-900-80-50-SM-8-W-UNV-DP-1-CT15(36'') |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 51 | 51 | Rajithan Sivapatharajahon |  | High Priority |  | D2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77853-3 | 77853 | 3 | 1 | Regular | SLMLED-12 | SP18426(1)-SLLED-SL 80/20-900-80-50-SM-12-W-UNV-DP-1-CT15(36'') |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 14 | 14 | Rajithan Sivapatharajahon |  | High Priority |  | D3 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77853-4 | 77853 | 4 | 1 | Regular | SLMLED-4 | SP18426(1)-SLLED-SL 80/20-1500-80-50-SM-4-W-UNV-DP-1-CT15(36'') |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 5 | 5 | Rajithan Sivapatharajahon |  | High Priority |  | D4 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77853-5 | 77853 | 5 | 1 | Regular | SLMLED-8 | SP18426(1)-SLLED-SL 80/20-1500-80-50-SM-8-W-UNV-DP-1-CT15(36'') |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rajithan Sivapatharajahon |  | High Priority |  | D5 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-1 | 77854 | 1 | 1 | Regular | B3LED-4' | BMRLED-800-80-30-FL-4'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 93 | 93 | Rajithan Sivapatharajahon |  | Regular |  | F3-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-2 | 77854 | 2 | 1 | Regular | SKLPTP-13' 7 1/2" | SCPLED-500-80-30-FL-13' 7 1/2"-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F4-13' 7 1/2" EM(1) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-3 | 77854 | 3 | 1 | Regular | SKLPTP-21' 8" | SCPLED-500-80-30-FL-21' 8"-W-UNV-DP-1+E(2)-DS |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F4-21' 8" EM(2) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-6 | 77854 | 6 | 1 | Regular | SKLPTP-64' 2 3/4" | SCPLED-500-80-30-FL-64' 2 3/4"-W-UNV-DP-1+E(5)-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 6 | Rajithan Sivapatharajahon |  | Regular |  | F4-64' 2 3/4" EM(5) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-7 | 77854 | 7 | 1 | Regular | SKLPTP-139' 5 3/8" | SCPLED-500-80-30-FL-139' 5 3/8"-W-UNV-DP-1+E(9)-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 12 | Rajithan Sivapatharajahon |  | Regular |  | F4-139' 5 3/8" EM(9) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-8 | 77854 | 8 | 1 | Regular | B2LED-13' 7 1/2" | BRLED-500-80-30-FL-13' 7 1/2"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 4 | Rajithan Sivapatharajahon |  | Regular |  | F4A-13 '7 1/2" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-9 | 77854 | 9 | 1 | Regular | B2LED-24' 1" | BRLED-500-80-30-FL-24' 1"-W-UNV-DP-1-DS-C( NO FLANGE ON BOTH ENDS) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Rajithan Sivapatharajahon |  | Regular |  | F4A-24'1" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-10 | 77854 | 10 | 1 | Regular | B2LED-28' 2 1/2" | BRLED-500-80-30-FL-28' 2 1/2"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Rajithan Sivapatharajahon |  | Regular |  | F4A-28' 2 1/2" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-11 | 77854 | 11 | 1 | Regular | AULED-24 | AULED-24-3100-80-30-SO-W-UNV-DP-1-ST |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F8 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77854-12 | 77854 | 12 | 1 | Regular | B3PLED-10' 4 1/4" | BMPRLED-400-80-30-RG2-10' 4 1/4"-W-UNV-DP-1-DS-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 3 | Rajithan Sivapatharajahon |  | Regular |  | F9-10' 4 1/4" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-13 | 77854 | 13 | 1 | Regular | B3PLED-15' 1/4" | BMPRLED-400-80-30-RG2-15' 1/4"-W-UNV-DP-1-DS-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F9-15' 1/4" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-14 | 77854 | 14 | 1 | Regular | B3PLED-109" | BMPRLED-500-80-30-RG2-109"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 9 | 9 | Rajithan Sivapatharajahon |  | Regular |  | F9A-109" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-15 | 77854 | 15 | 1 | Regular | B3PLED-14'5" | BMPRLED-500-80-30-RG2-14'5"-W-UNV-DP-1-TG9-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F9A-14'5" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-16 | 77854 | 16 | 1 | Regular | B2LED-25' 6 1/2" | BRLED-500-80-30-FL-25' 6 1/2"-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 6 | Rajithan Sivapatharajahon |  | Regular |  | F10-25' 6 1/2" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-17 | 77854 | 17 | 1 | Regular | TB3LED-UNV | SP18477(1)-TB3WDILED-800-80-30-SLA-7'0"-W-UNV-DP-1-C(TWIN BEAM 3 WALL INDIRECT ONLY SLA) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F11-7'0" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-18 | 77854 | 18 | 1 | Regular | SLMLED-5' | SLWLED-SL 100/0-800-80-30-NO-5'-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Rajithan Sivapatharajahon |  | Regular |  | F16-5' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-19 | 77854 | 19 | 1 | Regular | SCULPT-72' | SCDIPAT-REC-90(4)-500-500-80-30-BW-FL-72'-EX-BLK-UNV-DP-2-CA(36) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 8 | Rajithan Sivapatharajahon |  | Regular |  | D3 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-20 | 77854 | 20 | 1 | Regular | SKLPTP-43' 4 3/8" | SCPLED-500-80-30-FL-43' 4 3/8"-W-UNV-DP-1+E(3)-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 4 | Rajithan Sivapatharajahon |  | Regular |  | F4-43' 4 3/8" EM(4) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-21 | 77854 | 21 | 1 | Regular | SKLPTP-9' 5 3/4" | SCPLED-500-80-30-FL-9' 5 3/4"-W-UNV-DP-1+E(1)-DS |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | F4-9' 5 3/4" EM(4) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-22 | 77854 | 22 | 1 | Regular | SKLPTP-11' 10 5/8" | SCPLED-500-80-30-FL-11' 10 5/8"-W-UNV-DP-1+E(1)-DS |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | F4-11' 10 5/8" EM(5) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-23 | 77854 | 23 | 1 | Regular | SKLPTP-69' 4 7/8" | SCPLED-500-80-30-FL-69' 4 7/8"-W-UNV-DP-1+E(4)-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 6 | Rajithan Sivapatharajahon |  | Regular |  | F4-69' 4 7/8" EM(5) | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-24 | 77854 | 24 | 1 | Regular | B3PLED-9' 7 5/8" | BMPRLED-400-80-30-RG2-9' 7 5/8"-W-UNV-DP-1-DS-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | F9-9' 7 5/8" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-25 | 77854 | 25 | 1 | Regular | B3PLED-8' 8 3/4" | BMPRLED-400-80-30-RG2-8' 8 3/4"-W-UNV-DP-1-DS-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | F9-8' 8 3/4" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-26 | 77854 | 26 | 1 | Regular | B3PLED-114 7/8" | BMPRLED-500-80-30-RG2-114 7/8"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | F9A-114 7/8" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-27 | 77854 | 27 | 1 | Regular | B3PLED-111" | BMPRLED-500-80-30-RG2-111"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | F9A-111" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-28 | 77854 | 28 | 1 | Regular | B3PLED-115 1/8" | BMPRLED-500-80-30-RG2-115 1/8"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F9A-115 1/8" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-29 | 77854 | 29 | 1 | Regular | B3PLED-115" | BMPRLED-500-80-30-RG2-115"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F9A-115" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77854-30 | 77854 | 30 | 1 | Regular | B3PLED-115 3/8" | BMPRLED-500-80-30-RG2-115 3/8"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | F9A-115 3/8" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77856-1 | 77856 | 1 | 1 | Regular | B4LED-8' | BBRLED-750-80-35-FL-8'-W-UNV-D-1-TB15 |  | Scheduled/Released |  |  | 2019-03-15 | 2019-03-20 | 17 | 17 | Zahra Vatani |  | Regular |  | V | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77856-2 | 77856 | 2 | 1 | Regular | B4LED-4' | BBDLED-400-80-35-SO-4'-W-UNV-DP-1-CT9(36) |  | Scheduled/Released |  |  | 2019-03-15 | 2019-03-20 | 108 | 108 | Zahra Vatani |  | Regular |  | U2 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77868-1 | 77868 | 1 | 1 | Regular | PERFKT-CCWH | SP16308(2)-CCWH-SL-1100-80-27-CP(197' 2")-C(NATATORIUM)-120-DP-2-C |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 22 | Rohan Srivastava |  | Regular |  | LT-05D-21'X77' 7" RECT | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77868-2 | 77868 | 2 | 1 | Regular | PERFKT-CCH | SP16308(2)-CCH-SL-1100-80-27-CP(103' 7")-C(NATATORIUM)-120-DP-1-C |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 13 | Rohan Srivastava |  | Regular |  | LT-25D-80'X23' 7"- L SHAPE | 4 | TRUE | FALSE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77891-1 | 77891 | 1 | 1 | Regular | STNCLS-10' | STSLF-SO-400-80-30-10'-C(PS541B8222)-UNV-MD-1-SB15 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 5 | 10 | Rohan Srivastava |  | Regular |  | LT-3 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77892-1 | 77892 | 1 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-35-CL(14')-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Jessica Pasternyk |  | Regular |  | L1-14' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77892-2 | 77892 | 2 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-35-CL(14')-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Jessica Pasternyk |  | Regular |  | L1A-14' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77892-3 | 77892 | 3 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-35-CL(14')-W-UNV-DP-1-AC |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Jessica Pasternyk |  | Regular |  | L1B-14' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
77898-1 | 77898 | 1 | 1 | Regular | B2SLED-17' | B2SQDLED-1000-80-30-SO-17'-AP-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-31 | 10:56:39 | 2019-01-31 | 2019-02-05 | 1 | 2 | George Bacalla |  | Regular |  | A-17' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:11 |  | TRUE | FALSE
77900-1 | 77900 | 1 | 1 | Regular | SLMLED-4 | SLLED-SL 25/75-1000-80-35-VL-4-W-UNV-DP-1-CA(72) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 16 | 16 | Sacha Lempka |  | Regular |  | A1 | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-2 | 77900 | 2 | 1 | Regular | SLMLED-4 | SLLED-SL 25/75-1000-80-35-VL-4-W-UNV-DP-1-CA(72)-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 8 | 8 | Sacha Lempka |  | Regular |  | A1E | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-3 | 77900 | 3 | 1 | Regular | SLMLED-4 | SLWLED-SL 75/25-1000-80-35-VL-4-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 12 | 12 | Sacha Lempka |  | Regular |  | A3 | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-4 | 77900 | 4 | 1 | Regular | SLMLED-4' | SLWLED-SL 75/25-1000-80-35-VL-4'-W-UNV-DP-1-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 4 | 4 | Sacha Lempka |  | Regular |  | A3E | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-5 | 77900 | 5 | 1 | Regular | B4LED-4 | BBWDILED-1000-1000-80-35-SO-4-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 30 | 30 | Sacha Lempka |  | Regular |  | E1 | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-6 | 77900 | 6 | 1 | Regular | SLMLED-28' | SLLED-SL 25/75-1000-80-35-VL-28'-W-UNV-DP-1-CA(72)-B1(BSL310LP)-C(EM LAST 4' SECTION) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Sacha Lempka |  | Regular |  | A1-28'-EA | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-7 | 77900 | 7 | 1 | Regular | SLMLED-36' | SLLED-SL 25/75-1000-80-35-VL-36'-W-UNV-DP-1-CA(72)-B1(BSL310LP)-C(EM LAST 4' SECTION) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 15 | 45 | Sacha Lempka |  | Regular |  | A1-36'-EA | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-8 | 77900 | 8 | 1 | Regular | SLMLED-12 | SLLED-SL 25/75-1000-80-35-VL-12-W-UNV-DP-1-CA(72) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Sacha Lempka |  | Regular |  | A1-12' | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-9 | 77900 | 9 | 1 | Regular | SLMLED-28' | SLLED-SL 25/75-1000-80-35-VL-28'-W-UNV-DP-1-CA(72)-B1(BSL310LP)-C(EM MIDDLE 4' SECTION) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Sacha Lempka |  | Regular |  | A1-28'-EB | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77900-10 | 77900 | 10 | 1 | Regular | SLMLED-36' | SLLED-SL 25/75-1000-80-35-VL-36'-W-UNV-DP-1-CA(72)-B1(BSL310LP)-C(EM MIDDLE 4' SECTION) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 6 | 18 | Sacha Lempka |  | Regular |  | A1-36'-EB | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77908-1 | 77908 | 1 | 1 | Regular | SCULPT-12'0" | SCDI-300-500-80-35-SO-2M-12'0"-AP-UNV-DP-1-CA(36) |  | Wiring Started | 2019-01-31 | 00:48:17 | 2019-01-31 | 2019-02-05 | 2 | 2 | Gaurav Jain | Picked - Complete | Regular |  | A3-12' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | FALSE
77908-2 | 77908 | 2 | 1 | Regular | SCULPT-20'0" | SCDI-300-500-80-35-SO-2M-20'0"-AP-UNV-DP-1-CA(36) |  | Wiring Started | 2019-01-30 | 23:35:23 | 2019-01-31 | 2019-02-05 | 2 | 4 | Gaurav Jain | Picked - Complete | Regular |  | A3-20' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | FALSE
77908-3 | 77908 | 3 | 1 | Regular | SCULPT-24'0" | SCDI-300-500-80-35-SO-2M-24'0"-AP-UNV-DP-1-CA(36) | Wrong part in BOM | Wiring Started | 2019-01-31 | 00:48:43 | 2019-01-31 | 2019-02-05 | 1 | 2 | Gaurav Jain | Picked - Complete | Regular |  | A3-24' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | TRUE
77908-4 | 77908 | 4 | 1 | Regular | SCULPT-28'0" | SCDI-300-500-80-35-SO-2M-28'0"-AP-UNV-DP-1-CA(36) |  | Wiring Started | 2019-02-01 | 07:30:27 | 2019-01-31 | 2019-02-05 | 2 | 6 | Gaurav Jain | Picked - Complete | Regular |  | A3-28' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | TRUE | 2019-02-01 11:02 |  | TRUE | FALSE
77908-5 | 77908 | 5 | 1 | Regular | SCULPT-32'0" | SCDI-300-500-80-35-SO-2M-32'0"-AP-UNV-DP-1-CA(36) |  | Wiring Started | 2019-01-30 | 23:35:36 | 2019-01-31 | 2019-02-05 | 2 | 6 | Gaurav Jain | Picked - Complete | Regular |  | A3-32' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | FALSE
77908-6 | 77908 | 6 | 1 | Regular | SCULPT-4'0" | SCR-500-80-35-0.5P-4'0"-W-UNV-DP-1-TB9 |  | Wiring Started | 2019-01-30 | 23:35:39 | 2019-01-31 | 2019-02-05 | 5 | 5 | Gaurav Jain | Picked - Complete | Regular |  | A4 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | FALSE
77908-7 | 77908 | 7 | 1 | Regular | SCULPT-4'0" | SCR-500-80-35-0.5P-4'0"-W-UNV-DP-1-TB9-B1(BSL10LST) |  | Wiring Started | 2019-01-30 | 23:35:43 | 2019-01-31 | 2019-02-05 | 4 | 4 | Gaurav Jain | Picked - Complete | Regular |  | A4E | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | FALSE
77908-8 | 77908 | 8 | 1 | Regular | SKSLED-22 | SKSLED-22-3200-80-35-GL-FL-UNV-DP-1-TB15 |  | Wiring Started |  |  | 2019-01-31 | 2019-02-05 | 12 | 12 | Gaurav Jain |  | Regular |  | D | 10 | TRUE | FALSE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
77908-9 | 77908 | 9 | 1 | Regular | TWGLED-8'0" | TWRWLED-SL 90/10-1250-80-35-SO-8'0"-W-UNV-DP-1-B1(BSL10LST) | PM wrong/missing info | Wiring Started | 2019-01-31 | 22:27:30 | 2019-01-31 | 2019-02-05 | 12 | 12 | Gaurav Jain | Picked - Complete | Regular |  | QE | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:02 |  | TRUE | TRUE
77908-10 | 77908 | 10 | 1 | Regular | SCULPT-32'0" | SCDI-300-500-80-35-SO-2M-32'0"-AP-UNV-DP-1-CA(36)-B3(BSL10LST) |  | Wiring Started | 2019-01-31 | 00:48:46 | 2019-01-31 | 2019-02-05 | 1 | 3 | Gaurav Jain | Picked - Complete | Regular |  | A3-32' EM(3) | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:06 |  | TRUE | FALSE
77910-1 | 77910 | 1 | 1 | Regular | B3LED-16' | BMRLED-500-80-35-FL-16'-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 4 | 8 | Joshua Zimet | Picked - Complete | Regular |  | H | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77910-2 | 77910 | 2 | 1 | Regular | B3LED-16' | BMRLED-500-80-35-FL-16'-W-UNV-DP-1+E(1)-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 4 | Joshua Zimet | Picked - Complete | Regular |  | H-EM | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77922-1 | 77922 | 1 | 1 | Regular | TB4LED-8' | TB4DILED-640-400-80-35-SL-SO-8'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Zahra Vatani |  | Priority |  | P4-8' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-2 | 77922 | 2 | 1 | Regular | TB4LED-12' | TB4DILED-640-400-80-35-SL-SO-12'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 5 | 5 | Zahra Vatani |  | Priority |  | P4-12' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-3 | 77922 | 3 | 1 | Regular | TB4LED-18' | TB4DILED-640-400-80-35-SL-SO-18'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 10 | 20 | Zahra Vatani |  | Priority |  | P4-18' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-4 | 77922 | 4 | 1 | Regular | TB4LED-20' | TB4DILED-640-400-80-35-SL-SO-20'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 4 | 8 | Zahra Vatani |  | Priority |  | P4-20' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-5 | 77922 | 5 | 1 | Regular | TB4LED-22' | TB4DILED-640-400-80-35-SL-SO-22'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 8 | 16 | Zahra Vatani |  | Priority |  | P4-22' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-6 | 77922 | 6 | 1 | Regular | TB4LED-24' | TB4DILED-640-400-80-35-SL-SO-24'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 6 | Zahra Vatani |  | Priority |  | P4-24' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-7 | 77922 | 7 | 1 | Regular | TB4LED-28' | TB4DILED-640-400-80-35-SL-SO-28'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 9 | Zahra Vatani |  | Priority |  | P4-28' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-8 | 77922 | 8 | 1 | Regular | TB2LED-4' | TB2WDILED-1100-1000-80-35-SO-SO-4'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 22 | 22 | Zahra Vatani |  | Priority |  | S1-4' | 4 | TRUE | FALSE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-9 | 77922 | 9 | 1 | Regular | PERFKT-CCH | CCH-SL-900-80-35-CL(23)-W-UNV-DP-1-C |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 2 | Zahra Vatani |  | Priority |  | C2-23' | 4 | TRUE | FALSE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-10 | 77922 | 10 | 1 | Regular | TB4LED-10' | TB4DILED-640-400-80-35-SL-SO-10'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Zahra Vatani |  | Priority |  | P4-10' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77922-11 | 77922 | 11 | 1 | Regular | TB4LED-16' | TB4DILED-640-400-80-35-SL-SO-16'-W-UNV-DP-2-CA(120) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 4 | 8 | Zahra Vatani |  | Priority |  | P4-16' | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77926-1 | 77926 | 1 | 1 | Regular | SKFLED-22 | SKFLED-22-2400-80-35-4SF-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 72 | 72 | Philip Halsey |  | Regular |  | AL4-4SF | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77932-1 | 77932 | 1 | 1 | Regular | PERFKT-CCWH | SP16308(2)-CCWH-SL-1100-80-27-86'-C(NATATORIUM)-120-DP-1-C |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 21 | Rohan Srivastava |  | Regular |  | LT19D-86' | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77938-1 | 77938 | 1 | 1 | Regular | STENCL-16' | SP18489(1)-STFDI-SLI-500-DSO-400-16'-90-30-AL(4')-AP-120-DP-2-CA(36")-SC | Missing parts in BOM | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 4 | Jessica Pasternyk | Picked - Complete | Regular |  | A-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  | ToDo | ToDo |  |  |  |  | TRUE |  | Done | FALSE |  |  | FALSE | TRUE
77939-3 | 77939 | 3 | 1 | Regular | STSFR | STSFR-SO(32-200)-80-35-AL(4)+AI(2)-W-UNV-MD-1-SB15 | Others | Machine Shop Started |  |  | 2019-01-28 | 2019-01-31 | 1 | 6 | Philip Halsey |  | Regular |  | F-12X4 | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77939-4 | 77939 | 4 | 1 | Regular | STNCLS-STSFR | STSFR-SO(36-200)-80-35-AL(4)+AI(2)-W-UNV-MD-1-SB15 | Shortage | Machine Shop Started |  |  | 2019-01-28 | 2019-01-31 | 1 | 6 | Philip Halsey |  | Regular |  | F-12X6 | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
77943-1 | 77943 | 1 | 1 | Regular | SCULPT-4X4 | SCR-300-90-30-FL-4X4-W-UNV-DP-1-MFTB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 13 | 13 | Stan Buyansky |  | High Priority |  | F5 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77943-2 | 77943 | 2 | 1 | Regular | SCULPT-2X2 | SCR-300-90-30-FL-2X2-W-UNV-DP-1-MFTB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Stan Buyansky |  | High Priority |  | F6 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77943-3 | 77943 | 3 | 1 | Regular | SCULPT-16' 6" | SCR-400-90-30-FL-16' 6"-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 3 | 6 | Stan Buyansky |  | High Priority |  | Z-17 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77943-4 | 77943 | 4 | 1 | Regular | SCULPT-7' 4" | SCR-400-90-30-FL-7' 4"-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Stan Buyansky |  | High Priority |  | Z-8 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77943-5 | 77943 | 5 | 1 | Regular | SCULPT-5' 6" | SCR-400-90-30-FL-5' 6"-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Stan Buyansky |  | High Priority |  | Z-6 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77943-6 | 77943 | 6 | 1 | Regular | SCULPT-3' 10" | SCR-400-90-30-FL-3' 10"-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Stan Buyansky |  | High Priority |  | Z-4.5 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77943-7 | 77943 | 7 | 1 | Regular | SCULPT-4' 10" | SCR-400-90-30-FL-4' 10"-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Stan Buyansky |  | High Priority |  | Z-5.5 | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
77945-1 | 77945 | 1 | 1 | Regular | B2SLED-6 | SP000-B2SQILED-1100-80-TW2750-SL-6-BLK-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Mechanical issue | Machine Shop Finished | 2019-01-24 | 14:34:12 | 2019-01-17 | 2019-01-22 | 3 | 3 | Stan Buyansky | Picked - Complete | High Priority |  | L01A - 6 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-29 11:53 |  | TRUE | FALSE
77945-2 | 77945 | 2 | 1 | Regular | B2SLED-32 | SP000-B2SQILED-1100-80-TW2750-SLA-32-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Mechanical issue | Machine Shop Finished | 2019-01-23 | 09:28:40 | 2019-01-17 | 2019-01-22 | 7 | 21 | Stan Buyansky | Picked - Complete | High Priority |  | L01B - 32 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-23 16:17 |  | TRUE | FALSE
77945-3 | 77945 | 3 | 1 | Regular | B2SLED-18 | SP000-B2SQILED-1100-80-TW2750-SLA-18-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Shortage | Machine Shop Finished | 2019-01-23 | 09:28:44 | 2019-01-17 | 2019-01-22 | 1 | 2 | Stan Buyansky | Picked - Complete | High Priority |  | L01B - 18 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-23 16:18 |  | TRUE | FALSE
77947-1 | 77947 | 1 | 1 | Regular | B2SLED-34 | SP000-B2SQILED-1100-80-TW2750-SLA-34-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Mechanical issue | Machine Shop Finished | 2019-01-21 | 15:08:08 | 2019-01-17 | 2019-01-22 | 1 | 3 | Stan Buyansky | Picked - Complete | High Priority |  | L01B - 34 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-23 16:21 |  | TRUE | FALSE
77947-2 | 77947 | 2 | 1 | Regular | B2SLED-24 | SP000-B2SQILED-1100-80-TW2750-SLA-24-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Mechanical issue | Machine Shop Finished | 2019-01-21 | 15:08:18 | 2019-01-17 | 2019-01-22 | 4 | 8 | Stan Buyansky | Picked - Complete | High Priority |  | L01B - 24 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-23 16:21 |  | TRUE | FALSE
77947-15 | 77947 | 15 | 1 | Regular | B2SLED-37' 5" | SP000-B2SQILED-1100-80-TW2750-SLA-37' 5"-W-277-O(ELDOLED)-1-CA(36)-C(NIO EZ-CCT. NLIGHT) | Mechanical issue | Machine Shop Finished | 2019-01-28 | 16:13:57 | 2019-01-17 | 2019-01-22 | 1 | 4 | Stan Buyansky | Picked - Complete | High Priority |  | L01B-37 | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-23 16:21 |  | TRUE | FALSE
78001-3 | 78001 | 3 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CP(45')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 14 | George Bacalla |  | High Priority |  | A-45' MTG ROOM #2 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78001-4 | 78001 | 4 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CP(46')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 12 | George Bacalla |  | High Priority |  | B-46' MTG ROOM #1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78001-5 | 78001 | 5 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CP(66')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 15 | George Bacalla |  | High Priority |  | C-66' DINING ROOM | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78001-6 | 78001 | 6 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CP(38')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 14 | George Bacalla |  | High Priority |  | D-38' LIVING ROOM | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78001-7 | 78001 | 7 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CL(15')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | George Bacalla |  | High Priority |  | E-15' MTG ROOM #3A | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78001-8 | 78001 | 8 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CP(33')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 16 | George Bacalla |  | High Priority |  | F-33' MTG ROOM #3B | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78001-9 | 78001 | 9 | 1 | Regular | PERFKT-CCH | SP19029-CCH-SL-750-80-35-CL(2')-W-UNV-O(ERP DRIVER)-1-C |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 6 | 6 | George Bacalla |  | High Priority |  | LB-2' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78009-1 | 78009 | 1 | 1 | Regular | STNCLS-STSFF | SP19042(1)-STSFF-SO(40'-200)-90-30-AL(4)+AI(2)-AP-120-MD-1-SG9 |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 6 | Zahra Vatani |  | Regular |  | LD-8'x12' REC | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78009-2 | 78009 | 2 | 1 | Regular | SKETCH-AL(7'10 1/4") | SK-10003-CIR-AL(7'10 1/4")-700-90-30-SO-W-120-LT(LDE1)-1-DS |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 20 | 80 | Zahra Vatani |  | Regular |  | RD-7'10 1/4" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78014-1 | 78014 | 1 | 1 | Regular | B6LED-32' | B6DILEDPAT-OPR-90(2)-1000-300-80-35-SO-32'-EX-W-UNV-DP-1-CA(36") |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 8 | Jessica Pasternyk |  | Regular |  | L-8'X16'X8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78014-2 | 78014 | 2 | 1 | Regular | B6LED-40' | B6RLEDPAT-OPR-90-400-80-35-SO-FL-40'-EX-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 4 | Jessica Pasternyk |  | Regular |  | R-12'X16'X12' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78030-1 | 78030 | 1 | 1 | Regular | GRAZE-12'0" | GPRLED-EXNW-1200-80-35-RG2-12'0"-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 2 | 2 | Gaurav Jain | Picked - Complete | Regular |  | W-1 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78047-1 | 78047 | 1 | 1 | Regular | B4LED-4' | BBDILED-640-400-80-35-SO-4'-W-UNV-DP-1-CT9(36) |  | Machine Shop Finished | 2019-01-25 | 09:45:52 | 2019-02-05 | 2019-02-08 | 9 | 9 | Philip Halsey | Picked - Complete | Regular |  | LT-02 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
78047-2 | 78047 | 2 | 1 | Regular | B4LED-8' | BBDILED-640-400-80-35-SO-8'-W-UNV-DP-1-CT9(36) |  | Machine Shop Finished | 2019-01-25 | 09:45:53 | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | LT-02A | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
78047-3 | 78047 | 3 | 1 | Regular | AIRLED-2' | ARWLED-600-80-35-S-2'-W-UNV-DP-1 |  | Machine Shop Finished | 2019-01-29 | 07:59:56 | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | LT-05 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
78047-4 | 78047 | 4 | 1 | Regular | B4LED-4' | BBRLED-400-80-35-1.5M-4'-W-UNV-DP-1-TB9 |  | Machine Shop Finished | 2019-01-25 | 14:40:01 | 2019-02-05 | 2019-02-08 | 3 | 3 | Philip Halsey | Picked - Complete | Regular |  | LT-18 | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
78047-5 | 78047 | 5 | 1 | Regular | B4LED-4' | BBRLED-400-80-35-1.5M-4'-W-UNV-DP-1-TB9-B1(BSL310LP) |  | Machine Shop Finished | 2019-01-25 | 14:40:02 | 2019-02-05 | 2019-02-08 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | LT-18EM | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
78050-1 | 78050 | 1 | 1 | Regular | AIRLED-4' | ARSLED-600-80-30-S-4'-AP-120-DP-1-SC | Wrong part in BOM | Machine Shop Finished | 2019-01-30 | 14:28:30 | 2019-02-04 | 2019-02-07 | 10 | 10 | Rohan Srivastava |  | Regular |  | A-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 10:26 |  | TRUE | TRUE
78053-2 | 78053 | 2 | 1 | Regular | SKETCH-AL#23' 6 3/4" | SK-10005-CIR-AL#23' 6 3/4"-400-80-30-SO-W-UNV-DP-1-DS |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 8 | Rajithan Sivapatharajahon | Picked - Complete | High Priority |  | C1-10005 | 1 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78058-1 | 78058 | 1 | 1 | Regular | B4LED-6'0" | BBRLED-500-80-35-FL-6'0"-W-UNV-DP-1-D |  | Machine Shop Finished | 2019-02-04 | 09:15:32 | 2019-01-30 | 2019-02-04 | 9 | 9 | Rajithan Sivapatharajahon |  | Regular |  | C-6' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78085-1 | 78085 | 1 | 1 | Regular | STENCL-S75' | STI-250-80-35-S75'-AP-UNV-MD-1-CA(144)-RC |  | Scheduled/Released |  |  | 2019-04-24 | 2019-04-30 | 4 | 40 | Gaurav Jain |  | Regular |  | K | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78098-1 | 78098 | 1 | 1 | Regular | TB3LED-8 | TB3DILED-700-700-80-35-SL-SO-8-BLK-UNV-DP-1-CT9(36) | PM wrong/missing info | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 12 | 12 | Christina Torok | Picked - Complete | High Priority |  | F-01-8 | 18 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
78098-2 | 78098 | 2 | 1 | Regular | TB3LED-12 | TB3DILED-700-700-80-35-SL-SO-12-BLK-UNV-DP-1-CT9(36) | PM wrong/missing info | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 4 | 4 | Christina Torok | Picked - Complete | High Priority |  | F-01-12 | 18 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
78098-3 | 78098 | 3 | 1 | Regular | TB3LED-12 | TB3DILED-700-700-80-35-SL-SO-12-BLK-UNV-DP-1+E(1)-CT9(36) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 2 | 2 | Christina Torok | Picked - Complete | High Priority |  | F-01-12-EM | 18 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-4 | 78098 | 4 | 1 | Regular | TB3LED-16 | TB3DILED-700-700-80-35-SL-SO-16-BLK-UNV-DP-1-CT9(36) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 3 | 6 | Christina Torok | Picked - Complete | High Priority |  | F-01-16 | 18 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-5 | 78098 | 5 | 1 | Regular | TB3LED-16 | TB3DILED-700-700-80-35-SL-SO-16-BLK-UNV-DP-1+E(1)-CT9(36) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | High Priority |  | F-01-16-EM | 18 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-6 | 78098 | 6 | 1 | Regular | B4PLED-3 | BBPRLED-700-80-35-RG4-3-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | High Priority |  | F-04-3-GYP | 18 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-7 | 78098 | 7 | 1 | Regular | B4PLED-5 | BBPRLED-700-80-35-RG4-5-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | High Priority |  | F-04-5-GYP | 18 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-8 | 78098 | 8 | 1 | Regular | B4PLED-6 | BBPRLED-700-80-35-RG4-6-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 2 | 2 | Christina Torok | Picked - Complete | High Priority |  | F-04-6 | 18 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-9 | 78098 | 9 | 1 | Regular | B4PLED-6 | BBPRLED-700-80-35-RG4-6-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 3 | 3 | Christina Torok | Picked - Complete | High Priority |  | F-04-6-GYP | 18 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78098-10 | 78098 | 10 | 1 | Regular | B4PLED-8 | BBPRLED-700-80-35-RG4-8-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | High Priority |  | F-04-8-GYP | 18 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78105-1 | 78105 | 1 | 1 | Regular | TB3LED-24' | TB3DILED-400-400-90-30-0.25G-0.25G-24'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Zahra Vatani |  | Regular |  | C-24' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-2 | 78105 | 2 | 1 | Regular | TB3LED-8' | TB3DILED-400-400-90-30-0.25G-0.25G-8'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Zahra Vatani |  | Regular |  | C-8' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-3 | 78105 | 3 | 1 | Regular | TB3LED-32' | TB3DILED-400-400-90-30-0.25G-0.25G-32'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 3 | Zahra Vatani |  | Regular |  | C-32' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-4 | 78105 | 4 | 1 | Regular | TB3LED-20' | TB3DILED-400-400-90-30-0.25G-0.25G-20'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Zahra Vatani |  | Regular |  | C-20' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-5 | 78105 | 5 | 1 | Regular | TB3LED-28' | TB3DILED-400-400-90-30-0.25G-0.25G-28'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 3 | 9 | Zahra Vatani |  | Regular |  | C-28' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-6 | 78105 | 6 | 1 | Regular | TB3LED-8' | TB3DILED-400-1000-90-30-0.25G-0.25G-8'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 4 | 4 | Zahra Vatani |  | Regular |  | D-8' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-7 | 78105 | 7 | 1 | Regular | TB3LED-6' | TB3DILED-400-1000-90-30-0.25G-0.25G-6'-W-UNV-DP-2-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 3 | 3 | Zahra Vatani |  | Regular |  | D-6' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78105-8 | 78105 | 8 | 1 | Regular | WWPRFK-8' | WW-SL-750-90-30-8'-W-UNV-DP-1-CA(48") |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Zahra Vatani |  | Regular |  | J-8' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78106-1 | 78106 | 1 | 1 | Regular | B4LED-4' | BBRLED-500-80-35-FL-4'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 3 | 3 | Philip Halsey | Picked - Complete | Regular |  | GL2 | 12 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78106-2 | 78106 | 2 | 1 | Regular | B4PLED-6' 9" | BBPRLED-500-80-35-RG4-6' 9"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | WL3, 6' 9" | 12 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78106-3 | 78106 | 3 | 1 | Regular | B4PLED-10' 10" | BBPRLED-500-80-35-RG4-10' 10"-W-UNV-DP-1-ST-TS(1) |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | WL3, 10' 10" | 12 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78106-4 | 78106 | 4 | 1 | Regular | B4PLED-16' | BBPRLED-OPRI(1)-500-80-35-FL-16'-W-UNV-DP-1-DS-TS(1)-C( 9FT 8.6IN X 6FT) |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Philip Halsey | Picked - Complete | Regular |  | WL2 | 12 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78110-1 | 78110 | 1 | 1 | Regular | B3LED-8' | BMDLED-1000-90-35-SO-8'-W-UNV-DP-1-CA(60) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 9 | 9 | Joshua Zimet | Picked - Complete | Regular |  | B-8' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78110-2 | 78110 | 2 | 1 | Regular | B3LED-8' | BMDLED-1000-90-35-SO-8'-W-UNV-DP-2-CA(60) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 10 | 10 | Joshua Zimet | Picked - Complete | Regular |  | B-2C | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78110-3 | 78110 | 3 | 1 | Regular | B3LED-8' | BMRLED-1000-90-35-RG-8'-W-UNV-DP-1-TG9-CP |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | B-8R | 12 | TRUE | TRUE | TRUE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78124-1 | 78124 | 1 | 1 | Regular | TB2LED-4 | TB2DLED-1000-80-40-L-4-W-UNV-DP-1-CA(96) |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 12 | 12 | Jessica Pasternyk |  | Priority |  | L3 | 12 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-1 | 78126 | 1 | 1 | Regular | TB3LED-4' | TB3DILED-700-700-80-35-SL-SO-4'-BLK-UNV-DP-1-CT9(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 6 | 6 | Christina Torok |  | Regular |  | 1-F-01-4'- FIRST FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-2 | 78126 | 2 | 1 | Regular | TB3LED-4' | TB3DILED-700-700-80-35-SL-SO-4'-W-UNV-DP-1-CA(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Christina Torok |  | Regular |  | 1-F-01-4'-GYP - FIRST FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-3 | 78126 | 3 | 1 | Regular | TB3LED-6' | TB3DILED-700-700-80-35-SL-SO-6'-BLK-UNV-DP-1-CT9(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Christina Torok |  | Regular |  | 1-F-01-6' - FIRST FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-4 | 78126 | 4 | 1 | Regular | TB3LED-8' | TB3DILED-700-700-80-35-SL-SO-8'-W-UNV-DP-1-CA(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 3 | Christina Torok |  | Regular |  | 1-F-01-8'-GYP - FIRST FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-5 | 78126 | 5 | 1 | Regular | TB3LED-16' | TB3DILED-700-700-80-35-SL-SO-16'-W-UNV-DP-1-CA(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 3 | 6 | Christina Torok |  | Regular |  | 1-F-01-16' GYP - FIRST FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-6 | 78126 | 6 | 1 | Regular | TB3LED-4' | TB3DILED-700-700-80-35-SL-SO-4'-BLK-UNV-DP-1-CT9(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Christina Torok |  | Regular |  | 2-F-01-4' - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-7 | 78126 | 7 | 1 | Regular | TB3LED-4' | TB3DILED-700-700-80-35-SL-SO-4'-W-UNV-DP-1-CA(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Christina Torok |  | Regular |  | 2-F-01-4-GYP- SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-8 | 78126 | 8 | 1 | Regular | TB3LED-6' | TB3DILED-700-700-80-35-SL-SO-6'-BLK-UNV-DP-1-CT9(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 11 | 11 | Christina Torok |  | Regular |  | 2-F-01-6' - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-9 | 78126 | 9 | 1 | Regular | TB3LED-8' | TB3DILED-700-700-80-35-SL-SO-8'-W-UNV-DP-1-CA(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 1 | Christina Torok |  | Regular |  | 2-F-01-8'-GYP - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-10 | 78126 | 10 | 1 | Regular | TB3LED-16' | TB3DILED-700-700-80-35-SL-SO-16'-W-UNV-DP-1-CT9(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 4 | Christina Torok |  | Regular |  | 2-F-01-16' - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78126-11 | 78126 | 11 | 1 | Regular | TB3LED-24' | TB3DILED-700-700-80-35-SL-SO-24'-W-UNV-DP-1+E(2)-CT9(48") | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 2 | Christina Torok |  | Regular |  | 2-F-01-24'-EM - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78126-12 | 78126 | 12 | 1 | Regular | TB3LED-28' | TB3DILED-700-700-80-35-SL-SO-28'-W-UNV-DP-1-CT9(48") | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 6 | Christina Torok |  | Regular |  | 2-F-01-28' - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78126-13 | 78126 | 13 | 1 | Regular | TB3LED-28' | TB3DILED-700-700-80-35-SL-SO-28'-W-UNV-DP-1+E(2)-CT9(48") | Others | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 1 | 3 | Christina Torok |  | Regular |  | 2-F-01-28'-EM - SECOND FLOOR | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78126-14 | 78126 | 14 | 1 | Regular | TB3LED-6' | TB3DILED-700-700-80-35-SL-SO-6'-W-UNV-DP-1-CT9(48") |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Christina Torok |  | Regular |  | 2-F-01-6' - SECOND FLOOR - W | 4 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78142-1 | 78142 | 1 | 1 | Regular | B3LED-10'0" | BMRLED-600-80-30-RG-10'0"-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 3 | Sacha Lempka |  | Regular |  | F6A | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78142-2 | 78142 | 2 | 1 | Regular | B3LED-5'0" | BMRLED-600-80-30-RG-5'0"-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 22 | 22 | Sacha Lempka |  | Regular |  | F6B | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78142-3 | 78142 | 3 | 1 | Regular | ZEN-11'0" | ZERLED-TR-500-80-30-11'0"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Sacha Lempka |  | Regular |  | F9 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78142-4 | 78142 | 4 | 1 | Regular | B3LED-20'0" | BMSLED-400-80-30-SO-20'0"-W-UNV-DP-1-SB9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Sacha Lempka |  | Regular |  | F11 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78150-1 | 78150 | 1 | 1 | Regular | STNCLS-8' | STSLF-SO-400-80-35-8'-AP-UNV-MD-1-SC | Others | Machine Shop Finished | 2019-02-04 | 09:55:09 | 2019-01-29 | 2019-02-01 | 3 | 3 | Jessica Pasternyk |  | Regular |  | L1-8' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78150-2 | 78150 | 2 | 1 | Regular | STNCLS-12' | STSLF-SO-400-80-35-12'-AP-UNV-MD-1-SC | Shortage | Machine Shop Finished | 2019-02-04 | 09:55:06 | 2019-01-29 | 2019-02-01 | 1 | 1 | Jessica Pasternyk |  | Regular |  | L2-12' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78150-3 | 78150 | 3 | 1 | Regular | STNCLS-9' | STSLF-SO-400-B(3')-80-35-9'-AP-UNV-MD-1-SC-AC(4)-R-D35-AP |  | Machine Shop Finished | 2019-02-04 | 09:55:04 | 2019-01-29 | 2019-02-01 | 1 | 1 | Jessica Pasternyk |  | Regular |  | L3-9' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78165-1 | 78165 | 1 | 1 | Regular | B2LED-34 | BRLEDPAT-OPI-90(4)-400-80-35-SO-FL-34-NL-W-UNV-DP-1-DB |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 9 | Christina Torok |  | Regular |  | B | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | Ready | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78165-2 | 78165 | 2 | 1 | Regular | B2LED-32 | BRLEDPAT-OPI-90(4)-400-80-35-SO-FL-32-NL-W-UNV-DP-1-DB |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 9 | Christina Torok |  | Regular |  | B1 | 7 | TRUE | FALSE | FALSE | TRUE | ToDo | Ready | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78165-3 | 78165 | 3 | 1 | Regular | SKFLED-22 | SKFLED-22-3200-80-35-FL-W-120-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 11 | 11 | Christina Torok |  | Regular |  | C | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78165-4 | 78165 | 4 | 1 | Regular | SKFLED-22 | SKFLED-22-3200-80-35-1SF-W-120-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 5 | 5 | Christina Torok |  | Regular |  | C1 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78165-5 | 78165 | 5 | 1 | Regular | SKFLED-22 | SKFLED-22-3200-80-35-2SF-W-120-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 7 | 7 | Christina Torok |  | Regular |  | C2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78165-6 | 78165 | 6 | 1 | Regular | SKFLED-22 | SKFLED-22-3200-80-35-3SF-W-120-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 7 | 7 | Christina Torok |  | Regular |  | C3 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78165-7 | 78165 | 7 | 1 | Regular | B6LED-8 | B6RLED-750-80-35-2M-8-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Christina Torok |  | Regular |  | F | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78170-1 | 78170 | 1 | 1 | Regular | SCULPT-58' | SCRPAT-REC-90(4)-500-80-30-2M-58'-EX-W-UNV-DP-1-TB9-B4(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 10 | Philip Halsey | Picked - Complete | Regular |  | D, REC | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78170-2 | 78170 | 2 | 1 | Regular | SCULPT-29' | SCRPAT-OPR-90(2)-300-80-30-2P-29'-EX-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 5 | Philip Halsey | Picked - Complete | Regular |  | D1, "U" | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78171-1 | 78171 | 1 | 1 | Regular | WWPRFK-4'0" | WWR-SL-500-90-40-4'0"-W-UNV-DP-1-TB15 |  | Machine Shop Finished | 2019-01-31 | 13:41:45 | 2019-02-05 | 2019-02-08 | 7 | 7 | Sacha Lempka | Picked - Complete | Regular |  | AW1 | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:25 |  | TRUE | FALSE
78174-1 | 78174 | 1 | 1 | Regular | STFC | STFC-SLI(8-250)-DSO(8-400)-80-30-AG(8)-W-UNV-MD-1-CA(36")-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 8 | Joe Brier |  | Regular |  | 15 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-2 | 78174 | 2 | 1 | Regular | AULED-22 | AULED-22-2500-80-30-SO-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 17 | 17 | Joe Brier |  | Regular |  | 16 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-3 | 78174 | 3 | 1 | Regular | SCULPT-6' 8" | SCS-500-80-30-FL-6' 8"-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Joe Brier |  | Regular |  | 2 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-4 | 78174 | 4 | 1 | Regular | SCULPT-5 | SCR-500-80-30-FL-5-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 8 | 8 | Joe Brier |  | Regular |  | 6 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-5 | 78174 | 5 | 1 | Regular | SCULPT-4 | SCR-500-80-30-FL-4-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 12 | 12 | Joe Brier |  | Regular |  | 4 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-6 | 78174 | 6 | 1 | Regular | SCULPT-17 | SCS-500-80-30-FL-17-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Joe Brier |  | Regular |  | 9 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-7 | 78174 | 7 | 1 | Regular | SCULPT-5 | SCS-500-80-30-FL-5-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Joe Brier |  | Regular |  | 1 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-10 | 78174 | 10 | 1 | Regular | STENCL-4 | STI-1000-80-30-4-W-UNV-MD-1-CT15(36")-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 9 | 9 | Joe Brier |  | Regular |  | 20 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-11 | 78174 | 11 | 1 | Regular | STENCL-4 | STD-ML-600-80-30-4-W-UNV-MD-1-CA(36")-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Joe Brier |  | Regular |  | 18B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-12 | 78174 | 12 | 1 | Regular | STENCL-8 | STD-SO-400-80-30-8-W-UNV-MD-1-CA(36")-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Joe Brier |  | Regular |  | 19B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-13 | 78174 | 13 | 1 | Regular | SCULPT-4 | SCS-500-80-30-FL-4-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 4 | 16 | Joe Brier |  | Regular |  | 10 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-14 | 78174 | 14 | 1 | Regular | STNCLS-STSFF | STSFF-SO(8-200)-80-30-AL(4)-W-UNV-MD-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 8 | Joe Brier |  | Regular |  | 31 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-15 | 78174 | 15 | 1 | Regular | STNCLS-STSFF | STSFF-SO(16-200)-80-30-AL(4)-W-UNV-MD-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 8 | Joe Brier |  | Regular |  | 29 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-16 | 78174 | 16 | 1 | Regular | STNCLS-STSFF | STSFF-SO(24-200)-80-30-AL(4)-W-UNV-MD-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 4 | Joe Brier |  | Regular |  | 30 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-17 | 78174 | 17 | 1 | Regular | STNCLS-STSFF | STSFF-SO(16-200)-80-30-AL(4)-W-UNV-MD-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 4 | Joe Brier |  | Regular |  | 28 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-18 | 78174 | 18 | 1 | Regular | SCULPT-10 | SCS-500-80-30-FL-10-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 2 | Joe Brier |  | Regular |  | 03-A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-19 | 78174 | 19 | 1 | Regular | SCULPT-50' | SCSPAT-OPR-90-500-80-30-FL-50'-NL-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 6 | Joe Brier |  | Regular |  | 09-B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-20 | 78174 | 20 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-35-CL(4')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 36 | 36 | Joe Brier |  | Regular |  | T-13-4 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-21 | 78174 | 21 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-35-CL(3')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Joe Brier |  | Regular |  | T-13-3 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-22 | 78174 | 22 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-35-CL(2')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 11 | 11 | Joe Brier |  | Regular |  | T-13-2 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-23 | 78174 | 23 | 1 | Regular | STENCL-4' | STD-ML-600-80-30-4'-W-UNV-MD-1-CT15(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 9 | 9 | Joe Brier |  | Regular |  | 18-A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-24 | 78174 | 24 | 1 | Regular | STENCL-6' | STD-ML-600-80-30-6'-W-UNV-MD-1-CT15(36)-RC |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 3 | 3 | Joe Brier |  | Regular |  | 18A-6 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-25 | 78174 | 25 | 1 | Regular | AULED-22 | AULED-22-4000-80-30-SO-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Joe Brier |  | Regular |  | 32 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-26 | 78174 | 26 | 1 | Regular | AULED-22 | AULED-22-3000-80-30-SO-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Joe Brier |  | Regular |  | 33 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-27 | 78174 | 27 | 1 | Regular | SCULPT-10 | SCR-500-80-30-FL-10-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Joe Brier |  | Regular |  | 34 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78174-29 | 78174 | 29 | 1 | Regular | ACCENT-4 | SCAC-AC(3)-D36-D-CC-80-30-4-BLK-UNV-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Joe Brier |  | Regular |  | 24 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78177-1 | 78177 | 1 | 1 | Regular | B2LED-7'0" | BRLED-750-90-30-FL-7'0"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 4 | Gagandeep Singh |  | Regular |  | BN/G-7' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78177-2 | 78177 | 2 | 1 | Regular | B2LED-8'0" | BRLED-750-90-30-FL-8'0"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 2 | Gagandeep Singh |  | Regular |  | BN/G-8' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78177-3 | 78177 | 3 | 1 | Regular | B2LED-9'0" | BRLED-750-90-30-FL-9'0"-W-UNV-DP-1+E(1)-DF |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 1 | Gagandeep Singh |  | Regular |  | BN/G-9' EMCKT | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-1 | 78220 | 1 | 1 | Regular | TB2LED-16 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 8 | Zahra Vatani | Picked - Complete | High Priority |  | F1-16'-15TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-2 | 78220 | 2 | 1 | Regular | TB2LED-14 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 2 | Zahra Vatani | Picked - Complete | High Priority |  | F1-14'-15TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-3 | 78220 | 3 | 1 | Regular | TB2LED-12 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 16 | 32 | Zahra Vatani | Picked - Complete | High Priority |  | F1-12'-15TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-4 | 78220 | 4 | 1 | Regular | TB2LED-10 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-10-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 2 | Zahra Vatani | Picked - Complete | High Priority |  | F1-10'-15TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-5 | 78220 | 5 | 1 | Regular | TB2LED-8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 3 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | F1-8'-15TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-6 | 78220 | 6 | 1 | Regular | TB2LED-6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-6-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F1-6'-15TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-7 | 78220 | 7 | 1 | Regular | WWPRFK-13 | WWR-SL-750-80-30-13-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3-1B-13'-15TH | 4 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-8 | 78220 | 8 | 1 | Regular | WWPRFK-10 | WWR-SL-750-80-30-10-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 2 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3-1B-10'-15TH | 4 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-9 | 78220 | 9 | 1 | Regular | WWPRFK-6 | WWR-SL-750-80-30-6-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 1 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3-1B-6'-15TH | 4 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-10 | 78220 | 10 | 1 | Regular | WWPRFK-2 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 10 | 10 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3B-2'-15TH | 4 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-11 | 78220 | 11 | 1 | Regular | B4PLED-26' 6" | BBPRLED-300-80-30-FL-26' 6"-W-UNV-DP-1+E(2)-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-26' 6"-15TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-12 | 78220 | 12 | 1 | Regular | B4PLED-92' 11" | BBPRLED-300-80-30-FL-92' 11"-W-UNV-DP-2+E(6)-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 12 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-92' 11"-15TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-13 | 78220 | 13 | 1 | Regular | B4PLED-39' 5" | BBPRLED-300-80-30-FL-39' 5"-W-UNV-DP-1+E(3)-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 5 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-39' 5"-15TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-14 | 78220 | 14 | 1 | Regular | B4PLED-19' 5" | BBPRLED-300-80-30-FL-19' 5"-W-UNV-DP-1+E(1)-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-19' 5"-15TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78220-15 | 78220 | 15 | 1 | Regular | B4PLED-26' 5" | BBPRLED-300-80-30-FL-26' 5"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-26' 5"-15TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-1 | 78221 | 1 | 1 | Regular | TB2LED-22 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-22-W-UNV-DP-1-CT9(36") | PM wrong/missing info | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 6 | Zahra Vatani | Picked - Complete | Regular |  | F1-22'-16TH | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78221-2 | 78221 | 2 | 1 | Regular | TB2LED-14 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | Shortage | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 6 | 12 | Zahra Vatani | Picked - Complete | Regular |  | F1-14'-16TH | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-3 | 78221 | 3 | 1 | Regular | TB2LED-12 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 6 | Zahra Vatani | Picked - Complete | Regular |  | F1-12'-16TH | 4 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-4 | 78221 | 4 | 1 | Regular | TB2LED-8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Zahra Vatani | Picked - Complete | Regular |  | F1-8'-16TH | 4 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-5 | 78221 | 5 | 1 | Regular | WWPRFK-2 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 15 | 15 | Zahra Vatani | Picked - Complete | Regular |  | F4-3B-2'-16TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-6 | 78221 | 6 | 1 | Regular | WWPRFK-10 | WWR-SL-750-80-30-10-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 4 | Zahra Vatani | Picked - Complete | Regular |  | F4-3-1B-10'-16TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-7 | 78221 | 7 | 1 | Regular | WWPRFK-6 | WWR-SL-750-80-30-6-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Zahra Vatani | Picked - Complete | Regular |  | F4-3-1B-6'-16TH | 4 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-8 | 78221 | 8 | 1 | Regular | B4PLED-97' | BBPRLED-300-80-30-FL-97'-W-UNV-DP-2+E(7)-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 13 | Zahra Vatani | Picked - Complete | Regular |  | F3C-97'-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-9 | 78221 | 9 | 1 | Regular | B4PLED-18' 8" | BBPRLED-300-80-30-FL-18' 8"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Zahra Vatani | Picked - Complete | Regular |  | F3C-18' 8"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-10 | 78221 | 10 | 1 | Regular | B4PLED-23' 8" | BBPRLED-300-80-30-FL-23' 8"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Zahra Vatani | Picked - Complete | Regular |  | F3C-23' 8"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-11 | 78221 | 11 | 1 | Regular | B4PLED-76' 2" | BBPRLED-300-80-30-FL-76' 2"-W-UNV-DP-2+E(5)-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 10 | Zahra Vatani | Picked - Complete | Regular |  | F3C-76' 2"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-12 | 78221 | 12 | 1 | Regular | B4PLED-18' 9" | BBPRLED-300-80-30-FL-18' 9"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 4 | Zahra Vatani | Picked - Complete | Regular |  | F3C-18' 9"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-13 | 78221 | 13 | 1 | Regular | B4PLED-11' 5" | BBPRLED-300-80-30-FL-11' 5"-W-UNV-DP-1+E(1)-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Zahra Vatani | Picked - Complete | Regular |  | F3C-11' 5"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-14 | 78221 | 14 | 1 | Regular | B4PLED-17' 11" | BBPRLED-300-80-30-FL-17' 11"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Zahra Vatani | Picked - Complete | Regular |  | F3C-17' 11"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-15 | 78221 | 15 | 1 | Regular | B4PLED-18' 3" | BBPRLED-300-80-30-FL-18' 3"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Zahra Vatani | Picked - Complete | Regular |  | F3C-18' 3"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78221-16 | 78221 | 16 | 1 | Regular | B4PLED-75' 9" | BBPRLED-300-80-30-FL-75' 9"-W-UNV-DP-2+E(5)-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 11 | Zahra Vatani | Picked - Complete | Regular |  | F3C-75' 9"-16TH | 4 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78225-1 | 78225 | 1 | 1 | Regular | TB2LED-22 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-22-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-01-31 | 07:39:47 | 2019-02-05 | 2019-02-08 | 2 | 6 | Zahra Vatani | Picked - Complete | High Priority |  | F1-22'-17TH | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-2 | 78225 | 2 | 1 | Regular | TB2LED-16 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-01-31 | 07:39:52 | 2019-02-05 | 2019-02-08 | 15 | 30 | Zahra Vatani | Picked - Complete | High Priority |  | F1-16'-17TH | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-3 | 78225 | 3 | 1 | Regular | TB2LED-14 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-01-31 | 07:39:54 | 2019-02-05 | 2019-02-08 | 5 | 10 | Zahra Vatani | Picked - Complete | High Priority |  | F1-14'-17TH | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-4 | 78225 | 4 | 1 | Regular | TB2LED-8 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-8-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-01-31 | 07:39:56 | 2019-02-05 | 2019-02-08 | 6 | 6 | Zahra Vatani | Picked - Complete | High Priority |  | F1-8'-17TH | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-5 | 78225 | 5 | 1 | Regular | TB2LED-6 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-6-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-01-31 | 07:40:00 | 2019-02-05 | 2019-02-08 | 1 | 1 | Zahra Vatani | Picked - Complete | High Priority |  | F1-6'-17TH | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-6 | 78225 | 6 | 1 | Regular | WWPRFK-2 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 |  | Machine Shop Finished | 2019-01-30 | 09:40:27 | 2019-02-05 | 2019-02-08 | 24 | 24 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3B-2'-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-7 | 78225 | 7 | 1 | Regular | WWPRFK-13 | WWR-SL-750-80-30-13-W-UNV-DP-1-DS |  | Machine Shop Finished | 2019-01-30 | 09:40:29 | 2019-02-05 | 2019-02-08 | 2 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3-1B-13'-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-8 | 78225 | 8 | 1 | Regular | WWPRFK-14 | WWR-SL-750-80-30-14-W-UNV-DP-1-DS |  | Machine Shop Finished | 2019-01-30 | 09:40:40 | 2019-02-05 | 2019-02-08 | 1 | 2 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3-1B-14'-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78225-9 | 78225 | 9 | 1 | Regular | B4PLED-18' 9" | BBPRLED-300-80-30-FL-18' 9"-W-UNV-DP-1+E(3)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-18' 9"-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78225-10 | 78225 | 10 | 1 | Regular | B4PLED-97' 3" | BBPRLED-300-80-30-FL-97' 3"-W-UNV-DP-2+E(7)-TG9 | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 13 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-97' 3"-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
78225-11 | 78225 | 11 | 1 | Regular | B4PLED-18' 10" | BBPRLED-300-80-30-FL-18' 10"-W-UNV-DP-1+E(1)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-18' 10"-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78225-12 | 78225 | 12 | 1 | Regular | B4PLED-18' 6" | BBPRLED-300-80-30-FL-18' 6"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-18' 6"-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78225-13 | 78225 | 13 | 1 | Regular | B4PLED-38' 1" | BBPRLED-300-80-30-FL-38' 1"-W-UNV-DP-1+E(2)-DF |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 5 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-38' 1"-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78225-14 | 78225 | 14 | 1 | Regular | B4PLED-55' 9" | BBPRLED-300-80-30-FL-55' 9"-W-UNV-DP-2+E(4)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 7 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-55' 9"-17TH | 7 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78226-1 | 78226 | 1 | 1 | Regular | TB2LED-16 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-16-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-02-01 | 08:46:11 | 2019-02-05 | 2019-02-08 | 4 | 8 | Zahra Vatani | Picked - Complete | High Priority |  | F1-16'-18TH | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78226-2 | 78226 | 2 | 1 | Regular | TB2LED-14 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-14-W-UNV-DP-1-CT9(36") | Shortage | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 14 | 28 | Zahra Vatani | Picked - Complete | High Priority |  | F1-14'-18TH | 4 | TRUE | TRUE | TRUE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78226-3 | 78226 | 3 | 1 | Regular | TB2LED-12 | SP18497(1)-TB2DILED-625-250-80-30-SL-SO-12-W-UNV-DP-1-CT9(36") |  | Machine Shop Finished | 2019-02-01 | 08:45:54 | 2019-02-05 | 2019-02-08 | 10 | 10 | Zahra Vatani | Picked - Complete | High Priority |  | F1-12'-18TH | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78226-4 | 78226 | 4 | 1 | Regular | WWPRFK-2 | WWR-SL-750-80-30-2-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 45 | 45 | Zahra Vatani | Picked - Complete | High Priority |  | F4-3B-2'-18TH | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78226-5 | 78226 | 5 | 1 | Regular | B4PLED-28' 6" | BBPRLED-300-80-30-FL-28' 6"-W-UNV-DP-1+E(3)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-28' 6"-18TH | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78226-6 | 78226 | 6 | 1 | Regular | B4PLED-90' 6" | BBPRLED-300-80-30-FL-90' 6"-W-UNV-DP-2+E(6)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 12 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-90' 6"-18TH | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78226-7 | 78226 | 7 | 1 | Regular | B4PLED-18' 11" | BBPRLED-300-80-30-FL-18' 11"-W-UNV-DP-1+E(2)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-18' 11"-18TH | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78226-8 | 78226 | 8 | 1 | Regular | B4PLED-73' 5" | BBPRLED-300-80-30-FL-73' 5"-W-UNV-DP-2+E(6)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 8 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-73' 5"-18TH | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78226-9 | 78226 | 9 | 1 | Regular | B4PLED-28' | BBPRLED-300-80-30-FL-28'-W-UNV-DP-1+E(3)-TG9 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | F3C-28'-18TH | 4 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78240-1 | 78240 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(4-250)-DML(4-225)-80-35-AL(4)-W-UNV-MD-1-CT15(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 9 | 36 | Jessica Pasternyk |  | Regular |  | L3D/UA | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78240-2 | 78240 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(8-250)-DML(8-225)-80-35-AL(4)-W-UNV-MD-1-CT15(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 4 | 16 | Jessica Pasternyk |  | Regular |  | L3D/UB | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78240-3 | 78240 | 3 | 1 | Regular | STENCL-STFC | STFC-NO-DML(6-600)-B(6)-80-35-AL(4)-BLK-UNV-MD-1-CA(180)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 12 | Jessica Pasternyk |  | Regular |  | L3DA | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78240-4 | 78240 | 4 | 1 | Regular | STENCL-STFC | STFC-NO-DML(10-600)-B(10)-80-35-AL(4)-BLK-UNV-MD-1-CA(180)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 8 | Jessica Pasternyk |  | Regular |  | L3DC | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78240-5 | 78240 | 5 | 1 | Regular | STENCL-STFC | STFC-NO-DML(8-600)-B(8)-80-35-AL(4)-BLK-UNV-MD-1-CA(180)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Jessica Pasternyk |  | Regular |  | L3DB | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78266-1 | 78266 | 1 | 1 | Regular | SLMLED-8 | SLLED-SL 25/75-1000-80-40-SM-8-W-277-DP-2-CT9(36) | Shortage | Given to Shipping | 2019-01-27 | 13:41:42 | 2019-01-30 | 2019-02-04 | 26 | 26 | Zahra Vatani |  | Regular |  | L | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-31 13:09 |  | TRUE | TRUE
78272-1 | 78272 | 1 | 1 | Regular | TEKLED-4 | TEK6LED-R-580-90-35-S-4-W-120-D-1-TG9-FW(6) | Shortage | Machine Shop Started |  |  | 2019-01-28 | 2019-01-31 | 6 | 6 | Rohan Srivastava |  | Regular |  | L16-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78272-2 | 78272 | 2 | 1 | Regular | TEKLED-4 | TEK6LED-R-580-90-35-S-4-W-120-D-1-TG9-B1(BSL310LP)-FW(6) | Shortage | Machine Shop Started |  |  | 2019-01-28 | 2019-01-31 | 3 | 3 | Rohan Srivastava |  | Regular |  | L16-4' EM | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78279-1 | 78279 | 1 | 1 | Regular | B4LED-8 | BBDILED-400-400-80-30-SO-8-BLK-UNV-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Joe Brier |  | Regular |  | B | 18 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78279-2 | 78279 | 2 | 1 | Regular | B3LED-4 | BMRLED-650-80-30-FL-4-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 30 | 30 | Joe Brier |  | Regular |  | F | 18 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78290-1 | 78290 | 1 | 1 | Regular | ZEN-12 | ZELED-SL 65/35-1100-80-35-MSO-W-12-AP-UNV-MD-1-CA(18") |  | Machine Shop Finished | 2019-02-03 | 12:56:42 | 2019-01-30 | 2019-02-04 | 2 | 2 | Jessica Pasternyk |  | Regular |  | JL1 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:48 |  | TRUE | FALSE
78302-2 | 78302 | 2 | 1 | Regular | BEAM2-40 | BWD-F-40-NL4-T8-1-AP-120-E-1 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Sacha Lempka |  | High Priority |  | B | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78306-1 | 78306 | 1 | 1 | NPI | ACCENT-6'0" | SCILAC-AC(2)-D24-D-500-80-30-BW-6'0"-C(BRIGHT COPPER)-120-DP-2-CA(36) | Shortage | Machine Shop Started |  |  | 2019-01-29 | 2019-02-06 | 1 | 1 | Sacha Lempka |  | Regular |  | COPPER-6' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo |  | ToDo |  | ToDo |  |  |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78328-1 | 78328 | 1 | 1 | Regular | B4SLED-12 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 7 | 7 | Stan Buyansky |  | Regular |  | P2 12' | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-2 | 78328 | 2 | 1 | Regular | B4SLED-12 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-2-CA(48)-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 7 | 7 | Stan Buyansky |  | Regular |  | P2 12' 2CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-3 | 78328 | 3 | 1 | Regular | B4SLED-24 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-2-CA(48)-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 5 | 10 | Stan Buyansky |  | Regular |  | P2 24' 2CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-4 | 78328 | 4 | 1 | Regular | B4SLED-24 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 4 | Stan Buyansky |  | Regular |  | P2 24' | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-5 | 78328 | 5 | 1 | Regular | B4SLED-8 | BBLED2-SL-500-750-80-35-SO-8-W-UNV-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Stan Buyansky |  | Regular |  | P3 8' | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-6 | 78328 | 6 | 1 | Regular | B2LED-12 | BRLED-750-80-35-FL-12-W-UNV-DP-1-DS-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Stan Buyansky |  | Regular |  | G2E 12' | 7 | TRUE | FALSE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78328-7 | 78328 | 7 | 1 | Regular | B2LED-12 | BRLED-750-80-35-FL-12-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 4 | 4 | Stan Buyansky |  | Regular |  | G2 12' | 7 | TRUE | FALSE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-8 | 78328 | 8 | 1 | Regular | B2LED-6 | BRLED-750-80-35-FL-6-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 5 | 5 | Stan Buyansky |  | Regular |  | G2 6' | 7 | TRUE | FALSE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78328-9 | 78328 | 9 | 1 | Regular | B2LED-6 | BRLED-750-80-35-FL-6-W-UNV-DP-1-DS-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Stan Buyansky |  | Regular |  | G2E 6' | 7 | TRUE | FALSE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready |  |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78328-10 | 78328 | 10 | 1 | Regular | B4SLED-12 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 5 | 5 | Stan Buyansky |  | Regular |  | P2 12' | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-11 | 78328 | 11 | 1 | Regular | B4SLED-12 | BBLED2-SL-640-500-80-35-SO-12-W-UNV-DP-2-CA(48)-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 4 | 4 | Stan Buyansky |  | Regular |  | P2 12' 2CKT | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-12 | 78328 | 12 | 1 | Regular | B4SLED-18 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 4 | Stan Buyansky |  | Regular |  | P2 18' | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-13 | 78328 | 13 | 1 | Regular | B4SLED-18 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 7 | 14 | Stan Buyansky |  | Regular |  | P2 18' 2CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-14 | 78328 | 14 | 1 | Regular | B4SLED-18 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48)-B3(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 6 | Stan Buyansky |  | Regular |  | P2E3-18' 2CKT | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-15 | 78328 | 15 | 1 | Regular | B4SLED-18 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-2-CA(48)-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 8 | 16 | Stan Buyansky |  | Regular |  | P2E2-18' 2CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-16 | 78328 | 16 | 1 | Regular | B4SLED-18 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-3-CA(48) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 2 | Stan Buyansky |  | Regular |  | P2 18' 3CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-17 | 78328 | 17 | 1 | Regular | B4SLED-18 | BBLED2-SL-640-500-80-35-SO-18-W-UNV-DP-3-CA(48)-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 4 | Stan Buyansky |  | Regular |  | P2E 18' 3CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78328-18 | 78328 | 18 | 1 | Regular | B4SLED-24 | BBLED2-SL-640-500-80-35-SO-24-W-UNV-DP-2-CA(48)-B2(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 6 | Stan Buyansky |  | Regular |  | P2 24' 2CKT | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78335-1 | 78335 | 1 | 1 | Regular | LTLED-8 | LTLED-SL 80/20-800-80-35-SO-8-AP-UNV-DP-1-CA(48") | Others | Given to Shipping | 2019-01-31 | 13:49:26 | 2019-01-30 | 2019-02-04 | 5 | 5 | Jessica Pasternyk | Picked - Complete | Regular |  | A | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:48 |  | TRUE | TRUE
78346-1 | 78346 | 1 | 1 | Regular | AULED-14 | AULED-14-2400-90-40-SO-W-UNV-DP-1-TB15-FW(6) |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 50 | 50 | Rohan Srivastava |  | Regular |  | L7 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-1 | 78355 | 1 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 37 | 37 | Philip Halsey |  | Regular |  | F1 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-2 | 78355 | 2 | 1 | Regular | AULED-22 | AULED-22-3000-80-35-SO-W-UNV-DP-1-TB15-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 3 | Philip Halsey |  | Regular |  | F2A | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-3 | 78355 | 3 | 1 | Regular | SKFLED-22 | SKFLED-22-1000-80-30-4SF-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 3 | 3 | Philip Halsey |  | Regular |  | F2B | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-4 | 78355 | 4 | 1 | Regular | SKFLED-22 | SKFLED-22-1000-80-30-6SF-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Philip Halsey |  | Regular |  | F2C | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-5 | 78355 | 5 | 1 | Regular | CLICK-8 | CLKLED-400-80-30-SO-8-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 17 | 17 | Philip Halsey |  | Regular |  | F4 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-6 | 78355 | 6 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-30-CL(22' 8")-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 4 | Philip Halsey |  | Regular |  | F13-22' 8" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78355-7 | 78355 | 7 | 1 | Regular | PERFKT-CCWH | CCWH-SL-700-80-30-CL(21' 6")-W-UNV-DP-1-AC |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Philip Halsey |  | Regular |  | F14-21'6" | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78360-1 | 78360 | 1 | 1 | Regular | GRAZE-23 | GPSLED-1200-90-27-RG2-23-W-120-DP-1-SC |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 2 | Stan Buyansky | Picked - Complete | High Priority |  | LT8 | 12 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78381-2 | 78381 | 2 | 1 | Regular | B4LED-11' | BBRLEDPAT-OPI-90(1)-400-80-35-SO-11'-NL-W-277-DP-1-D | Others | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 9 | 27 | Stan Buyansky |  | Regular |  | LR1A | 18 | TRUE | FALSE | FALSE | TRUE | [7 empty] | ToDo | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78386-1 | 78386 | 1 | 1 | Regular | B2LED-5 | BDLED-1000-90-40-SO-5-W-UNV-DP-1-CA(56)-C(OVERALL LENGTH) |  | Wiring Started | 2019-01-25 | 07:11:57 | 2019-01-30 | 2019-02-04 | 3 | 3 | Joshua Zimet |  | Regular |  | C5'/C5'EM | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 09:28 |  | TRUE | FALSE
78386-2 | 78386 | 2 | 1 | Regular | B2LED-6 | BDLED-1000-90-40-SO-6-W-UNV-DP-1-CA(56)-C(OVERALL LENGTH) |  | Wiring Started | 2019-01-25 | 07:12:00 | 2019-01-30 | 2019-02-04 | 3 | 3 | Joshua Zimet |  | Regular |  | C6'/C6'EM | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 09:28 |  | TRUE | FALSE
78386-3 | 78386 | 3 | 1 | Regular | B2LED-4 | BDLED-1000-90-40-SO-4-W-UNV-DP-1-CA(56) |  | Wiring Started | 2019-02-01 | 10:50:12 | 2019-01-30 | 2019-02-04 | 13 | 13 | Joshua Zimet |  | Regular |  | CP/CPEM | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 09:28 |  | TRUE | FALSE
78388-1 | 78388 | 1 | 1 | Regular | STNCLS-6 | STSLR-SO-400-80-35-6-AP-UNV-MD-1-SB9 | Others | Machine Shop Finished | 2019-02-01 | 11:25:34 | 2019-01-29 | 2019-02-01 | 4 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | H | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78391-1 | 78391 | 1 | 1 | Regular | CUBLED-16 | CUBLED-SL 75/25-800-80-35-VL-16-AP-UNV-DP-1-CT15(36") | Shortage | Given to Shipping | 2019-01-31 | 22:14:52 | 2019-01-29 | 2019-01-28 | 20 | 40 | Zahra Vatani | Picked - Complete | Regular |  | A | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 07:29 |  | TRUE | TRUE
78394-1 | 78394 | 1 | 1 | Regular | B4LED-8 | BBRLED-500-80-40-FL-8-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-03-11 | 2019-03-14 | 38 | 38 | Zahra Vatani |  | Priority |  | G | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78401-1 | 78401 | 1 | 1 | Regular | B4LED-24 | BBDLED-750-80-35-SO-24-W-UNV-DP-1-CA(120) |  | Machine Shop Finished | 2019-01-25 | 09:52:24 | 2019-02-05 | 2019-02-08 | 1 | 2 | Stan Buyansky | Picked - Complete | High Priority |  | F17A | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78401-2 | 78401 | 2 | 1 | Regular | B4LED-8 | BBDLED-750-80-35-SO-8-W-UNV-DP-1-CA(120) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Stan Buyansky | Picked - Complete | High Priority |  | F17B | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78408-1 | 78408 | 1 | 1 | Regular | B3LED-4 | BMDLED-1000-80-40-ASO-4-W-120-DP-1-CA(48) |  | Machine Shop Finished | 2019-02-04 | 07:48:39 | 2019-02-13 | 2019-02-18 | 2 | 2 | Sacha Lempka |  | Regular |  | L11-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78408-2 | 78408 | 2 | 1 | Regular | B3LED-8 | BMDLED-1000-80-40-ASO-8-W-120-DP-1-CA(48) |  | Machine Shop Finished | 2019-02-04 | 07:48:43 | 2019-02-13 | 2019-02-18 | 6 | 6 | Sacha Lempka |  | Regular |  | L11-8' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78408-3 | 78408 | 3 | 1 | Regular | B3LED-12 | BMDLED-1000-80-40-ASO-12-W-120-DP-1-CA(48) |  | Machine Shop Finished | 2019-02-04 | 07:48:47 | 2019-02-13 | 2019-02-18 | 2 | 2 | Sacha Lempka |  | Regular |  | L11-12' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78410-1 | 78410 | 1 | 1 | Regular | STNCLS-8' | STSLR-SO-400-80-40-8'-BLK-UNV-MD-1-SG15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 11 | 11 | Jessica Kennedy |  | Regular |  | F2 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78410-2 | 78410 | 2 | 1 | Regular | STNCLS-12' | STSLR-SO-400-80-40-12'-BLK-UNV-MD-1-SG15 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 6 | 6 | Jessica Kennedy |  | Regular |  | F2A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78413-1 | 78413 | 1 | 1 | Regular | B4LED-4 | BBRLED-400-80-40-FL-4-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | R2 4' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78413-2 | 78413 | 2 | 1 | Regular | B4LED-6 | BBRLED-400-80-40-FL-6-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 7 | 7 | Rajithan Sivapatharajahon |  | Regular |  | R-2 6' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78413-3 | 78413 | 3 | 1 | Regular | B4LED-2 | BBRLED-400-80-40-FL-2-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Rajithan Sivapatharajahon |  | Regular |  | R2 2' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78413-4 | 78413 | 4 | 1 | Regular | B4LED-10 | BBRLED-400-80-40-FL-10-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Rajithan Sivapatharajahon |  | Regular |  | R2 10' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78413-5 | 78413 | 5 | 1 | Regular | B6PLED-4 | B6PRLED-425-80-40-FL-4-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rajithan Sivapatharajahon |  | Regular |  | R3/R3A 4' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78413-6 | 78413 | 6 | 1 | Regular | B6PLED-10 | B6PRLED-425-80-40-FL-10-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | R3/R3A 10' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78423-8 | 78423 | 8 | 1 | Regular | SCULPT-5' 4" | SP19018(1)-SCR-1000-80-35-FL-5' 4"-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 3 | 3 | Philip Halsey | Picked - Complete | Regular |  | F1 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78423-9 | 78423 | 9 | 1 | Regular | SCULPT-5' 4" | SP19018(1)-SCR-1000-80-35-FL-5' 4"-W-UNV-DP-1-TG9-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | F1 EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78423-10 | 78423 | 10 | 1 | Regular | SCULPT-6' 3" | SP19018(1)-SCR-1000-80-35-FL-6' 3"-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | F2 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78423-11 | 78423 | 11 | 1 | Regular | SCULPT-6' 3" | SP19018(1)-SCR-1000-80-35-FL-6' 3"-W-UNV-DP-1-TG9-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | F2 EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78423-12 | 78423 | 12 | 1 | Regular | SCULPT-5' 6" | SP19018(1)-SCR-1000-80-35-FL-5' 6"-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | F3 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78423-13 | 78423 | 13 | 1 | Regular | SCULPT-6' 3" | SP19018(1)-SCD-1000-80-35-FL-6' 3"-W-UNV-DP-1-SA(18) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | F4 | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78423-14 | 78423 | 14 | 1 | Regular | SCULPT-6' 3" | SP19018(1)-SCD-1000-80-35-FL-6' 3"-W-UNV-DP-1-SA(18)-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | F4 EM | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78436-1 | 78436 | 1 | 1 | Regular | STENCL-STCO | STCO-SLI(4-1000)-DSO(8-400)-90-30-AI(2)-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 11 | 33 | Christina Torok |  | High Priority |  | H1-12'/H3-12' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-2 | 78436 | 2 | 1 | Regular | STENCL-STCO | STCO-SLI(8-1000)-NO-90-30-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Christina Torok |  | High Priority |  | H1-8' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-3 | 78436 | 3 | 1 | Regular | STENCL-STCO | STCO-SLI(4-1000)-NO-90-30-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 9 | 9 | Christina Torok |  | High Priority |  | H1-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-4 | 78436 | 4 | 1 | Regular | STENCL-STCO | STCO-SLI(12-1000)-DSO(16-400)-90-30-AI(6)-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 7 | Christina Torok |  | High Priority |  | H1-28' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-6 | 78436 | 6 | 1 | Regular | STENCL-STCO | STCO-SLI(6-1000)-NO-90-30-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Christina Torok |  | High Priority |  | H1-6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-7 | 78436 | 7 | 1 | Regular | STENCL-STCO | STCO-SLI(4-1000)-DSO(6-400)-90-30-AI(2)-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 3 | Christina Torok |  | High Priority |  | H1-10' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-8 | 78436 | 8 | 1 | Regular | STENCL-STCO | STCO-SLI(4-1000)-DSO(4-400)-90-30-AI(2)-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 8 | 24 | Christina Torok |  | High Priority |  | H3-8'DID | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-9 | 78436 | 9 | 1 | Regular | STENCL-STCO | STCO-SLI(4-1000)-DSO(4-400)-90-30-AI(1)-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 4 | Christina Torok |  | High Priority |  | H3-8'DI | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-10 | 78436 | 10 | 1 | Regular | STENCL-STCO | STCO-SLI(2-1000)-DSO(4-400)-90-30-AI(2)-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 5 | 15 | Christina Torok |  | High Priority |  | H1-6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78436-11 | 78436 | 11 | 1 | Regular | STENCL-STCO | STCO-NO-DSO(4-400)-90-30-W-UNV-MD-1-CA(120")-SC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Christina Torok |  | High Priority |  | H3-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78442-1 | 78442 | 1 | 1 | Regular | TB2LED-6' | TB2WDILED-750-750-90-35-SLA-SO-6'-AP-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 2 | 2 | Sacha Lempka |  | Regular |  | FF-6 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-1 | 78448 | 1 | 1 | Regular | SCULPT-1'3" | SCR-300-80-30-FL-1'3"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | D2-1'3" F | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-2 | 78448 | 2 | 1 | Regular | SCULPT-10'2" | SCR-300-80-30-FL-10'2"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D2-10'2" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-3 | 78448 | 3 | 1 | Regular | SCULPT-6'10" | SCR-300-80-30-FL-6'10"-W-UNV-DP-1-DS-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D2E-6'10" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo |  |  |  | ToDo |  |  |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-4 | 78448 | 4 | 1 | Regular | SCULPT-10'7 3/4" | SCD-300-80-30-FL-10'7 3/4"-BLK-UNV-DP-1-CA(48)-C(BLK CANOPIES AND CORD) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | D1-11-10'7 3/4" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-5 | 78448 | 5 | 1 | Regular | SCULPT-16'8 1/2" | SCD-300-80-30-FL-16'8 1/2"-BLK-UNV-DP-1-CA(48)-C(BLK CANOPIES AND CORD) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 4 | Philip Halsey | Picked - Complete | Regular |  | D1-16-16'8 1/2" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-6 | 78448 | 6 | 1 | Regular | SCULPT-10'7 3/4" | SCD-300-80-30-FL-10'7 3/4"-BLK-UNV-DP-1-CA(48)-B1(BSL310LP)-C(BLK CANOPIES AND CORD) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D1E-11-10'7 3/4" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-7 | 78448 | 7 | 1 | Regular | SCULPT-16'8 1/2" | SCD-300-80-30-FL-16'8 1/2"-BLK-UNV-DP-1-CA(48)-B1(BSL310LP)-C(BLK CANOPIES AND CORD) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 4 | Philip Halsey | Picked - Complete | Regular |  | D1E-16-16'8 1/2" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78448-8 | 78448 | 8 | 1 | Regular | SCULPT-55'4" | SCRPAT-REC-90(4)-300-80-30-FL-55'4"-NL-W-UNV-DP-1-DS-C(RECT 13' 6" X 14' 2") |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 8 | Philip Halsey | Picked - Complete | Regular |  | D2-RECT162-7/16"X170-3/4" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78448-9 | 78448 | 9 | 1 | Regular | SCULPT-48'0" | SCRPAT-REC-90(4)-300-80-30-FL-48'0"-NL-W-UNV-DP-1-DS-C(RECT 12' 3" X 10' 8") |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 8 | Philip Halsey | Picked - Complete | Regular |  | D2-RECT147-3/8"X128-5/8" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78448-10 | 78448 | 10 | 1 | Regular | SCULPT-1'0" | SCRV-300-80-30-FL-1'0"-W-UNV-DP-1-DS-C(DRIVER TO BE REMOTE, NO FLANGE ON ONE END) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D3-1' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo |  |  |  | ToDo |  |  |  |  | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-11 | 78448 | 11 | 1 | Regular | SCULPT-2'0" | SCRV-300-80-30-FL-2'0"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | D3-2' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-12 | 78448 | 12 | 1 | Regular | SCULPT-3'0" | SCRV-300-80-30-FL-3'0"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 4 | 4 | Philip Halsey | Picked - Complete | Regular |  | D3-3' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-13 | 78448 | 13 | 1 | Regular | SCULPT-5'0" | SCRV-300-80-30-FL-5'0"-W-UNV-DP-1-Ds-C(NO FLANGE ON ONE END) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 2 | Philip Halsey | Picked - Complete | Regular |  | D3-5' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-14 | 78448 | 14 | 1 | Regular | ZENSQ-8' | ZESQDI-SL 25/75-1050-80-30-MSO-8'-BLK-UNV-MD-1-CA(48) | Shortage | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 22 | 22 | Philip Halsey | Picked - Complete | Regular |  | H-8' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-15 | 78448 | 15 | 1 | Regular | ZENSQ-8' | ZESQDI-SL 25/75-1050-80-30-MSO-8'-BLK-UNV-MD-1-CA(48)-B1(BSL310LP) | Missing parts in BOM | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 18 | 18 | Philip Halsey | Picked - Complete | Regular |  | HE-8' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo |  |  |  | ToDo |  |  |  |  | FALSE |  | Done | FALSE |  |  | FALSE | TRUE
78448-16 | 78448 | 16 | 1 | Regular | SCULPT-53'10 6/8" | SCRPAT-REC-90(4)-300-80-30-FL-53'10 6/8"-NL-W-UNV-DP-1-DS-C(RECT 15' 4" 3/8"X 11' 7") |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 8 | Philip Halsey | Picked - Complete | Regular |  | D2-RECT184-3/8 8"X139" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78448-17 | 78448 | 17 | 1 | Regular | SCULPT-3'0" | SCRV-300-80-30-FL-3'0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D3-3' F | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-18 | 78448 | 18 | 1 | Regular | SCULPT-2'0" | SCRV-300-80-30-FL-2'0"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 3 | 3 | Philip Halsey | Picked - Complete | Regular |  | D3-2' | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-19 | 78448 | 19 | 1 | Regular | SCULPT-10'2" | SCR-300-80-30-FL-10'2"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D2-10'2" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78448-20 | 78448 | 20 | 1 | Regular | SCULPT-1'3" | SCR-300-80-30-FL-1'3"-W-UNV-DP-1-DS-C(NO FLANGE ON ONE END) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | D2-1'3" | 1 | TRUE | TRUE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78469-1 | 78469 | 1 | 1 | Regular | B3LED-7'4" | BMRLED-750-90-30-FL-7'4"-W-120-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Philip Halsey |  | Regular |  | J17 7'4" | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78469-2 | 78469 | 2 | 1 | Regular | B3LED-8' | BMRLED-750-90-30-FL-8'-W-120-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 1 | Philip Halsey |  | Regular |  | J17 8' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78471-1 | 78471 | 1 | 1 | Regular | B4LED-29' | BBRLED-750-80-40-FL-29'-CB20946(2)-W-UNV-DP-1+LDI-D | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | George Bacalla |  | Regular |  | F1-29' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78471-2 | 78471 | 2 | 1 | Regular | B4LED-11' | BBRLED-750-80-40-FL-11'-CB20946(2)-W-UNV-DP-1+LDI-D | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | George Bacalla |  | Regular |  | F2-11' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78471-3 | 78471 | 3 | 1 | Regular | B4LED-20' | BBRLED-750-80-40-FL-20'-CB20946(2)-W-UNV-DP-1+LDI-D |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | George Bacalla |  | Regular |  | F3-20' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78471-4 | 78471 | 4 | 1 | Regular | B4LED-18' | BBDILED-640-400-80-40-SO-18'-W-UNV-DP-1-CTS(36) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 6 | George Bacalla |  | Regular |  | G1-18' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78476-1 | 78476 | 1 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-30-CL(12' 6")-W-UNV-DP-1-AC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 4 | Jessica Kennedy |  | Regular |  | L-12'-6" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78476-2 | 78476 | 2 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-30-CP(17')-W-UNV-DP-1-AC | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 14 | Jessica Kennedy |  | Regular |  | L-8'X9' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78476-3 | 78476 | 3 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-30-CP(13')-W-UNV-DP-1-AC | PM wrong/missing info | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 8 | Jessica Kennedy |  | Regular |  | L-6'X7' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78476-4 | 78476 | 4 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-30-CL(9')-W-UNV-DP-1-AC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 1 | Jessica Kennedy |  | Regular |  | L-9' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78476-5 | 78476 | 5 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-30-CL(32')-W-UNV-DP-1-AC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Jessica Kennedy |  | Regular |  | I-32' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78484-1 | 78484 | 1 | 1 | Regular | DIALED-DIALED | DIALED-22-3000-80-35-VL-W-277-LT(L3D)-1-TG9-AR |  | Wiring Started | 2019-01-31 | 08:50:41 | 2019-01-29 | 2019-02-01 | 4 | 4 | Zahra Vatani |  | Regular |  | A | 10 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78491-1 | 78491 | 1 | 1 | Regular | B2LED-4' | BDLED-1000-90-30-SO-4'-AP-UNV-DP-1-CA(72) |  | Machine Shop Finished | 2019-02-04 | 07:28:36 | 2019-02-01 | 2019-02-06 | 21 | 21 | Philip Halsey |  | Regular |  | PENDANT-4' | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78498-1 | 78498 | 1 | 1 | Regular | B3LED-2 | BMRLED-600-80-35-FL-2-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 6 | 6 | Sacha Lempka |  | Regular |  | L1A-3RD | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78498-2 | 78498 | 2 | 1 | Regular | B3LED-2 | BMRLED-600-80-35-FL-2-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 47 | 47 | Sacha Lempka |  | Regular |  | L1B-3RD | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78498-3 | 78498 | 3 | 1 | Regular | B3LED-6 | BMRLED-750-80-35-FL-6-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Sacha Lempka |  | Regular |  | L1D-6-3RD | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78498-4 | 78498 | 4 | 1 | Regular | B3LED-8 | BMRLED-750-80-35-FL-8-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Sacha Lempka |  | Regular |  | L1D-8-3RD | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78498-5 | 78498 | 5 | 1 | Regular | B3LED-14 | BMRLED-750-80-35-FL-14-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 5 | 10 | Sacha Lempka |  | Regular |  | L1D-14-3RD | 1 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78498-6 | 78498 | 6 | 1 | Regular | B3LED-2 | BMRLED-600-80-35-ASO-2-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Sacha Lempka |  | Regular |  | L2-2-3RD | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78498-7 | 78498 | 7 | 1 | Regular | B3LED-6 | BMRLED-600-80-35-ASO-6-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Sacha Lempka |  | Regular |  | L2-6-3RD | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78498-8 | 78498 | 8 | 1 | Regular | B3LED-2 | BMDLED-750-80-35-SO-2-W-UNV-DP-1-CT9(36) |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 5 | 5 | Sacha Lempka |  | Regular |  | P4-3RD | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78500-1 | 78500 | 1 | 1 | Regular | SCULPT-8 | SCDI-750-500-80-30-BW-FL-8-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 5 | 5 | Rohan Srivastava |  | Priority |  | F1-8'-27TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-2 | 78500 | 2 | 1 | Regular | SCULPT-10' | SCDI-750-500-80-30-BW-FL-10'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Rohan Srivastava |  | Priority |  | F1-10'-27TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-3 | 78500 | 3 | 1 | Regular | SCULPT-18' | SCDI-750-500-80-30-BW-FL-18'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 4 | Rohan Srivastava |  | Priority |  | F1-18'-27TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-4 | 78500 | 4 | 1 | Regular | SCULPT-20' | SCDI-750-500-80-30-BW-FL-20'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Rohan Srivastava |  | Priority |  | F1-20'-27TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-5 | 78500 | 5 | 1 | Regular | MINLED-6 | MBWLED-600-80-30-S-6-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Rohan Srivastava |  | Priority |  | F7-6'-27TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-6 | 78500 | 6 | 1 | Regular | SCULPT-6' | SCDI-750-500-80-30-BW-FL-6'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Rohan Srivastava |  | Priority |  | F1-6'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-7 | 78500 | 7 | 1 | Regular | SCULPT-8' | SCDI-750-500-80-30-BW-FL-8'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Rohan Srivastava |  | Priority |  | F1-8'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-8 | 78500 | 8 | 1 | Regular | SCULPT-9' | SCDI-750-500-80-30-BW-FL-9'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Rohan Srivastava |  | Priority |  | F1-9'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-9 | 78500 | 9 | 1 | Regular | SCULPT-10' | SCDI-750-500-80-30-BW-FL-10'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 5 | 5 | Rohan Srivastava |  | Priority |  | F1-10'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-10 | 78500 | 10 | 1 | Regular | SCULPT-12' | SCDI-750-500-80-30-BW-FL-12'-W-120-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 2 | Rohan Srivastava |  | Priority |  | F1-12'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-11 | 78500 | 11 | 1 | Regular | B3LED-12' | BMRLED-750-80-30-FL-12'-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 4 | Rohan Srivastava |  | Priority |  | F5-12'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78500-12 | 78500 | 12 | 1 | Regular | MINLED-6' | MBWLED-600-80-30-S-6'-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Rohan Srivastava |  | Priority |  | F7-6'-28TH FL | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78502-1 | 78502 | 1 | 1 | Regular | AIRLED-8 | ARWLED-1000-80-35-S-8-W-347-DP-1 |  | Machine Shop Finished | 2019-01-30 | 14:29:08 | 2019-01-31 | 2019-02-05 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | E | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 11:33 |  | TRUE | FALSE
78503-1 | 78503 | 1 | 1 | Regular | B3LED-6' | BMSLED-750-80-30-SO-6'-M16LEDB(2)-BLK-UNV-DP-1+M-SC |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 48 | 48 | George Bacalla |  | High Priority |  | FAJ-M6 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78503-2 | 78503 | 2 | 1 | Regular | B3LED-6' | BMSLED-750-80-30-SO-6'-M16LEDB(2)-AP-UNV-DP-1+M-S |  | Scheduled/Released |  |  | 2019-02-27 | 2019-03-04 | 110 | 110 | George Bacalla |  | High Priority |  | FAQ-G6 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78505-1 | 78505 | 1 | 1 | Replacement | SKETCH-AL( 58 29/32") | SK-10013-ASO-AL( 58 29/32")-400-80-40-SO-W-UNV-DP-1-DF-C(JOIN TO EXISTING) | PM wrong/missing info | Given to Shipping | 2019-01-30 | 12:50:07 | 2019-01-29 | 2019-02-01 | 1 | 4 | Daljit Singh | Picked - Complete | High Priority |  | B | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:41 |  | TRUE | TRUE
78506-1 | 78506 | 1 | 1 | Regular | STENCL-8' | STLDI-I-500-DSO-400-8'-80-35-W-UNV-DP-1-CTS(60)-RC |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 6 | 6 | Zahra Vatani | Picked - Complete | High Priority |  | A1-8' | 7 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78506-2 | 78506 | 2 | 1 | Regular | STENCL-4' | STLDI-I-500-DSO-400-4'-80-35-W-UNV-DP-1-CTS(36)-RC | Missing parts in BOM | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 3 | 3 | Zahra Vatani | Picked - Complete | High Priority |  | A2-4' | 7 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78506-3 | 78506 | 3 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(8-400)-80-35-AL(4)-W-UNV-MD-1-CA(76)-RC-C(SWIVEL GRIP LOCK) |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 2 | 8 | Zahra Vatani | Picked - Complete | High Priority |  | C | 7 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78506-4 | 78506 | 4 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(16-400)-80-35-AL(4)-W-UNV-MD-1-CA(70)-RC-C(SWIVEL GRIP LOCK) |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 1 | 4 | Zahra Vatani | Picked - Complete | High Priority |  | B | 7 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78511-1 | 78511 | 1 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-35-CL(184')-W-277-DP-2-AC | Shortage | Machine Shop Finished | 2019-02-04 | 07:25:16 | 2019-02-01 | 2019-02-06 | 1 | 16 | Rohan Srivastava |  | Regular |  | LC-184' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78511-2 | 78511 | 2 | 1 | Regular | PERFKT-CCL | CCL-SL-300-80-35-CL(45')-W-277-DP-1-AC |  | Machine Shop Finished | 2019-02-04 | 07:25:21 | 2019-02-01 | 2019-02-06 | 1 | 4 | Rohan Srivastava |  | Regular |  | LC-45' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78515-1 | 78515 | 1 | 1 | Regular | B2LED-6 | BSLED-400-80-30-SO-6-AP-120-DP-1-S |  | Machine Shop Finished | 2019-02-01 | 02:30:31 | 2019-02-04 | 2019-02-07 | 5 | 5 | Sacha Lempka |  | Regular |  | A | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 10:27 |  | TRUE | FALSE
78517-1 | 78517 | 1 | 1 | Regular | PERFKT-CCWL | CCWL-SL-300-90-35-CL(8)-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-01-30 | 22:12:15 | 2019-02-05 | 2019-02-08 | 1 | 1 | Sacha Lempka |  | Regular |  | F1-8 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78517-2 | 78517 | 2 | 1 | Regular | WWPRFK-3 | WWR-SL-400-80-35-3-W-UNV-DP-1-D-FW(6) |  | Machine Shop Finished | 2019-01-30 | 22:20:06 | 2019-02-05 | 2019-02-08 | 2 | 2 | Sacha Lempka |  | Regular |  | J-3 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78521-1 | 78521 | 1 | 1 | Regular | WWPRFK-2 | WWR-SL-1000-80-30-2-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-01-29 | 07:27:39 | 2019-01-31 | 2019-02-05 | 1 | 1 | Stan Buyansky |  | Regular |  | H | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-31 11:33 |  | TRUE | FALSE
78522-25 | 78522 | 25 | 1 | Regular | B3LED-13' 6" | BMWDLED-750-80-30-SO-13' 6"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rohan Srivastava |  | Regular |  | TA-6, 13' 6", 3RD | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-26 | 78522 | 26 | 1 | Regular | B3LED-4' 6" | BMWDLED-750-80-30-SO-4' 6"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rohan Srivastava |  | Regular |  | TA-6, 4' 6", 3RD | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-27 | 78522 | 27 | 1 | Regular | B3LED-10' | BMWDLED-750-80-30-SO-10'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rohan Srivastava |  | Regular |  | TA-6, 10', 3RD | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-28 | 78522 | 28 | 1 | Regular | B3LED-5' 6" | BMWDLED-750-80-30-SO-5' 6"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rohan Srivastava |  | Regular |  | TA-6, 5' 6", 3RD | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-29 | 78522 | 29 | 1 | Regular | B3LED-13' 6" | BMWDLED-750-80-30-SO-13' 6"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Rohan Srivastava |  | Regular |  | TA-6, 13' 6", 4TH | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-30 | 78522 | 30 | 1 | Regular | B3LED-4' 6" | BMWDLED-750-80-30-SO-4' 6"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rohan Srivastava |  | Regular |  | TA-6, 4' 6", 4TH | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-31 | 78522 | 31 | 1 | Regular | B3LED-10' | BMWDLED-750-80-30-SO-10'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rohan Srivastava |  | Regular |  | TA-6, 10', 4TH | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-32 | 78522 | 32 | 1 | Regular | B3LED-6' | BMWDLED-750-80-30-SO-6'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | Rohan Srivastava |  | Regular |  | TA-6, 6', 4TH | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-33 | 78522 | 33 | 1 | Regular | B3LED-26' 4" | BMWDLED-750-80-30-SO-26' 4"-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 3 | Rohan Srivastava |  | Regular |  | TA-6, 26' 4", 5TH | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-34 | 78522 | 34 | 1 | Regular | B3LED-10' | BMWDLED-750-80-30-SO-10'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Rohan Srivastava |  | Regular |  | TA-6, 10', 5TH | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78522-35 | 78522 | 35 | 1 | Regular | B4PLED-39' 8" | BBPRLED-750-80-30-FL-39' 8"-W-UNV-DP-1+E(2)-TG9 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 4 | Rohan Srivastava |  | Regular |  | TC, 39' 8" EM(2), 200-C2 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78525-1 | 78525 | 1 | 1 | Regular | SCULPT-K(2X6) | SCDI-300-500-80-35-SO-FL-K(2X6)-BLK-UNV-DP-1-CA(48")-C(SWIVEL MOUNTING) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Jessica Kennedy | Picked - Complete | Regular |  | A-2'X6' RECT | 12 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78529-1 | 78529 | 1 | 1 | Regular | B4LED-12' | BBRLED-1000-80-35-FL-12'-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-01 | 01:36:48 | 2019-02-04 | 2019-02-07 | 1 | 1 | George Bacalla | Picked - Complete | Regular |  | 1-12' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78529-2 | 78529 | 2 | 1 | Regular | B4LED-20' | BBRLED-1000-80-35-FL-20'-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-01 | 01:36:50 | 2019-02-04 | 2019-02-07 | 1 | 2 | George Bacalla | Picked - Complete | Regular |  | 1-20' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78529-3 | 78529 | 3 | 1 | Regular | B4LED-4' | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-01 | 01:36:51 | 2019-02-04 | 2019-02-07 | 25 | 25 | George Bacalla | Picked - Complete | Regular |  | 1-4' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78529-4 | 78529 | 4 | 1 | Regular | B4LED-8' | BBRLED-1000-80-35-FL-8'-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-01 | 01:36:55 | 2019-02-04 | 2019-02-07 | 1 | 1 | George Bacalla | Picked - Complete | Regular |  | 1-8' | 15 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78530-1 | 78530 | 1 | 1 | Regular | B3LED-4 | BMDLED-1000-80-40-ASO-4-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Sacha Lempka |  | Regular |  | L11-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78530-2 | 78530 | 2 | 1 | Regular | B3LED-8 | BMDLED-1000-80-40-ASO-8-W-120-DP-1-CA(48) |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | Sacha Lempka |  | Regular |  | L11-8' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78534-1 | 78534 | 1 | 1 | Regular | B4LED-4' | BBRLED-950-80-35-FL-4'-W-UNV-DP-1-TG15-CP |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 70 | 70 | Joshua Zimet |  | Regular |  | R4 | 15 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78534-2 | 78534 | 2 | 1 | Regular | B4LED-2' | BBRLED-950-80-35-FL-2'-W-UNV-DP-1-TG15-CP |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 19 | 19 | Joshua Zimet |  | Regular |  | R4A | 15 | TRUE | TRUE | TRUE | TRUE | Ready | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78535-1 | 78535 | 1 | 1 | Regular | B3LED-4' | BMRLED-500-80-30-ASO-4'-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 3 | 3 | George Bacalla |  | Regular |  | LI04-4' | 7 | TRUE | FALSE | FALSE | TRUE | ToDo |  | ToDo | [7 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78535-2 | 78535 | 2 | 1 | Regular | B3LED-2' | BMRLED-500-80-30-ASO-2'-W-277-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 4 | George Bacalla |  | Regular |  | LI05-2' | 7 | TRUE | FALSE | FALSE | TRUE | ToDo |  | ToDo | [7 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78535-3 | 78535 | 3 | 1 | Regular | B3LED-2' | BMRLED-500-80-30-FL-2'-W-277-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 12 | 12 | George Bacalla |  | Regular |  | LI05D-2' | 7 | TRUE | FALSE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78535-4 | 78535 | 4 | 1 | Regular | B3LED-10' | SP19011-BMRLEDPAT-OPR-90(1)-500-80-30-ASO-FL-10'-NL-W-UNV-DP-1-DF | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 3 | George Bacalla |  | Regular |  | LI05/LI04-L-10' | 7 | TRUE | FALSE | FALSE | FALSE | ToDo |  | ToDo | [5 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78538-4 | 78538 | 4 | 1 | Regular | BEAM4-8' | BBS-S-8'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 24 | 24 | Zahra Vatani | Picked - Complete | High Priority |  | L6-8' EM | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78538-5 | 78538 | 5 | 1 | Regular | BEAM4-6' | BBS-S-6'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 12 | 12 | Zahra Vatani | Picked - Complete | High Priority |  | L6-6' EM | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78538-6 | 78538 | 6 | 1 | Regular | BEAM4-16' | BBS-S-16'-NL-T5HO-1-W-277-ERS-1-S-B1(LP600) | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 10 | 20 | Zahra Vatani | Picked - Complete | High Priority |  | L6-16' EM | 7 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78542-1 | 78542 | 1 | 1 | Regular | B2SLED-6' | B2SQDLED-400-80-30-L-6'-W-UNV-DP-1-CA(36") | Missing info. In SD | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Zahra Vatani |  | High Priority |  | P5-6' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78542-2 | 78542 | 2 | 1 | Regular | B2SLED-9' | B2SQDLED-400-80-30-L-8'-W-UNV-DP-1-CA(36") |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Zahra Vatani |  | High Priority |  | P6-8' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78542-3 | 78542 | 3 | 1 | Regular | B2SLED-4' | B2SQSLED-400-80-30-L-4'-W-UNV-DP-1-SC | Others | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 7 | 7 | Zahra Vatani |  | High Priority |  | P7-4' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78542-4 | 78542 | 4 | 1 | Regular | B2SLED-4' | B2SQDLED-400-80-30-L-4'-W-UNV-DP-1-CA(36") |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 6 | 6 | Zahra Vatani |  | High Priority |  | P4-4' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78545-1 | 78545 | 1 | 1 | Regular | ACCENT-4' | SCDLAC-AC(2)-D36-HX-D-500-80-30-FL-4'-BLK-UNV-DP-1-CT9(60") |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 6 | 6 | Zahra Vatani | Picked - Complete | Regular |  | A-4' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78553-1 | 78553 | 1 | 1 | Regular | B2LED-6' | BWDLED-400-80-35-SO-6'-W-277-DP-1 |  | Wiring Started | 2019-01-29 | 15:23:15 | 2019-01-30 | 2019-02-04 | 1 | 1 | Zahra Vatani |  | Regular |  | AG04 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 14:48 |  | FALSE | FALSE
78559-1 | 78559 | 1 | 1 | Regular | DIALED-22 | DIALED-22-2500-80-35-VL-W-277-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 39 | 39 | Rohan Srivastava |  | Regular |  | F01A | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-2 | 78559 | 2 | 1 | Regular | DIALED-22 | DIALED-22-4400-80-35-VL-W-277-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 80 | 80 | Rohan Srivastava |  | Regular |  | F01B | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-3 | 78559 | 3 | 1 | Regular | DIALED-24 | DIALED-24-7000-80-35-VL-W-UNV-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 11 | 11 | Rohan Srivastava |  | Regular |  | F02 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-4 | 78559 | 4 | 1 | Regular | MINLED-4' | MBSLED-600-80-35-S-4'-W-UNV-DP-1-S |  | Machine Shop Finished | 2019-02-03 | 14:48:58 | 2019-02-08 | 2019-02-13 | 5 | 5 | Rohan Srivastava |  | Regular |  | F03-4' | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78559-5 | 78559 | 5 | 1 | Regular | AULED-22 | AULED-22-2500-80-35-SO-W-277-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 22 | 22 | Rohan Srivastava |  | Regular |  | F04 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-6 | 78559 | 6 | 1 | Regular | DIALED-22 | DIALED-22-2500-80-35-VL-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 33 | 33 | Rohan Srivastava |  | Regular |  | F1A/EM | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-7 | 78559 | 7 | 1 | Regular | DIALED-22 | DIALED-22-4400-80-35-VL-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 10 | 10 | Rohan Srivastava |  | Regular |  | F1B/EM | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-8 | 78559 | 8 | 1 | Regular | MINLED-4' | MBSLED-600-80-35-S-4'-W-UNV-DP-1-S-B1(BSL310LP) |  | Machine Shop Finished | 2019-02-03 | 14:48:59 | 2019-02-08 | 2019-02-13 | 1 | 1 | Rohan Srivastava |  | Regular |  | F03-4' EM | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78559-9 | 78559 | 9 | 1 | Regular | AULED-22 | AULED-22-2500-80-35-SO-W-277-DP-1-TG9-B1(BSL310LP)-FW(6) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Rohan Srivastava |  | Regular |  | F04/EM | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78559-10 | 78559 | 10 | 1 | Regular | MINLED-4' | MBLED-500-80-35-S-4'-W-UNV-DP-1-CA(36) |  | Machine Shop Finished | 2019-02-03 | 14:49:06 | 2019-02-08 | 2019-02-13 | 2 | 2 | Rohan Srivastava |  | Regular |  | F05-4' | 10 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78563-1 | 78563 | 1 | 1 | Regular | PERFKT-CCL | SP19045(2)-CCL-SL-500-80-30-CL(6')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 2 | 4 | Zahra Vatani |  | High Priority |  | CL-6' | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78563-2 | 78563 | 2 | 1 | Regular | PERFKT-CCL | SP19045(2)-CCL-SL-500-80-30-CL(7')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 2 | 4 | Zahra Vatani |  | High Priority |  | CL-6' 8" | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78563-3 | 78563 | 3 | 1 | Regular | PERFKT-CCL | SP19045(2)-CCL-SL-500-80-30-CL(9')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 4 | 4 | Zahra Vatani |  | High Priority |  | CL-9' | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78565-1 | 78565 | 1 | 1 | Regular | AULED-14 | AULED-14-2400-90-40-SO-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 57 | 57 | George Bacalla |  | High Priority |  | L7 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78565-2 | 78565 | 2 | 1 | Regular | B4LED-8' | BBSLED-400-90-35-SO-8'-W-277-DP-1-SC |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | George Bacalla |  | High Priority |  | L12-8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78565-3 | 78565 | 3 | 1 | Regular | B4LED-16' | BBSLED-400-90-35-SO-16'-W-277-DP-1-SC |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 2 | 4 | George Bacalla |  | High Priority |  | L12-16' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78569-1 | 78569 | 1 | 1 | Regular | WB4LED-5 | WBRLED-500-80-30-S-5-C(RAL 7030)-UNV-DP-1-D | Shortage | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 31 | 31 | Stan Buyansky |  | High Priority |  | SD-5 | 18 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78580-1 | 78580 | 1 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST | Others | Wiring Started | 2019-01-30 | 07:18:10 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 108 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-2 | 78580 | 2 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST | Others | Wiring Started | 2019-01-30 | 07:18:13 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 113 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-3 | 78580 | 3 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:15 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 123 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-4 | 78580 | 4 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:16 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 127 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-5 | 78580 | 5 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:18 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 201 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-6 | 78580 | 6 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:19 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 210A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:03 |  | TRUE | FALSE
78580-7 | 78580 | 7 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:21 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 301 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-8 | 78580 | 8 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:22 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 302 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:03 |  | TRUE | FALSE
78580-9 | 78580 | 9 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:24 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 312A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:03 |  | TRUE | FALSE
78580-10 | 78580 | 10 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:26 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 315A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:03 |  | TRUE | FALSE
78580-11 | 78580 | 11 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:27 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 322 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-12 | 78580 | 12 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:29 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 402 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-13 | 78580 | 13 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:30 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 406A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-14 | 78580 | 14 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:32 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 407 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-15 | 78580 | 15 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:34 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 407A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-16 | 78580 | 16 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:36 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 415 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-17 | 78580 | 17 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:38 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 500-E1 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-18 | 78580 | 18 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:40 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 503 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-19 | 78580 | 19 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:41 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 504 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-20 | 78580 | 20 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:43 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 505 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-21 | 78580 | 21 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:44 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 506 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-22 | 78580 | 22 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:46 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 507 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-23 | 78580 | 23 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:47 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 508 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-24 | 78580 | 24 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:49 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 509A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-25 | 78580 | 25 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:50 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 520 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-26 | 78580 | 26 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:52 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', B106 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-27 | 78580 | 27 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:53 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', B116 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-28 | 78580 | 28 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:55 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', B117A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-29 | 78580 | 29 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:56 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G100-V | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-30 | 78580 | 30 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:07 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G101A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-31 | 78580 | 31 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:18:59 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G104A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-32 | 78580 | 32 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:01 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G107 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-33 | 78580 | 33 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:03 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G120 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-34 | 78580 | 34 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:11 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G124 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:07 |  | TRUE | FALSE
78580-35 | 78580 | 35 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:15 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G130C | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:13 |  | TRUE | FALSE
78580-36 | 78580 | 36 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:20 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G130D | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:13 |  | TRUE | FALSE
78580-37 | 78580 | 37 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:24 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G132 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:13 |  | TRUE | FALSE
78580-38 | 78580 | 38 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:28 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', G132B | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:13 |  | TRUE | FALSE
78580-39 | 78580 | 39 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:32 | 2019-02-01 | 2019-02-06 | 4 | 4 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', T100-GH | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:13 |  | TRUE | FALSE
78580-40 | 78580 | 40 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:36 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 4', 403 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-41 | 78580 | 41 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:40 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 18', 317A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-42 | 78580 | 42 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:45 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 18', 510A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-43 | 78580 | 43 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:19:49 | 2019-02-01 | 2019-02-06 | 2 | 4 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 18', G106 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-44 | 78580 | 44 | 1 | Regular | B3LED-30' | BMRLED-750-80-30-FL-30'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:19:53 | 2019-02-01 | 2019-02-06 | 1 | 4 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 30', 101 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-45 | 78580 | 45 | 1 | Regular | B3LED-30' | BMRLED-750-80-30-FL-30'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:19:57 | 2019-02-01 | 2019-02-06 | 3 | 12 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 30', 210D | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-46 | 78580 | 46 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:01 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 102 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-47 | 78580 | 47 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:06 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 111 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-48 | 78580 | 48 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:18 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 203 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-49 | 78580 | 49 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:38 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 204 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-50 | 78580 | 50 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:41 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 301 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-51 | 78580 | 51 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:45 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 322 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-52 | 78580 | 52 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:49 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 115C | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-53 | 78580 | 53 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:54 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 115E | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-54 | 78580 | 54 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:20:58 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 401 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-55 | 78580 | 55 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:02 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', 402 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:14 |  | TRUE | FALSE
78580-56 | 78580 | 56 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:06 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', B113 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-57 | 78580 | 57 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:10 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', G107 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-58 | 78580 | 58 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:14 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', G121 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-59 | 78580 | 59 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:19 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', G130C | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-60 | 78580 | 60 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:23 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 8', G132-1 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-61 | 78580 | 61 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:27 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 103 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-62 | 78580 | 62 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:31 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 115B | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-63 | 78580 | 63 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:35 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 115G | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-64 | 78580 | 64 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:40 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 212 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-65 | 78580 | 65 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:44 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 316 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-66 | 78580 | 66 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:48 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 324A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-67 | 78580 | 67 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:52 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 401 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-68 | 78580 | 68 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:22:08 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 404 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-69 | 78580 | 69 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:21:57 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', 510 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-70 | 78580 | 70 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:40 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', G114 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-71 | 78580 | 71 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:31 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', G136C | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-72 | 78580 | 72 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:29 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10', G137 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-73 | 78580 | 73 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:26:25 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10' E, B105-1 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-74 | 78580 | 74 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:26:20 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10' E, 316 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:15 |  | TRUE | FALSE
78580-75 | 78580 | 75 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:26:17 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 10' E, 315 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:16 |  | TRUE | FALSE
78580-76 | 78580 | 76 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:15 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 103 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:16 |  | TRUE | FALSE
78580-77 | 78580 | 77 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:12 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 106 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:16 |  | TRUE | FALSE
78580-78 | 78580 | 78 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:09 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 115A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:16 |  | TRUE | FALSE
78580-79 | 78580 | 79 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:06 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 115F | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:13 |  | TRUE | FALSE
78580-80 | 78580 | 80 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:04 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 117 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-81 | 78580 | 81 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:26:00 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 119 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-82 | 78580 | 82 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:58 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 121 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-83 | 78580 | 83 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:55 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 201 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-84 | 78580 | 84 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:53 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 303 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-85 | 78580 | 85 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:50 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 305 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-86 | 78580 | 86 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:47 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 308 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-87 | 78580 | 87 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:44 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 405 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-88 | 78580 | 88 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:41 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 405A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-89 | 78580 | 89 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:38 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', 415 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-90 | 78580 | 90 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:34 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', B104 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-91 | 78580 | 91 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:31 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', G101B | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-92 | 78580 | 92 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:29 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', G117 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-93 | 78580 | 93 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:25 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6', G125 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-94 | 78580 | 94 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:21 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 105 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-95 | 78580 | 95 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:18 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 107 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-96 | 78580 | 96 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:15 | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 109 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-97 | 78580 | 97 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:11 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 201 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-98 | 78580 | 98 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:08 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 204A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-99 | 78580 | 99 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:04 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 209 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-100 | 78580 | 100 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:25:01 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 209A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-101 | 78580 | 101 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:24:58 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 303 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-102 | 78580 | 102 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:24:55 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 312A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-103 | 78580 | 103 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:24:52 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 320A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-104 | 78580 | 104 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:24:49 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 400E | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-105 | 78580 | 105 | 1 | Regular | B3LED-2' | BMRLED-750-80-30-FL-2'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:24:46 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 2', 516A | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-106 | 78580 | 106 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(2)-ST |  | Wiring Started | 2019-01-30 | 07:24:43 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 18' E, G118 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-107 | 78580 | 107 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:24:40 | 2019-02-01 | 2019-02-06 | 2 | 6 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 20', 123 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-108 | 78580 | 108 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:24:37 | 2019-02-01 | 2019-02-06 | 2 | 6 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 20', 127 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:02 |  | TRUE | FALSE
78580-110 | 78580 | 110 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:24:31 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 20' E, 127 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-112 | 78580 | 112 | 1 | Regular | B3LED-14' | BMRLED-750-80-30-FL-14'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:24:25 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 14', 201 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-114 | 78580 | 114 | 1 | Regular | B3LED-14' | BMRLED-750-80-30-FL-14'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:24:19 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 14', 513 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-116 | 78580 | 116 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:24:13 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 20' E, 123 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-119 | 78580 | 119 | 1 | Regular | B3LED-14' | BMRLED-750-80-30-FL-14'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:23:20 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 14', 401 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-122 | 78580 | 122 | 1 | Regular | B3LED-14' | BMRLED-750-80-30-FL-14'-W-UNV-DP-2-ST |  | Wiring Started | 2019-01-30 | 07:23:12 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 14', 516 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-123 | 78580 | 123 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:23:27 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 20' E, 129 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:01 |  | TRUE | FALSE
78580-124 | 78580 | 124 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-E(1)-ST |  | Wiring Started | 2019-01-30 | 07:23:05 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6' E, G117 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:12 |  | TRUE | FALSE
78580-134 | 78580 | 134 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-FL-6'-W-UNV-DP-E(1)-ST |  | Wiring Started | 2019-01-30 | 07:22:31 | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 6' E, 401 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:11 |  | TRUE | FALSE
78580-135 | 78580 | 135 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-1+E(1)-ST |  | Wiring Started | 2019-01-30 | 07:22:25 | 2019-02-01 | 2019-02-06 | 1 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 16' E, G132 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:11 |  | TRUE | FALSE
78580-137 | 78580 | 137 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:22:19 | 2019-02-01 | 2019-02-06 | 2 | 4 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 16', G132-1 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:11 |  | TRUE | FALSE
78580-138 | 78580 | 138 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-1-ST |  | Wiring Started | 2019-01-30 | 07:22:15 | 2019-02-01 | 2019-02-06 | 3 | 6 | Rohan Srivastava | Picked - Complete | Regular |  | TA, 16', G132 | 1 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-01-29 15:11 |  | TRUE | FALSE
78581-1 | 78581 | 1 | 1 | Regular | B3LED-14' | BMRLED-750-80-30-FL-14'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 14' E, B104 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-2 | 78581 | 2 | 1 | Regular | B3LED-22' | BMRLED-750-80-30-FL-22'-W-UNV-DP-1+E(2)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 22' E, B114 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-3 | 78581 | 3 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 8', G132-1 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-4 | 78581 | 4 | 1 | Regular | B3LED-24' | BMRLED-750-80-30-FL-24'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 24', G132-1 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-5 | 78581 | 5 | 1 | Regular | B3PLED-10' 3" | BMPRLED-750-80-30-RG3-10' 3"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 10' 3", B108 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-6 | 78581 | 6 | 1 | Regular | B3PLED-10' 6" | BMPRLED-750-80-30-RG3-10' 6"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 10' 6", 500A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-7 | 78581 | 7 | 1 | Regular | B3PLED-10' 7" | BMPRLED-750-80-30-RG3-10' 7"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 10' 7", G127 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-8 | 78581 | 8 | 1 | Regular | B3PLED-11' 10" | BMPRLED-750-80-30-RG3-11' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 11' 10", 101A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-9 | 78581 | 9 | 1 | Regular | B3PLED-11' 10" | BMPRLED-750-80-30-RG3-11' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 11' 10", 101B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-10 | 78581 | 10 | 1 | Regular | B3PLED-12' | BMPRLED-750-80-30-RG3-12'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 12', 500B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-11 | 78581 | 11 | 1 | Regular | B3PLED-12' | BMPRLED-750-80-30-RG3-12'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 12', G131 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-12 | 78581 | 12 | 1 | Regular | B3PLED-12' | BMPRLED-750-80-30-RG3-12'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 12', G133 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-13 | 78581 | 13 | 1 | Regular | B3PLED-13' | BMPRLED-750-80-30-RG3-13'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 13', 413 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-14 | 78581 | 14 | 1 | Regular | B3PLED-14' 10" | BMPRLED-750-80-30-RG3-14' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 14' 10", 202 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-15 | 78581 | 15 | 1 | Regular | B3PLED-14' 4" | BMPRLED-750-80-30-RG3-14' 4"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 14' 4", B107 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-16 | 78581 | 16 | 1 | Regular | B3PLED-15' 3" | BMPRLED-750-80-30-RG3-15' 3"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 15' 3", 500A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-17 | 78581 | 17 | 1 | Regular | B3PLED-15' 6" | BMPRLED-750-80-30-RG3-15' 6"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 15' 6", B100B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-18 | 78581 | 18 | 1 | Regular | B3PLED-16' 1" | BMPRLED-750-80-30-RG3-16' 1"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 16' 1", 300A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-19 | 78581 | 19 | 1 | Regular | B3PLED-16' 2" | BMPRLED-750-80-30-RG3-16' 2"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 16' 2", 200A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-20 | 78581 | 20 | 1 | Regular | B3PLED-16' 9" | BMPRLED-750-80-30-RG3-16' 9"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 16' 9", 413 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-21 | 78581 | 21 | 1 | Regular | B3PLED-16' | BMPRLED-750-80-30-RG3-16'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 16', 202 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-22 | 78581 | 22 | 1 | Regular | B3PLED-16' | BMPRLED-750-80-30-RG3-16'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 16', 400A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-23 | 78581 | 23 | 1 | Regular | B3PLED-17' | BMPRLED-750-80-30-RG3-17'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 17', 307 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-24 | 78581 | 24 | 1 | Regular | B3PLED-19' 11" | BMPRLED-750-80-30-RG3-19' 11"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 19' 11", B100B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-25 | 78581 | 25 | 1 | Regular | B3PLED-21' 4" | BMPRLED-750-80-30-RG3-21' 4"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 21' 4", 300A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-26 | 78581 | 26 | 1 | Regular | B3PLED-21' 5" | BMPRLED-750-80-30-RG3-21' 5"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 21' 5", 200A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-27 | 78581 | 27 | 1 | Regular | B3PLED-21' 6" | BMPRLED-750-80-30-RG3-21' 6"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 21' 6", 400A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-28 | 78581 | 28 | 1 | Regular | B3PLED-21' | BMPRLED-750-80-30-RG3-21'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 21', 307 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-29 | 78581 | 29 | 1 | Regular | B3PLED-22' 2" | BMPRLED-750-80-30-RG3-22' 2"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 22' 2", 100A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-30 | 78581 | 30 | 1 | Regular | B3PLED-22' 2" | BMPRLED-750-80-30-RG3-22' 2"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 22' 2", 100B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-31 | 78581 | 31 | 1 | Regular | B3PLED-22' 9" | BMPRLED-750-80-30-RG3-22' 9"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 22' 9", G127 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-32 | 78581 | 32 | 1 | Regular | B3PLED-22' | BMPRLED-750-80-30-RG3-22'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-1, 22', G100A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-33 | 78581 | 33 | 1 | Regular | B3PLED-24' 3" | BMPRLED-750-80-30-RG3-24' 3"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TA-1, 24' 3", 100B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-34 | 78581 | 34 | 1 | Regular | B3PLED-27' 11" | BMPRLED-750-80-30-RG3-27' 11"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TA-1, 27' 11", G100A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-35 | 78581 | 35 | 1 | Regular | B3PLED-27' 3" | BMPRLED-750-80-30-RG3-27' 3"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TA-1, 27' 3", 100A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-36 | 78581 | 36 | 1 | Regular | B3PLED-3' 5" | BMPRLED-750-80-30-RG3-3' 5"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 3' 5", G138 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-37 | 78581 | 37 | 1 | Regular | B3PLED-3' 5" | BMPRLED-750-80-30-RG3-3' 5"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 3' 5", G140 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-38 | 78581 | 38 | 1 | Regular | B3PLED-4' 10" | BMPRLED-750-80-30-RG3-4' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 4' 10", G138 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-39 | 78581 | 39 | 1 | Regular | B3PLED-5' 1" | BMPRLED-750-80-30-RG3-5' 1"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 5' 1", G140 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-40 | 78581 | 40 | 1 | Regular | B3PLED-5' 2" | BMPRLED-750-80-30-RG3-5' 2"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 5' 2", G127 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-41 | 78581 | 41 | 1 | Regular | B3PLED-7' 10" | BMPRLED-750-80-30-RG3-7' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 10", 512 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-42 | 78581 | 42 | 1 | Regular | B3PLED-7' 10" | BMPRLED-750-80-30-RG3-7' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 10", 514 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-43 | 78581 | 43 | 1 | Regular | B3PLED-7' 2" | BMPRLED-750-80-30-RG3-7' 2"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 2", 300B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-44 | 78581 | 44 | 1 | Regular | B3PLED-7' 5" | BMPRLED-750-80-30-RG3-7' 5"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 5", 213 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-45 | 78581 | 45 | 1 | Regular | B3PLED-7' 5" | BMPRLED-750-80-30-RG3-7' 5"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 5", 400C | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-46 | 78581 | 46 | 1 | Regular | B3PLED-7' 6" | BMPRLED-750-80-30-RG3-7' 6"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 6", 413 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-47 | 78581 | 47 | 1 | Regular | B3PLED-7' 6" | BMPRLED-750-80-30-RG3-7' 6"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7' 6", 500B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-48 | 78581 | 48 | 1 | Regular | B3PLED-7' | BMPRLED-750-80-30-RG3-7'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 7', 152B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-49 | 78581 | 49 | 1 | Regular | B3PLED-8' 10" | BMPRLED-750-80-30-RG3-8' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8' 10", G112A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-50 | 78581 | 50 | 1 | Regular | B3PLED-8' 10" | BMPRLED-750-80-30-RG3-8' 10"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8' 10", G112B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-51 | 78581 | 51 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', 115D | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-52 | 78581 | 52 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', 123B | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-53 | 78581 | 53 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', 127A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-54 | 78581 | 54 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', 400D | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-55 | 78581 | 55 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', G109 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-56 | 78581 | 56 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', G113A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-57 | 78581 | 57 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', G114A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-58 | 78581 | 58 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', G118A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-59 | 78581 | 59 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', G120A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-60 | 78581 | 60 | 1 | Regular | B3PLED-8' | BMPRLED-750-80-30-RG3-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 8', G124A | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-61 | 78581 | 61 | 1 | Regular | B3PLED-9' 4" | BMPRLED-750-80-30-RG3-9' 4"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 9' 4", 100PB | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-62 | 78581 | 62 | 1 | Regular | B3PLED-9' 8" | BMPRLED-750-80-30-RG3-9' 8"-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 9' 8", 215 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-63 | 78581 | 63 | 1 | Regular | B3PLED-9' | BMPRLED-750-80-30-RG3-9'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA-1, 9', 100PA | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-64 | 78581 | 64 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-1+E(1)-DS |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA-2, 20' EM | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-65 | 78581 | 65 | 1 | Regular | B6LED-2' | SP19057(1)-B6RLED-1500-80-30-FL-2'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 114 | 114 | Rohan Srivastava |  | Priority |  | TA-4 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-66 | 78581 | 66 | 1 | Regular | B6LED-2' | SP19057(1)-B6RLED-1500-80-30-FL-2'-W-UNV-DP-E(1)-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 43 | 43 | Rohan Srivastava |  | Priority |  | TA-4 EM | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-67 | 78581 | 67 | 1 | Regular | B3LED-4 | BMSLED-750-80-30-SO-4-W-UNV-DP-E(1)-S |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 40 | 40 | Rohan Srivastava |  | Priority |  | TA-5 EM | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-68 | 78581 | 68 | 1 | Regular | B3LED-4' | BMSLED-750-80-30-SO-4'-BLK-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 3 | Rohan Srivastava |  | Priority |  | TA-5BLK | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-69 | 78581 | 69 | 1 | Regular | B3LED-4' | BMSLED-750-80-30-SO-4'-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 82 | 82 | Rohan Srivastava |  | Priority |  | TA-5W | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-70 | 78581 | 70 | 1 | Regular | B3LED-14' | BMWDLED-750-80-30-SO-14'-W-UNV-DP-1-C(TOP FEED) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA-6' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-71 | 78581 | 71 | 1 | Regular | B4PLED-31' 1" | BBPRLED-750-80-30-FL-31' 1"-W-UNV-DP-1+E(2)-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 31' 1"EM(2), 400-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-72 | 78581 | 72 | 1 | Regular | B4PLED-12' 10" | BBPRLED-750-80-30-FL-12' 10"-W-UNV-DP-1+E(1)-TG9-C(9'NO EM + 4'EM) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 2 | Rohan Srivastava |  | Priority |  | TC, 12' 10"EM, 400-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-73 | 78581 | 73 | 1 | Regular | B4PLED-27' | BBPRLED-750-80-30-FL-27'-W-UNV-DP-1+E(1)-TG9-C(10'NO EM + 4'EM+13'NO EM) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 27'EM, 400-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-74 | 78581 | 74 | 1 | Regular | B4PLED-28' 9" | BBPRLED-750-80-30-FL-28' 9"-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 28' 9", 300-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-75 | 78581 | 75 | 1 | Regular | B4PLED-30' | BBPRLED-750-80-30-FL-30'-W-UNV-DP-1+E(2)-TG9-C(EM ON ENDS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 30'EM, 100-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-76 | 78581 | 76 | 1 | Regular | B4PLED- 31' 1" | BBPRLED-750-80-30-FL- 31' 1"-W-UNV-DP-1+E(2)-TG9-C(EM ON ENDS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 31' 1"EM(2), 300-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-77 | 78581 | 77 | 1 | Regular | B4PLED-31' 2" | BBPRLED-750-80-30-FL-31' 2"-W-UNV-DP-1+E(2)-TG9-C(EM ON ENDS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 31' 2"EM(2), 200-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-78 | 78581 | 78 | 1 | Regular | B4PLED-31' 2" | BBPRLED-750-80-30-FL-31' 2"-W-UNV-DP-1+E(2)-TG9-C(EM ON ENDS) |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 3 | Rohan Srivastava |  | Priority |  | TC, 31' 2"EM(2), 500-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-79 | 78581 | 79 | 1 | Regular | B4PLED-39' 6" | BBPRLED-750-80-30-FL-39' 6"-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 2 | 8 | Rohan Srivastava |  | Priority |  | TC, 39' 6", 500-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-80 | 78581 | 80 | 1 | Regular | B4PLED-4' 10" | BBPRLED-750-80-30-FL-4' 10"-W-UNV-DP-E(1)-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 1 | Rohan Srivastava |  | Priority |  | TC, 4' 10"EM, 100-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-81 | 78581 | 81 | 1 | Regular | B4PLED-40' 2" | BBPRLED-750-80-30-FL-40' 2"-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 1 | 4 | Rohan Srivastava |  | Priority |  | TC, 40' 2", 100-C2 | 1 | TRUE | FALSE | FALSE | FALSE | ToDo | [6 empty] | ToDo |  |  | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-82 | 78581 | 82 | 1 | Regular | B2LED-21' 10"X25' | BRLEDPAT-ASO-112.5-750-80-30-SO-FL-21' 10"X25'-EX-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 5 | Rohan Srivastava |  | Priority |  | TZ, 46' 10", | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-83 | 78581 | 83 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16' E, B105-2 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-84 | 78581 | 84 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 16' E, B111 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-85 | 78581 | 85 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16' E, G114 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-86 | 78581 | 86 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 16' E, 302 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-87 | 78581 | 87 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16' E, 511 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-88 | 78581 | 88 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Rohan Srivastava |  | Priority |  | TA, 10' E, 129 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-89 | 78581 | 89 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10' E, 103 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-90 | 78581 | 90 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10' E, 404 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-91 | 78581 | 91 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10' E, 415 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-92 | 78581 | 92 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10' E, G114 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-93 | 78581 | 93 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10' E, G137 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-94 | 78581 | 94 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16', 402 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-95 | 78581 | 95 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16', 404 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-96 | 78581 | 96 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16', 516 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-97 | 78581 | 97 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 16', B105-2 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-98 | 78581 | 98 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 16', B111 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-99 | 78581 | 99 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 16', 209 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-100 | 78581 | 100 | 1 | Regular | B3LED-16' | BMRLED-750-80-30-FL-16'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 16', 407 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-101 | 78581 | 101 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10', 201 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-102 | 78581 | 102 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10', 302 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-103 | 78581 | 103 | 1 | Regular | B3LED-10' | BMRLED-750-80-30-FL-10'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 10', 406 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-104 | 78581 | 104 | 1 | Regular | B3LED-4' | BMSLED-750-80-30-SO-4'-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Rohan Srivastava |  | Priority |  | TA-5, 8', 210A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-105 | 78581 | 105 | 1 | Regular | B3LED-14' | BMRLED-750-80-30-FL-14'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 14', B104 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-106 | 78581 | 106 | 1 | Regular | B3LED-22' | BMRLED-750-80-30-FL-22'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 6 | Rohan Srivastava |  | Priority |  | TA, 22', B114 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-107 | 78581 | 107 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18', 415 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-108 | 78581 | 108 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 18', G114 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-109 | 78581 | 109 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 6 | Rohan Srivastava |  | Priority |  | TA, 18', G118 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-110 | 78581 | 110 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 6 | Rohan Srivastava |  | Priority |  | TA, 18', G120 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-111 | 78581 | 111 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 3 | 6 | Rohan Srivastava |  | Priority |  | TA, 18', G124 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-112 | 78581 | 112 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-2-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18', 101 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-113 | 78581 | 113 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 121 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-114 | 78581 | 114 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 204 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-115 | 78581 | 115 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 218 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-116 | 78581 | 116 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 314 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-117 | 78581 | 117 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 316 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-118 | 78581 | 118 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 317 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-119 | 78581 | 119 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 403 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-120 | 78581 | 120 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 406 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-121 | 78581 | 121 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-1+E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 4 | Rohan Srivastava |  | Priority |  | TA, 18' E, 510 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-122 | 78581 | 122 | 1 | Regular | B3LED-18' | BMRLED-750-80-30-FL-18'-W-UNV-DP-E(4)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 18' E, 511A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-123 | 78581 | 123 | 1 | Regular | B3LED-20' | BMRLED-750-80-30-FL-20'-W-UNV-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 2 | Rohan Srivastava |  | Priority |  | TA, 20', G132-1 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-124 | 78581 | 124 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-E(1)-ST |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 1 | 1 | Rohan Srivastava |  | Priority |  | TA, 4', G132 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-125 | 78581 | 125 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Rohan Srivastava |  | Priority |  | TA, 4', 100-F1 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-126 | 78581 | 126 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Rohan Srivastava |  | Priority |  | TA, 4', 326 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-127 | 78581 | 127 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Rohan Srivastava |  | Priority |  | TA, 4', 328 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78581-128 | 78581 | 128 | 1 | Regular | B3LED-8' | BMRLED-750-80-30-FL-8'-W-UNV-DP-1-D |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 2 | 2 | Rohan Srivastava |  | Priority |  | TA, 8', 318 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78588-1 | 78588 | 1 | 1 | Regular | SCULPT-26 | SCIPAT-REC-90(4)-500-80-30-SO-26-NL-C(RAL6022)-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-08 | 2019-02-13 | 1 | 4 | Gagandeep Singh |  | High Priority |  | ELEV LOBBY-6'X12' NORTH | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78588-2 | 78588 | 2 | 1 | Regular | SCULPT-26 | SCIPAT-REC-90(4)-500-80-30-SO-26-NL-C(RAL6022)-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-08 | 2019-02-13 | 1 | 4 | Gagandeep Singh |  | High Priority |  | ELEV LOBBY-6'X12' SOUTH | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78590-1 | 78590 | 1 | 1 | Regular | STNCLS-12' | STSLF-SO-400-80-35-12'-BLK-UNV-MD-1-SG9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 9 | 9 | Jessica Kennedy | Picked - Complete | Regular |  | D-12' | 12 | TRUE | TRUE | FALSE | TRUE |  | ToDo |  |  | ToDo | [5 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78593-1 | 78593 | 1 | 1 | Regular | SL2LED-4 | SL2HLED-2XSL-1000-750-80-40-SM-4-AP-UNV-DP-2-CA(36) |  | Machine Shop Finished | 2019-01-30 | 19:26:51 | 2019-01-29 | 2019-02-01 | 3 | 3 | Christina Torok | Picked - Complete | High Priority |  | LD | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78593-2 | 78593 | 2 | 1 | Regular | SL2LED-4 | SL2HLED-2XSL-1000-750-80-40-SM-4-AP-UNV-DP-2-CA(36)-B1(BSL10LST) |  | Machine Shop Finished | 2019-01-30 | 15:00:54 | 2019-01-29 | 2019-02-01 | 2 | 2 | Christina Torok | Picked - Complete | High Priority |  | LDE | 4 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78593-3 | 78593 | 3 | 1 | Regular | SCULPT-6 | SCS-750-80-40-0.5P-6-AP-UNV-DP-1-S |  | Machine Shop Finished | 2019-02-01 | 11:28:38 | 2019-01-29 | 2019-02-01 | 2 | 2 | Christina Torok | Picked - Complete | High Priority |  | LG | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78593-4 | 78593 | 4 | 1 | Regular | SCULPT-20 | SCDPAT-SQ-90(4)-750-80-40-0.5M-20-NL-AP-UNV-DP-1-CA(36) |  | Machine Shop Finished | 2019-02-04 | 10:29:25 | 2019-01-29 | 2019-02-01 | 4 | 16 | Christina Torok | Picked - Complete | High Priority |  | LH | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78594-1 | 78594 | 1 | 1 | Regular | B3LED-44' | BMRLEDPAT-REC-90-500-90-30-SO-FL-44'-EX-W-277-DP-1-TG9-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 2 | 16 | Gagandeep Singh |  | Regular |  | LT51B/19-8'X14' RECT | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-2 | 78594 | 2 | 1 | Regular | CLICK-6' | SP19052(1)-CLKLED-750-90-30-SO-6'-W-277-DP-1-TG9-FW(6)-C(ADDITIONAL SPRING IN CENTER) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 4 | 4 | Gagandeep Singh |  | Regular |  | LT54/18-6' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-3 | 78594 | 3 | 1 | Regular | CLICK-6' | SP19052(1)-CLKLED-750-90-30-SO-6'-W-277-DP-1-TG9-FW(6)-C(ADDITIONAL SPRING IN CENTER) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 79 | 79 | Gagandeep Singh |  | Regular |  | LT54/19-6' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-4 | 78594 | 4 | 1 | Regular | CLICK-8' | SP19052(1)-CLKLED-750-90-30-SO-8'-W-277-DP-1-TG9-FW(6)-C(ADDITIONAL SPRING IN CENTER) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 9 | 9 | Gagandeep Singh |  | Regular |  | LT54A/18-8' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-5 | 78594 | 5 | 1 | Regular | CLICK-8' | SP19052(1)-CLKLED-750-90-30-SO-8'-W-277-DP-1-TG9-FW(6)-C(ADDITIONAL SPRING IN CENTER) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 10 | 10 | Gagandeep Singh |  | Regular |  | LT54A/19-8' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-6 | 78594 | 6 | 1 | Regular | CLICK-4' | CLKLED-750-90-30-SO-4'-W-277-DP-1-TG9-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 40 | 40 | Gagandeep Singh |  | Regular |  | LT54B/18-4' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-7 | 78594 | 7 | 1 | Regular | CLICK-4' | CLKLED-750-90-30-SO-4'-W-277-DP-1-TG9-FW(6) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 8 | 8 | Gagandeep Singh |  | Regular |  | LT54B/19-4' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78594-8 | 78594 | 8 | 1 | Regular | CLICK-16' | SP19052(1)-CLKLED-750-90-30-SO-16'-W-277-DP-1-TG9-FW(6)-C(ADDITIONAL SPRING IN CENTER) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 2 | 4 | Gagandeep Singh |  | Regular |  | LT54E/19-16' | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78596-1 | 78596 | 1 | 1 | Regular | SCULPT-10' | SCDI-750-500-80-30-BW-FL-10'-W-347-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 2 | 2 | George Bacalla |  | High Priority |  | L2-10' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78596-2 | 78596 | 2 | 1 | Regular | SLMLED-8' | SLLED-SL 100/0-1500-80-30-NO-8'-W-347-DP-1-CA(120) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 21 | 21 | George Bacalla |  | High Priority |  | L4A-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78596-3 | 78596 | 3 | 1 | Regular | SLMLED-8' | SLLED-SL 25/75-800-80-30-VL-8'-W-347-DP-1-CA(120) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 7 | 7 | George Bacalla |  | High Priority |  | L4B-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78596-4 | 78596 | 4 | 1 | Regular | SCULPT-8' | SCDI-750-500-80-30-BW-FL-8'-W-347-DP-1-CA(36) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 3 | 3 | George Bacalla |  | High Priority |  | L2-8' | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78603-1 | 78603 | 1 | 1 | Regular | STENCL-6' | STD-SO-300-80-35-6'-C(RAL 1023)-UNV-MD-1-CA(36)-RC | Shortage | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | George Bacalla |  | Regular |  | D-6' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78603-2 | 78603 | 2 | 1 | Regular | STENCL-5' | STD-SO-300-80-35-5'-C(RAL 5018)-UNV-MD-1-CA(36)-RC |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | George Bacalla |  | Regular |  | E-5' | 1 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78607-1 | 78607 | 1 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(4'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 11 | 22 | Christina Torok |  | Regular |  | L30-2X2 | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78607-2 | 78607 | 2 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(10'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 9 | 18 | Christina Torok |  | Regular |  | L30-5X5 | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78607-3 | 78607 | 3 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(6'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 6 | Christina Torok |  | Regular |  | L30-3X3 | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78607-4 | 78607 | 4 | 1 | Regular | STENCL-STFC | STFC-NO-DSO(8'-400)-80-40-AH(1)-AP-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 6 | Christina Torok |  | Regular |  | L30-4X4 | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78614-1 | 78614 | 1 | 1 | Regular | WDILED-2 | WBDIWLED-500-500-80-35-SO-SO-2-BLK-UNV-DP-1-BF | Shortage | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 24 | 24 | Jessica Kennedy | Picked - Complete | High Priority |  | W2 | 7 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78616-1 | 78616 | 1 | 1 | Regular | B4LED-8 | BBDLED-750-80-40-SO-8-BLK-UNV-DP-1-CA(36") | Shortage | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 2 | 2 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | D4 | 12 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78617-1 | 78617 | 1 | 1 | Regular | GRAZE-16'0" | GPRLED-NLNW-650-80-35-RG2-16'0"-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 2 | Joshua Zimet | Picked - Complete | High Priority |  | LT-6-16' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78624-1 | 78624 | 1 | 1 | Regular | SKFLED-22 | SKFLED-22-2000-80-30-2SF-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-28 | 2019-03-05 | 5 | 5 | Rajithan Sivapatharajahon |  | Regular |  | F1 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78624-2 | 78624 | 2 | 1 | Regular | SKFLED-22 | SKFLED-22-3000-80-30-2SF-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-28 | 2019-03-05 | 299 | 299 | Rajithan Sivapatharajahon |  | Regular |  | F2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78624-3 | 78624 | 3 | 1 | Regular | SKFLED-22 | SKFLED-22-4000-80-30-2SF-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-28 | 2019-03-05 | 31 | 31 | Rajithan Sivapatharajahon |  | Regular |  | F3 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78624-4 | 78624 | 4 | 1 | Regular | SKFLED-22 | SKFLED-22-2000-80-30-2SF-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-05 | 2019-02-08 | 25 | 25 | Rajithan Sivapatharajahon |  | Regular |  | F4 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78624-4 | 78624 | 4 | 2 | Regular | SKFLED-22 | SKFLED-22-2000-80-30-2SF-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-28 | 2019-03-05 | 223 | 223 | Rajithan Sivapatharajahon |  | Regular |  | F4 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78636-1 | 78636 | 1 | 1 | Regular | B3LED-4' | BMDLED-1000-80-30-SO-4'-BLK-UNV-DP-1-SA(48) |  | Wiring Started | 2019-01-30 | 07:08:05 | 2019-01-30 | 2019-02-04 | 1 | 1 | Jessica Kennedy | Picked - Complete | Regular |  | W3-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 14:48 |  | TRUE | FALSE
78637-1 | 78637 | 1 | 1 | Regular | CUBLED-8' | CUBLED-SL 75/25-1000-80-35-SO-8'-AP-UNV-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-31 | 13:50:28 | 2019-01-31 | 2019-02-05 | 1 | 1 | George Bacalla | Picked - Complete | Regular |  | J-8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:11 |  | TRUE | FALSE
78637-2 | 78637 | 2 | 1 | Regular | CUBLED-4' | CUBWLED-SL 75/25-1000-80-35-SO-4'-AP-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 3 | 3 | George Bacalla | Picked - Complete | Regular |  | K-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | TRUE | 2019-01-31 17:11 |  | TRUE | FALSE
78640-1 | 78640 | 1 | 1 | Regular | B2LED-4 | BRLED-536-90-40-FL-4-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Stan Buyansky | Picked - Complete | Regular |  | H-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78640-3 | 78640 | 3 | 1 | Regular | B2LED-32' | BRLED-536-90-40-FL-32'-W-277-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 3 | Stan Buyansky | Picked - Complete | Regular |  | H-32 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78642-1 | 78642 | 1 | 1 | Regular | B6LED-4 | B6SLED-600-80-30-SO-4-W-UNV-DP-1-S | Wrong info. In SD | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 63 | 63 | Stan Buyansky |  | Regular |  | F1 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78642-2 | 78642 | 2 | 1 | Regular | B6LED-8 | B6DLED-600-80-30-SO-8-W-UNV-DP-1-CA(96")+SM |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 3 | 3 | Stan Buyansky |  | Regular |  | F1A-96 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-3 | 78642 | 3 | 1 | Regular | B2LED-8' | BWDLED-500-80-30-SO-8'-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-04-10 | 2019-04-15 | 8 | 8 | Stan Buyansky |  | Regular |  | F1D | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-4 | 78642 | 4 | 1 | Regular | B6LED-8 | B6DLED-600-80-30-SO-8-W-UNV-DP-1-CA(120")+SM |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 3 | 3 | Stan Buyansky |  | Regular |  | F1A-120 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-5 | 78642 | 5 | 1 | Regular | B6LED-8 | B6DLED-600-80-30-SO-8-W-UNV-DP-1-CA(144")+SM |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 3 | 3 | Stan Buyansky |  | Regular |  | F1A-144 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-6 | 78642 | 6 | 1 | Regular | B6LED-4 | B6SLED-600-80-30-SO-4-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 30 | 30 | Stan Buyansky |  | Regular |  | F1B-4'-A | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-7 | 78642 | 7 | 1 | Regular | B6LED-6 | B6SLED-600-80-30-SO-6-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-04-10 | 2019-04-15 | 20 | 20 | Stan Buyansky |  | Regular |  | F1B-6 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-8 | 78642 | 8 | 1 | Regular | B6LED-4 | B6SLED-600-80-30-SO-4-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 19 | 19 | Stan Buyansky |  | Regular |  | F1B-4'-B | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-9 | 78642 | 9 | 1 | Regular | B6LED-8 | B6DLED-600-80-30-SO-8-W-UNV-DP-1-CA(96")+SM |  | Scheduled/Released |  |  | 2019-04-10 | 2019-04-15 | 2 | 2 | Stan Buyansky |  | Regular |  | F1C-CABLE-96 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-10 | 78642 | 10 | 1 | Regular | B6LED-8 | B6DLED-600-80-30-SO-8-W-UNV-DP-1-CA(120")+SM |  | Scheduled/Released |  |  | 2019-04-10 | 2019-04-15 | 2 | 2 | Stan Buyansky |  | Regular |  | F1C-CABLE-120 | 18 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78642-11 | 78642 | 11 | 1 | Regular | B6LED-4 | B6SLED-600-80-30-SO-4-W-UNV-DP-1-SC |  | Scheduled/Released |  |  | 2019-02-26 | 2019-03-01 | 91 | 91 | Stan Buyansky |  | Regular |  | F3 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78643-5 | 78643 | 5 | 1 | Regular | TB2LED-8' | TB2DILED-400-1000-80-35-SL-SO-8'-W-UNV-DP-1-CA(72) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 7 | 7 | George Bacalla |  | Regular |  | B-8' | 15 | TRUE | TRUE | TRUE | TRUE |  | InProg | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78645-1 | 78645 | 1 | 1 | Regular | TB2LED-6 | TB2DILED-750-500-80-40-SO-L-6-W-UNV-LT(LDE1)-1-CA(48)-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | Mechanical issue | Wiring Started | 2019-01-27 | 13:32:48 | 2019-01-29 | 2019-02-01 | 1 | 1 | Sacha Lempka |  | High Priority |  | L5-A | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 11:22 |  | TRUE | TRUE
78645-2 | 78645 | 2 | 1 | Regular | TB2LED-6 | TB2DILED-750-500-80-40-SO-L-6-W-UNV-LT(LDE1)-2-CA(48)-C(DFCSJ-OEM-RF & DFC-OEM-DBI) | Electrical issue | Wiring Started | 2019-01-27 | 13:32:52 | 2019-01-29 | 2019-02-01 | 1 | 1 | Sacha Lempka |  | High Priority |  | L5-NL | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-29 11:22 |  | TRUE | TRUE
78650-1 | 78650 | 1 | 1 | Regular | B4LED-8' | BBDLED-1000-80-35-SO-8'-W-UNV-DP-1-CT15(36) |  | Machine Shop Finished | 2019-02-04 | 10:36:11 | 2019-01-30 | 2019-02-04 | 3 | 3 | Sacha Lempka | Picked - Complete | High Priority |  | A-8' | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78650-2 | 78650 | 2 | 1 | Regular | B4LED-4' | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-01-30 | 2019-02-04 | 12 | 12 | Sacha Lempka | Picked - Complete | High Priority |  | A-4' | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78651-1 | 78651 | 1 | 1 | Regular | SLMLED-6 | SLWLED-SL 75/25-1000-80-35-RE-6-W-UNV-DP-1 |  | Machine Shop Finished | 2019-02-03 | 16:22:03 | 2019-01-31 | 2019-02-05 | 1 | 1 | Sacha Lempka | Picked - Complete | Regular |  | LW2-6 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78651-2 | 78651 | 2 | 1 | Regular | SLMLED-8 | SLWLED-SL 75/25-1000-80-35-RE-8-W-UNV-DP-1 |  | Machine Shop Finished | 2019-02-03 | 16:22:06 | 2019-01-31 | 2019-02-05 | 8 | 8 | Sacha Lempka | Picked - Complete | Regular |  | LW2-8 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78651-3 | 78651 | 3 | 1 | Regular | SLMLED-12 | SLWLED-SL 75/25-1000-80-35-RE-12-W-UNV-DP-1 |  | Machine Shop Finished | 2019-02-03 | 16:22:08 | 2019-01-31 | 2019-02-05 | 1 | 1 | Sacha Lempka | Picked - Complete | Regular |  | LW2-12 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78658-1 | 78658 | 1 | 1 | Regular | B3PLED-20'6" | BMPRLED-1000-80-30-FL-20'6"-W-120-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 2 | 4 | Rajithan Sivapatharajahon |  | Regular |  | F | 12 | TRUE | TRUE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78658-2 | 78658 | 2 | 1 | Regular | SCULPT-3 | SCRV-400-90-30-FL-3-W-120-DP-1-D |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 4 | 4 | Rajithan Sivapatharajahon |  | Regular |  | G | 12 | TRUE | TRUE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78659-1 | 78659 | 1 | 1 | Regular | SCULPT-2X2 | SCR-300-80-40-FL-2X2-W-UNV-DP-1-MFTB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 43 | 43 | Jessica Pasternyk |  | Regular |  | ML1-2X2 | 18 | TRUE | TRUE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78659-2 | 78659 | 2 | 1 | Regular | SCULPT-2X2 | SCR-500-80-40-FL-2X2-W-UNV-DP-1-MFTB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 57 | 57 | Jessica Pasternyk |  | Regular |  | ML2-2X2 | 18 | TRUE | TRUE | FALSE | FALSE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78661-1 | 78661 | 1 | 1 | Regular | WWPRFK-8 | WWR-SL-750-80-40-8-W-UNV-LT(LDE1)-1-TG9-C(DFCSJ-OEM-RF & DFC-OEM-DBI) |  | Machine Shop Started |  |  | 2019-01-29 | 2019-02-01 | 1 | 1 | Sacha Lempka |  | High Priority |  | L7 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78661-2 | 78661 | 2 | 1 | Regular | B4LED-4 | BBRLED-750-80-40-FL-4-W-UNV-LT(LDE1)-1-TG9-C(DFCSJ-OEM-RF & DFC-OEM-DBI) |  | Machine Shop Finished | 2019-02-01 | 01:32:32 | 2019-01-29 | 2019-02-01 | 2 | 2 | Sacha Lempka |  | High Priority |  | L12 | 12 | TRUE | TRUE | TRUE | TRUE | Ready | Ready |  |  |  |  | Ready | Ready |  |  | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78663-1 | 78663 | 1 | 1 | Regular | SCULPT-8 | SCDI-500-500-80-35-SO-0.5M-8-AP-UNV-DP-1-CA(36)-B1(BSL10LST) |  | Machine Shop Started |  |  | 2019-01-28 | 2019-02-05 | 3 | 3 | Joshua Zimet | Picked - Complete | Regular |  | F5 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78664-1 | 78664 | 1 | 1 | Regular | STENCL-12' | STD-SO-400-80-30-12'-W-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 8 | Joshua Zimet |  | Regular |  | F4-12' | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78664-2 | 78664 | 2 | 1 | Regular | STENCL-15' | STD-SO-400-80-30-15'-W-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 3 | 9 | Joshua Zimet |  | Regular |  | F4-15' | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78664-3 | 78664 | 3 | 1 | Regular | STENCL-25' | STD-SO-400-80-30-25'-W-UNV-MD-1-CT9(36)-RC |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 4 | 16 | Joshua Zimet |  | Regular |  | F4-25' | 7 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78667-1 | 78667 | 1 | 1 | Regular | B3LED-16' | BMRLED-500-80-30-1.25M-16'-W-277-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 2 | Jessica Kennedy |  | Regular |  | B1-16' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78680-1 | 78680 | 1 | 1 | Regular | TWGLED-4' | TWRWLED-SL 90/10-750-80-40-SO-4'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 9 | 9 | Zahra Vatani | Picked - Complete | High Priority |  | L106-4' | 18 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78687-1 | 78687 | 1 | 1 | Regular | B4LED-4' | BBDLED-900-80-35-SO-4'-W-UNV-DP-1-CT9(36)-C(4.5" CANOPIES) |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 6 | 6 | Gaurav Jain |  | Regular |  | L48 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78687-2 | 78687 | 2 | 1 | Regular | WWPRFK-2' | WWR-SL-500-80-35-L-2'-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Gaurav Jain |  | Regular |  | L24W | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78690-1 | 78690 | 1 | 1 | Regular | DIALED-24 | DIALED-24-3100-80-35-VL-W-UNV-DP-1-TB9 |  | Wiring Started | 2019-02-01 | 10:49:30 | 2019-01-30 | 2019-02-04 | 5 | 5 | Stan Buyansky |  | Regular |  | LE | 10 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78690-2 | 78690 | 2 | 1 | Regular | DIALED-24 | DIALED-24-3100-80-35-VL-W-UNV-DP-1-TB9-B1(BSL10LST) |  | Wiring Started | 2019-02-04 | 09:18:09 | 2019-01-30 | 2019-02-04 | 5 | 5 | Stan Buyansky |  | Regular |  | LE-EM | 10 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78694-1 | 78694 | 1 | 1 | Regular | B4LED-16 | BBDILED-400-750-90-35-SO-16-W-UNV-DP-1-CA(132) |  | Machine Shop Finished | 2019-01-28 | 14:56:51 | 2019-02-07 | 2019-02-12 | 10 | 20 | Stan Buyansky |  | Regular |  | D | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78694-2 | 78694 | 2 | 1 | Regular | B4LED-8 | BBRLED-1000-90-35-1.5M-8-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 8 | 8 | Stan Buyansky |  | Regular |  | K | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78694-3 | 78694 | 3 | 1 | Regular | B4LED-16 | BBDILED-400-750-90-35-SO-16-W-UNV-DP-1-CA(132)-B1(BSL10LST) |  | Machine Shop Finished | 2019-01-28 | 14:56:55 | 2019-02-07 | 2019-02-12 | 10 | 20 | Stan Buyansky |  | Regular |  | DE | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78699-1 | 78699 | 1 | 1 | Regular | B3LED-26' | BMDLED-1000-80-35-SO-26'-BLK-UNV-DP-1-CA(72") |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 3 | Zahra Vatani | Picked - Complete | Regular |  | D2-26' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78699-2 | 78699 | 2 | 1 | Regular | B3LED-24' | BMDLED-1000-80-35-SO-24'-BLK-UNV-DP-1-CA(72") | Others | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Zahra Vatani | Picked - Complete | Regular |  | D2-24' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | TRUE
78699-3 | 78699 | 3 | 1 | Regular | B3LED-16' | BMDLED-1000-80-35-SO-16'-BLK-UNV-DP-1-CA(72") |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 4 | Zahra Vatani | Picked - Complete | Regular |  | D2-16' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78699-4 | 78699 | 4 | 1 | Regular | B3LED-8' | BMDLED-1000-80-35-SO-8'-BLK-UNV-DP-1-CA(72") |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Zahra Vatani | Picked - Complete | Regular |  | D2-8' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78699-5 | 78699 | 5 | 1 | Regular | B3LED-9' | BMDLED-1000-80-35-SO-9'-BLK-UNV-DP-1-CA(72") |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Zahra Vatani | Picked - Complete | Regular |  | D2-9' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78699-6 | 78699 | 6 | 1 | Regular | B3LED-20' | BMDLED-1000-80-35-SO-20'-BLK-UNV-DP-1-CA(72") |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Zahra Vatani |  | Regular |  | D2-20' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78703-1 | 78703 | 1 | 1 | Regular | SCULPT-4' | SCWDI-750-500-80-35-SO-FL-4'-W-UNV-DP-1-B1(BSL10LST) | Missing parts in BOM | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | FT9-4' | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78706-1 | 78706 | 1 | 1 | Regular | SCULPT-8' | SCS-300-80-35-FL-8'-BLK-UNV-DP-1-SB9 |  | Machine Shop Finished | 2019-02-04 | 07:29:36 | 2019-02-04 | 2019-02-07 | 7 | 7 | Rohan Srivastava | Picked - Complete | Regular |  | D-8' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:49 |  | TRUE | FALSE
78706-2 | 78706 | 2 | 1 | Regular | SCULPT-8 | SCDI-300-300-80-35-SO-FL-8-BLK-UNV-DP-1-SA(48) |  | Machine Shop Finished | 2019-02-04 | 07:29:39 | 2019-02-04 | 2019-02-07 | 10 | 10 | Rohan Srivastava | Picked - Complete | Regular |  | F-8' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:49 |  | TRUE | FALSE
78707-1 | 78707 | 1 | 1 | Regular | SCULPT-K(4X4) | SCD-500-80-35-FL-K(4X4)-W-UNV-DP-1-CT9(48) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Stan Buyansky | Picked - Complete | Regular |  | F12 | 12 | TRUE | TRUE | FALSE | TRUE |  | Ready | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78708-1 | 78708 | 1 | 1 | Regular | CUBLED-4' | CUBWLED-SL 75/25-800-80-40-SO-4'-W-277-DP-1-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 4 | 4 | Zahra Vatani |  | High Priority |  | I-4' E | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78708-2 | 78708 | 2 | 1 | Regular | CUBLED-6 | CUBWLED-SL 75/25-800-80-40-SO-6'-W-277-DP-1-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 2 | Zahra Vatani |  | High Priority |  | I-6' E | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78708-3 | 78708 | 3 | 1 | Regular | CUBLED-24 | CUBWLED-SL 75/25-800-80-40-SO-24'-W-277-DP-1-B2(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 6 | 12 | Zahra Vatani |  | High Priority |  | I-24' E | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78708-4 | 78708 | 4 | 1 | Regular | CUBLED-4' | CUBWLED-SL 75/25-800-80-40-SO-4'-W-277-DP-1 |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 2 | Zahra Vatani |  | High Priority |  | I-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78710-1 | 78710 | 1 | 1 | Regular | SCULPT-2X6 | SCDI-300-300-80-40-SO-0.5M-2X6-W-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 2 | 2 | George Bacalla | Picked - Complete | Regular |  | A-2X6 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78710-2 | 78710 | 2 | 1 | Regular | SCULPT-6 | SCDI-300-300-80-40-SO-0.5M-6'-W-UNV-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-25 | 11:04:35 | 2019-02-01 | 2019-02-06 | 3 | 3 | George Bacalla | Picked - Complete | Regular |  | A1-6' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78710-3 | 78710 | 3 | 1 | Regular | SCULPT-4X4 | SCDI-300-300-80-40-SO-0.5M-4X4-W-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 1 | George Bacalla | Picked - Complete | Regular |  | B-4X4 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [6 empty] | Ready |  | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78711-1 | 78711 | 1 | 1 | Regular | B4LED-2' | BBWDILED-400-750-90-35-SO-2'-W-277-DP-1+GTD(1) |  | Machine Shop Finished | 2019-02-03 | 23:05:43 | 2019-02-01 | 2019-02-06 | 1 | 1 | Joshua Zimet | Picked - Complete | Regular |  | F3 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:03 |  | TRUE | FALSE
78715-1 | 78715 | 1 | 1 | Regular | ZENSQ-16 | ZESQDI-SL 75/25-900-80-35-MAL-16-W-UNV-MD-1-CA(36) | Shortage | Machine Shop Finished | 2019-02-04 | 07:27:46 | 2019-02-04 | 2019-02-07 | 1 | 2 | Rajithan Sivapatharajahon |  | Regular |  | P | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78720-1 | 78720 | 1 | 1 | Replacement | SKLPTP-52 | SCPLED-OPRI(4)-300-80-35-FL-52-W-UNV-DP-1-ST-C(10'X6'X10' PRE MITTERED CORNER) |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 8 | Robert Lipura | Picked - Complete | High Priority |  | F2-40'X6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78726-1 | 78726 | 1 | 1 | Regular | B3SLED-16' | B3RLED-SL-750-80-35-FL-16'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 2 | 4 | Rohan Srivastava |  | Regular |  | L17D-16' | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78726-2 | 78726 | 2 | 1 | Regular | B3SLED-4' | B3RLED-SL-750-80-35-FL-4'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 73 | 73 | Rohan Srivastava |  | Regular |  | L17F-4' | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78726-3 | 78726 | 3 | 1 | Regular | SKETCH-AL(7' 10 1/4") | SK-10003-CIR-AL(7' 10 1/4")-400-80-35-SO-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-14 | 2019-02-19 | 1 | 4 | Rohan Srivastava |  | Regular |  | L8-7'10 1/4" | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78727-1 | 78727 | 1 | 1 | Regular | B4PLED-30' | BBPRLED-400-80-30-RG2-30'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 6 | Jessica Pasternyk |  | Regular |  | F21-30'-ADD 1/4 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78729-1 | 78729 | 1 | 1 | Regular | WB4LED-2' | WBRLED-750-80-35-S-2'-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-01-29 | 07:50:28 | 2019-02-04 | 2019-02-07 | 58 | 58 | Zahra Vatani |  | High Priority |  | Z2-2' | 18 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-04 07:31 |  | TRUE | FALSE
78730-1 | 78730 | 1 | 1 | Regular | PERFKT-CCH | CCH-SL-900-80-40-CL(107')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 20 | Zahra Vatani |  | High Priority |  | I 107'-STACKS READING 101 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78730-2 | 78730 | 2 | 1 | Regular | PERFKT-CCH | CCH-SL-900-80-40-CL(28')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 4 | 12 | Zahra Vatani |  | High Priority |  | I 28'-COMPUTERS/STACKS 101 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78730-3 | 78730 | 3 | 1 | Regular | PERFKT-CCH | CCH-SL-900-80-40-CL(18')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 4 | 8 | Zahra Vatani |  | High Priority |  | I 18'-ADULTS MEETING 117 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78730-4 | 78730 | 4 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-40-CL(27')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 6 | Zahra Vatani |  | High Priority |  | Q 27'-CHILDREN 133 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78730-5 | 78730 | 5 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-40-CL(62')-W-UNV-DP-1-C |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 2 | 12 | Zahra Vatani |  | High Priority |  | Q 62'-CHILDREN 133 | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78731-1 | 78731 | 1 | 1 | Regular | DIALED-14 | DIALED-14-2400-80-35-VL-W-277-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 12 | 12 | Philip Halsey |  | Regular |  | SS | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78744-1 | 78744 | 1 | 1 | Regular | SCULPT-4' | SCD-500-90-40-FL-4'-W-UNV-DP-1-CA(72) |  | Machine Shop Finished | 2019-01-25 | 15:11:34 | 2019-01-31 | 2019-02-05 | 18 | 18 | Jessica Pasternyk | Picked - Complete | Regular |  | JL1-4' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78759-1 | 78759 | 1 | 1 | Regular | B2LED-10' | BRLED-300-90-35-FL-10'-W-UNV-DP-1-TB15 |  | Machine Shop Finished | 2019-02-01 | 10:25:11 | 2019-02-05 | 2019-02-08 | 6 | 6 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | 10 FT | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78759-2 | 78759 | 2 | 1 | Regular | B2LED-8' | BRLED-300-90-35-FL-8'-W-UNV-DP-1-TB15 |  | Machine Shop Finished | 2019-02-01 | 10:25:16 | 2019-02-05 | 2019-02-08 | 4 | 4 | Rajithan Sivapatharajahon | Picked - Complete | Regular |  | 8 FT | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78768-1 | 78768 | 1 | 1 | Regular | SLMLED-8 | SLLED-SL 0/100-1000-90-40-SM-8-8-W-UNV-DP-1-CA(72) | Wrong part in BOM | Wiring Started | 2019-01-31 | 21:26:42 | 2019-01-30 | 2019-02-04 | 1 | 1 | Stan Buyansky |  | Regular |  | A36 | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-31 17:10 |  | TRUE | TRUE
78776-1 | 78776 | 1 | 1 | Regular | STENCL-6 | STD-SO-300-80-30-6-C(CHESTNUT#DS733-1301/1)-120-MD-1-CTS(60)-RC |  | Scheduled/Released |  |  | 2019-03-06 | 2019-03-11 | 1 | 1 | Sacha Lempka |  | Regular |  | L4 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78778-1 | 78778 | 1 | 1 | Regular | PERFKT-CCWH | CCWH-SL-700-90-35-CL(45'8")-W-UNV-DP-1-AC |  | Machine Shop Finished | 2019-01-30 | 08:01:32 | 2019-02-04 | 2019-02-07 | 1 | 4 | Rajithan Sivapatharajahon |  | Regular |  | C1- 46' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:57 |  | TRUE | FALSE
78778-2 | 78778 | 2 | 1 | Regular | PERFKT-CCWH | CCWH-SL-700-90-35-CL(31'8")-W-UNV-DP-1-AC | Shortage | Machine Shop Finished | 2019-01-30 | 08:01:35 | 2019-02-04 | 2019-02-07 | 1 | 3 | Rajithan Sivapatharajahon |  | Regular |  | C1-30' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:57 |  | TRUE | FALSE
78789-1 | 78789 | 1 | 1 | Regular | WWPRFK-10' | WWR-SL-400-80-35-10'-W-UNV-DP-1-TG9 |  | Machine Shop Finished | 2019-01-31 | 13:42:34 | 2019-02-05 | 2019-02-08 | 1 | 1 | Philip Halsey | Picked - Complete | Regular |  | L3-10' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 13:24 |  | TRUE | FALSE
78796-1 | 78796 | 1 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 6 | 6 | Joe Brier |  | Regular |  | F8 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78796-2 | 78796 | 2 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-TG9-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 3 | Joe Brier |  | Regular |  | F8 EM | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78796-3 | 78796 | 3 | 1 | Regular | DIALED-22 | DIALED-22-3000-80-35-VL-W-UNV-DP-1-SM |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 5 | 5 | Joe Brier |  | Regular |  | F12 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78798-1 | 78798 | 1 | 1 | Regular | CLICK-4' | CLKLED-500-80-30-SO-4'-W-120-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 8 | 8 | Joe Brier |  | Regular |  | LF02-27TH FL | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78798-2 | 78798 | 2 | 1 | Regular | CLICK-4' | CLKLED-500-80-30-SO-4'-W-120-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 28 | 28 | Joe Brier |  | Regular |  | LF02D-27TH FL | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78806-1 | 78806 | 1 | 1 | Regular | B4LED-4' | BBRLED-1000-80-35-FL-4'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 2 | 2 | Rajithan Sivapatharajahon |  | High Priority |  | F1-4' | 15 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78806-2 | 78806 | 2 | 1 | Regular | SCULPT-8' | SCR-500-80-35-FL-8'-W-UNV-DP-1-MFTB9 |  | Machine Shop Finished | 2019-01-28 | 15:31:28 | 2019-01-31 | 2019-02-05 | 5 | 5 | Rajithan Sivapatharajahon |  | High Priority |  | F2-8' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78806-3 | 78806 | 3 | 1 | Regular | SCULPT-6' | SCD-500-80-35-FL-6'-BLK-UNV-DP-1-CA(36") |  | Machine Shop Finished | 2019-01-28 | 15:31:30 | 2019-01-31 | 2019-02-05 | 4 | 4 | Rajithan Sivapatharajahon |  | High Priority |  | K-6' | 15 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78812-1 | 78812 | 1 | 1 | Regular | DIALED-24 | DIALED-24-3100-90-30-VL-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava |  | Regular |  | A-2X4 | 10 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78812-2 | 78812 | 2 | 1 | Regular | DIALED-22 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 3 | 3 | Rohan Srivastava |  | Regular |  | A2-2X2 | 10 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78812-3 | 78812 | 3 | 1 | Regular | DIALED-22 | DIALED-22-3000-90-30-VL-W-120-DP-1-ST-FW(6) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava |  | Regular |  | A3-2X2 | 10 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78812-4 | 78812 | 4 | 1 | Regular | LTLED-4' | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-30 | 19:28:00 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | B1-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:02 |  | TRUE | FALSE
78812-5 | 78812 | 5 | 1 | Regular | LTLED-4' | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36) |  | Machine Shop Finished | 2019-01-30 | 19:28:01 | 2019-02-01 | 2019-02-06 | 9 | 9 | Rohan Srivastava | Picked - Complete | Regular |  | B2-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:02 |  | TRUE | FALSE
78812-6 | 78812 | 6 | 1 | Regular | LTLED-4' | LTLED-SL 80/20-800-90-30-SO-4'-W-120-DP-1-CA(36)-B1(BSL310LP) |  | Machine Shop Finished | 2019-01-30 | 19:28:02 | 2019-02-01 | 2019-02-06 | 5 | 5 | Rohan Srivastava | Picked - Complete | Regular |  | B2-4' EM | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:02 |  | TRUE | FALSE
78812-7 | 78812 | 7 | 1 | Regular | LTLED-8' | LTLED-SL 80/20-800-90-30-SO-8'-W-120-DP-1-CA(36)-DS(1) | Others | Machine Shop Finished | 2019-01-30 | 19:28:05 | 2019-02-01 | 2019-02-06 | 10 | 10 | Rohan Srivastava | Picked - Complete | Regular |  | B4-8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-01 11:02 |  | TRUE | FALSE
78819-1 | 78819 | 1 | 1 | Regular | B2LED-8' | BDLED-1000-80-35-SO-8'-W-UNV-DP-1-CA(36") |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | George Bacalla |  | Regular |  | A-8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78820-1 | 78820 | 1 | 1 | Regular | DIALED-22 | DIALED-22-2500-90-35-VL-W-277-LT(LDE5)-1-TB15-FW(6') | Shortage | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 7 | 7 | Rohan Srivastava |  | Regular |  | LT-62 | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78820-2 | 78820 | 2 | 1 | Regular | TB2LED-4' | TB2DILED-600-500-90-35-SO-SO-4'-W-UNV-LT(LDE5)-1-CT15(60) |  | Machine Shop Finished | 2019-02-01 | 07:35:55 | 2019-02-04 | 2019-02-07 | 14 | 14 | Rohan Srivastava |  | Regular |  | LT-103.4' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78820-3 | 78820 | 3 | 1 | Regular | TB2LED-8' | TB2DILED-600-500-90-35-SO-SO-8'-W-UNV-LT(LDE5)-1-CT15(60) |  | Machine Shop Finished | 2019-02-01 | 07:35:58 | 2019-02-04 | 2019-02-07 | 24 | 24 | Rohan Srivastava |  | Regular |  | LT-103.8' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78820-4 | 78820 | 4 | 1 | Regular | TB2LED-4' | TB2DILED-600-500-90-35-SO-SO-4'-W-UNV-LT(LDE5)-1-CA(96) |  | Machine Shop Finished | 2019-02-01 | 07:36:00 | 2019-02-04 | 2019-02-07 | 24 | 24 | Rohan Srivastava |  | Regular |  | LT-103.4'-CA | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78820-5 | 78820 | 5 | 1 | Regular | TB2LED-8' | TB2DILED-600-500-90-35-SO-SO-8'-W-UNV-LT(LDE5)-1-CA(96) |  | Machine Shop Finished | 2019-02-01 | 07:36:04 | 2019-02-04 | 2019-02-07 | 18 | 18 | Rohan Srivastava |  | Regular |  | LT-103.8'-CA | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | TRUE | FALSE
78822-1 | 78822 | 1 | 1 | Regular | B3LED-4' | BMRLED-750-80-30-FL-4'-W-UNV-DP-1-ST-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 2 | Jessica Kennedy | Picked - Complete | Regular |  | L7-4' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78822-2 | 78822 | 2 | 1 | Regular | B3LED-6' | BMRLED-750-80-30-ASO-6'-W-UNV-DP-1-ST |  | Machine Shop Finished | 2019-02-04 | 08:54:38 | 2019-02-05 | 2019-02-08 | 1 | 1 | Jessica Kennedy | Picked - Complete | Regular |  | L2-6' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78822-3 | 78822 | 3 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-30-CL(10')-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-02-04 | 08:52:04 | 2019-02-05 | 2019-02-08 | 3 | 3 | Jessica Kennedy | Picked - Complete | Regular |  | L5-10' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78822-4 | 78822 | 4 | 1 | Regular | PERFKT-CCL | CCL-SL-500-80-30-CL(7')-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-02-04 | 08:52:13 | 2019-02-05 | 2019-02-08 | 1 | 1 | Jessica Kennedy | Picked - Complete | Regular |  | L5-7' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78825-1 | 78825 | 1 | 1 | Regular | WB4LED-4' | WBSLED-500-80-35-S-4'-W-UNV-DP-1-SC-C(END FEED) |  | Machine Shop Finished | 2019-01-31 | 01:42:23 | 2019-02-07 | 2019-02-12 | 20 | 20 | Rajithan Sivapatharajahon |  | High Priority |  | F3 | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78825-2 | 78825 | 2 | 1 | Regular | WB4LED-4' | WBSLED-500-80-35-S-4'-W-UNV-DP-E(1)-SC-C(End Feed) |  | Machine Shop Finished | 2019-01-31 | 01:42:25 | 2019-02-07 | 2019-02-12 | 10 | 10 | Rajithan Sivapatharajahon |  | High Priority |  | F3E | 15 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78844-1 | 78844 | 1 | 1 | Regular | B4LED-6' | BBRLED-400-80-30-FL-6'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 4 | 4 | Rohan Srivastava |  | Regular |  | F3-6' | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78854-1 | 78854 | 1 | 1 | Regular | B3LED-4' | BMRLED-500-80-35-FL-4'-W-UNV-DP-1-D |  | Machine Shop Finished | 2019-01-27 | 09:23:54 | 2019-02-01 | 2019-02-06 | 2 | 2 | Rohan Srivastava | Picked - Complete | Regular |  | LF02A-4' | 12 | TRUE | TRUE | TRUE | TRUE | [7 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-01 11:03 |  | TRUE | FALSE
78861-1 | 78861 | 1 | 1 | Regular | DIALED-22 | DIALED-22-4000-90-30-VL-W-120-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 8 | 8 | Rohan Srivastava |  | Regular |  | G-2X2 | 10 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78861-2 | 78861 | 2 | 1 | Regular | DIALED-22 | DIALED-22-3000-90-30-VL-W-120-BI-1-TB9 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 5 | 5 | Rohan Srivastava |  | Regular |  | G1-2X2 | 10 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78864-1 | 78864 | 1 | 1 | Replacement | ZENSQ-8 | ZESQDI-SL 25/75-1050-80-35-SO-8-AP-UNV-MD-1-CA(96") |  | Machine Shop Finished | 2019-01-30 | 07:59:14 | 2019-01-30 | 2019-02-04 | 1 | 1 | Daljit Singh |  | Regular |  | C2-8'-96" | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 14:51 |  | TRUE | FALSE
78864-2 | 78864 | 2 | 1 | Replacement | ZENSQ-4 | ZESQDI-SL 25/75-1050-80-35-SO-4-AP-UNV-MD-1-CA(120") |  | Machine Shop Finished | 2019-01-30 | 07:59:16 | 2019-01-30 | 2019-02-04 | 1 | 1 | Daljit Singh |  | Regular |  | C1-4'-96" | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 14:51 |  | TRUE | FALSE
78866-1 | 78866 | 1 | 1 | Regular | B4PLED-4' | BBPRLED-700-80-35-RG4-4'-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | High Priority |  | F-04-4' | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78866-2 | 78866 | 2 | 1 | Regular | B4PLED-8' | BBPRLED-700-80-35-RG4-8'-W-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | High Priority |  | F-04-8'-GYP | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78875-1 | 78875 | 1 | 1 | Mockup/Samples | STENCL-STFC | STFC-SLI(4-350)-DSO(4-400)-90-30-AL(4)-W-UNV-MD-1-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 2 | 8 | Sacha Lempka | Picked - Complete | High Priority |  | A | 4 | FALSE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78887-1 | 78887 | 1 | 1 | Regular | SCULPT-8' | SCD-500-80-35-FL-8'-AP-120-DP-1-CT9(36) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 1 | George Bacalla |  | Regular |  | A-8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78889-1 | 78889 | 1 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(17' 4")-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-01-31 | 00:58:37 | 2019-02-05 | 2019-02-08 | 2 | 4 | Philip Halsey |  | Regular |  | C1-17' 4" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:57 |  | TRUE | FALSE
78889-2 | 78889 | 2 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(8' 6")-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-01-31 | 00:58:39 | 2019-02-05 | 2019-02-08 | 2 | 2 | Philip Halsey |  | Regular |  | C1 8' 6" | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:57 |  | TRUE | FALSE
78889-3 | 78889 | 3 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(17')-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-01-31 | 00:58:40 | 2019-02-05 | 2019-02-08 | 1 | 2 | Philip Halsey |  | Regular |  | C1 17' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:57 |  | TRUE | FALSE
78889-4 | 78889 | 4 | 1 | Regular | PERFKT-CCH | CCH-SL-1100-80-35-CL(16')-W-UNV-DP-1-C |  | Machine Shop Finished | 2019-01-31 | 00:58:43 | 2019-02-05 | 2019-02-08 | 1 | 2 | Philip Halsey |  | Regular |  | C1 16' | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-01 09:58 |  | TRUE | FALSE
78890-1 | 78890 | 1 | 1 | Regular | B4LED-4 | BBWDILED-405-300-80-35-SO-4-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 8 | 8 | Sacha Lempka |  | High Priority |  | D | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78893-1 | 78893 | 1 | 1 | Regular | B2LED-3 | BSLED-500-80-35-SO-3-W-UNV-DP-1-S |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 10 | 10 | Stan Buyansky |  | High Priority |  | LL-17 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78902-1 | 78902 | 1 | 1 | Regular | B2LED-6 | BRLED-1000-80-35-FL-6-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-03 | 22:53:17 | 2019-01-31 | 2019-02-05 | 2 | 2 | Joshua Zimet |  | Regular |  | A-6' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready |  |  |  |  | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-04 11:48 |  | TRUE | FALSE
78908-1 | 78908 | 1 | 1 | Regular | AULED-24 | AULED-24-4500-90-35-SO-W-UNV-DP-1-TB15 | Others | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 46 | 46 | George Bacalla |  | Regular |  | A | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78908-2 | 78908 | 2 | 1 | Regular | AULED-14 | AULED-14-4000-90-35-SO-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 10 | 10 | George Bacalla |  | Regular |  | A1 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78908-3 | 78908 | 3 | 1 | Regular | AULED-22 | AULED-22-2500-90-35-SO-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 80 | 80 | George Bacalla |  | Regular |  | A2 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78908-4 | 78908 | 4 | 1 | Regular | B4LED-4' | BBDILED-640-400-90-35-SO-4'-W-UNV-DP-1-CA(48) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 32 | 32 | George Bacalla |  | Regular |  | C1-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78908-5 | 78908 | 5 | 1 | Regular | B3LED-4' | BMRLED-500-90-35-ASO-4'-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | George Bacalla |  | Regular |  | D-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78908-6 | 78908 | 6 | 1 | Regular | AIRLED-2' | ARWLED-500-90-35-S-2'-AP-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 3 | 3 | George Bacalla |  | Regular |  | G-2' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78909-1 | 78909 | 1 | 1 | Regular | DIALED-22 | DIALED-22-4000-90-35-VL-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 2 | 2 | Sacha Lempka |  | Priority |  | 7 | 10 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78914-1 | 78914 | 1 | 1 | Regular | B3LED-5' | BMRLED-750-90-35-RG-5'-W-UNV-LT(LDE1)-1-DF |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 3 | 3 | George Bacalla |  | Regular |  | F11-5' | 12 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78914-2 | 78914 | 2 | 1 | Regular | B3LED-6' | BMRLED-750-90-35-RG-6'-W-UNV-LT(LDE1)-1-DF |  | Machine Shop Started |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | George Bacalla |  | Regular |  | F11-6' | 12 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78916-1 | 78916 | 1 | 1 | Regular | B4LED-4' | BBRLED-375-80-40-FL-4'-BLK-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 24 | 24 | Joshua Zimet |  | Regular |  | F10-4' | 18 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78916-2 | 78916 | 2 | 1 | Regular | B4LED-4' | BBRLED-375-80-40-FL-4'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 18 | 18 | Joshua Zimet |  | Regular |  | F10A-4' | 18 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78926-1 | 78926 | 1 | 1 | Regular | B4PLED-148 3/4" | BBPRLED-400-80-35-RG2-148 3/4"-W-UNV-DP-1-TG9-FW(6)-C(LENGTH IS BETWEEN TBARS) |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 1 | 1 | Sacha Lempka |  | Regular |  | L5-15 | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78927-1 | 78927 | 1 | 1 | Regular | DIALED-DIALED | DIALED-22-2500-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-C(ELDOLED DUALDRIVER) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 37 | 37 | Zahra Vatani | Picked - Complete | High Priority |  | LA | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78927-2 | 78927 | 2 | 1 | Regular | DIALED-DIALED | DIALED-22-2500-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-B1(BSL310LP)-C(ELDOLED DUALDRIVER) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 17 | 17 | Zahra Vatani | Picked - Complete | High Priority |  | LAE | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78927-3 | 78927 | 3 | 1 | Regular | DIALED-DIALED | DIALED-24-3100-80-TW2765-VL-W-UNV-DALIDT6-1-TB15-C(ELDOLED DUALDRIVER) |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 22 | 22 | Zahra Vatani | Picked - Complete | High Priority |  | LB | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78927-4 | 78927 | 4 | 1 | Regular | SCULPT-4' | SP000-SCDI-500-300-80-TW2765-SO-FL-4'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36") | Others | Machine Shop Finished | 2019-01-30 | 13:02:35 | 2019-02-01 | 2019-02-06 | 1 | 1 | Zahra Vatani |  | High Priority |  | LC-4' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 16:03 |  | TRUE | FALSE
78927-5 | 78927 | 5 | 1 | Regular | SCULPT-16' | SP000-SCDI-500-300-80-TW2765-SO-FL-16'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36") |  | Machine Shop Finished | 2019-01-30 | 13:02:39 | 2019-02-01 | 2019-02-06 | 4 | 8 | Zahra Vatani |  | High Priority |  | LC-16' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 16:03 |  | TRUE | FALSE
78927-6 | 78927 | 6 | 1 | Regular | SCULPT-16' | SP000-SCDI-500-300-80-TW2765-SO-FL-16'-W-UNV-O(ELDOLED DUALDRIVE)-2-CT15(36")-B1(BSL310LP) |  | Machine Shop Finished | 2019-01-30 | 13:10:14 | 2019-02-01 | 2019-02-06 | 4 | 8 | Zahra Vatani |  | High Priority |  | LCE-16' | 7 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-01-30 16:03 |  | TRUE | FALSE
78930-1 | 78930 | 1 | 1 | Replacement | B3LED-16'7 1/2" | BMSLEDPAT-OPR-90-600-80-35-SO-16'5 3/4"-EX-W-UNV-DP-1-S | PM wrong/missing info | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 3 | Daljit Singh | Picked - Complete | High Priority |  | F6-L3-1FL-A | 12 | TRUE | TRUE | FALSE | FALSE |  | ToDo | [6 empty] | ToDo |  | FALSE |  |  | FALSE |  |  | FALSE | TRUE
78931-1 | 78931 | 1 | 1 | Regular | B4LED-4' | BBDLED-1000-90-35-SO-4'-W-UNV-DP-1-CA(96)-C(BLACK CANOPIES & CORD) |  | Machine Shop Finished | 2019-01-25 | 09:47:07 | 2019-01-31 | 2019-02-05 | 2 | 2 | Stan Buyansky | Picked - Complete | Regular |  | A | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-31 11:34 |  | TRUE | FALSE
78933-1 | 78933 | 1 | 1 | Regular | DIALED-22 | DIALED-22-4000-80-35-VL-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 20 | 20 | Rajithan Sivapatharajahon |  | Regular |  | 2X2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78934-1 | 78934 | 1 | 1 | Regular | DIALED-22 | DIALED-22-4000-80-30-VL-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-03-01 | 2019-03-06 | 134 | 134 | George Bacalla |  | Regular |  | D | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78936-1 | 78936 | 1 | 1 | Regular | B4LED-8' | BBRLED-600-80-35-FL-8'-W-UNV-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 3 | 3 | Rohan Srivastava |  | Regular |  | F1-8' | 12 | TRUE | TRUE | TRUE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78943-1 | 78943 | 1 | 1 | Regular | SCULPT-8' | SCDI-750-500-80-30-SO-FL-8'-BLK-UNV-DP-1-CA(36) |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 3 | George Bacalla | Picked - Complete | Regular |  | L4A-8' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78949-1 | 78949 | 1 | 1 | Regular | B4LED-12' | BBDLED-400-80-30-SO-12'-W-UNV-DP-1-CTS(36) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Christina Torok | Picked - Complete | Regular |  | 13 LOBBY | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | TRUE | 2019-02-03 13:23 |  | TRUE | FALSE
78964-1 | 78964 | 1 | 1 | Replacement | PERFKT-CCH | CCH-SL-700-80-40-CL(22)-W-277-DP-1-C-F-C (SEE PDF ATTACHED JOINING TO EXISTING FIXTURE ON SITE) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 2 | 2 | Anil Surendra Sanchara |  | Regular |  | C26C-7FT ADDER | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
78967-1 | 78967 | 1 | 1 | Regular | B2LED-6' | BDLED-1000-80-35-SO-6'-BLK-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 8 | 8 | Jessica Pasternyk |  | Regular |  | L1-6' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-2 | 78967 | 2 | 1 | Regular | B2LED-18' | BDLED-1000-80-35-SO-18'-BLK-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 2 | Jessica Pasternyk |  | Regular |  | L2-18' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-3 | 78967 | 3 | 1 | Regular | B2LED-32' | BDLED-1000-80-35-SO-32'-BLK-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 3 | Jessica Pasternyk |  | Regular |  | L3-32' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-4 | 78967 | 4 | 1 | Regular | B2LED-4' | BDLED-1000-80-35-SO-4'-BLK-120-DP-E(1)-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 1 | Jessica Pasternyk |  | Regular |  | L4-4' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-5 | 78967 | 5 | 1 | Regular | B2LED-27' | BDLEDPAT-OPR-90(1)-500-90-35-SO-27'-EX-BLK-120-DP-1+E(2)-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 3 | Jessica Pasternyk |  | Regular |  | L5-27' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-6 | 78967 | 6 | 1 | Regular | B2LED-10' | BDLEDPAT-OPR-90(1)-500-90-35-SO-10'-EX-BLK-120-DP-1+E(2)-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 3 | Jessica Pasternyk |  | Regular |  | L6-5'X5' L SHAPE | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-7 | 78967 | 7 | 1 | Regular | B2LED-12' | BDLED-1000-80-35-SO-12'-BLK-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 1 | Jessica Pasternyk |  | Regular |  | L7-12' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-8 | 78967 | 8 | 1 | Regular | B2LED-12' | BDLED-1000-80-35-SO-12'-BLK-120-DP-1+E(1)-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 1 | Jessica Pasternyk |  | Regular |  | L7-12' E | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-9 | 78967 | 9 | 1 | Regular | B2LED-2' | BDLED-1000-80-35-SO-2'-BLK-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 10 | 10 | Jessica Pasternyk |  | Regular |  | L8-2' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78967-10 | 78967 | 10 | 1 | Regular | B2LED-3' | BDLED-1000-80-35-SO-3'-BLK-120-DP-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 9 | 9 | Jessica Pasternyk |  | Regular |  | L9-3' | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78968-1 | 78968 | 1 | 1 | Regular | B2LED-4' | BDLED-750-80-30-SO-4'-AP-120-DP-1-CT9(96") |  | Machine Shop Finished | 2019-02-04 | 11:13:37 | 2019-02-08 | 2019-02-13 | 4 | 4 | Jessica Pasternyk |  | Regular |  | A-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
78970-1 | 78970 | 1 | 1 | Regular | CLICK-4' | CLKLED-500-80-35-SO-4'-W-UNV-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 2 | 2 | Philip Halsey |  | Regular |  | R1-4' | 18 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78970-2 | 78970 | 2 | 1 | Regular | CLICK-8' | CLKLED-500-80-35-SO-8'-W-UNV-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 4 | 4 | Philip Halsey |  | Regular |  | R1-8' | 18 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78971-1 | 78971 | 1 | 1 | Mockup/Samples | B3LED-4' | BMWDLED-500-80-35-SO-4'-AP-UNV-DP-1-C(CORD & PLUG) |  | Machine Shop Finished | 2019-02-03 | 23:06:02 | 2019-01-31 | 2019-02-05 | 1 | 1 | George Bacalla | Picked - Complete | Regular |  | A-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 10:27 |  | TRUE | FALSE
78974-1 | 78974 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(12'-1000)-NO-80-35-BT(1)-W-120-MD-1+E(1)-CA(36)-RC |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 2 | 4 | Jessica Pasternyk |  | Regular |  | LT01D(EM) | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78982-1 | 78982 | 1 | 1 | Regular | B4LED-6' | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Jessica Kennedy |  | Regular |  | AL7-6' | 12 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78983-1 | 78983 | 1 | 1 | Regular | SCULPT-66' | SCR-500-80-35-FL-66'-W-UNV-DP-1-ST-CP |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 9 | Joshua Zimet |  | Regular |  | F9-66-A | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78983-2 | 78983 | 2 | 1 | Regular | SCULPT-66' | SCR-500-80-35-FL-66'-W-UNV-DP-3-ST-CP |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 2 | 18 | Joshua Zimet |  | Regular |  | F9-66-B | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78983-3 | 78983 | 3 | 1 | Regular | SCULPT-66' | SCR-500-80-35-FL-66'-W-UNV-DP-3+E(3)-ST-CP |  | Scheduled/Released |  |  | 2019-02-15 | 2019-02-20 | 1 | 9 | Joshua Zimet |  | Regular |  | F9-66 EM | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78984-1 | 78984 | 1 | 1 | Regular | STNCLS-8'0" | STSLF-SO-400-80-35-8'0"-W-UNV-MD-1-SG9 |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 3 | Rajithan Sivapatharajahon |  | High Priority |  | B1-8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
78986-1 | 78986 | 1 | 1 | Regular | B4LED-6' | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 4 | 4 | Jessica Kennedy | Picked - Complete | Regular |  | AL7-6' | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  |  | FALSE |  |  | TRUE | FALSE
78988-1 | 78988 | 1 | 1 | Regular | BEAM4-8' | BBR-S-FL-8'-NL-T5-2-W-UNV-ERS-1-TB9 | Shortage | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 17 | 17 | Zahra Vatani |  | High Priority |  | A-8' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78988-2 | 78988 | 2 | 1 | Regular | BEAM4-4 | BBR-S-FL-4-NL-T5-2-W-UNV-ERS-1-TB9 |  | Machine Shop Started |  |  | 2019-02-07 | 2019-02-12 | 7 | 7 | Zahra Vatani |  | High Priority |  | A1-4' | 12 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
78994-1 | 78994 | 1 | 1 | Regular | SCULPT-6 | SCDI-300-400-80-35-SO-FL-6-W-UNV-DP-1-CT15(72) | Wrong part in BOM | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 2 | 2 | Sacha Lempka | Picked - Complete | Regular |  | C6 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | TRUE | 2019-02-03 10:27 |  | TRUE | TRUE
78994-2 | 78994 | 2 | 1 | Regular | SCULPT-8 | SCDI-300-400-80-35-SO-FL-8-W-UNV-DP-1-CA(72)-C(4.5 CANOPIES) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Sacha Lempka | Picked - Complete | Regular |  | C8 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | TRUE | 2019-02-03 10:27 |  | TRUE | FALSE
78999-1 | 78999 | 1 | 1 | Replacement | B3PLED-10'7 1/2" | BMPRLED-750-80-35-RG3-10'7 1/2"-W-UNV-DP-1-TG9-TS(1)-C(ANGLED ENDS) | Missing info. In SD | Wiring Started | 2019-01-31 | 13:56:57 | 2019-01-29 | 2019-02-01 | 1 | 2 | Daljit Singh |  | Regular |  | F04-10'7-1/2"-05-33T | 12 | TRUE | TRUE | TRUE | TRUE | [7 empty] | Ready |  |  | TRUE |  | AfterWirin | TRUE | 2019-01-31 17:07 |  | TRUE | TRUE
79000-1 | 79000 | 1 | 1 | Regular | DIALED-14 | DIALED-14-2400-80-35-VL-W-120-DP-1-SM |  | Scheduled/Released |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Joshua Zimet |  | Regular |  | F5A | 10 | TRUE | FALSE | FALSE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
79001-1 | 79001 | 1 | 1 | Regular | SKSLED-22 | SKSLED-22-600-80-30-GL-FL-120-DP-1-TB15 |  | Machine Shop Finished | 2019-02-01 | 10:50:50 | 2019-01-30 | 2019-02-04 | 8 | 8 | Sacha Lempka |  | Regular |  | A | 10 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
79005-1 | 79005 | 1 | 1 | Regular | AURA-AULED | AULED-24-3100-80-30-SO-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 3 | 3 | Rajithan Sivapatharajahon |  | Regular |  | A2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79011-2 | 79011 | 2 | 1 | Replacement | SKYPOL-SKPLED | SKPLED-22-3200-80-35-0.5-W-UNV-DP-2-TB9 |  | Wiring Started | 2019-02-03 | 16:11:18 | 2019-01-29 | 2019-02-01 | 1 | 1 | Tajinder Singh | Picked - Complete | Regular |  | F42DM-AT17 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:47 |  | TRUE | FALSE
79011-3 | 79011 | 3 | 1 | Replacement | SKYPOL-SKPLED | SKPLED-22-3200-80-35-0.5-W-UNV-DP-2-TB15 |  | Wiring Started | 2019-02-03 | 16:11:25 | 2019-01-29 | 2019-02-01 | 1 | 1 | Tajinder Singh | Picked - Complete | Regular |  | F42DM-AT13 | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:47 |  | TRUE | FALSE
79012-1 | 79012 | 1 | 1 | Regular | B2LED-8' | BWDLED-500-80-40-SO-8'-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-04-29 | 2019-05-02 | 1 | 1 | Joe Brier |  | Regular |  | G-8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79014-1 | 79014 | 1 | 1 | Regular | B2LED-4' | BILED-640-90-30-C-4'-W-UNV-DP-1-CA(48") |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 2 | 2 | Rohan Srivastava |  | Regular |  | A-4' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79015-1 | 79015 | 1 | 1 | Regular | B3LED-16' | BMRLED-500-90-35-1.25M-16'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Rohan Srivastava |  | Regular |  | F15-16'-42ND FL | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79015-2 | 79015 | 2 | 1 | Regular | B3LED-16' | BMRLED-500-90-35-1.25M-16'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Rohan Srivastava |  | Regular |  | F15-16'-43RD FL | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79015-3 | 79015 | 3 | 1 | Regular | B3LED-16' | BMRLED-750-90-35-FL-16'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Rohan Srivastava |  | Regular |  | F1-16'-43RD FL | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79017-1 | 79017 | 1 | 1 | Regular | SCULPT-8' 11" | SCR-400-80-35-FL-8' 11"-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Rohan Srivastava | Picked - Complete | Regular |  | A-8'-11" | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
79019-1 | 79019 | 1 | 1 | Replacement | SCULPT-TR60X4 | SCR-500-90-40-FL-TR60X4-W-277-DP-1-MFTG9 |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Anil Surendra Sanchara | Picked - Complete | High Priority |  | FR5 - REPLACE | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79024-1 | 79024 | 1 | 1 | Regular | B6LED-5 | B6RLED-1000-90-40-FL-5-W-UNV-DP-1-TB9 |  | Machine Shop Finished | 2019-02-04 | 10:38:38 | 2019-01-31 | 2019-02-05 | 1 | 1 | George Bacalla | Picked - Complete | Regular |  | L8-5' | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [9 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
79034-1 | 79034 | 1 | 1 | Replacement | ZENSQ-44 | ZESQDI-SL 25/75-1050-80-35-MSO-44-BLK-UNV-MD-1-CA(96)-B2(BSL10LST) | Shortage | Machine Shop Finished | 2019-02-03 | 13:51:13 | 2019-01-30 | 2019-02-04 | 1 | 4 | Robert Lipura | Picked - Complete | High Priority |  | A- 44'EM | 4 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
79035-1 | 79035 | 1 | 1 | Replacement | SCULPT-10' | SCRPAT-ASO-90-300-80-35-0.5M-10'-EX-W-120-DP-1-MFTB9 |  | Scheduled/Released |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Robert Lipura | Picked - Complete | Regular |  | L1-4 & L1-2-4'X6' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79037-1 | 79037 | 1 | 1 | Replacement | B4LED-8 | BBRLED-500-80-35-FL-8-W-UNV-DP-1-TB9-B2(BSL10LST) |  | Machine Shop Finished | 2019-02-04 | 01:52:03 | 2019-01-31 | 2019-02-05 | 1 | 1 | Anil Surendra Sanchara |  | Regular |  | M8E - REPLACE | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [6 empty] | Ready |  |  | TRUE |  | Done | TRUE | 2019-02-03 10:27 |  | TRUE | FALSE
79041-1 | 79041 | 1 | 1 | Regular | SCULPT-4' | SCR-300-80-35-0.5M-4'-W-UNV-DP-1-TB15 |  | Machine Shop Started |  |  | 2019-02-13 | 2019-02-18 | 10 | 10 | Jessica Pasternyk |  | Regular |  | ALT-4' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
79042-13 | 79042 | 13 | 1 | Regular | DAYFLED-22 | DAYFLED-22-2500-80-35-SO-W-UNV-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 16 | 16 | Gagandeep Singh |  | Regular |  | F16-2X2 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79042-14 | 79042 | 14 | 1 | Regular | DAYFLED-22 | DAYFLED-22-2500-80-35-SO-W-UNV-DP-1-TG9-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-19 | 2019-02-22 | 1 | 1 | Gagandeep Singh |  | Regular |  | F16-2X2-EM | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79043-1 | 79043 | 1 | 1 | Regular | DIALED-22 | DIALED-22-3600-80-35-VL-W-277-LT(LDE1)-1-TG9-AR |  | Machine Shop Finished | 2019-02-04 | 09:19:37 | 2019-01-31 | 2019-02-05 | 10 | 10 | Rohan Srivastava |  | Regular |  | F1-2X2 | 10 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | FALSE |  |  | FALSE | FALSE
79048-1 | 79048 | 1 | 1 | Mockup/Samples | CLICK-4' | CLKLED-900-90-35-SO-4'-W-UNV-DP-1-AC-C(PLUG AND CORD ONLY) |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Jessica Kennedy | Picked - Complete | Regular |  | SAMPLE-4' | 1 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79049-1 | 79049 | 1 | 1 | Regular | B2LED-8' | BILED-640-90-40-C-8'-W-277-DP-1-CT15(48") |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 1 | 1 | Zahra Vatani |  | Regular |  | A-8' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79049-2 | 79049 | 2 | 1 | Regular | B2LED-5' | BILED-640-90-40-C-5'-W-277-DP-1-CT15(48") |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 5 | 5 | Zahra Vatani |  | Regular |  | A-5' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79050-1 | 79050 | 1 | 1 | Replacement | AULED-22 | AULED-22-3000-80-35-SO-W-UNV-DP-1-TB9 |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 2 | 2 | Daljit Singh |  | Regular |  | C | 10 | TRUE | TRUE | TRUE | FALSE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
79076-1 | 79076 | 1 | 1 | Replacement | B4LED-BBWDILED | BBWDILED-640-400-80-40SO-4-W-120-BI-1-OS(1 LOS-CDT)-C(SENSOR FOR INDIRECT ONLY) |  | Machine Shop Finished | 2019-02-03 | 14:49:45 | 2019-02-05 | 2019-02-08 | 1 | 1 | Anil Surendra Sanchara | Picked - Complete | Regular |  | L11 - REPLACE | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:49 |  | TRUE | FALSE
79078-1 | 79078 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(4-500)-DSO(8-400)-80-35-AY(1)+AH(2)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 5 | Christina Torok |  | Regular |  | 3RD FL AREA B- L6-B2A | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79078-2 | 79078 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(4-500)-DSO(8-400)-80-35-AY(1)+AH(2)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Machine Shop Started |  |  | 2019-02-11 | 2019-02-14 | 1 | 5 | Christina Torok |  | Regular |  | 3RD FL AREA B- L6E-B2B | 7 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79080-1 | 79080 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(10-500)-DSO(15-400)-80-35-AY(4)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 9 | Christina Torok |  | Regular |  | 3RD FL AREA A1- L6-A2A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79080-2 | 79080 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(12-500)-DSO(15-400)-80-35-AY(4)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 9 | Christina Torok |  | Regular |  | 3RD FL AREA A1-L6-A2B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79080-3 | 79080 | 3 | 1 | Regular | STENCL-STFC | STFC-SLI(5-500)-DSO(12-400)-80-35-AY(2)+AH(1)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 6 | Christina Torok |  | Regular |  | 3RD FL AREA A1- L6-A2C | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79082-1 | 79082 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(3-500)-DSO(6-400)-80-35-AY(1)-AP-UNV-MD-1-CA(36)-RC-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 3 | Christina Torok |  | Regular |  | 1ST FL AREA L6-H1A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79082-2 | 79082 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(8-500)-DSO(8-400)-80-35-AY(1)+AH(3)-AP-UNV-MD-1-CA(36)-RC-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 6 | Christina Torok |  | Regular |  | 1ST FL AREA L6-H1B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79083-1 | 79083 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(8-500)-DSO(8-400)-80-35-AL(4)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Christina Torok |  | Regular |  | 2ND FL F1A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79083-2 | 79083 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(4-500)-DSO(4-400)-80-35-AL(1)-AP-UNV-MD-1-CA(36)-RC-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Christina Torok |  | Regular |  | 2ND FL L6-F1B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79083-3 | 79083 | 3 | 1 | Regular | STENCL-STFC | STFC-SLI(8-500)-DSO(8-400)-80-35-AL(4)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Christina Torok |  | Regular |  | 2ND FL L6-F1C | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79084-1 | 79084 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(10-500)-DSO(14-400)-80-35-AY(3)+AH(2)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 9 | Christina Torok |  | Regular |  | 2ND FL AREA L6-E1A | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79084-2 | 79084 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(7-500)-DSO(12-400)-80-35-AY(3)+AH(1)-AP-UNV-MD-1-CA(36)-RC-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 8 | Christina Torok |  | Regular |  | 2ND FL AREA L6-E1B | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79084-3 | 79084 | 3 | 1 | Regular | STENCL-STFC | STFC-SLI(8-500)-DSO(11-400)-80-35-AY(3)+AH(1)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 8 | Christina Torok |  | Regular |  | 2ND FL AREA L6-E1C | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79084-4 | 79084 | 4 | 1 | Regular | STENCL-STFC | STFC-SLI(9-500)-DSO(15-400)-80-35-AY(4)+AH(1)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 10 | Christina Torok |  | Regular |  | 2ND FL AREA L6-E1D | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79085-1 | 79085 | 1 | 1 | Replacement | B4LED-2 | BBRLED-1000-90-40-FL-2-W-UNV-DP-1-TB15 |  | Wiring Started | 2019-01-31 | 00:33:47 | 2019-01-31 | 2019-02-05 | 88 | 88 | Daljit Singh |  | Regular |  | LR2-2' | 10 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready |  |  |  | TRUE |  | Done | TRUE | 2019-02-04 09:58 |  | TRUE | FALSE
79086-1 | 79086 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(16-500)-DSO(16-400)-80-35-AL(6)+AX(1)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 8 | Christina Torok |  | Regular |  | 1ST FL AREA L6-GA | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79086-2 | 79086 | 2 | 1 | Regular | STENCL-STFC | STFC-SLI(4-500)-DSO(4-400)-80-35-AL(1)-AP-UNV-MD-1-CA(36)-RC-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 2 | Christina Torok |  | Regular |  | 1ST FL AREA L6-GB | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79086-3 | 79086 | 3 | 1 | Regular | STENCL-STFC | STFC-SLI(8-500)-DSO(8-400)-80-35-AL(4)-AP-UNV-MD-1-CA(36)-RC-B1(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Christina Torok |  | Regular |  | 1ST FL AREA L6-GC | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79089-1 | 79089 | 1 | 1 | Regular | STENCL-STFC | STFC-SLI(16-500)-DSO(16-400)-80-35-AL(6)+AX(1)-AP-UNV-MD-1-CA(36)-RC-B2(BSL10LST)-C(WHITE PWR CORD & CANOPIES) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 8 | Christina Torok |  | Regular |  | 2ND FL AREA C- TYPE C1 | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79098-1 | 79098 | 1 | 1 | Regular | WB4LED-4' | WBRLED-500-90-30-S-4'-AP-UNV-DP-1-D |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 2 | 2 | Jessica Pasternyk |  | Regular |  | A-4' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79101-1 | 79101 | 1 | 1 | Regular | SLMLED-32 | SLLED-SL 80/20-1000-80-40-SM-32-W-277-DP-1-CA(72)-B2(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 1 | 3 | Jessica Kennedy |  | Regular |  | B-32' EM | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79104-1 | 79104 | 1 | 1 | Regular | AULED-22 | AULED-22-2500-80-30-SO-W-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 20 | 20 | Philip Halsey |  | Regular |  | R1 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79104-2 | 79104 | 2 | 1 | Regular | B3LED-2' | BMRLED-500-80-30-FL-2'-W-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 10 | 10 | Philip Halsey |  | Regular |  | R7-2' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79104-3 | 79104 | 3 | 1 | Regular | B3LED-2' | BMRLED-500-80-30-FL-2'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 4 | 4 | Philip Halsey |  | Regular |  | R7-2' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79104-4 | 79104 | 4 | 1 | Regular | B3LED-4' | BMRLED-500-80-30-FL-4'-W-UNV-DP-1-TG15 |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 7 | 7 | Philip Halsey |  | Regular |  | R8-4' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79104-5 | 79104 | 5 | 1 | Regular | B3LED-4' | BMRLED-500-80-30-FL-4'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-15 | 2019-02-20 | 3 | 3 | Philip Halsey |  | Regular |  | R8-4' | 15 | TRUE | FALSE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79106-1 | 79106 | 1 | 1 | Regular | B4LED-6' | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 3 | 3 | Jessica Kennedy | Picked - Complete | Priority |  | LT-09-6' G | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  |  | FALSE |  |  | TRUE | FALSE
79106-2 | 79106 | 2 | 1 | Regular | B4LED-6' | BBRLED-400-80-35-FL-6'-W-UNV-DP-1-D |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 3 | 3 | Jessica Kennedy | Picked - Complete | Priority |  | LT-09-6' F | 12 | TRUE | TRUE | TRUE | TRUE | Ready | [5 empty] | Ready | Ready |  |  | TRUE |  |  | FALSE |  |  | TRUE | FALSE
79110-1 | 79110 | 1 | 1 | Regular | POLED-22 | POLED-22-4400-90-35-VL-W-UNV-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 3 | 3 | Zahra Vatani |  | Regular |  | FT10-2X2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79116-1 | 79116 | 1 | 1 | Regular | BEAM6-4 | B6R-S-FL-4-NL4-T8-2-W-120-E-1-TG9 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 4 | 4 | Sacha Lempka | Picked - Complete | Priority |  | D2B | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79121-1 | 79121 | 1 | 1 | Replacement | STNCLS-8' | STSLF-ML-600-80-30-8'-BLK-277-MD-1-SB9 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 10 | 10 | Robert Lipura | Picked - Complete | Regular |  | LT-01-8'-23RD FL | 4 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79124-1 | 79124 | 1 | 1 | Mockup/Samples | CLICK-12' | CLKLED-750-80-30-SO-12'-W-277-DP-1-TG9-FW(6) |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 2 | Joe Brier |  | Regular |  | A1-SAMPLE | 18 | TRUE | FALSE | FALSE | TRUE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79125-1 | 79125 | 1 | 1 | Regular | WB4LED-5' | WBRLED-500-80-40-S-5'-AP-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Zahra Vatani |  | Regular |  | D-5' | 12 | TRUE | TRUE | TRUE | TRUE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79128-1 | 79128 | 1 | 1 | Replacement | DAYLED-DAYFLED | DAYFLED-14-4000-80-40-SO-W-120-LT(HI-LUME 0-10V 1%)-1-TB15 |  | Wiring Started |  |  | 2019-01-29 | 2019-02-01 | 24 | 24 | Anil Surendra Sanchara |  | Regular |  | F4A ALT REPLACE | 10 | TRUE | FALSE | FALSE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
79133-1 | 79133 | 1 | 1 | Replacement | SCULPT-5' 6" | SCWD-300-80-35-FL-5' 6"-AP-UNV-DP-1 | Wrong info. In SD | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Tajinder Singh | Picked - Complete | High Priority |  | F7A S3-7 | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | TRUE
79135-1 | 79135 | 1 | 1 | Regular | WB4LED-5' | WBRVLED-500-80-35-SO-5'-AP-UNV-DP-1-DS |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Philip Halsey |  | High Priority |  | VERT-5' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79149-1 | 79149 | 1 | 1 | Regular | SCULPT-4 | SCD-300-80-35-FL-4-W-UNV-DP-1-CT9(36) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 3 | 3 | Stan Buyansky |  | Regular |  | L4P | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79151-1 | 79151 | 1 | 1 | Regular | B4LED-205 1/2" | BBRLEDPAT-OPR-90+90-700-80-40-SO-205 1/2"-EX-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 8 | 40 | Jessica Kennedy |  | Regular |  | C7-79.5X38"X79.5" | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79157-1 | 79157 | 1 | 1 | Regular | B3LED-6' | SP000-BMRLED-100-90-30-ASO-6'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Zahra Vatani |  | Regular |  | W5-6' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79157-2 | 79157 | 2 | 1 | Regular | B3LED-8' | SP000-BMRLED-100-90-30-ASO-8'-W-UNV-DP-1-TG9 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 3 | 3 | Zahra Vatani |  | Regular |  | W4-8' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79157-3 | 79157 | 3 | 1 | Regular | B3LED-8' | SP000-BMRLED-100-90-30-ASO-8'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Zahra Vatani |  | Regular |  | W6-8' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79163-1 | 79163 | 1 | 1 | Regular | SCULPT-4' | SCR-500-80-30-FL-4'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | George Bacalla |  | High Priority |  | L2-4' | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79163-2 | 79163 | 2 | 1 | Regular | SCULPT-4' | SCWDI-300-400-80-30-SO-0.5M-4'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 5 | 5 | George Bacalla |  | High Priority |  | L3-4' | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79163-3 | 79163 | 3 | 1 | Regular | SCULPT-6' | SCWD-300-80-30-FL-6'-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-18 | 2019-02-21 | 1 | 1 | George Bacalla |  | High Priority |  | L3A-6' | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79164-1 | 79164 | 1 | 1 | Regular | B2LED-8' | BRLED-750-80-40-FL-8'-W-UNV-DP-1+NL(1)-TB15 |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | George Bacalla |  | Regular |  | L39A-8' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79168-1 | 79168 | 1 | 1 | Regular | B6LED-4' | B6RLED-400-80-35-RG-4'-W-120-DP-1-D |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 6 | 6 | George Bacalla | Picked - Complete | Regular |  | C-4' | 12 | TRUE | TRUE | FALSE | TRUE | ToDo | [9 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79169-1 | 79169 | 1 | 1 | Replacement | B4LED-10' | BBRLED-400-80-30-RG-10'-W-UNV-DP-1-ST-B1(BSL10LST)-C(JOIN TO EXISTING) |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 1 | 1 | Robert Lipura |  | Regular |  | L-18'-EM#2 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79170-1 | 79170 | 1 | 1 | Replacement | MK-R-DW-1X1-1 | RECESSED DRYWALL MOUNTING KITS- POWERED 3 WIRES - DAY-DIA-DUO-PLANO-WAVE - 1X1 |  | Wiring Started |  |  | 2019-01-29 | 2019-02-01 | 80 | 0 | Daljit Singh |  | Regular |  |  | 10 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  |  | FALSE |  |  | FALSE | FALSE
79183-1 | 79183 | 1 | 1 | Regular | SCULPT-PN60X2 | SCR-300-80-35-FL-PN60X2-W-UNV-DP-1-MFTG9-C(UPDATED MOUNTING TO MFTG9 AND 60 DEGREE NEGATIVE 2FT) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 4 | 4 | Rajithan Sivapatharajahon |  | Regular |  | S-PN | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79183-2 | 79183 | 2 | 1 | Regular | SCULPT-PP60X2 | SCR-300-80-35-FL-PP60X2-W-UNV-DP-1-MFTG9-C(UPDATED MOUNTING TO MFTG9 AND 60 DEGREE POSITIVE 2FT) |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 5 | 5 | Rajithan Sivapatharajahon |  | Regular |  | S-PP | 7 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79186-1 | 79186 | 1 | 1 | Replacement | B4LED-28 | SP000-BBDILED-300-750-80-35-SO-28-BLK-UNV-DP-1-CA(36)-C(SECTION #3 ONLY TO JOIN TO EXISTING) | Shortage | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Tajinder Singh | Picked - Complete | Regular |  | LP3-28 | 12 | TRUE | TRUE | FALSE | FALSE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79187-1 | 79187 | 1 | 1 | NPI | ZENSQ-48 | ZESQDI-SL 75/25-1350-80-35-MAL-48-W-UNV-MD-2-CA(96) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Stan Buyansky |  | Regular |  | A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79187-2 | 79187 | 2 | 1 | NPI | ZENSQ-32 | ZESQDI-SL 50/50-1200-80-35-MSO-32-W-UNV-MD-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 4 | Stan Buyansky |  | Regular |  | B | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79187-3 | 79187 | 3 | 1 | NPI | ZENSQ-61 | SP19044(2)-ZESQDI-SL XX/XX-XXXX-90-35-MSO-61-W-UNV-MD-1-CA(96) |  | Scheduled/Released |  |  | 2019-02-11 | 2019-02-14 | 1 | 7 | Stan Buyansky |  | Regular |  | C | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79189-1 | 79189 | 1 | 1 | Replacement | B4LED-4'7" | BBRLED-400-80-30-RG-4'7"-W-120-DP-1-D-B1(BSL310LP) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Anil Surendra Sanchara | Picked - Complete | Regular |  | 12E 604 HALL @ 55" | 12 | TRUE | TRUE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79194-1 | 79194 | 1 | 1 | Regular | CLICK-4 | CLKLED-500-80-40-SO-4-W-UNV-DP-1-AC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 21 | 21 | George Bacalla |  | High Priority |  | A | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79194-2 | 79194 | 2 | 1 | Regular | CLICK-8 | CLKLED-500-80-40-SO-8-W-UNV-DP-1-AC |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 12 | 12 | George Bacalla |  | High Priority |  | A1 | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79194-3 | 79194 | 3 | 1 | Regular | SCULPT-TR60X2 | SCR-300-80-40-FL-TR60X2-W-UNV-DP-1-MFTG9 |  | Scheduled/Released |  |  | 2019-02-12 | 2019-02-15 | 9 | 9 | George Bacalla |  | High Priority |  | B | 1 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79198-1 | 79198 | 1 | 1 | Regular | SCULPT-14' | SCR-500-80-30-FL-14'-W-UNV-DP-1-DF |  | Machine Shop Finished | 2019-02-03 | 22:20:39 | 2019-01-31 | 2019-02-05 | 6 | 12 | Joe Brier | Picked - Complete | High Priority |  | F1-14' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-04 11:49 |  | TRUE | FALSE
79201-1 | 79201 | 1 | 1 | Regular | CUBIC-24 | CU-S-24-T8-3-W-0-0-UNV-E-1-CT9(36) |  | Scheduled/Released |  |  | 2019-02-08 | 2019-02-13 | 2 | 4 | Philip Halsey |  | Regular |  | L1-24' | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79206-1 | 79206 | 1 | 1 | Quick Ship+ | B4LED-8' | BBDLED-1000-80-35-SO-8'-AP-UNV-DP-1-CA(36) |  | Given to Shipping | 2019-01-30 | 19:23:10 | 2019-01-31 | 2019-02-05 | 6 | 6 | Philip Halsey |  | Regular |  | 8' | 12 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | Done | TRUE | 2019-01-31 11:34 |  | TRUE | FALSE
79217-1 | 79217 | 1 | 1 | Regular | SCULPT-8 | SCDI-300-500-80-35-SO-FL-8-BLK-277-DP-1-CA(60)-F-C(BLACK CORD AND CANOPY) |  | Scheduled/Released |  |  | 2019-02-14 | 2019-02-19 | 17 | 17 | Gaurav Jain |  | Regular |  | A | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79220-1 | 79220 | 1 | 1 | Regular | POLED-22 | POLED-22-3000-80-35-VL-W-120-DP-1-ST |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 21 | 21 | Stan Buyansky |  | Regular |  | F6 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79225-1 | 79225 | 1 | 1 | Regular | SCULPT-6 | SCDI-750-500-80-30-SO-FL-6-W-120-DP-1-CA(36)-C(4.5 CANOPIES) |  | Scheduled/Released |  |  | 2019-02-20 | 2019-02-25 | 1 | 1 | Sacha Lempka |  | Regular |  | LU3 | 0 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79234-1 | 79234 | 1 | 1 | Regular | B3LED-12' | BMRLED-700-80-40-FL-12'-W-UNV-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 1 | 1 | Joe Brier |  | Regular |  | A-12' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79240-1 | 79240 | 1 | 1 | Regular | DIALED-22 | DIALED-22-3000-90-35-VL-W-120-DP-1-ST |  | Machine Shop Started |  |  | 2019-02-01 | 2019-02-06 | 6 | 6 | Rohan Srivastava |  | Regular |  | A2 | 10 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79240-2 | 79240 | 2 | 1 | Regular | DIALED-22 | DIALED-22-3000-90-35-VL-W-120-DP-1-ST-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-01 | 2019-02-06 | 1 | 1 | Rohan Srivastava |  | Regular |  | A2EM | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79245-1 | 79245 | 1 | 1 | Regular | PLNLED-POLED | POLED-22-2500-90-35-VL-W-120-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 12 | 12 | Stan Buyansky |  | Regular |  | F | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79245-2 | 79245 | 2 | 1 | Regular | PLNLED-POLED | POLED-22-2500-90-35-VL-W-120-DP-1-TG9-B1(BSL10LST) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 12 | 12 | Stan Buyansky |  | Regular |  | FE | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79248-1 | 79248 | 1 | 1 | Regular | SLMLED-8 | SLLED-SL 0/100-800-80-30-PL-8-W-UNV-DP-1-SA(48) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Stan Buyansky |  | Regular |  | LT-03 | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79264-1 | 79264 | 1 | 1 | Regular | B4LED-4 | BBWDLED-400-80-40-SO-4-W-UNV-DP-1 |  | Machine Shop Started |  |  | 2019-02-08 | 2019-02-13 | 2 | 2 | Gaurav Jain |  | Regular |  | SC1, 4' | 12 | TRUE | FALSE | FALSE | TRUE | [10 empty] | FALSE |  | Done | FALSE |  |  | FALSE | FALSE
79282-1 | 79282 | 1 | 1 | Regular | DIALED-22 | DIALED-22-2500-80-30-VL-W-UNV-DP-1-TB9 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Rohan Srivastava |  | Regular |  | L235-38TH FL | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79284-1 | 79284 | 1 | 1 | Mockup/Samples | B2SLED-2 | B2SQWILED-1100-80-35-SLA-2-W-UNV-DP-1-C(AXIS CORD PLUG DIMMER) | Others | Machine Shop Finished | 2019-02-01 | 11:11:12 | 2019-01-29 | 2019-02-01 | 1 | 1 | Lazer Framovitz | Picked - Complete | High Priority |  | W8 SAMPLE | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [7 empty] | Done | TRUE |  | Done | TRUE | 2019-01-31 17:07 |  | TRUE | FALSE
79285-1 | 79285 | 1 | 1 | Regular | B2LED-11 | BRLED-500-80-30-FL-11-W-120-DP-1-DF |  | Machine Shop Started |  |  | 2019-02-06 | 2019-02-11 | 1 | 1 | Rajithan Sivapatharajahon |  | Regular |  | LC-11' | 12 | TRUE | FALSE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79303-1 | 79303 | 1 | 1 | Regular | LTLED-4' | LTWLED-SL 80/20-1000-80-35-SO-4'-AP-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 8 | 8 | Zahra Vatani |  | Regular |  | F17A-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79303-2 | 79303 | 2 | 1 | Regular | B2LED-4' | BSLED-650-80-35-SO-4'-AP-UNV-DP-1-SB15 |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 33 | 33 | Zahra Vatani |  | Regular |  | F37-S-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79303-3 | 79303 | 3 | 1 | Regular | B2LED-4' | BSLED-650-80-35-SO-4'-AP-UNV-DP-1-SB15-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 4 | 4 | Zahra Vatani |  | Regular |  | F37E-S-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79303-4 | 79303 | 4 | 1 | Regular | B2LED-4' | BRLED-650-80-35-FL-4'-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 46 | 46 | Zahra Vatani |  | Regular |  | F37-R-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79303-5 | 79303 | 5 | 1 | Regular | B2LED-4' | BRLED-650-80-35-FL-4'-W-UNV-DP-1-TB15-B1(BSL310LP) |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 4 | 4 | Zahra Vatani |  | Regular |  | F37RE-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79303-6 | 79303 | 6 | 1 | Regular | B2LED-4' | BSLED-400-80-35-SO-4'-AP-UNV-DP-1-SB15 |  | Scheduled/Released |  |  | 2019-02-25 | 2019-02-28 | 14 | 14 | Zahra Vatani |  | Regular |  | F37B-4' | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79307-5 | 79307 | 5 | 1 | Replacement | SCULPT-K(L4X4) | SCS-400-80-35-FL-K(L4X4)-W-UNV-DP-1-S |  | Machine Shop Started |  |  | 2019-02-05 | 2019-02-08 | 1 | 1 | Daljit Singh | Picked - Complete | Regular |  | L15A-L | 12 | TRUE | TRUE | FALSE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79309-1 | 79309 | 1 | 1 | Regular | DAY-DAYF | DAYF-22-S-T5-3-W-277-BI-2-TB9-C(STEPDIMMING) |  | Scheduled/Released |  |  | 2019-02-13 | 2019-02-18 | 6 | 6 | Philip Halsey |  | Regular |  | A | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79311-1 | 79311 | 1 | 1 | Replacement | PERFKT-CCH | CCH-SL-1100-80-35-CL(26")-W-UNV-DP-1-C-C(23 7/16" LENGTH TO ADD TO EXISTING) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Daljit Singh |  | Regular |  | CL1L-23 7/16" | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79311-2 | 79311 | 2 | 1 | Replacement | PERFKT-CCH | CCH-SL-1100-80-35-CL(48")-W-UNV-DP-1-C-C(46 3/4" LENGTH TO ADD TO EXISTING) |  | Machine Shop Started |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Daljit Singh |  | Regular |  | CL1L-46 3/4" | 4 | TRUE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79316-1 | 79316 | 1 | 1 | Regular | B4LED-4 | BBWDILED-500-500-80-30-SO-4-AP-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 2 | 2 | Christina Torok |  | Regular |  | F | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79320-1 | 79320 | 1 | 1 | Regular | B2LED-32' | BDLED-700-80-30-SO-32'-W-UNV-DP-1-CA(36) |  | Wiring Started | 2019-02-03 | 22:26:27 | 2019-01-30 | 2019-02-04 | 1 | 4 | Rohan Srivastava | Picked - Complete | High Priority |  | B2-32' | 12 | TRUE | TRUE | TRUE | TRUE |  | Ready | [8 empty] | TRUE |  | Done | TRUE | 2019-02-03 10:27 |  | TRUE | FALSE
79322-1 | 79322 | 1 | 1 | Replacement | GRAZE-24 3/4" | GPRLED-FC2W-1200-90-27-RG2-24 3/4"-W-UNV-DP-1-DF |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Tajinder Singh | Picked - Complete | Regular |  | CAJ. | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79342-1 | 79342 | 1 | 1 | Regular | AULED-24 | AULED-24-3100-80-30-SO-W-277-DP-1-TB15-FW(6) |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Joe Brier |  | Regular |  | LF06 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79347-1 | 79347 | 1 | 1 | Replacement | B2SLED-110 1/2" | B2SQDLED-750-80-30-SO-110 1/2"-W-UNV-DP-1-CT9(72)-C( ADD TO EXISITING) |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 1 | 1 | Daljit Singh |  | Regular |  | ED-28' 5" | 12 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79370-1 | 79370 | 1 | 1 | Regular | DIALED-22 | DIALED-22-2500-80-30-VL-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-22 | 2019-02-27 | 29 | 29 | Rajithan Sivapatharajahon |  | Regular |  | D22 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79373-1 | 79373 | 1 | 1 | Regular | SCULPT-4' | SCD-500-90-30-FL-4'-BLK-UNV-DP-1-CA(72) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 12 | 12 | Joshua Zimet |  | High Priority |  | A | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79373-2 | 79373 | 2 | 1 | Regular | SCULPT-6' | SCD-500-90-30-FL-6'-BLK-UNV-DP-1-CA(72) |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 6 | 6 | Joshua Zimet |  | High Priority |  | B | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79373-3 | 79373 | 3 | 1 | Regular | SCULPT-24' | SCWDI-500-500-90-30-BW-0.5P-24'-W-UNV-DP-1 |  | Scheduled/Released |  |  | 2019-02-18 | 2019-02-21 | 1 | 2 | Joshua Zimet |  | High Priority |  | C | 15 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79375-1 | 79375 | 1 | 1 | Mockup/Samples | SKETCH-AL 1' 11 9/16" | SK-10003-ARC-AL 1' 11 9/16"-400-80-35-SO-W-UNV-DP-1-DS-C(CORD AND PLUG) |  | Machine Shop Finished | 2019-02-04 | 08:28:33 | 2019-01-29 | 2019-02-01 | 1 | 1 | Stan Buyansky | Picked - Complete | High Priority |  | A | 1 | TRUE | TRUE | TRUE | TRUE | [10 empty] | TRUE |  | AfterWirin | TRUE | 2019-02-04 10:27 |  | TRUE | FALSE
79411-1 | 79411 | 1 | 1 | Regular | DAYFLED-22 | DAYFLED-22-3000-80-35-SO-W-UNV-DP-1-TB15 |  | Scheduled/Released |  |  | 2019-02-04 | 2019-02-07 | 37 | 37 | Philip Halsey |  | High Priority |  | L6 | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79418-1 | 79418 | 1 | 1 | Mockup/Samples | ZEN-4 | ZELED-SL 65/35-700-80-35-MSO-W-4-W-UNV-MD-1-CT15(36) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Joe Brier | Picked - Complete | High Priority |  | ZEN-A | 4 | TRUE | TRUE | TRUE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79418-2 | 79418 | 2 | 1 | Mockup/Samples | ZEN-4 | ZELED-SL 65/35-700-80-35-MAL-W-4-W-UNV-MD-1-CT15(36) |  | Machine Shop Started |  |  | 2019-01-31 | 2019-02-05 | 1 | 1 | Joe Brier | Picked - Complete | High Priority |  | ZEN-B | 4 | TRUE | TRUE | TRUE | FALSE |  | ToDo | [8 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE
79431-1 | 79431 | 1 | 1 | Quick Ship+ | AULED-22 | AULED-22-4400-80-35-SO-W-277-DP-1-TG9 |  | Scheduled/Released |  |  | 2019-02-07 | 2019-02-12 | 75 | 75 | Rajithan Sivapatharajahon |  | High Priority |  | A | 10 | FALSE | FALSE | FALSE | FALSE | [10 empty] | FALSE |  |  | FALSE |  |  | FALSE | FALSE

## Hmi-Data
Production Group | Order | Line | Column1 | Total Sec | Ship Date | Status | Remaining | Date | Assembly cell | 8:00 AM | 9:00 AM | 10:00 AM | 11:00 AM | 12:30 PM | 1:30 PM | 2:30 PM | 3:30 PM | Column3 | Total Section Completed | Open Value | Per section $ value | Completed $ value | Target By Hour | Final Target | Column2 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34
1 | 78945 | 1 | 78945-1 | 14 | 2019-02-04 | #N/A | 11 | 2019-02-01 | 1 | 2 |  |  | 1 |  |  |  |  | NO | 3 | 21840 | 1560 | 4680 |  |  | Column2: 0; Column25: #REF!; Column29: 11772; Column30: 436; Column31: 2616; Column34: 0
1 | 78580 | 11 | 78580-11 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 2 | 1 | [7 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 11772; Column30: 436; Column31: 1308; Column34: 0
1 | 78580 | 6 | 78580-6 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 | 2 | [7 empty] | YES | 2 | 440 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 11772; Column30: 436; Column31: 1744; Column34: 0
1 | 78580 | 10 | 78580-10 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 | 2 | [7 empty] | YES | 2 | 440 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 11772; Column30: 436; Column31: 8720; Column34: 0
1 | 78580 | 25 | 78580-25 | 3 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 | 1 | 2 | [6 empty] | YES | 3 | 660 | 220 | 660 |  |  | Column2: 0; Column25: #REF!; Column29: 1020; Column30: 510; Column31: 510; Column34: 0
1 | 78580 | 24 | 78580-24 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 | 2 | [7 empty] | YES | 2 | 440 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 78580 | 3 | 78580-3 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 | 1 | [7 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 78580 | 32 | 78580-32 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 3 | 1 | [7 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 78580 | 5 | 78580-5 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 3 | 1 | 1 | [6 empty] | YES | 2 | 440 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 2040; Column30: 510; Column31: 510; Column34: 0
1 | 78580 | 9 | 78580-9 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 3 | 1 | [7 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1020; Column30: 510; Column31: 1020; Column34: 0
1 | 78580 | 7 | 78580-7 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 3 | 1 | [7 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1020; Column30: 510; Column31: 510; Column34: 0
4 | 78266 | 1 | 78266-1 | 26 | 2019-02-04 | #N/A | 0 | 2019-02-01 | 4 | 2 | 5 | 3 | 3 | 5 | 6 | 2 |  | NO | 26 | 21060 | 810 | 21060 |  |  | Column2: 0; Column25: #REF!; Column29: 20094; Column30: 591; Column31: 20094; Column34: 0
4 | 77268 | 1 | 77268-1 | 40 | 2019-01-24 | #N/A | 37 | 2019-02-01 | 5 | 3 | [7 empty] | NO | 3 | 21865 | 546.625 | 1639.875 |  |  | Column2: 0; Column25: #REF!; Column29: 4328; Column30: 360.6667; Column31: 4328; Column34: 0
4 | 76336 | 13 | 76336-13 | 2 | 2019-02-05 | #N/A | 1 | 2019-02-01 | 5 | 1 | [7 empty] | YES | 1 | 1830 | 915 | 915 |  |  | Column2: 0; Column25: #REF!; Column29: 3928; Column30: 392.8; Column31: 3928; Column34: 0
4 | 77268 | 1 | 77268-1 | 40 | 2019-01-24 | #N/A | 32 | 2019-02-01 | 6 | 4 | 4 | [6 empty] | NO | 8 | 21865 | 546.625 | 4373 |  |  | Column2: 0; Column25: #REF!; Column29: 650; Column30: 650; Column31: 650; Column34: 0
7 | 70411 | 4 | 70411-4 | 254 | 2019-02-01 | #N/A | 204 | 2019-02-01 | 7 | 10 | 10 | 10 | 10 | 10 |  |  |  | NO | 50 | 64770 | 255 | 12750 |  |  | Column2: 0; Column25: #REF!; Column29: 3448; Column30: 862; Column31: 3448; Column34: 0
7 | 70411 | 4 | 70411-4 | 254 | 2019-02-01 | #N/A | 192 | 2019-02-01 | 8 | 10 | 10 | 10 | 10 | 10 | 12 |  |  | NO | 62 | 64770 | 255 | 15810 |  |  | Column2: 0; Column25: #REF!; Column29: 8692; Column30: 1086.5; Column31: 7605.5; Column34: 0
7 | 70411 | 4 | 70411-4 | 254 | 2019-02-01 | #N/A | 208 | 2019-02-01 | 9 | 8 | 8 | 8 | 10 | 10 | 2 |  |  | NO | 46 | 64770 | 255 | 11730 |  |  | Column2: 0; Column25: #REF!; Column29: 7750; Column30: 516.6667; Column31: 3616.6667; Column34: 0
10 | 75966 | 1 | 75966-1 | 290 | 2019-02-14 | #N/A | 213 | 2019-02-01 | 10 | 10 | 14 | 10 | 14 | 5 |  | 12 | 12 | YES | 77 | 53650 | 185 | 14245 |  |  | Column2: 0; Column25: #REF!; Column29: 1092; Column30: 182; Column31: 1092; Column34: 0
10 | 75966 | 1 | 75966-1 | 290 | 2019-02-14 | #N/A | 228 | 2019-02-01 | 11 | 10 | 10 | 8 | 12 | 10 |  |  | 12 | YES | 62 | 53650 | 185 | 11470 |  |  | Column2: 0; Column25: #REF!; Column29: 2310; Column30: 165; Column31: 2310; Column34: 0
12 | 78947 | 1 | 78947-1 | 4 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 12 | 4 | [7 empty] | NO | 4 | 1152 | 288 | 1152 |  |  | Column2: 0; Column25: #REF!; Column29: 8592; Column30: 358; Column31: 8592; Column34: 0
12 | 78633 | 1 | 78633-1 | 1 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 12 | 1 | [7 empty] | NO | 1 | 75 | 75 | 75 |  |  | Column2: 0; Column25: #REF!; Column29: 4032; Column30: 504; Column31: 4032; Column34: 0
12 | 78824 | 1 | 78824-1 | 2 | 2019-02-04 | #N/A | 0 | 2019-02-01 | 12 | 2 | [7 empty] | NO | 2 | 570 | 285 | 570 |  |  | Column2: 0; Column25: #REF!; Column29: 4628; Column30: 356; Column31: 4628; Column34: 0
12 | 77601 | 1 | 77601-1 | 1 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 12 | 1 | [7 empty] | NO | 1 | 1250 | 1250 | 1250 |  |  | Column2: 0; Column25: #REF!; Column29: 19800; Column30: 450; Column31: 4500; Column34: 0
12 | 78682 | 1 | 78682-1 | 6 | 2019-02-04 | #N/A | 0 | 2019-02-01 | 13 | 6 | [7 empty] | NO | 6 | 1920 | 320 | 1920 |  |  | Column2: 0; Column25: #REF!; Column29: 19800; Column30: 450; Column31: 2700; Column34: 0
12 | 76087 | 3 | 76087-3 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 13 | 1 | 2 | [6 empty] | NO | 3 | 945 | 315 | 945 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
18 | 73887 | 7 | 73887-7 | 30 | 2019-02-05 | Packaging Finished | 0 | 2019-02-01 | 18 | 10 | 10 | 10 | [5 empty] | YES | 30 | 7500 | 250 | 7500 |  |  | Column2: 0; Column25: #REF!; Column29: 1020; Column30: 510; Column31: 1020; Column34: 0
1 | 78580 | 17 | 78580-17 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 1 |  | 1 | [6 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 2040; Column30: 510; Column31: 510; Column34: 0
1 | 78580 | 33 | 78580-33 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 1 |  | 1 | [6 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 680; Column34: 0
1 | 78580 | 19 | 78580-19 | 3 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 1 |  | 2 | [6 empty] | YES | 2 | 660 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 18 | 78580-18 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 1 |  | 1 | [6 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 23 | 78580-23 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 1 |  |  | 1 | [5 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 41 | 78580-41 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 1 |  |  | 1 | [5 empty] | YES | 1 | 990 | 495 | 495 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1462.5; Column34: 0
1 | 78580 | 97 | 78580-97 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 1 |  |  | 1 | [5 empty] | YES | 1 | 110 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 94 | 78580-94 | 3 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 1 |  |  | 2 | [5 empty] | YES | 2 | 330 | 110 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 2 | 78580-2 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  | 2 | [6 empty] | YES | 2 | 440 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 2758; Column30: 394; Column31: 2758; Column34: 0
1 | 78580 | 1 | 78580-1 | 3 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 2 |  | 2 | [6 empty] | YES | 2 | 660 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 1401; Column30: 233.5; Column31: 1401; Column34: 0
1 | 78580 | 30 | 78580-30 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 2 |  | 1 | [6 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 439; Column30: 439; Column31: 439; Column34: 0
1 | 78580 | 4 | 78580-4 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  | 1 | [6 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 5118; Column30: 853; Column31: 5118; Column34: 0
1 | 78580 | 20 | 78580-20 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 2 |  | 1 | [6 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 4485; Column30: 747.5; Column31: 4485; Column34: 0
1 | 78580 | 32 | 78580-32 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 2 |  |  | 1 | [5 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 10115; Column30: 722.5; Column31: 10115; Column34: 0
1 | 78580 | 8 | 78580-8 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  |  | 1 | [5 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 23625; Column30: 675; Column31: 23625; Column34: 0
1 | 78580 | 12 | 78580-12 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  |  | 1 | [5 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 2802; Column30: 467; Column31: 2802; Column34: 0
1 | 78580 | 13 | 78580-13 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 2 |  |  | 1 | [5 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 933.82; Column30: 466.91; Column31: 933.82; Column34: 0
1 | 78580 | 34 | 78580-34 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  |  | 1 | [5 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 2134.34; Column30: 533.585; Column31: 2134.34; Column34: 0
1 | 78580 | 15 | 78580-15 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  |  | 2 | [5 empty] | YES | 2 | 440 | 220 | 440 |  |  | Column2: 0; Column25: #REF!; Column29: 1900; Column30: 475; Column31: 1900; Column34: 0
1 | 78580 | 26 | 78580-26 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  |  | 1 | [5 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1250; Column30: 416.6667; Column31: 416.6667; Column34: 0
1 | 75668 | 6 | 75668-6 | 2 | 2019-01-31 | #N/A | 1 | 2019-02-01 | 3 |  | 1 | [6 empty] | NO | 1 | 7370 | 3685 | 3685 |  |  | Column2: 0; Column25: #REF!; Column29: 600; Column30: 600; Column31: 600; Column34: 0
1 | 78580 | 18 | 78580-18 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 3 |  | 1 | [6 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 600; Column30: 600; Column31: 600; Column34: 0
1 | 78580 | 13 | 78580-13 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 3 |  | 1 | [6 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 11000; Column30: 550; Column31: 2750; Column34: 0
1 | 78580 | 16 | 78580-16 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 3 |  | 1 | [6 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 78580 | 35 | 78580-35 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 3 |  |  | 1 | [5 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 78580 | 22 | 78580-22 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 3 |  |  | 1 | [5 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 78580 | 39 | 78580-39 | 4 | 2019-02-06 | #N/A | 3 | 2019-02-01 | 3 |  |  | 1 | [5 empty] | YES | 1 | 880 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 680; Column34: 0
1 | 78580 | 1 | 78580-1 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 3 |  |  | 1 | [5 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 101 | 78580-101 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 3 |  |  | 1 | [5 empty] | YES | 1 | 110 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 78580 | 94 | 78580-94 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 3 |  |  | 1 | [5 empty] | YES | 1 | 330 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1462.5; Column34: 0
4 | 77632 | 2 | 77632-2 | 7 | 2019-01-25 | #N/A | 0 | 2019-02-01 | 5 |  | 1 | 1 | 2 |  | 1 | 1 | 1 | NO | 7 | 7413 | 1059 | 7413 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1462.5; Column34: 0
4 | 76817 | 9 | 76817-9 | 8 | 2019-02-04 | Given to Shipping | 3 | 2019-02-01 | 6 |  |  | 5 | [5 empty] | NO | 5 | 4608 | 576 | 2880 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
12 | 78464 | 1 | 78464-1 | 1 | 2019-02-04 | #N/A | 0 | 2019-02-01 | 12 |  | 1 | [6 empty] | NO | 1 | 1085 | 1085 | 1085 |  |  | Column2: 0; Column25: #REF!; Column29: 3528; Column30: 441; Column31: 3528; Column34: 0
12 | 78622 | 1 | 78622-1 | 2 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 12 |  |  | 2 | 0 |  |  |  |  | NO | 2 | 660 | 330 | 660 |  |  | Column2: 0; Column25: #REF!; Column29: 1653; Column30: 330.6; Column31: 661.2; Column34: 0
12 | 76087 | 4 | 76087-4 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 13 |  | 3 | [6 empty] | NO | 3 | 1431 | 477 | 1431 |  |  | Column2: 0; Column25: #REF!; Column29: 3558; Column30: 395.3333; Column31: 3558; Column34: 0
12 | 76087 | 1 | 76087-1 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 13 |  | 2 | 1 | [5 empty] | NO | 3 | 945 | 315 | 945 |  |  | Column2: 0; Column25: #REF!; Column29: 8512; Column30: 1064; Column31: 8512; Column34: 0
12 | 76087 | 2 | 76087-2 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 13 |  |  | 3 | [5 empty] | NO | 3 | 1431 | 477 | 1431 |  |  | Column2: 0; Column25: #REF!; Column29: 345; Column30: 345; Column31: 345; Column34: 0
1 | 75692 | 6 | 75692-6 | 3 | 2019-01-24 | #N/A | 1 | 2019-02-01 | 1 |  |  |  | 2 |  |  |  |  | NO | 2 | 864 | 288 | 576 |  |  | Column2: 0; Column25: #REF!; Column29: 1250; Column30: 250; Column31: 1250; Column34: 0
1 | 78580 | 95 | 78580-95 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-01 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 4200; Column30: 840; Column31: 4200; Column34: 0
1 | 78580 | 102 | 78580-102 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-01 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 110 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 3360; Column30: 840; Column31: 3360; Column34: 0
1 | 78580 | 96 | 78580-96 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-01 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 330 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 1680; Column30: 420; Column31: 1680; Column34: 0
1 | 78580 | 44 | 78580-44 | 4 | 2019-02-06 | #N/A | 3 | 2019-02-01 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 1650 | 412.5 | 412.5 |  |  | Column2: 0; Column25: #REF!; Column29: 667; Column30: 333.5; Column31: 667; Column34: 0
1 | 77005 | 1 | 77005-1 | 16 | 2019-01-29 | #N/A | 13 | 2019-02-01 | 3 |  |  |  | 3 |  |  |  |  | NO | 3 | 9500 | 593.75 | 1781.25 |  |  | Column2: 0; Column25: #REF!; Column29: 4783; Column30: 797.1667; Column31: 4783; Column34: 0
1 | 75668 | 4 | 75668-4 | 1 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 3 |  |  |  | 1 |  |  |  |  | NO | 1 | 3885 | 3885 | 3885 |  |  | Column2: 0; Column25: #REF!; Column29: 2392; Column30: 1196; Column31: 1196; Column34: 0
4 | 77361 | 11 | 77361-11 | 2 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 4 |  |  |  | 2 |  |  |  |  | NO | 2 | 600 | 300 | 600 |  |  | Column2: 0; Column25: #REF!; Column29: 11000; Column30: 550; Column31: 1100; Column34: 0
4 | 76817 | 9 | 76817-9 | 8 | 2019-02-04 | Given to Shipping | 5 | 2019-02-01 | 6 |  |  |  | 3 |  |  |  |  | NO | 3 | 4608 | 576 | 1728 |  |  | Column2: 0; Column25: #REF!; Column29: 1200; Column30: 600; Column31: 600; Column34: 0
4 | 76817 | 12 | 76817-12 | 4 | 2019-02-04 | Given to Shipping | 0 | 2019-02-01 | 6 |  |  |  | 3 | 1 |  |  |  | NO | 4 | 2592 | 648 | 2592 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
12 | 78377 | 1 | 78377-1 | 3 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 13 |  |  | 1 | 2 |  |  |  |  | NO | 3 | 2940 | 980 | 2940 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
18 | 73887 | 21 | 73887-21 | 7 | 2019-02-05 | Packaging Finished | 0 | 2019-02-01 | 18 |  |  |  | 7 |  |  |  |  | YES | 7 | 1764 | 252 | 1764 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
18 | 73887 | 3 | 73887-3 | 34 | 2019-02-05 | Packaging Finished | 0 | 2019-02-01 | 18 |  |  |  | 3 | 13 | 17 |  | 1 | YES | 34 | 7956 | 234 | 7956 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
1 | 77005 | 1 | 77005-1 | 16 | 2019-01-29 | #N/A | 14 | 2019-02-01 | 1 |  |  |  |  | 2 |  |  |  | NO | 2 | 9500 | 593.75 | 1187.5 |  |  | Column2: 0; Column25: #REF!; Column29: 3188; Column30: 398.5; Column31: 3188; Column34: 0
1 | 75745 | 13 | 75745-13 | 5 | 2019-01-28 | Wiring Started | 1 | 2019-02-01 | 1 |  |  |  |  | 3 | 1 |  |  | NO | 4 | 2770 | 554 | 2216 |  |  | Column2: 1; Column25: #REF!; Column29: 1738; Column30: 347.6; Column31: 1042.8; Column34: 0
1 | 78391 | 1 | 78391-1 | 40 | 2019-01-28 | #N/A | 30 | 2019-02-01 | 1 | [5 empty] | 5 | 3 | 2 | NO | 10 | 22400 | 560 | 5600 |  |  | Column2: 0; Column25: #REF!; Column29: 6420; Column30: 1284; Column31: 6420; Column34: 0
1 | 77005 | 1 | 77005-1 | 16 | 2019-01-29 | #N/A | 5 | 2019-02-01 | 2 |  |  |  | 5 | 1 | 5 |  |  | NO | 11 | 9500 | 593.75 | 6531.25 |  |  | Column2: 0; Column25: #REF!; Column29: 2030; Column30: 406; Column31: 2030; Column34: 0
1 | 78391 | 1 | 78391-1 | 40 | 2019-01-28 | #N/A | 27 | 2019-02-01 | 3 |  |  |  |  | 6 | 5 | 0 | 2 | NO | 13 | 22400 | 560 | 7280 |  |  | Column2: 0; Column25: #REF!; Column29: 1648; Column30: 206; Column31: 1648; Column34: 0
4 | 78406 | 7 | 78406-7 | 2 | 2019-01-31 | #N/A | 1 | 2019-02-01 | 5 |  |  |  |  | 1 |  |  |  | NO | 1 | 895 | 447.5 | 447.5 |  |  | Column2: 0; Column25: #REF!; Column29: 11648; Column30: 448; Column31: 11648; Column34: 0
4 | 78406 | 4 | 78406-4 | 6 | 2019-01-31 | #N/A | 5 | 2019-02-01 | 5 |  |  |  |  | 1 |  |  |  | NO | 1 | 2340 | 390 | 390 |  |  | Column2: 0; Column25: #REF!; Column29: 450; Column30: 450; Column31: 450; Column34: 0
4 | 77632 | 1 | 77632-1 | 2 | 2019-01-25 | #N/A | 0 | 2019-02-01 | 5 | [5 empty] | 1 | 1 |  | NO | 2 | 1764 | 882 | 1764 |  |  | Column2: 0; Column25: #REF!; Column29: 375; Column30: 375; Column31: 375; Column34: 0
4 | 76817 | 13 | 76817-13 | 2 | 2019-02-04 | Given to Shipping | 0 | 2019-02-01 | 6 |  |  |  |  | 2 |  |  |  | NO | 2 | 1008 | 504 | 1008 |  |  | Column2: 0; Column25: #REF!; Column29: 3210; Column30: 1070; Column31: 3210; Column34: 0
4 | 76817 | 14 | 76817-14 | 1 | 2019-02-04 | Given to Shipping | 0 | 2019-02-01 | 6 |  |  |  |  | 1 |  |  |  | NO | 1 | 432 | 432 | 432 |  |  | Column2: 0; Column25: #REF!; Column29: 3210; Column30: 1070; Column31: 3210; Column34: 0
4 | 76817 | 10 | 76817-10 | 2 | 2019-02-04 | Given to Shipping | 0 | 2019-02-01 | 6 |  |  |  |  | 2 |  |  |  | NO | 2 | 1476 | 738 | 1476 |  |  | Column2: 0; Column25: #REF!; Column29: 6029.58; Column30: 1004.93; Column31: 6029.58; Column34: 0
4 | 76817 | 11 | 76817-11 | 4 | 2019-02-04 | Given to Shipping | 3 | 2019-02-01 | 6 | [5 empty] | 1 |  |  | NO | 1 | 2916 | 729 | 729 |  |  | Column2: 0; Column25: #REF!; Column29: 2392; Column30: 1196; Column31: 2392; Column34: 0
7 | 75664 | 12 | 75664-12 | 8 | 2019-01-04 | #N/A | 0 | 2019-02-01 | 7 | [5 empty] | 8 |  |  | NO | 8 | 3710 | 463.75 | 3710 |  |  | Column2: 0; Column25: #REF!; Column29: 2153; Column30: 717.6667; Column31: 2153; Column34: 0
7 | 77908 | 3 | 77908-3 | 2 | 2019-02-05 | Packaging Finished | 0 | 2019-02-01 | 9 | [5 empty] | 2 |  |  | YES | 2 | 1560 | 780 | 1560 |  |  | Column2: 0; Column25: #REF!; Column29: 14348; Column30: 1793.5; Column31: 14348; Column34: 0
7 | 77908 | 6 | 77908-6 | 5 | 2019-02-05 | Packaging Finished | 0 | 2019-02-01 | 9 | [5 empty] | 5 |  |  | YES | 5 | 1100 | 220 | 1100 |  |  | Column2: 0; Column25: #REF!; Column29: 11000; Column30: 550; Column31: 7150; Column34: 0
7 | 77908 | 1 | 77908-1 | 2 | 2019-02-05 | Packaging Finished | 1 | 2019-02-01 | 9 | [5 empty] | 1 | 0 |  | YES | 1 | 1560 | 780 | 780 |  |  | Column2: 0; Column25: #REF!; Column29: 11000; Column30: 550; Column31: 6600; Column34: 0
10 | 78453 | 1 | 78453-1 | 2 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 10 |  |  |  |  | 2 |  |  |  | NO | 2 | 370 | 185 | 370 |  |  | Column2: 0; Column25: #REF!; Column29: 1050; Column30: 525; Column31: 1050; Column34: 0
10 | 78453 | 3 | 78453-3 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 10 |  |  |  |  | 3 |  |  |  | NO | 3 | 555 | 185 | 555 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 1360; Column34: 0
10 | 78453 | 5 | 78453-5 | 2 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 10 |  |  |  |  | 2 |  |  |  | NO | 2 | 370 | 185 | 370 |  |  | Column2: 0; Column25: #REF!; Column29: 680; Column30: 680; Column31: 680; Column34: 0
10 | 78453 | 6 | 78453-6 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 10 | [5 empty] | 3 |  |  | NO | 3 | 555 | 185 | 555 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 680; Column34: 0
10 | 77346 | 1 | 77346-1 | 1 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 10 | [5 empty] | 1 |  |  | NO | 1 | 100 | 100 | 100 |  |  | Column2: 0; Column25: #REF!; Column29: 1360; Column30: 680; Column31: 680; Column34: 0
10 | 79121 | 1 | 79121-1 | 1 | 2019-02-12 | Scheduled/Released | 0 | 2019-02-01 | 10 | [5 empty] | 1 |  |  | YES | 1 | 4400 | 4400 | 4400 |  |  | Column2: 0; Column25: #REF!; Column29: 2040; Column30: 510; Column31: 1020; Column34: 0
10 | 78915 | 1 | 78915-1 | 7 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 10 | [5 empty] | 5 | 2 |  | NO | 7 | 1610 | 230 | 1610 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
10 | 78484 | 1 | 78484-1 | 4 | 2019-02-01 | Wiring Started | 0 | 2019-02-01 | 10 | [5 empty] | 4 |  |  | NO | 4 | 960 | 240 | 960 |  |  | Column2: 0; Column25: #REF!; Column29: 6139.25; Column30: 511.6042; Column31: 6139.25; Column34: 0
10 | 79128 | 1 | 79128-1 | 24 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 11 |  |  |  |  | 2 | 12 | 10 |  | NO | 24 | 6576 | 274 | 6576 |  |  | Column2: 0; Column25: #REF!; Column29: 1484; Column30: 296.8; Column31: 1187.2; Column34: 0
12 | 77826 | 2 | 77826-2 | 5 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 12 | [5 empty] | 5 |  |  | NO | 5 | 4120 | 824 | 4120 |  |  | Column2: 0; Column25: #REF!; Column29: 1738; Column30: 347.6; Column31: 695.2; Column34: 0
12 | 77826 | 1 | 77826-1 | 4 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 12 | [5 empty] | 4 |  |  | NO | 4 | 2900 | 725 | 2900 |  |  | Column2: 0; Column25: #REF!; Column29: 1653; Column30: 330.6; Column31: 991.8; Column34: 0
12 | 78697 | 1 | 78697-1 | 1 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 12 |  |  |  |  | 1 |  |  |  | NO | 1 | 150.55 | 150.55 | 150.55 |  |  | Column2: 0; Column25: #REF!; Column29: 750; Column30: 375; Column31: 750; Column34: 0
12 | 78761 | 1 | 78761-1 | 4 | 2019-01-31 | #N/A | 0 | 2019-02-01 | 13 |  |  |  |  | 4 |  |  |  | NO | 4 | 2720 | 680 | 2720 |  |  | Column2: 0; Column25: #REF!; Column29: 1925; Column30: 275; Column31: 1925; Column34: 0
12 | 78512 | 1 | 78512-1 | 7 | 2019-02-04 | #N/A | 0 | 2019-02-01 | 13 |  |  |  |  | 3 | 4 |  |  | NO | 7 | 4410 | 630 | 4410 |  |  | Column2: 0; Column25: #REF!; Column29: 1615; Column30: 807.5; Column31: 1615; Column34: 0
12 | 78512 | 1 | 78512-1 | 7 | 2019-02-04 | #N/A | 6 | 2019-02-01 | 13 | [5 empty] | 1 |  |  | NO | 1 | 4410 | 630 | 630 |  |  | Column2: 0; Column25: #REF!; Column29: 3120; Column30: 240; Column31: 2640; Column34: 0
1 | 77005 | 2 | 77005-2 | 16 | 2019-01-29 | #N/A | 0 | 2019-02-01 | 2 | [6 empty] | 12 | 4 | NO | 16 | 11400 | 712.5 | 11400 |  |  | Column2: 0; Column25: #REF!; Column29: 7245; Column30: 1449; Column31: 7245; Column34: 0
4 | 76817 | 7 | 76817-7 | 24 | 2019-02-04 | Given to Shipping | 23 | 2019-02-01 | 6 | [6 empty] | 1 |  | NO | 1 | 12828 | 534.5 | 534.5 |  |  | Column2: 0; Column25: #REF!; Column29: 9391.26; Column30: 1565.21; Column31: 9391.26; Column34: 0
7 | 76468 | 1 | 76468-1 | 29 | 2019-02-07 | #N/A | 13 | 2019-02-01 | 7 | [6 empty] | 9 | 7 | YES | 16 | 6264 | 216 | 3456 |  |  | Column2: 0; Column25: #REF!; Column29: 600; Column30: 300; Column31: 300; Column34: 0
7 | 76468 | 3 | 76468-3 | 65 | 2019-02-07 | #N/A | 40 | 2019-02-01 | 8 | [6 empty] | 12 | 13 | YES | 25 | 17290 | 266 | 6650 |  |  | Column2: 0; Column25: #REF!; Column29: 1100; Column30: 550; Column31: 550; Column34: 0
12 | 79184 | 1 | 79184-1 | 1 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 12 | [6 empty] | 1 |  | NO | 1 | 300 | 300 | 300 |  |  | Column2: 0; Column25: #REF!; Column29: 900; Column30: 450; Column31: 900; Column34: 0
12 | 77673 | 1 | 77673-1 | 2 | 2019-02-01 | #N/A | 0 | 2019-02-01 | 12 | [6 empty] | 2 |  | NO | 2 | 1220 | 610 | 1220 |  |  | Column2: 0; Column25: #REF!; Column29: 900; Column30: 450; Column31: 450; Column34: 0
12 | 78548 | 1 | 78548-1 | 2 | 2019-02-04 | #N/A | 0 | 2019-02-01 | 13 | [6 empty] | 2 |  | NO | 2 | 3100 | 1550 | 3100 |  |  | Column2: 0; Column25: #REF!; Column29: 3400; Column30: 850; Column31: 3400; Column34: 0
18 | 73887 | 16 | 73887-16 | 12 | 2019-02-05 | Packaging Finished | 0 | 2019-02-01 | 18 | [6 empty] | 6 | 6 | YES | 12 | 2808 | 234 | 2808 |  |  | Column2: 0; Column25: #REF!; Column29: 1020; Column30: 1020; Column31: 1020; Column34: 0
1 | 75692 | 8 | 75692-8 | 2 | 2019-01-24 | #N/A | 0 | 2019-02-01 | 1 | [7 empty] | 2 | NO | 2 | 1152 | 576 | 1152 |  |  | Column2: 0; Column25: #REF!; Column29: 1950; Column30: 487.5; Column31: 1950; Column34: 0
1 | 75692 | 9 | 75692-9 | 2 | 2019-01-24 | #N/A | 0 | 2019-02-01 | 1 | [7 empty] | 2 | NO | 2 | 1440 | 720 | 1440 |  |  | Column2: 0; Column25: #REF!; Column29: 1385; Column30: 692.5; Column31: 1385; Column34: 0
1 | 75692 | 6 | 75692-6 | 3 | 2019-01-24 | #N/A | 2 | 2019-02-01 | 1 | [7 empty] | 1 | NO | 1 | 864 | 288 | 288 |  |  | Column2: 0; Column25: #REF!; Column29: 1131.25; Column30: 1131.25; Column31: 1131.25; Column34: 0
1 | 75692 | 7 | 75692-7 | 1 | 2019-01-24 | #N/A | 0 | 2019-02-01 | 1 | [7 empty] | 1 | NO | 1 | 432 | 432 | 432 |  |  | Column2: 0; Column25: #REF!; Column29: 40462; Column30: 2247.8889; Column31: 40462; Column34: 0
1 | 78505 | 1 | 78505-1 | 16 | 2019-02-01 | #N/A | 15 | 2019-02-01 | 2 | [7 empty] | 1 | NO | 1 | 5420 | 338.75 | 338.75 |  |  | Column2: 0; Column25: #REF!; Column29: 400; Column30: 200; Column31: 400; Column34: 0
1 | 77848 | 4 | 77848-4 | 3 | 2019-01-25 | #N/A | 2 | 2019-02-01 | 3 | [7 empty] | 1 | NO | 1 | 400 | 133.3333 | 133.3333 |  |  | Column2: 0; Column25: #REF!; Column29: 1272; Column30: 212; Column31: 1272; Column34: 0
1 | 77848 | 3 | 77848-3 | 2 | 2019-01-25 | #N/A | 0 | 2019-02-01 | 3 | [7 empty] | 2 | NO | 2 | 400 | 200 | 400 |  |  | Column2: 0; Column25: #REF!; Column29: 1160; Column30: 232; Column31: 1160; Column34: 0
1 | 77848 | 2 | 77848-2 | 1 | 2019-01-25 | #N/A | 0 | 2019-02-01 | 3 | [7 empty] | 1 | NO | 1 | 400 | 400 | 400 |  |  | Column2: 0; Column25: #REF!; Column29: 13200; Column30: 220; Column31: 8140; Column34: 0
7 | 77908 | 4 | 77908-4 | 6 | 2019-02-05 | Packaging Finished | 1 | 2019-02-01 | 9 | [7 empty] | 5 | YES | 5 | 3640 | 606.6667 | 3033.3333 |  |  | Column2: 0; Column25: #REF!; Column29: 420; Column30: 420; Column31: 420; Column34: 0
12 | 77177 | 1 | 77177-1 | 18 | 2019-01-04 | #N/A | 16 | 2019-02-01 | 12 | [7 empty] | 2 | NO | 2 | 10800 | 600 | 1200 |  |  | Column2: 0; Column25: #REF!; Column29: 1415.88; Column30: 1415.88; Column31: 1415.88; Column34: 0
1 | 78391 | 1 | 78391-1 | 40 | 2019-01-28 | #N/A | 33 | 2019-02-04 | 1 | 6 | 1 | [6 empty] | NO | 7 | 22400 | 560 | 3920 |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 350; Column31: 700; Column34: 0
1 | 78580 | 98 | 78580-98 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 | 1 | [7 empty] | YES | 1 | 110 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 3120; Column30: 240; Column31: 720; Column34: 0
1 | 78580 | 105 | 78580-105 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 | 1 | [7 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 3151.76; Column30: 787.94; Column31: 3151.76; Column34: 0
1 | 78580 | 95 | 78580-95 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 350; Column31: 350; Column34: 0
1 | 78580 | 96 | 78580-96 | 3 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  | 1 | 1 | [5 empty] | YES | 2 | 330 | 110 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 350; Column31: 700; Column34: 0
1 | 78580 | 99 | 78580-99 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 900; Column30: 450; Column31: 450; Column34: 0
1 | 78580 | 100 | 78580-100 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 900; Column30: 450; Column31: 900; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 1520; Column30: 380; Column31: 1520; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 810; Column30: 405; Column31: 810; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 2632.5; Column30: 1316.25; Column31: 2632.5; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 3564; Column30: 1188; Column31: 3564; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 410; Column30: 410; Column31: 410; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 7595; Column30: 1085; Column31: 7595; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 13200; Column30: 220; Column31: 3960; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 3060; Column30: 340; Column31: 3060; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 1601; Column30: 800.5; Column31: 1601; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 353; Column30: 353; Column31: 353; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 960; Column30: 480; Column31: 960; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 750; Column30: 375; Column31: 375; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 1250; Column30: 416.6667; Column31: 416.6667; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 350; Column31: 350; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 1250; Column30: 250; Column31: 250; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 550; Column30: 550; Column31: 550; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 800; Column30: 400; Column31: 400; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 500; Column30: 500; Column31: 500; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 1250; Column30: 250; Column31: 250; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 950; Column30: 475; Column31: 475; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 350; Column31: 350; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 2174; Column30: 1087; Column31: 2174; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 4230; Column30: 705; Column31: 2820; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 8160; Column30: 680; Column31: 4080; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 780; Column30: 390; Column31: 780; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 5040; Column30: 360; Column31: 3600; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 3255; Column30: 1085; Column31: 3255; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 680; Column30: 340; Column31: 680; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 2700; Column30: 900; Column31: 2700; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 320; Column30: 320; Column31: 320; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 3000; Column30: 1000; Column31: 3000; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 5184; Column30: 432; Column31: 864; Column34: 0
#REF! |  |  | - |  | #REF! | 0 | #VALUE! | #REF! | [9 empty] | #REF! | 0 |  | #VALUE! | #VALUE! |  |  | Column2: 0; Column25: #REF!; Column29: 768; Column30: 384; Column31: 768; Column34: 0
1 | 78580 | 103 | 78580-103 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 110 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 600; Column30: 300; Column31: 300; Column34: 0
1 | 78580 | 67 | 78580-67 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 11000; Column30: 550; Column31: 550; Column34: 0
1 | 78580 | 68 | 78580-68 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 350; Column31: 350; Column34: 0
1 | 78580 | 42 | 78580-42 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 990 | 495 | 495 |  |  | Column2: 0; Column25: #REF!; Column29: 500; Column30: 500; Column31: 500; Column34: 0
1 | 78580 | 72 | 78580-72 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  | 1 | [6 empty] | YES | 1 | 1100 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 7690; Column30: 384.5; Column31: 3076; Column34: 0
1 | 78580 | 63 | 78580-63 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  | 2 | [5 empty] | YES | 2 | 1100 | 550 | 1100 |  |  | Column2: 0; Column25: #REF!; Column29: 3845; Column30: 384.5; Column31: 1538; Column34: 0
1 | 78580 | 83 | 78580-83 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  | 1 | [5 empty] | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 23240; Column30: 363.125; Column31: 6899.375; Column34: 0
1 | 78580 | 79 | 78580-79 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  | 2 | [5 empty] | YES | 2 | 660 | 330 | 660 |  |  | Column2: 0; Column25: #REF!; Column29: 8160; Column30: 680; Column31: 680; Column34: 0
1 | 78580 | 84 | 78580-84 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  | 1 | [5 empty] | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 3800; Column30: 950; Column31: 3800; Column34: 0
1 | 78580 | 105 | 78580-105 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  | 1 | [5 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 2600; Column30: 1300; Column31: 2600; Column34: 0
1 | 78580 | 88 | 78580-88 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  | 1 | [5 empty] | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 1600; Column30: 1600; Column31: 1600; Column34: 0
1 | 78580 | 43 | 78580-43 | 4 | 2019-02-06 | #N/A | 2 | 2019-02-04 | 2 |  | 1 | 1 | [5 empty] | YES | 2 | 1980 | 495 | 990 |  |  | Column2: 0; Column25: #REF!; Column29: 3212; Column30: 292; Column31: 1460; Column34: 0
1 | 78580 | 65 | 78580-65 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  | 1 | [6 empty] | YES | 1 | 1100 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 11340; Column30: 270; Column31: 5400; Column34: 0
1 | 78580 | 64 | 78580-64 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 2 |  | 1 | [6 empty] | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 3212; Column30: 292; Column31: 1752; Column34: 0
1 | 78580 | 100 | 78580-100 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  | 1 | [6 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 744; Column30: 186; Column31: 744; Column34: 0
1 | 78580 | 99 | 78580-99 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  | 1 | [6 empty] | YES | 1 | 220 | 110 | 110 |  |  | Column2: 0; Column25: #REF!; Column29: 36361; Column30: 2272.5625; Column31: 22725.625; Column34: 0
1 | 78580 | 106 | 78580-106 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  |  | 1 | [5 empty] | YES | 1 | 990 | 495 | 495 |  |  | Column2: 0; Column25: #REF!; Column29: 20171; Column30: 3361.8333; Column31: 3361.8333; Column34: 0
1 | 78580 | 23 | 78580-23 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  |  | 1 | [5 empty] | YES | 1 | 440 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 36361; Column30: 2272.5625; Column31: 4545.125; Column34: 0
1 | 78580 | 14 | 78580-14 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 2 |  |  | 1 | [5 empty] | YES | 1 | 220 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 40462; Column30: 2247.8889; Column31: 6743.6667; Column34: 0
1 | 78580 | 22 | 78580-22 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-04 | 2 |  |  | 1 | [5 empty] | YES | 1 | 660 | 220 | 220 |  |  | Column2: 0; Column25: #REF!; Column29: 20171; Column30: 3361.8333; Column31: 6723.6667; Column34: 0
1 | 78580 | 76 | 78580-76 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  |  | 1 | [5 empty] | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 36361; Column30: 2272.5625; Column31: 6817.6875; Column34: 0
1 | 78580 | 86 | 78580-86 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 2 |  |  | 1 | [5 empty] | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 20171; Column30: 3361.8333; Column31: 13447.3333; Column34: 0
1 | 78391 | 1 | 78391-1 | 40 | 2019-01-28 | #N/A | 27 | 2019-02-04 | 3 | 7 | 3 | 1 | 2 |  |  |  |  | NO | 13 | 22400 | 560 | 7280 |  |  | Column2: 0; Column25: #REF!; Column29: 1600; Column30: 400; Column31: 1600; Column34: 0
1 | 78580 | 66 | 78580-66 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 3 |  | 1 | [6 empty] | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 1150; Column30: 383.3333; Column31: 1150; Column34: 0
1 | 78580 | 62 | 78580-62 | 2 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 3 |  | 1 | 1 | [5 empty] | YES | 2 | 1100 | 550 | 1100 |  |  | Column2: 0; Column25: #REF!; Column29: 3325; Column30: 475; Column31: 3325; Column34: 0
1 | 78580 | 41 | 78580-41 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 3 |  | 1 | [6 empty] | YES | 1 | 990 | 495 | 495 |  |  | Column2: 0; Column25: #REF!; Column29: 2640; Column30: 440; Column31: 2640; Column34: 0
1 | 78580 | 61 | 78580-61 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 3 |  |  | 1 | [5 empty] | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 3720; Column30: 620; Column31: 3720; Column34: 0
1 | 78580 | 77 | 78580-77 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 3 |  |  | 1 | [5 empty] | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 2250; Column30: 450; Column31: 2250; Column34: 0
1 | 78580 | 81 | 78580-81 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 3 |  |  | 1 | [5 empty] | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 2020; Column30: 505; Column31: 2020; Column34: 0
1 | 78580 | 91 | 78580-91 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 3 |  |  | 1 | [5 empty] | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 384; Column30: 384; Column31: 384; Column34: 0
4 | 76817 | 7 | 76817-7 | 24 | 2019-02-04 | Given to Shipping | 19 | 2019-02-04 | 4 |  | 4 | 1 | [5 empty] | NO | 5 | 12828 | 534.5 | 2672.5 |  |  | Column2: 0; Column25: #REF!; Column29: 409; Column30: 409; Column31: 409; Column34: 0
4 | 75398 | 2 | 75398-2 | 129 | 2019-01-16 | Wiring Started | 103 | 2019-02-04 | 4 |  |  | 5 | 4 | 4 | 4 | 4 | 5 | NO | 26 | 156520 | 1213.3333 | 31546.6667 |  |  | Column2: 0; Column25: #REF!; Column29: 2905; Column30: 363.125; Column31: 1452.5; Column34: 0
4 | 76817 | 8 | 76817-8 | 8 | 2019-02-04 | Given to Shipping | 4 | 2019-02-04 | 5 | 2 | 2 | [6 empty] | NO | 4 | 4924 | 615.5 | 2462 |  |  | Column2: 0; Column25: #REF!; Column29: 3400; Column30: 340; Column31: 1360; Column34: 0
4 | 76817 | 7 | 76817-7 | 24 | 2019-02-04 | Given to Shipping | 15 | 2019-02-04 | 5 | 5 | 4 | [6 empty] | NO | 9 | 12828 | 534.5 | 4810.5 |  |  | Column2: 0; Column25: #REF!; Column29: 730; Column30: 365; Column31: 730; Column34: 0
4 | 76817 | 2 | 76817-2 | 4 | 2019-02-04 | Given to Shipping | 3 | 2019-02-04 | 5 |  | 1 | [6 empty] | NO | 1 | 1912 | 478 | 478 |  |  | Column2: 0; Column25: #REF!; Column29: 4420; Column30: 736.6667; Column31: 4420; Column34: 0
4 | 75398 | 2 | 75398-2 | 129 | 2019-01-16 | Wiring Started | 118 | 2019-02-04 | 5 |  |  | 5 | 0 | 2 | 2 | 2 |  | NO | 11 | 156520 | 1213.3333 | 13346.6667 |  |  | Column2: 0; Column25: #REF!; Column29: 11340; Column30: 270; Column31: 6210; Column34: 0
4 | 76817 | 7 | 76817-7 | 24 | 2019-02-04 | Given to Shipping | 14 | 2019-02-04 | 6 | 2 | 3 | 1 |  |  | 2 | 2 |  | NO | 10 | 12828 | 534.5 | 5345 |  |  | Column2: 0; Column25: #REF!; Column29: 4284; Column30: 252; Column31: 4284; Column34: 0
4 | 76817 | 11 | 76817-11 | 4 | 2019-02-04 | Given to Shipping | 1 | 2019-02-04 | 6 | 2 |  | 1 | [5 empty] | NO | 3 | 2916 | 729 | 2187 |  |  | Column2: 0; Column25: #REF!; Column29: 5520; Column30: 345; Column31: 5520; Column34: 0
4 | 76817 | 1 | 76817-1 | 1 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 6 | 1 | [7 empty] | NO | 1 | 227 | 227 | 227 |  |  | Column2: 0; Column25: #REF!; Column29: 4300; Column30: 860; Column31: 4300; Column34: 0
4 | 76817 | 5 | 76817-5 | 2 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 6 |  | 1 | 1 | [5 empty] | NO | 2 | 680 | 340 | 680 |  |  | Column2: 0; Column25: #REF!; Column29: 3440; Column30: 860; Column31: 2580; Column34: 0
4 | 76817 | 6 | 76817-6 | 2 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 6 |  | 1 |  |  | 1 |  |  |  | NO | 2 | 1232 | 616 | 1232 |  |  | Column2: 0; Column25: #REF!; Column29: 1100; Column30: 550; Column31: 1100; Column34: 0
4 | 76817 | 4 | 76817-4 | 1 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 6 |  |  | 1 | [5 empty] | NO | 1 | 502 | 502 | 502 |  |  | Column2: 0; Column25: #REF!; Column29: 1776; Column30: 444; Column31: 1776; Column34: 0
4 | 76817 | 9 | 76817-9 | 8 | 2019-02-04 | Given to Shipping | 7 | 2019-02-04 | 6 |  |  | 1 | [5 empty] | NO | 1 | 4608 | 576 | 576 |  |  | Column2: 0; Column25: #REF!; Column29: 2160; Column30: 720; Column31: 2160; Column34: 0
4 | 76817 | 2 | 76817-2 | 4 | 2019-02-04 | Given to Shipping | 2 | 2019-02-04 | 6 |  |  | 1 | 1 |  |  |  |  | NO | 2 | 1912 | 478 | 956 |  |  | Column2: 0; Column25: #REF!; Column29: 720; Column30: 720; Column31: 720; Column34: 0
7 | 76468 | 1 | 76468-1 | 29 | 2019-02-07 | #N/A | 17 | 2019-02-04 | 7 | 7 | 5 | [6 empty] | YES | 12 | 6264 | 216 | 2592 |  |  | Column2: 0; Column25: #REF!; Column29: 13120; Column30: 3280; Column31: 13120; Column34: 0
7 | 76468 | 2 | 76468-2 | 2 | 2019-02-07 | #N/A | 0 | 2019-02-04 | 7 |  | 2 | [6 empty] | YES | 2 | 690 | 345 | 690 |  |  | Column2: 0; Column25: #REF!; Column29: 660; Column30: 330; Column31: 660; Column34: 0
7 | 76468 | 4 | 76468-4 | 1 | 2019-02-07 | #N/A | 0 | 2019-02-04 | 7 |  | 1 | [6 empty] | YES | 1 | 216 | 216 | 216 |  |  | Column2: 0; Column25: #REF!; Column29: 2256; Column30: 564; Column31: 2256; Column34: 0
7 | 76468 | 5 | 76468-5 | 1 | 2019-02-07 | #N/A | 0 | 2019-02-04 | 7 |  | 1 | [6 empty] | YES | 1 | 345 | 345 | 345 |  |  | Column2: 0; Column25: #REF!; Column29: 1728; Column30: 192; Column31: 1728; Column34: 0
7 | 71407 | 5 | 71407-5 | 16 | 2019-02-07 | #N/A | 3 | 2019-02-04 | 7 |  |  | 7 | 6 |  |  |  |  | YES | 13 | 6635.33 | 414.7081 | 5391.2056 |  |  | Column2: 0; Column25: #REF!; Column29: 23240; Column30: 363.125; Column31: 9441.25; Column34: 0
7 | 76468 | 6 | 76468-6 | 1 | 2019-02-07 | #N/A | 0 | 2019-02-04 | 8 | 1 | [7 empty] | YES | 1 | 266 | 266 | 266 |  |  | Column2: 0; Column25: #REF!; Column29: 4420; Column30: 736.6667; Column31: 4420; Column34: 0
7 | 76468 | 3 | 76468-3 | 65 | 2019-02-07 | #N/A | 54 | 2019-02-04 | 8 | 7 |  | 4 | [5 empty] | YES | 11 | 17290 | 266 | 2926 |  |  | Column2: 0; Column25: #REF!; Column29: 4420; Column30: 736.6667; Column31: 4420; Column34: 0
7 | 77908 | 9 | 77908-9 | 24 | 2019-02-05 | Packaging Finished | 16 | 2019-02-04 | 8 |  | 4 | 4 | [5 empty] | YES | 8 | 11280 | 470 | 3760 |  |  | Column2: 0; Column25: #REF!; Column29: 2480; Column30: 310; Column31: 2480; Column34: 0
7 | 77908 | 5 | 77908-5 | 6 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 9 | 5 | 1 | [6 empty] | YES | 6 | 4160 | 693.3333 | 4160 |  |  | Column2: 0; Column25: #REF!; Column29: 2188; Column30: 729.3333; Column31: 2188; Column34: 0
7 | 77908 | 2 | 77908-2 | 4 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 9 |  | 3 | 1 | [5 empty] | YES | 4 | 2600 | 650 | 2600 |  |  | Column2: 0; Column25: #REF!; Column29: 3440; Column30: 860; Column31: 860; Column34: 0
7 | 77908 | 4 | 77908-4 | 6 | 2019-02-05 | Packaging Finished | 5 | 2019-02-04 | 9 |  | 1 | [6 empty] | YES | 1 | 3640 | 606.6667 | 606.6667 |  |  | Column2: 0; Column25: #REF!; Column29: 8301.15; Column30: 922.35; Column31: 8301.15; Column34: 0
7 | 77908 | 10 | 77908-10 | 3 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 9 |  | 2 | 1 | [5 empty] | YES | 3 | 2620 | 873.3333 | 2620 |  |  | Column2: 0; Column25: #REF!; Column29: 954; Column30: 318; Column31: 954; Column34: 0
7 | 77908 | 7 | 77908-7 | 4 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 9 |  |  | 4 | [5 empty] | YES | 4 | 1600 | 400 | 1600 |  |  | Column2: 0; Column25: #REF!; Column29: 590; Column30: 295; Column31: 590; Column34: 0
10 | 75966 | 8 | 75966-8 | 520 | 2019-02-11 | Machine Shop Started | 478 | 2019-02-04 | 10 | 10 | 10 | 8 | 10 | 4 |  |  |  | YES | 42 | 130000 | 250 | 10500 |  |  | Column2: 0; Column25: #REF!; Column29: 4400; Column30: 733.3333; Column31: 4400; Column34: 0
10 | 75966 | 1 | 75966-1 | 290 | 2019-02-14 | #N/A | 278 | 2019-02-04 | 11 | 10 | 2 | [6 empty] | YES | 12 | 53650 | 185 | 2220 |  |  | Column2: 0; Column25: #REF!; Column29: 6300; Column30: 420; Column31: 5040; Column34: 0
10 | 75966 | 8 | 75966-8 | 520 | 2019-02-11 | Machine Shop Started | 504 | 2019-02-04 | 11 |  | 6 | 8 | 2 |  |  |  |  | YES | 16 | 130000 | 250 | 4000 |  |  | Column2: 0; Column25: #REF!; Column29: 3360; Column30: 280; Column31: 3360; Column34: 0
12 | 75164 | 1 | 75164-1 | 9 | 2019-02-01 | Wiring Started | 1 | 2019-02-04 | 12 | 3 | 3 | [5 empty] | 2 | NO | 8 | 9706.5 | 1078.5 | 8628 |  |  | Column2: 0; Column25: #REF!; Column29: 1302; Column30: 217; Column31: 1302; Column34: 0
12 | 75164 | 2 | 75164-2 | 2 | 2019-02-01 | Packaging Finished | 0 | 2019-02-04 | 12 |  |  | 2 | [5 empty] | NO | 2 | 696.6 | 348.3 | 696.6 |  |  | Column2: 0; Column25: #REF!; Column29: 424; Column30: 212; Column31: 424; Column34: 0
12 | 75164 | 3 | 75164-3 | 1 | 2019-02-01 | Packaging Finished | 0 | 2019-02-04 | 12 |  |  | 1 | [5 empty] | NO | 1 | 1044.9 | 1044.9 | 1044.9 |  |  | Column2: 0; Column25: #REF!; Column29: 8492; Column30: 424.6; Column31: 3821.4; Column34: 0
12 | 78856 | 1 | 78856-1 | 2 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 13 | 2 | [7 empty] | NO | 2 | 764 | 382 | 764 |  |  | Column2: 0; Column25: #REF!; Column29: 6186; Column30: 386.625; Column31: 2706.375; Column34: 0
12 | 79146 | 1 | 79146-1 | 3 | 2019-02-04 | #N/A | 2 | 2019-02-04 | 13 | 1 | [7 empty] | NO | 1 | 370 | 123.3333 | 123.3333 |  |  | Column2: 0; Column25: #REF!; Column29: 2905; Column30: 363.125; Column31: 1089.375; Column34: 0
12 | 78335 | 1 | 78335-1 | 5 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 13 |  | 5 | [6 empty] | NO | 5 | 3750 | 750 | 3750 |  |  | Column2: 0; Column25: #REF!; Column29: 4434; Column30: 369.5; Column31: 2586.5; Column34: 0
12 | 78743 | 1 | 78743-1 | 2 | 2019-02-01 | #N/A | 0 | 2019-02-04 | 13 |  | 1 | 1 | [5 empty] | NO | 2 | 816 | 408 | 816 |  |  | Column2: 0; Column25: #REF!; Column29: 1700; Column30: 850; Column31: 1700; Column34: 0
12 | 79206 | 1 | 79206-1 | 14 | 2019-02-05 | #N/A | 8 | 2019-02-04 | 13 |  |  | 6 | [5 empty] | YES | 6 | 4560 | 325.7143 | 1954.2857 |  |  | Column2: 0; Column25: #REF!; Column29: 6120; Column30: 612; Column31: 6120; Column34: 0
18 | 73887 | 19 | 73887-19 | 4 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 | 4 | [7 empty] | YES | 4 | 1872 | 468 | 1872 |  |  | Column2: 0; Column25: #REF!; Column29: 2480; Column30: 310; Column31: 2480; Column34: 0
18 | 73887 | 4 | 73887-4 | 1 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 | 1 | [7 empty] | YES | 1 | 468 | 468 | 468 |  |  | Column2: 0; Column25: #REF!; Column29: 4642; Column30: 422; Column31: 4220; Column34: 0
18 | 73887 | 18 | 73887-18 | 3 | 2019-02-05 | Packaging Finished | 1 | 2019-02-04 | 18 | 1 | 1 | [6 empty] | YES | 2 | 1404 | 468 | 936 |  |  | Column2: 0; Column25: #REF!; Column29: 1095; Column30: 365; Column31: 1095; Column34: 0
18 | 73887 | 6 | 73887-6 | 1 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 | 1 | [7 empty] | YES | 1 | 702 | 702 | 702 |  |  | Column2: 0; Column25: #REF!; Column29: 1460; Column30: 365; Column31: 1460; Column34: 0
18 | 73887 | 23 | 73887-23 | 2 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  | 1 |  | 1 |  |  |  |  | YES | 2 | 702 | 351 | 702 |  |  | Column2: 0; Column25: #REF!; Column29: 91575.6; Column30: 455.6; Column31: 4100.4; Column34: 0
18 | 73887 | 20 | 73887-20 | 3 | 2019-02-05 | Packaging Finished | 2 | 2019-02-04 | 18 |  | 1 | [6 empty] | YES | 1 | 2106 | 702 | 702 |  |  | Column2: 0; Column25: #REF!; Column29: 400; Column30: 200; Column31: 400; Column34: 0
18 | 73887 | 8 | 73887-8 | 1 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  | 1 | [6 empty] | YES | 1 | 750 | 750 | 750 |  |  | Column2: 0; Column25: #REF!; Column29: 4240; Column30: 424; Column31: 4240; Column34: 0
18 | 73887 | 5 | 73887-5 | 2 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  | 1 |  | 1 |  |  |  |  | YES | 2 | 936 | 468 | 936 |  |  | Column2: 0; Column25: #REF!; Column29: 47488.584; Column30: 456.621; Column31: 17808.219; Column34: 0
18 | 73887 | 26 | 73887-26 | 3 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  | 1 |  |  | 1 |  |  | 1 | YES | 3 | 1578 | 526 | 1578 |  |  | Column2: 0; Column25: #REF!; Column29: 2160; Column30: 360; Column31: 2160; Column34: 0
18 | 73887 | 12 | 73887-12 | 8 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  | 2 | 4 | 2 |  |  |  |  | YES | 8 | 2200 | 275 | 2200 |  |  | Column2: 0; Column25: #REF!; Column29: 424; Column30: 424; Column31: 424; Column34: 0
18 | 73887 | 11 | 73887-11 | 4 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  | 4 | [6 empty] | YES | 4 | 1372 | 343 | 1372 |  |  | Column2: 0; Column25: #REF!; Column29: 960; Column30: 240; Column31: 720; Column34: 0
18 | 73887 | 1 | 73887-1 | 7 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  |  | 7 | [5 empty] | YES | 7 | 1638 | 234 | 1638 |  |  | Column2: 0; Column25: #REF!; Column29: 19800; Column30: 450; Column31: 7200; Column34: 0
1 | 78580 | 82 | 78580-82 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  |  | 1 |  |  |  |  | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 7690; Column30: 384.5; Column31: 3460.5; Column34: 0
1 | 78580 | 85 | 78580-85 | 3 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  |  | 2 |  |  |  |  | YES | 2 | 990 | 330 | 660 |  |  | Column2: 0; Column25: #REF!; Column29: 8492; Column30: 424.6; Column31: 2972.2; Column34: 0
1 | 78580 | 89 | 78580-89 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  |  | 1 |  |  |  |  | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 936; Column30: 234; Column31: 936; Column34: 0
1 | 78580 | 93 | 78580-93 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  |  | 1 |  |  |  |  | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 1710; Column30: 855; Column31: 1710; Column34: 0
1 | 78580 | 92 | 78580-92 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-04 | 1 |  |  |  | 1 |  |  |  |  | YES | 1 | 990 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 18086.61; Column30: 1004.8117; Column31: 18086.61; Column34: 0
1 | 78580 | 80 | 78580-80 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  |  | 1 |  |  |  |  | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 93735; Column30: 1735.8333; Column31: 59018.3333; Column34: 0
1 | 78580 | 87 | 78580-87 | 3 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  |  | 1 | 1 |  |  |  | YES | 2 | 990 | 330 | 660 |  |  | Column2: 0; Column25: #REF!; Column29: 91575.6; Column30: 455.6; Column31: 16401.6; Column34: 0
1 | 78580 | 124 | 78580-124 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  |  |  | 1 |  |  |  | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 1450; Column30: 483.3333; Column31: 1450; Column34: 0
1 | 78580 | 134 | 78580-134 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  |  |  | 1 |  |  |  | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 2160; Column30: 360; Column31: 1440; Column34: 0
1 | 78580 | 90 | 78580-90 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  |  |  | 1 |  |  |  | YES | 1 | 330 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 475; Column30: 475; Column31: 475; Column34: 0
1 | 78580 | 119 | 78580-119 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  |  |  | 1 |  |  |  | YES | 1 | 770 | 385 | 385 |  |  | Column2: 0; Column25: #REF!; Column29: 2160; Column30: 360; Column31: 720; Column34: 0
1 | 78580 | 77 | 78580-77 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 1 |  |  |  |  | 1 |  |  |  | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 19800; Column30: 450; Column31: 6750; Column34: 0
1 | 78580 | 74 | 78580-74 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 |  |  |  |  | 1 |  |  |  | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 2717; Column30: 339.625; Column31: 1018.875; Column34: 0
1 | 64752 | 20 | 64752-20 | 18 | 2019-02-05 | Wiring Started | 10 | 2019-02-04 | 1 |  |  |  |  | 1 | 3 | 2 | 2 | YES | 8 | 9000 | 500 | 4000 |  |  | Column2: 0; Column25: #REF!; Column29: 936; Column30: 468; Column31: 936; Column34: 0
1 | 78580 | 89 | 78580-89 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 660 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 1404; Column30: 351; Column31: 1404; Column34: 0
1 | 78580 | 85 | 78580-85 | 3 | 2019-02-06 | #N/A | 2 | 2019-02-04 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 990 | 330 | 330 |  |  | Column2: 0; Column25: #REF!; Column29: 2040; Column30: 680; Column31: 2040; Column34: 0
1 | 78580 | 69 | 78580-69 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 1100 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 765; Column30: 382.5; Column31: 382.5; Column34: 0
1 | 78580 | 72 | 78580-72 | 2 | 2019-02-06 | #N/A | 1 | 2019-02-04 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 1100 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 765; Column30: 382.5; Column31: 382.5; Column34: 0
1 | 78580 | 75 | 78580-75 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 2565; Column30: 855; Column31: 1710; Column34: 0
1 | 64752 | 10 | 64752-10 | 27 | 2019-02-05 | Wiring Started | 20 | 2019-02-04 | 2 |  |  |  |  | 4 |  |  | 3 | YES | 7 | 13500 | 500 | 3500 |  |  | Column2: 0; Column25: #REF!; Column29: 1330; Column30: 665; Column31: 1330; Column34: 0
1 | 78580 | 108 | 78580-108 | 6 | 2019-02-06 | #N/A | 5 | 2019-02-04 | 2 |  |  |  |  | 1 |  |  |  | YES | 1 | 2200 | 366.6667 | 366.6667 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 15 | 64752-15 | 32 | 2019-02-05 | Wiring Started | 24 | 2019-02-04 | 2 |  |  |  |  | 1 | 5 | 2 |  | YES | 8 | 12800 | 400 | 3200 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 72049 | 4 | 72049-4 | 4 | 2019-01-29 | Wiring Started | 0 | 2019-02-04 | 3 |  |  |  | 3 | 1 |  |  |  | NO | 4 | 10000 | 2500 | 10000 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 72049 | 16 | 72049-16 | 4 | 2019-01-29 | Wiring Started | 1 | 2019-02-04 | 3 |  |  |  |  | 1 | 1 | 1 |  | NO | 3 | 10000 | 2500 | 7500 |  |  | Column2: 0; Column25: #REF!; Column29: 1200; Column30: 600; Column31: 1200; Column34: 0
4 | 76817 | 8 | 76817-8 | 8 | 2019-02-04 | Given to Shipping | 5 | 2019-02-04 | 6 |  |  |  | 1 | 1 |  | 1 |  | NO | 3 | 4924 | 615.5 | 1846.5 |  |  | Column2: 0; Column25: #REF!; Column29: 700; Column30: 700; Column31: 700; Column34: 0
4 | 76817 | 3 | 76817-3 | 4 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 6 |  |  |  | 3 |  |  | 1 |  | NO | 4 | 3142 | 785.5 | 3142 |  |  | Column2: 0; Column25: #REF!; Column29: 6300; Column30: 420; Column31: 1680; Column34: 0
7 | 77611 | 3 | 77611-3 | 12 | 2019-01-23 | #N/A | 0 | 2019-02-04 | 7 |  |  |  |  | 4.5 | 4.5 | 3 |  | NO | 12 | 4940 | 411.6667 | 4940 |  |  | Column2: 0; Column25: #REF!; Column29: 2160; Column30: 360; Column31: 720; Column34: 0
7 | 76823 | 11 | 76823-11 | 81 | 2019-02-04 | Wiring Started | 32 | 2019-02-04 | 8 |  |  |  | 9 | 10 | 10 | 10 | 10 | NO | 49 | 27450 | 338.8889 | 16605.5556 |  |  | Column2: 0; Column25: #REF!; Column29: 1460; Column30: 365; Column31: 1460; Column34: 0
7 | 76468 | 3 | 76468-3 | 65 | 2019-02-07 | #N/A | 23 | 2019-02-04 | 9 |  |  |  | 10 | 10 | 10 | 10 | 2 | YES | 42 | 17290 | 266 | 11172 |  |  | Column2: 0; Column25: #REF!; Column29: 2456; Column30: 614; Column31: 2456; Column34: 0
10 | 78690 | 2 | 78690-2 | 5 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 10 |  |  |  |  | 5 |  |  |  | NO | 5 | 3062.5 | 612.5 | 3062.5 |  |  | Column2: 0; Column25: #REF!; Column29: 1734; Column30: 867; Column31: 1734; Column34: 0
10 | 79085 | 1 | 79085-1 | 88 | 2019-02-05 | Wiring Started | 30 | 2019-02-04 | 11 |  |  |  | 10 | 12 | 12 | 12 | 12 | YES | 58 | 17600 | 200 | 11600 |  |  | Column2: 0; Column25: #REF!; Column29: 867; Column30: 867; Column31: 867; Column34: 0
12 | 76370 | 1 | 76370-1 | 3 | 2019-02-01 | #N/A | 0 | 2019-02-04 | 12 |  |  |  | 1 |  |  | 2 |  | NO | 3 | 3247.05 | 1082.35 | 3247.05 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
12 | 78768 | 1 | 78768-1 | 1 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 12 | [5 empty] | 1 |  |  | NO | 1 | 1112.5 | 1112.5 | 1112.5 |  |  | Column2: 0; Column25: #REF!; Column29: 6186; Column30: 386.625; Column31: 2319.75; Column34: 0
12 | 78636 | 1 | 78636-1 | 1 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 12 | [5 empty] | 1 |  |  | NO | 1 | 300 | 300 | 300 |  |  | Column2: 0; Column25: #REF!; Column29: 4434; Column30: 369.5; Column31: 1108.5; Column34: 0
12 | 78553 | 1 | 78553-1 | 1 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 12 | [5 empty] | 1 |  |  | NO | 1 | 375 | 375 | 375 |  |  | Column2: 0; Column25: #REF!; Column29: 1530; Column30: 765; Column31: 1530; Column34: 0
12 | 78905 | 1 | 78905-1 | 1 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 12 |  |  |  |  | 1 |  |  |  | NO | 1 | 400 | 400 | 400 |  |  | Column2: 0; Column25: #REF!; Column29: 1020; Column30: 510; Column31: 1020; Column34: 0
12 | 75738 | 2 | 75738-2 | 9 | 2019-02-04 | Packaging Finished | 0 | 2019-02-04 | 13 |  |  |  | 3 | 3 | 3 |  |  | NO | 9 | 2673 | 297 | 2673 |  |  | Column2: 0; Column25: #REF!; Column29: 1689.47; Column30: 563.1567; Column31: 1689.47; Column34: 0
12 | 78735 | 1 | 78735-1 | 4 | 2019-02-05 | #N/A | 0 | 2019-02-04 | 13 |  |  |  |  | 4 |  |  |  | YES | 4 | 3408 | 852 | 3408 |  |  | Column2: 0; Column25: #REF!; Column29: 3640; Column30: 910; Column31: 3640; Column34: 0
12 | 79320 | 1 | 79320-1 | 4 | 2019-02-04 | Packaging Finished | 0 | 2019-02-04 | 13 | [5 empty] | 4 |  |  | NO | 4 | 2080 | 520 | 2080 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
18 | 73887 | 24 | 73887-24 | 3 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  |  |  | 3 |  |  |  |  | YES | 3 | 1053 | 351 | 1053 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
18 | 73887 | 13 | 73887-13 | 4 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  |  |  | 4 |  |  |  |  | YES | 4 | 2032 | 508 | 2032 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
18 | 73887 | 10 | 73887-10 | 4 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  |  |  | 1 | 3 |  |  |  | YES | 4 | 2500 | 625 | 2500 |  |  | Column2: 0; Column25: #REF!; Column29: 93735; Column30: 1735.8333; Column31: 8679.1667; Column34: 0
18 | 73887 | 9 | 73887-9 | 2 | 2019-02-05 | Packaging Finished | 0 | 2019-02-04 | 18 |  |  |  |  | 2 |  |  |  | YES | 2 | 998 | 499 | 998 |  |  | Column2: 0; Column25: #REF!; Column29: 47488.584; Column30: 456.621; Column31: 913.242; Column34: 0
18 | 77808 | 1 | 77808-1 | 18 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 18 |  |  |  |  | 5 | 11 | 2 |  | NO | 18 | 6840 | 380 | 6840 |  |  | Column2: 0; Column25: #REF!; Column29: 1800; Column30: 450; Column31: 1800; Column34: 0
18 | 78386 | 3 | 78386-3 | 13 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 18 | [6 empty] | 11 | 2 | NO | 13 | 3796 | 292 | 3796 |  |  | Column2: 0; Column25: #REF!; Column29: 8492; Column30: 424.6; Column31: 2123; Column34: 0
1 | 78580 | 70 | 78580-70 | 1 | 2019-02-06 | #N/A | 0 | 2019-02-04 | 1 | [5 empty] | 1 |  |  | YES | 1 | 550 | 550 | 550 |  |  | Column2: 0; Column25: #REF!; Column29: 23240; Column30: 363.125; Column31: 1815.625; Column34: 0
1 | 64752 | 10 | 64752-10 | 27 | 2019-02-05 | Wiring Started | 21 | 2019-02-04 | 1 | [5 empty] | 4 | 1 | 1 | YES | 6 | 13500 | 500 | 3000 |  |  | Column2: 0; Column25: #REF!; Column29: 2717; Column30: 339.625; Column31: 1358.5; Column34: 0
1 | 64752 | 15 | 64752-15 | 32 | 2019-02-05 | Wiring Started | 18 | 2019-02-04 | 1 | [5 empty] | 4 | 8 | 2 | YES | 14 | 12800 | 400 | 5600 |  |  | Column2: 0; Column25: #REF!; Column29: 1180; Column30: 590; Column31: 1180; Column34: 0
1 | 64752 | 11 | 64752-11 | 15 | 2019-02-05 | Wiring Started | 12 | 2019-02-04 | 1 | [7 empty] | 3 | YES | 3 | 9000 | 600 | 1800 |  |  | Column2: 0; Column25: #REF!; Column29: 12870; Column30: 495; Column31: 495; Column34: 0
1 | 64752 | 18 | 64752-18 | 2 | 2019-02-05 | Wiring Started | 1 | 2019-02-04 | 1 | [7 empty] | 1 | YES | 1 | 800 | 400 | 400 |  |  | Column2: 0; Column25: #REF!; Column29: 1980; Column30: 495; Column31: 1980; Column34: 0
1 | 64752 | 19 | 64752-19 | 4 | 2019-02-05 | Wiring Started | 3 | 2019-02-04 | 1 | [7 empty] | 1 | YES | 1 | 1800 | 450 | 450 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 12 | 64752-12 | 116 | 2019-02-05 | Wiring Started | 115 | 2019-02-04 | 1 | [7 empty] | 1 | YES | 1 | 2300 | 19.8276 | 19.8276 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 17 | 64752-17 | 2 | 2019-02-05 | Wiring Started | 0 | 2019-02-04 | 2 | [5 empty] | 2 |  |  | YES | 2 | 700 | 350 | 700 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 18 | 64752-18 | 2 | 2019-02-05 | Wiring Started | 1 | 2019-02-04 | 2 | [5 empty] | 1 |  |  | YES | 1 | 800 | 400 | 400 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 20 | 64752-20 | 18 | 2019-02-05 | Wiring Started | 15 | 2019-02-04 | 2 | [6 empty] | 3 |  | YES | 3 | 9000 | 500 | 1500 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 19 | 64752-19 | 4 | 2019-02-05 | Wiring Started | 2 | 2019-02-04 | 2 | [6 empty] | 2 |  | YES | 2 | 1800 | 450 | 900 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 11 | 64752-11 | 15 | 2019-02-05 | Wiring Started | 13 | 2019-02-04 | 2 | [6 empty] | 1 | 1 | YES | 2 | 9000 | 600 | 1200 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 15 | 64752-15 | 32 | 2019-02-05 | Wiring Started | 26 | 2019-02-04 | 3 | [6 empty] | 3 | 3 | YES | 6 | 12800 | 400 | 2400 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
7 | 77440 | 1 | 77440-1 | 12 | 2019-02-01 | Given to Shipping | 0 | 2019-02-04 | 7 | [6 empty] | 3 | 9 | NO | 12 | 1324 | 110.3333 | 1324 |  |  | Column2: 0; Column25: #REF!; Column29: 91575.6; Column30: 455.6; Column31: 5011.6; Column34: 0
7 | 71407 | 10 | 71407-10 | 16 | 2019-02-07 | #N/A | 13 | 2019-02-04 | 7 |  |  |  | 3 |  |  |  |  | YES | 3 | 1531.26 | 95.7037 | 287.1112 |  |  | Column2: 0; Column25: #REF!; Column29: 1014; Column30: 338; Column31: 1014; Column34: 0
7 | 73829 | 1 | 73829-1 | 24 | 2019-02-06 | Wiring Started | 15 | 2019-02-04 | 9 | [7 empty] | 9 | YES | 9 | 26756.464 | 1114.8527 | 10033.674 |  |  | Column2: 0; Column25: #REF!; Column29: 1209; Column30: 604.5; Column31: 1209; Column34: 0
10 | 78690 | 1 | 78690-1 | 5 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 10 | [5 empty] | 5 |  |  | NO | 5 | 1937.5 | 387.5 | 1937.5 |  |  | Column2: 0; Column25: #REF!; Column29: 1800; Column30: 450; Column31: 1800; Column34: 0
10 | 79000 | 1 | 79000-1 | 1 | 2019-02-04 | Scheduled/Released | 0 | 2019-02-04 | 10 | [5 empty] | 1 |  |  | NO | 1 | 239 | 239 | 239 |  |  | Column2: 0; Column25: #REF!; Column29: 1050; Column30: 525; Column31: 525; Column34: 0
10 | 77854 | 11 | 77854-11 | 2 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 10 | [5 empty] | 2 |  |  | NO | 2 | 500 | 250 | 500 |  |  | Column2: 0; Column25: #REF!; Column29: 1820; Column30: 606.6667; Column31: 1820; Column34: 0
10 | 79001 | 1 | 79001-1 | 8 | 2019-02-04 | #N/A | 0 | 2019-02-04 | 10 | [5 empty] | 1 | 7 |  | NO | 8 | 2889.2 | 361.15 | 2889.2 |  |  | Column2: 0; Column25: #REF!; Column29: 746.72; Column30: 746.72; Column31: 746.72; Column34: 0
10 | 77908 | 8 | 77908-8 | 12 | 2019-02-05 | Packaging Finished | 4 | 2019-02-04 | 10 | [7 empty] | 8 | YES | 8 | 3420 | 285 | 2280 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
12 | 79198 | 1 | 79198-1 | 12 | 2019-02-05 | Wiring Started | 11 | 2019-02-04 | 13 | [6 empty] | 0 | 1 | YES | 1 | 5880 | 490 | 490 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 1795.3; Column34: 0
18 | 78386 | 1 | 78386-1 | 3 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 18 | [7 empty] | 3 | NO | 3 | 1095 | 365 | 1095 |  |  | Column2: 0; Column25: #REF!; Column29: 2154.37; Column30: 1077.185; Column31: 1077.185; Column34: 0
18 | 78386 | 2 | 78386-2 | 3 | 2019-02-04 | Given to Shipping | 0 | 2019-02-04 | 18 | [7 empty] | 3 | NO | 3 | 1314 | 438 | 1314 |  |  | Column2: 0; Column25: #REF!; Column29: 960; Column30: 480; Column31: 480; Column34: 0
1 | 64752 | 15 | 64752-15 | 32 | 2019-02-05 | Wiring Started | 29 | 2019-02-05 | 1 | 2 | 1 | [6 empty] | YES | 3 | 12800 | 400 | 1200 |  |  | Column2: 0; Column25: #REF!; Column29: 1050; Column30: 525; Column31: 525; Column34: 0
1 | 64752 | 10 | 64752-10 | 27 | 2019-02-05 | Wiring Started | 19 | 2019-02-05 | 1 | 3 | 2 | 3 | [5 empty] | YES | 8 | 13500 | 500 | 4000 |  |  | Column2: 0; Column25: #REF!; Column29: 980; Column30: 490; Column31: 980; Column34: 0
1 | 64752 | 12 | 64752-12 | 116 | 2019-02-05 | Wiring Started | 114 | 2019-02-05 | 1 | 1 | 1 | [6 empty] | YES | 2 | 2300 | 19.8276 | 39.6552 |  |  | Column2: 0; Column25: #REF!; Column29: 2160; Column30: 360; Column31: 1080; Column34: 0
1 | 64752 | 20 | 64752-20 | 18 | 2019-02-05 | Wiring Started | 10 | 2019-02-05 | 1 | 2 | 3 | 1 | 2 |  |  |  |  | YES | 8 | 9000 | 500 | 4000 |  |  | Column2: 0; Column25: #REF!; Column29: 960; Column30: 480; Column31: 480; Column34: 0
1 | 64752 | 11 | 64752-11 | 15 | 2019-02-05 | Wiring Started | 12 | 2019-02-05 | 1 |  | 2 |  | 1 |  |  |  |  | YES | 3 | 9000 | 600 | 1800 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
1 | 64752 | 11 | 64752-11 | 15 | 2019-02-05 | Wiring Started | 8 | 2019-02-05 | 2 | 2 | 2 | 3 | [5 empty] | YES | 7 | 9000 | 600 | 4200 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 1795.3; Column34: 0
1 | 64752 | 13 | 64752-13 | 5 | 2019-02-05 | Wiring Started | 3 | 2019-02-05 | 2 |  | 1 | 1 | [5 empty] | YES | 2 | 3000 | 600 | 1200 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
1 | 64752 | 10 | 64752-10 | 27 | 2019-02-05 | Wiring Started | 21 | 2019-02-05 | 2 |  | 4 | 2 | [5 empty] | YES | 6 | 13500 | 500 | 3000 |  |  | Column2: 0; Column25: #REF!; Column29: 8350; Column30: 835; Column31: 5845; Column34: 0
1 | 72049 | 3 | 72049-3 | 12 | 2019-01-29 | Machine Shop Started | 0 | 2019-02-05 | 3 | 1 |  | 2 | 1 | 4 | 3 | 1 |  | NO | 12 | 14720 | 1226.6667 | 14720 |  |  | Column2: 0; Column25: #REF!; Column29: 3640; Column30: 910; Column31: 3640; Column34: 0
1 | 72049 | 15 | 72049-15 | 12 | 2019-01-29 | Machine Shop Started | 0 | 2019-02-05 | 3 | 3 |  |  | 3 | 1 | 4 | 1 |  | NO | 12 | 14720 | 1226.6667 | 14720 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 72049 | 16 | 72049-16 | 4 | 2019-01-29 | Wiring Started | 3 | 2019-02-05 | 3 | 1 | [7 empty] | NO | 1 | 10000 | 2500 | 2500 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
1 | 64752 | 37 | 64752-37 | 12 | 2019-02-05 | Wiring Started | 6 | 2019-02-05 | 3 |  | 4 | 2 | [5 empty] | YES | 6 | 2400 | 200 | 1200 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
4 | 75398 | 2 | 75398-2 | 129 | 2019-01-16 | Wiring Started | 101 | 2019-02-05 | 4 | 4 | 4 | 4 | 4 | 5 | 7 |  |  | NO | 28 | 156520 | 1213.3333 | 33973.3333 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
4 | 75398 | 2 | 75398-2 | 129 | 2019-01-16 | Wiring Started | 99 | 2019-02-05 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | NO | 30 | 156520 | 1213.3333 | 36400 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
4 | 75398 | 2 | 75398-2 | 129 | 2019-01-16 | Wiring Started | 109 | 2019-02-05 | 6 | 0 | 0 | 6 | 5 | 0 | 9 |  |  | NO | 20 | 156520 | 1213.3333 | 24266.6667 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
7 | 76823 | 11 | 76823-11 | 81 | 2019-02-04 | Wiring Started | 71 | 2019-02-05 | 7 | 10 | [7 empty] | NO | 10 | 27450 | 338.8889 | 3388.8889 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
7 | 70411 | 37 | 70411-37 | 281 | 2019-02-08 | Machine Shop Finished | 228 | 2019-02-05 | 7 |  | 10 | 10 | 11 | 11 | 11 |  |  | YES | 53 | 71655 | 255 | 13515 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
7 | 76823 | 11 | 76823-11 | 81 | 2019-02-04 | Wiring Started | 60 | 2019-02-05 | 8 | 10 | 10 | 1 | [5 empty] | NO | 21 | 27450 | 338.8889 | 7116.6667 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
7 | 73829 | 1 | 73829-1 | 24 | 2019-02-06 | Wiring Started | 4 | 2019-02-05 | 9 | 8 | 1 | 4 | 6 | 1 |  |  |  | YES | 20 | 26756.464 | 1114.8527 | 22297.0533 |  |  | Column2: 0; Column25: #REF!; Column29: 855; Column30: 855; Column31: 855; Column34: 0
7 | 76823 | 11 | 76823-11 | 81 | 2019-02-04 | Wiring Started | 71 | 2019-02-05 | 9 |  | 8 | 2 | [5 empty] | NO | 10 | 27450 | 338.8889 | 3388.8889 |  |  | Column2: 0; Column25: #REF!; Column29: 1380; Column30: 460; Column31: 1380; Column34: 0
10 | 78731 | 1 | 78731-1 | 110 | 2019-02-06 | Machine Shop Started | 98 | 2019-02-05 | 10 | 6 | 6 | [6 empty] | YES | 12 | 5520 | 50.1818 | 602.1818 |  |  | Column2: 0; Column25: #REF!; Column29: 6486; Column30: 1081; Column31: 6486; Column34: 0
10 | 78927 | 1 | 78927-1 | 37 | 2019-02-06 | Machine Shop Started | 0 | 2019-02-05 | 10 |  | 4 | 12 | 15 | 6 |  |  |  | YES | 37 | 13660.4 | 369.2 | 13660.4 |  |  | Column2: 0; Column25: #REF!; Column29: 93735; Column30: 1735.8333; Column31: 20830; Column34: 0
10 | 79085 | 1 | 79085-1 | 88 | 2019-02-05 | Wiring Started | 46 | 2019-02-05 | 11 | 12 | 12 | 12 | 6 |  |  |  |  | YES | 42 | 17600 | 200 | 8400 |  |  | Column2: 0; Column25: #REF!; Column29: 3616; Column30: 904; Column31: 3616; Column34: 0
12 | 78999 | 1 | 78999-1 | 2 | 2019-02-01 | Wiring Started | 0 | 2019-02-05 | 12 | 2 | [7 empty] | NO | 2 | 1135 | 567.5 | 1135 |  |  | Column2: 0; Column25: #REF!; Column29: 3218; Column30: 804.5; Column31: 3218; Column34: 0
12 | 78645 | 1 | 78645-1 | 1 | 2019-02-01 | Wiring Started | 0 | 2019-02-05 | 12 |  | 1 | [6 empty] | NO | 1 | 1077 | 1077 | 1077 |  |  | Column2: 0; Column25: #REF!; Column29: 62205; Column30: 165; Column31: 19140; Column34: 0
12 | 78645 | 2 | 78645-2 | 1 | 2019-02-01 | Wiring Started | 0 | 2019-02-05 | 12 |  | 1 | [6 empty] | NO | 1 | 1102 | 1102 | 1102 |  |  | Column2: 0; Column25: #REF!; Column29: 21000; Column30: 350; Column31: 21000; Column34: 0
12 | 79198 | 1 | 79198-1 | 12 | 2019-02-05 | Wiring Started | 1 | 2019-02-05 | 13 | 8 | 3 | 0 | [5 empty] | YES | 11 | 5880 | 490 | 5390 |  |  | Column2: 0; Column25: #REF!; Column29: 730; Column30: 365; Column31: 730; Column34: 0
12 | 75738 | 1 | 75738-1 | 9 | 2019-02-04 | Wiring Started | 0 | 2019-02-05 | 13 |  | 5 | 4 | [5 empty] | NO | 9 | 2851.2 | 316.8 | 2851.2 |  |  | Column2: 0; Column25: #REF!; Column29: 645; Column30: 215; Column31: 645; Column34: 0
18 | 75212 | 30 | 75212-30 | 14 | 2019-02-01 | Wiring Started | 0 | 2019-02-05 | 18 | 7 | 7 | [6 empty] | NO | 14 | 2800 | 200 | 2800 |  |  | Column2: 0; Column25: #REF!; Column29: 1800; Column30: 600; Column31: 1800; Column34: 0
18 | 77693 | 4 | 77693-4 | 8 | 2019-02-05 | Wiring Started | 0 | 2019-02-05 | 18 | 4 | 4 | [6 empty] | YES | 8 | 2565.2 | 320.65 | 2565.2 |  |  | Column2: 0; Column25: #REF!; Column29: 3468; Column30: 867; Column31: 3468; Column34: 0
1 | 64752 | 13 | 64752-13 | 5 | 2019-02-05 | Wiring Started | 2 | 2019-02-05 | 1 |  |  | 3 | [5 empty] | YES | 3 | 3000 | 600 | 1800 |  |  | Column2: 0; Column25: #REF!; Column29: 2072; Column30: 259; Column31: 2072; Column34: 0
1 | 64752 | 12 | 64752-12 | 116 | 2019-02-05 | Wiring Started | 115 | 2019-02-05 | 2 |  |  | 1 | [5 empty] | YES | 1 | 2300 | 19.8276 | 19.8276 |  |  | Column2: 0; Column25: #REF!; Column29: 702; Column30: 234; Column31: 702; Column34: 0
7 | 76823 | 7 | 76823-7 | 24 | 2019-02-04 | Wiring Started | 0 | 2019-02-05 | 8 |  |  | 9 | 10 | 5 |  |  |  | NO | 24 | 8250 | 343.75 | 8250 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
7 | 76823 | 8 | 76823-8 | 15 | 2019-02-04 | Wiring Started | 0 | 2019-02-05 | 9 |  |  | 2 | 3 | 8 | 2 |  |  | NO | 15 | 5130 | 342 | 5130 |  |  | Column2: 0; Column25: #REF!; Column29: 2585.25; Column30: 861.75; Column31: 1723.5; Column34: 0
12 | 77898 | 1 | 77898-1 | 2 | 2019-02-05 | Machine Shop Finished | 0 | 2019-02-05 | 12 |  |  | 2 | [5 empty] | YES | 2 | 1666 | 833 | 1666 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 897.65; Column34: 0
12 | 75164 | 1 | 75164-1 | 9 | 2019-02-01 | Wiring Started | 8 | 2019-02-05 | 12 |  |  | 1 | [5 empty] | NO | 1 | 9706.5 | 1078.5 | 1078.5 |  |  | Column2: 0; Column25: #REF!; Column29: 2800.68; Column30: 933.56; Column31: 933.56; Column34: 0
12 | 79106 | 1 | 79106-1 | 3 | 2019-02-07 | Machine Shop Finished | 0 | 2019-02-05 | 13 |  |  | 2 | 1 |  |  |  |  | YES | 3 | 1710 | 570 | 1710 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
12 | 79106 | 2 | 79106-2 | 3 | 2019-02-07 | Machine Shop Finished | 0 | 2019-02-05 | 13 |  |  | 1 | 2 |  |  |  |  | YES | 3 | 1710 | 570 | 1710 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
18 | 77693 | 8 | 77693-8 | 30 | 2019-02-05 | Wiring Started | 15 | 2019-02-05 | 18 |  |  | 8 | 5 | 2 |  |  |  | YES | 15 | 12185.4 | 406.18 | 6092.7 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
1 | 64752 | 16 | 64752-16 | 2 | 2019-02-05 | Wiring Started | 1 | 2019-02-05 | 1 |  |  |  | 1 |  |  |  |  | YES | 1 | 500 | 250 | 250 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 897.65; Column34: 0
1 | 64752 | 31 | 64752-31 | 10 | 2019-02-05 | Wiring Started | 8 | 2019-02-05 | 1 |  |  |  | 2 |  |  |  |  | YES | 2 | 600 | 60 | 120 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 897.65; Column34: 0
1 | 64752 | 30 | 64752-30 | 26 | 2019-02-01 | Wiring Started | 7 | 2019-02-05 | 1 |  |  |  | 3 | 8 | 8 |  |  | NO | 19 | 10400 | 400 | 7600 |  |  | Column2: 0; Column25: #REF!; Column29: 1831.22; Column30: 1831.22; Column31: 1831.22; Column34: 0
1 | 64752 | 15 | 64752-15 | 32 | 2019-02-05 | Wiring Started | 31 | 2019-02-05 | 2 |  |  |  | 1 |  |  |  |  | YES | 1 | 12800 | 400 | 400 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
1 | 64752 | 22 | 64752-22 | 1 | 2019-02-01 | Wiring Started | 0 | 2019-02-05 | 2 |  |  |  | 1 |  |  |  |  | NO | 1 | 450 | 450 | 450 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
1 | 64752 | 23 | 64752-23 | 16 | 2019-02-01 | Machine Shop Finished | 8 | 2019-02-05 | 2 |  |  |  | 1 | 7 |  |  |  | NO | 8 | 5760 | 360 | 2880 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
4 | 75398 | 3 | 75398-3 | 1 | 2019-01-16 | Wiring Started | 0 | 2019-02-05 | 6 |  |  |  | 1 |  |  |  |  | NO | 1 | 585 | 585 | 585 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 897.65; Column34: 0
7 | 76823 | 10 | 76823-10 | 3 | 2019-02-04 | Wiring Started | 0 | 2019-02-05 | 8 |  |  |  |  | 3 |  |  |  | NO | 3 | 1470 | 490 | 1470 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 897.65; Column34: 0
7 | 76823 | 9 | 76823-9 | 2 | 2019-02-04 | Wiring Started | 0 | 2019-02-05 | 8 |  |  |  |  | 2 |  |  |  | NO | 2 | 1190 | 595 | 1190 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 1795.3067; Column34: 0
10 | 78927 | 3 | 78927-3 | 8 | 2019-02-06 | Machine Shop Started | -6 | 2019-02-05 | 10 |  |  |  |  | 4 | 10 |  |  | YES | 14 | 10914.2 | 1364.275 | 19099.85 |  |  | Column2: 0; Column25: #REF!; Column29: 2800.68; Column30: 933.56; Column31: 933.56; Column34: 0
10 | 79050 | 1 | 79050-1 | 2 | 2019-02-05 | Machine Shop Started | 0 | 2019-02-05 | 11 |  |  |  | 2 |  |  |  |  | YES | 2 | 300 | 150 | 300 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 2692.95; Column34: 0
10 | 78909 | 1 | 78909-1 | 2 | 2019-02-06 | Machine Shop Started | 0 | 2019-02-05 | 11 |  |  |  | 2 |  |  |  |  | YES | 2 | 500 | 250 | 500 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.96; Column30: 897.6533; Column31: 897.6533; Column34: 0
10 | 79005 | 1 | 79005-1 | 3 | 2019-02-05 | Machine Shop Started | 0 | 2019-02-05 | 11 |  |  |  | 3 |  |  |  |  | YES | 3 | 870 | 290 | 870 |  |  | Column2: 0; Column25: #REF!; Column29: 2692.95; Column30: 897.65; Column31: 897.65; Column34: 0
10 | 79043 | 1 | 79043-1 | 10 | 2019-02-05 | Machine Shop Finished | 0 | 2019-02-05 | 11 |  |  |  |  | 10 |  |  |  | YES | 10 | 2950 | 295 | 2950 |  |  | Column2: 0; Column25: #REF!; Column29: 15664; Column30: 356; Column31: 15664; Column34: 0
10 | 78812 | 1 | 78812-1 | 1 | 2019-02-06 | Machine Shop Started | 0 | 2019-02-05 | 11 |  |  |  |  | 1 |  |  |  | YES | 1 | 355 | 355 | 355 |  |  | Column2: 0; Column25: #REF!; Column29: 1911; Column30: 273; Column31: 1911; Column34: 0
10 | 78812 | 3 | 78812-3 | 1 | 2019-02-06 | Machine Shop Started | 0 | 2019-02-05 | 11 |  |  |  |  | 1 |  |  |  | YES | 1 | 255 | 255 | 255 |  |  | Column2: 0; Column25: #REF!; Column29: 4626; Column30: 257; Column31: 4369; Column34: 0
12 | 78637 | 1 | 78637-1 | 1 | 2019-02-05 | Machine Shop Finished | 0 | 2019-02-05 | 12 |  |  |  |  | 1 |  |  |  | YES | 1 | 669.6 | 669.6 | 669.6 |  |  | Column2: 0; Column25: #REF!; Column29: 768; Column30: 192; Column31: 768; Column34: 0
12 | 78637 | 2 | 78637-2 | 3 | 2019-02-05 | Machine Shop Finished | 1 | 2019-02-05 | 12 |  |  |  |  | 2 |  |  |  | YES | 2 | 1026 | 342 | 684 |  |  | Column2: 0; Column25: #REF!; Column29: 1285; Column30: 257; Column31: 1285; Column34: 0
12 | 79037 | 1 | 79037-1 | 1 | 2019-02-05 | Machine Shop Finished | 0 | 2019-02-05 | 12 |  |  |  |  | 1 |  |  |  | YES | 1 | 568 | 568 | 568 |  |  | Column2: 0; Column25: #REF!; Column29: 2289.44; Column30: 763.1467; Column31: 2289.44; Column34: 0
12 | 78502 | 1 | 78502-1 | 3 | 2019-02-05 | Machine Shop Finished | 2 | 2019-02-05 | 12 |  |  |  | 1 |  |  |  |  | YES | 1 | 870 | 290 | 290 |  |  | Column2: 0; Column25: #REF!; Column29: 360; Column30: 360; Column31: 360; Column34: 0
12 | 78515 | 1 | 78515-1 | 5 | 2019-02-07 | Machine Shop Finished | 0 | 2019-02-05 | 13 |  |  |  | 5 |  |  |  |  | YES | 5 | 2335 | 467 | 2335 |  |  | Column2: 0; Column25: #REF!; Column29: 343.42; Column30: 343.42; Column31: 343.42; Column34: 0
12 | 72844 | 1 | 72844-1 | 8 | 2019-02-07 | Machine Shop Started | 0 | 2019-02-05 | 13 |  |  |  | 1 | 7 |  |  |  | YES | 8 | 3104 | 388 | 3104 |  |  | Column2: 0; Column25: #REF!; Column29: 2289.45; Column30: 763.15; Column31: 2289.45; Column34: 0
18 | 77693 | 1 | 77693-1 | 13 | 2019-02-05 | Wiring Started | 3 | 2019-02-05 | 18 |  |  |  | 3 | 7 |  |  |  | YES | 10 | 3890.77 | 299.29 | 2992.9 |  |  | Column2: 0; Column25: #REF!; Column29: 91575.6; Column30: 455.6; Column31: 28247.2; Column34: 0
1 | 64752 | 24 | 64752-24 | 4 | 2019-02-01 | Wiring Started | 0 | 2019-02-05 | 2 | [5 empty] | 4 |  |  | NO | 4 | 1260 | 315 | 1260 |  |  | Column2: 0; Column25: #REF!; Column29: 14950; Column30: 1495; Column31: 14950; Column34: 0
4 | 78889 | 3 | 78889-3 | 7 | 2019-02-08 | Machine Shop Finished | 6 | 2019-02-05 | 4 |  |  |  |  | 1 |  |  |  | YES | 1 | 1360 | 194.2857 | 194.2857 |  |  | Column2: 0; Column25: #REF!; Column29: 12560; Column30: 1570; Column31: 12560; Column34: 0
4 | 78889 | 2 | 78889-2 | 2 | 2019-02-08 | Machine Shop Finished | 0 | 2019-02-05 | 4 |  |  |  |  | 2 |  |  |  | YES | 2 | 1440 | 720 | 1440 |  |  | Column2: 0; Column25: #REF!; Column29: 56000; Column30: 500; Column31: 500; Column34: 0
7 | 76823 | 12 | 76823-12 | 24 | 2019-02-04 | Wiring Started | 12 | 2019-02-05 | 8 | [5 empty] | 12 |  |  | NO | 12 | 4920 | 205 | 2460 |  |  | Column2: 0
7 | 76823 | 12 | 76823-12 | 24 | 2019-02-04 | Wiring Started | 21 | 2019-02-05 | 9 | [5 empty] | 3 |  |  | NO | 3 | 4920 | 205 | 615 |  |  | Column2: 0
7 | 73829 | 2 | 73829-2 | 27 | 2019-02-06 | Wiring Started | 22 | 2019-02-05 | 9 | [5 empty] | 5 |  |  | YES | 5 | 23279.526 | 862.2047 | 4311.0233 |  |  | Column2: 0
10 | 78812 | 2 | 78812-2 | 3 | 2019-02-06 | Machine Shop Started | 0 | 2019-02-05 | 11 | [5 empty] | 3 |  |  | YES | 3 | 765 | 255 | 765 |  |  | Column2: 0
10 | 78861 | 1 | 78861-1 | 8 | 2019-02-06 | Machine Shop Started | 0 | 2019-02-05 | 11 | [5 empty] | 8 |  |  | YES | 8 | 1344 | 168 | 1344 |  |  | Column2: 0
10 | 78861 | 2 | 78861-2 | 5 | 2019-02-06 | Machine Shop Started | 3 | 2019-02-05 | 11 | [5 empty] | 2 |  |  | YES | 2 | 840 | 168 | 336 |  |  | Column2: 0
12 | 70426 | 1 | 70426-1 | 3 | 2019-02-04 | Machine Shop Finished | 2 | 2019-02-05 | 12 | [5 empty] | 1 |  |  | NO | 1 | 352 | 117.3333 | 117.3333 |  |  | Column2: 0
12 | 79024 | 1 | 79024-1 | 1 | 2019-02-05 | Machine Shop Finished | 0 | 2019-02-05 | 12 | [5 empty] | 1 |  |  | YES | 1 | 396 | 396 | 396 |  |  | Column2: 0
12 | 78902 | 1 | 78902-1 | 2 | 2019-02-05 | Machine Shop Finished | 0 | 2019-02-05 | 12 | [5 empty] | 2 |  |  | YES | 2 | 816 | 408 | 816 |  |  | Column2: 0
12 | 78812 | 4 | 78812-4 | 5 | 2019-02-06 | Machine Shop Finished | 0 | 2019-02-05 | 13 | [5 empty] | 5 |  |  | YES | 5 | 1000 | 200 | 1000 |  |  | Column2: 0
18 | 77693 | 5 | 77693-5 | 7 | 2019-02-05 | Wiring Started | 0 | 2019-02-05 | 18 | [5 empty] | 7 |  |  | YES | 7 | 2933 | 419 | 2933 |  |  | Column2: 0

## Order-dates
Check ORDER | Date
75467-2 | 2018-12-28
75467-4 | 2018-12-28
75467-6 | 2018-12-28
74900-1 | 2018-12-28
75808-1 | 2018-12-28
75808-2 | 2018-12-28
75808-3 | 2018-12-28
77782-1 | 2018-12-28
75412-1 | 2018-12-27
77858-1 | 2018-12-28
74900-8 | 2018-12-28
74900-9 | 2018-12-28
74900-10 | 2018-12-28
74900-11 | 2018-12-28
74900-12 | 2018-12-28
74900-14 | 2018-12-28
74900-15 | 2018-12-28
74900-17 | 2018-12-28
74900-18 | 2018-12-28
74900-19 | 2018-12-28
75664-11 | 2018-12-27
73976-3 | 2019-01-02
73976-4 | 2019-01-02
73976-5 | 2019-01-02
73976-6 | 2019-01-02
73976-9 | 2019-01-02
73976-10 | 2019-01-02
73976-11 | 2019-01-02
73976-12 | 2019-01-02
73976-15 | 2019-01-02
73976-16 | 2019-01-02
77858-2 | 2018-12-28
75827-2 | 2018-12-28
74003-1 | 2018-12-27
74003-2 | 2018-12-27
74003-3 | 2018-12-27
74003-4 | 2018-12-27
74003-5 | 2018-12-27
74003-6 | 2018-12-27
74003-7 | 2018-12-27
75827-6 | 2018-12-28
74276-1 | 2018-12-28
74276-2 | 2018-12-28
77075-1 | 2018-12-27
76580-1 | 2018-12-27
76580-2 | 2018-12-27
76580-3 | 2018-12-27
76580-4 | 2018-12-27
76580-9 | 2018-12-27
76463-1 | 2018-12-28
76463-2 | 2018-12-28
77067-1 | 2018-12-28
70947-1 | 2018-12-27
70947-2 | 2018-12-27
70947-3 | 2018-12-27
70947-4 | 2018-12-27
75452-1 | 2018-12-27
75452-2 | 2018-12-27
75452-3 | 2018-12-27
75452-4 | 2018-12-27
75452-14 | 2018-12-27
75452-16 | 2018-12-27
75452-17 | 2018-12-27
75452-18 | 2018-12-27
75452-19 | 2018-12-27
75452-20 | 2018-12-27
75452-21 | 2018-12-27
75452-22 | 2018-12-27
75452-23 | 2018-12-27
75452-24 | 2018-12-27
75452-25 | 2018-12-27
75452-26 | 2018-12-27
75452-28 | 2018-12-27
75452-29 | 2018-12-27
75452-30 | 2018-12-27
75452-31 | 2018-12-27
75452-32 | 2018-12-27
75452-33 | 2018-12-27
75452-34 | 2018-12-27
75452-35 | 2018-12-27
75452-36 | 2018-12-27
75452-37 | 2018-12-27
75452-39 | 2018-12-27
75452-41 | 2018-12-27
75452-42 | 2018-12-27
75452-43 | 2018-12-27
75452-44 | 2018-12-27
75452-48 | 2018-12-27
75452-50 | 2018-12-27
77618-1 | 2018-12-27
77618-2 | 2018-12-27
77618-3 | 2018-12-27
76997-1 | 2018-12-28
76997-2 | 2018-12-28
77075-2 | 2018-12-27
75868-1 | 2018-12-28
72351-80 | 2018-12-28
72351-83 | 2018-12-28
72351-84 | 2018-12-28
72351-85 | 2018-12-28
72351-86 | 2018-12-28
72351-87 | 2018-12-28
72351-92 | 2018-12-28
72351-93 | 2018-12-28
78011-1 | 2018-12-28
78011-2 | 2018-12-28
78011-3 | 2018-12-28
78011-4 | 2018-12-28
78011-5 | 2018-12-28
78011-6 | 2018-12-28
78011-7 | 2018-12-28
78011-8 | 2018-12-28
78011-9 | 2018-12-28
78011-10 | 2018-12-28
78011-11 | 2018-12-28
78011-12 | 2018-12-28
78011-13 | 2018-12-28
78011-14 | 2018-12-28
78011-15 | 2018-12-28
78011-16 | 2018-12-28
78011-17 | 2018-12-28
78011-18 | 2018-12-28
78011-19 | 2018-12-28
78011-20 | 2018-12-28
78011-21 | 2018-12-28
78011-22 | 2018-12-28
78011-23 | 2018-12-28
76783-1 | 2018-12-28
77132-1 | 2018-12-31
76783-2 | 2018-12-28
77342-1 | 2018-12-28
77158-1 | 2018-12-28
77539-1 | 2018-12-21
75203-9 | 2018-12-28
77579-1 | 2018-12-27
76828-1 | 2018-12-28
77633-1 | 2018-12-28
77337-1 | 2018-12-28
75718-1 | 2018-12-28
75718-3 | 2018-12-28
75718-4 | 2018-12-28
75718-6 | 2018-12-28
75718-7 | 2018-12-28
75718-8 | 2018-12-28
75718-9 | 2018-12-28
75718-10 | 2018-12-28
75718-11 | 2018-12-28
75718-12 | 2018-12-28
75718-13 | 2018-12-28
75718-14 | 2018-12-28
75718-15 | 2018-12-28
75718-16 | 2018-12-28
75718-17 | 2018-12-28
75718-18 | 2018-12-28
75718-19 | 2018-12-28
75718-20 | 2018-12-28
75718-21 | 2018-12-28
75718-22 | 2018-12-28
75718-23 | 2018-12-28
75718-24 | 2018-12-28
75718-25 | 2018-12-28
75718-26 | 2018-12-28
75718-27 | 2018-12-28
75718-28 | 2018-12-28
75718-29 | 2018-12-28
75718-30 | 2018-12-28
75718-31 | 2018-12-28
75718-32 | 2018-12-28
75718-33 | 2018-12-28
75718-34 | 2018-12-28
75718-35 | 2018-12-28
75718-36 | 2018-12-28
75718-37 | 2018-12-28
75718-38 | 2018-12-28
75718-39 | 2018-12-28
75718-40 | 2018-12-28
75718-41 | 2018-12-28
75718-42 | 2018-12-28
75718-43 | 2018-12-28
75718-44 | 2018-12-28
75718-45 | 2018-12-28
75718-46 | 2018-12-28
75718-47 | 2018-12-28
75718-48 | 2018-12-28
75718-49 | 2018-12-28
75718-50 | 2018-12-28
75718-51 | 2018-12-28
75718-52 | 2018-12-28
75718-53 | 2018-12-28
75718-54 | 2018-12-28
75718-55 | 2018-12-28
75718-56 | 2018-12-28
75718-57 | 2018-12-28
75718-58 | 2018-12-28
75718-59 | 2018-12-28
75718-60 | 2018-12-28
75718-61 | 2018-12-28
75718-62 | 2018-12-28
75718-63 | 2018-12-28
75718-64 | 2018-12-28
75718-65 | 2018-12-28
75718-66 | 2018-12-28
75718-67 | 2018-12-28
75718-68 | 2018-12-28
75718-69 | 2018-12-28
75718-70 | 2018-12-28
75718-71 | 2018-12-28
75718-72 | 2018-12-28
75718-73 | 2018-12-28
75718-74 | 2018-12-28
75718-75 | 2018-12-28
75718-76 | 2018-12-28
75718-77 | 2018-12-28
75718-78 | 2018-12-28
75718-79 | 2018-12-28
75718-80 | 2018-12-28
75718-81 | 2018-12-28
75718-82 | 2018-12-28
75718-83 | 2018-12-28
75718-84 | 2018-12-28
75718-85 | 2018-12-28
75718-86 | 2018-12-28
75718-87 | 2018-12-28
75718-88 | 2018-12-28
76116-3 | 2018-12-28
76116-4 | 2018-12-28
76386-1 | 2018-12-27
76991-1 | 2018-12-28
77337-2 | 2018-12-28
77337-3 | 2018-12-28
75808-4 | 2018-12-28
75904-1 | 2018-12-28
77345-1 | 2018-12-28
76484-1 | 2018-12-28
77747-1 | 2018-12-28
77327-1 | 2018-12-31
77327-2 | 2018-12-31
77001-1 | 2018-12-28
77034-1 | 2018-12-28
77034-2 | 2018-12-28
77034-3 | 2018-12-28
68574-5 | 2018-12-28
68574-6 | 2018-12-28
68574-7 | 2018-12-28
76315-1 | 2018-12-28
76315-2 | 2018-12-28
76315-3 | 2018-12-28
76315-4 | 2018-12-28
75442-2 | 2018-12-27
75442-3 | 2018-12-27
75844-1 | 2018-12-27
75844-2 | 2018-12-27
75844-3 | 2018-12-27
75844-4 | 2018-12-27
70411-34 | 2018-12-27
75475-1 | 2019-01-02
75475-2 | 2019-01-02
75475-3 | 2019-01-02
75475-4 | 2019-01-02
75475-11 | 2019-01-02
75475-12 | 2019-01-02
75475-13 | 2019-01-02
75475-14 | 2019-01-02
75475-15 | 2019-01-02
75475-16 | 2019-01-02
75475-17 | 2019-01-02
75475-18 | 2019-01-02
75475-19 | 2019-01-02
75475-24 | 2019-01-02
75693-1 | 2018-12-28
75693-2 | 2018-12-28
75693-3 | 2018-12-28
75693-10 | 2018-12-28
75693-11 | 2018-12-28
75693-15 | 2018-12-28
75693-16 | 2018-12-28
75745-11 | 2018-12-27
75745-12 | 2018-12-27
75745-14 | 2018-12-27
75745-15 | 2018-12-27
75745-16 | 2018-12-27
75745-17 | 2018-12-27
75745-18 | 2018-12-27
75745-19 | 2018-12-27
75745-20 | 2018-12-27
75745-29 | 2018-12-27
76200-1 | 2018-12-28
76200-2 | 2018-12-28
76200-3 | 2018-12-28
76200-4 | 2018-12-28
76200-5 | 2018-12-28
76200-6 | 2018-12-28
76200-7 | 2018-12-28
76200-8 | 2018-12-28
76200-9 | 2018-12-28
76200-10 | 2018-12-28
76200-11 | 2018-12-28
76200-12 | 2018-12-28
76200-13 | 2018-12-28
76210-1 | 2018-12-27
75761-15 | 2018-12-27
74380-1 | 2018-12-27
74380-2 | 2018-12-27
74380-3 | 2018-12-27
74380-4 | 2018-12-27
74380-6 | 2018-12-27
74380-7 | 2018-12-27
74380-8 | 2018-12-27
74380-9 | 2018-12-27
74380-10 | 2018-12-27
74380-11 | 2018-12-27
74380-12 | 2018-12-27
74380-13 | 2018-12-27
74380-14 | 2018-12-27
74380-15 | 2018-12-27
74380-16 | 2018-12-27
74380-17 | 2018-12-27
75967-1 | 2018-12-28
77008-1 | 2018-12-28
73689-7 | lens after 02/01
73689-8 | lens after 02/01
73689-9 | lens after 02/01
73689-10 | lens after 02/01
76338-7 | 2019-01-02
76338-8 | 2019-01-02
76338-9 | 2019-01-02
76338-10 | 2019-01-02
76338-36 | 2019-01-02
76338-37 | 2019-01-02
76338-40 | 2019-01-02
76338-41 | 2019-01-02
76338-42 | 2019-01-02
76338-43 | 2019-01-02
74864-18 | 2018-12-28
74864-19 | 2018-12-28
77467-1 | 2018-12-27
73092-1 | 2018-12-28
73092-2 | 2018-12-28
73092-3 | 2018-12-28
72160-1 | 2018-12-28
72160-2 | 2018-12-28
75918-1 | 2018-12-28
75918-2 | 2018-12-28
75918-3 | 2018-12-28
75918-4 | 2018-12-28
75918-5 | 2018-12-28
76875-1 | 2018-12-28
76875-2 | 2018-12-28
76875-3 | 2018-12-28
76875-4 | 2018-12-28
76875-5 | 2018-12-28
76875-6 | 2018-12-28
76875-7 | 2018-12-28
76875-8 | 2018-12-28
76875-9 | 2018-12-28
76875-10 | 2018-12-28
76875-11 | 2018-12-28
76875-12 | 2018-12-28
76875-13 | 2018-12-28
71483-3 | 2018-12-28
75674-1 | 2018-12-27
75674-2 | 2018-12-27
75674-4 | 2018-12-27
75674-5 | 2018-12-27
75674-6 | 2018-12-27
75674-7 | 2018-12-27
75674-8 | 2018-12-27
75674-9 | 2018-12-27
75674-10 | 2018-12-27
77247-1 | 2018-12-28
76912-1 | 2018-12-27
76912-2 | 2018-12-27
76912-3 | 2018-12-27
76912-4 | 2018-12-27
76912-5 | 2018-12-27
76912-6 | 2018-12-27
76912-7 | 2018-12-27
76912-8 | 2018-12-27
76912-9 | 2018-12-27
76912-10 | 2018-12-27
76912-11 | 2018-12-27
76912-12 | 2018-12-27
76912-13 | 2018-12-27
76912-14 | 2018-12-27
76912-15 | 2018-12-27
76912-16 | 2018-12-27
76912-17 | 2018-12-27
76912-18 | 2018-12-28
76912-19 | 2018-12-28
76912-20 | 2018-12-28
76912-21 | 2018-12-28
76912-22 | 2018-12-28
76912-23 | 2018-12-28
76912-24 | 2018-12-28
76912-25 | 2018-12-28
76912-26 | 2018-12-28
76912-27 | 2018-12-28
76912-28 | 2018-12-28
76912-29 | 2018-12-28
76912-30 | 2018-12-28
76912-31 | 2018-12-28
76912-32 | 2018-12-28
76912-33 | 2018-12-28
76912-34 | 2018-12-28
76912-35 | 2018-12-28
76789-1 | 2018-12-27
76789-2 | 2018-12-27
76789-3 | 2018-12-27
76789-4 | 2018-12-27

## Order Calculation
Scheduled Ship Date | Order | Line | Status | Sum of Rep. Count
2018-11-29 | 75467 |  |  | 1
11/29/2018 Total |  |  |  | 1
2019-01-08 | 74294 | 4 | Machine Shop Finished | 1
| 74294 Total |  |  | 1
1/8/2019 Total |  |  |  | 1
2019-01-10 | 77249 | 2 | Machine Shop Finished | 0
| 77249 Total |  |  | 0
1/10/2019 Total |  |  |  | 0
2019-01-16 | 75398 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
|  | 3 | Wiring Started | 0
|  | 4 | Packaging Finished | 1
|  | 5 | Packaging Finished | 0
| 75398 Total |  |  | 2
| 75692 | 11 | Wiring Started | 1
| 75692 Total |  |  | 1
1/16/2019 Total |  |  |  | 3
2019-01-17 | 76191 | 1 | Machine Shop Started | 1
| 76191 Total |  |  | 1
| 77011 | 1 | Given to Shipping | 1
| 77011 Total |  |  | 1
1/17/2019 Total |  |  |  | 2
2019-01-18 | 77249 | 1 | Machine Shop Finished | 1
|  | 4 | Machine Shop Finished | 0
| 77249 Total |  |  | 1
1/18/2019 Total |  |  |  | 1
2019-01-22 | 77945 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
| 77945 Total |  |  | 1
| 77947 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 15 | Machine Shop Finished | 0
| 77947 Total |  |  | 1
1/22/2019 Total |  |  |  | 2
2019-01-24 | 77249 | 3 | Machine Shop Finished | 0
|  | 10 | Machine Shop Started | 1
|  | 11 | Machine Shop Finished | 0
|  | 15 | Machine Shop Finished | 0
| 77249 Total |  |  | 1
1/24/2019 Total |  |  |  | 1
2019-01-28 | 75745 | 13 | Wiring Started | 1
| 75745 Total |  |  | 1
| 76528 | 1 | Machine Shop Finished | 1
| 76528 Total |  |  | 1
1/28/2019 Total |  |  |  | 2
2019-01-29 | 72049 |  |  | 1
| 74968 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
| 74968 Total |  |  | 1
| 77393 | 1 | Machine Shop Finished | 1
| 77393 Total |  |  | 1
1/29/2019 Total |  |  |  | 3
2019-01-30 | 76192 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
| 76192 Total |  |  | 1
1/30/2019 Total |  |  |  | 1
2019-02-01 | 70634 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 70634 Total |  |  | 1
| 79375 | 1 | Wiring Started | 1
| 79375 Total |  |  | 1
| 79170 | 1 | Order UnShipped | 1
| 79170 Total |  |  | 1
| 78150 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
| 78150 Total |  |  | 1
| 78593 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
|  | 3 | Wiring Started | 1
|  | 4 | Wiring Started | 0
| 78593 Total |  |  | 2
| 79010 | 1 | Machine Shop Started | 1
| 79010 Total |  |  | 1
| 78645 | 1 | Packaging Finished | 1
|  | 2 | Packaging Finished | 0
| 78645 Total |  |  | 1
| 78661 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
| 78661 Total |  |  | 1
| 75811 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
|  | 3 | Wiring Started | 0
| 75811 Total |  |  | 1
| 78388 | 1 | Machine Shop Finished | 1
| 78388 Total |  |  | 1
| 77440 | 1 | Given to Shipping | 1
| 77440 Total |  |  | 1
| 75212 | 30 | Given to Shipping | 1
| 75212 Total |  |  | 1
| 79284 | 1 | Packaging Finished | 1
| 79284 Total |  |  | 1
| 79011 | 2 | Wiring Started | 1
|  | 3 | Wiring Started | 0
| 79011 Total |  |  | 1
2/1/2019 Total |  |  |  | 15
2019-02-06 | 59584 | 10 | Machine Shop Started | 1
|  | 12 | Machine Shop Started | 0
|  | 66 | Machine Shop Started | 0
|  | 67 | Machine Shop Started | 0
| 59584 Total |  |  | 1
| 75103 | 3 | Machine Shop Finished | 1
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
|  | 7 | Machine Shop Finished | 0
|  | 10 | Machine Shop Finished | 0
|  | 11 | Machine Shop Finished | 0
|  | 12 | Machine Shop Finished | 0
|  | 13 | Machine Shop Finished | 0
|  | 14 | Machine Shop Finished | 0
|  | 15 | Machine Shop Finished | 0
| 75103 Total |  |  | 1
| 76884 | 1 | Wiring Started | 1
| 76884 Total |  |  | 1
| 77560 | 1 | Machine Shop Finished | 1
| 77560 Total |  |  | 1
| 78927 | 1 | Wiring Started | 1
|  | 2 | Machine Shop Started | 1
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Finished | 1
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
| 78927 Total |  |  | 3
| 78306 | 1 | Machine Shop Started | 1
| 78306 Total |  |  | 1
| 78511 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78511 Total |  |  | 1
| 76762 | 4 | Machine Shop Started | 1
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
| 76762 Total |  |  | 1
| 79240 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 79240 Total |  |  | 1
| 78710 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Finished | 1
|  | 3 | Machine Shop Started | 0
| 78710 Total |  |  | 2
| 78812 | 1 | Packaging Finished | 1
|  | 2 | Packaging Finished | 0
|  | 3 | Packaging Finished | 0
|  | 4 | Wiring Started | 1
|  | 5 | Wiring Started | 0
|  | 6 | Wiring Started | 0
|  | 7 | Wiring Started | 0
| 78812 Total |  |  | 2
| 79502 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 79502 Total |  |  | 1
| 78491 | 1 | Machine Shop Finished | 1
| 78491 Total |  |  | 1
| 78711 | 1 | Machine Shop Finished | 1
| 78711 Total |  |  | 1
| 77207 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
|  | 7 | Machine Shop Finished | 0
|  | 8 | Machine Shop Finished | 0
|  | 9 | Machine Shop Finished | 0
|  | 10 | Machine Shop Finished | 0
|  | 11 | Machine Shop Finished | 0
|  | 12 | Machine Shop Finished | 0
|  | 13 | Machine Shop Finished | 0
|  | 14 | Machine Shop Started | 1
|  | 15 | Machine Shop Started | 0
|  | 16 | Machine Shop Started | 0
|  | 17 | Machine Shop Started | 0
|  | 18 | Machine Shop Started | 0
|  | 19 | Machine Shop Started | 0
|  | 20 | Machine Shop Started | 0
| 77207 Total |  |  | 2
| 78854 | 1 | Machine Shop Finished | 1
| 78854 Total |  |  | 1
| 78643 | 5 | Machine Shop Finished | 1
| 78643 Total |  |  | 1
| 78667 | 1 | Machine Shop Finished | 1
| 78667 Total |  |  | 1
| 73829 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
|  | 3 | Wiring Started | 0
|  | 4 | Wiring Started | 0
|  | 5 | Wiring Started | 0
|  | 6 | Wiring Started | 0
|  | 7 | Wiring Started | 0
|  | 8 | Wiring Started | 0
| 73829 Total |  |  | 1
| 77060 | 2 | Machine Shop Started | 1
| 77060 Total |  |  | 1
| 77378 | 1 | Machine Shop Started | 1
| 77378 Total |  |  | 1
| 78861 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
| 78861 Total |  |  | 1
| 78731 | 1 | Packaging Finished | 1
| 78731 Total |  |  | 1
| 78170 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78170 Total |  |  | 1
2/6/2019 Total |  |  |  | 29
2019-02-07 | 72906 | 2 | Machine Shop Finished | 1
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
|  | 7 | Machine Shop Finished | 0
|  | 8 | Machine Shop Finished | 0
| 72906 Total |  |  | 1
| 79106 | 1 | Packaging Finished | 1
|  | 2 | Packaging Finished | 0
| 79106 Total |  |  | 1
| 79342 | 1 | Scheduled/Released | 1
| 79342 Total |  |  | 1
| 73251 | 28 | Machine Shop Started | 1
|  | 29 | Machine Shop Started | 0
|  | 30 | Machine Shop Started | 0
|  | 31 | Machine Shop Started | 0
|  | 32 | Machine Shop Started | 0
|  | 33 | Machine Shop Started | 0
|  | 36 | Machine Shop Started | 0
|  | 37 | Machine Shop Started | 0
|  | 41 | Machine Shop Started | 0
|  | 42 | Machine Shop Started | 0
|  | 43 | Machine Shop Started | 0
| 73251 Total |  |  | 1
| 78614 | 1 | Machine Shop Started | 1
| 78614 Total |  |  | 1
| 78720 | 1 | Machine Shop Started | 1
| 78720 Total |  |  | 1
| 78933 | 1 | Machine Shop Started | 1
| 78933 Total |  |  | 1
| 78529 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 78529 Total |  |  | 1
| 78545 | 1 | Machine Shop Started | 1
| 78545 Total |  |  | 1
| 72221 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Started | 1
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 72221 Total |  |  | 2
| 78706 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78706 Total |  |  | 1
| 78949 | 1 | Machine Shop Started | 1
| 78949 Total |  |  | 1
| 79189 | 1 | Machine Shop Started | 1
| 79189 Total |  |  | 1
| 78050 | 1 | Machine Shop Finished | 1
| 78050 Total |  |  | 1
| 79322 | 1 | Machine Shop Started | 1
| 79322 Total |  |  | 1
| 77187 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 77187 Total |  |  | 1
| 72844 | 1 | Given to Shipping | 1
| 72844 Total |  |  | 1
| 78616 | 1 | Machine Shop Started | 1
| 78616 Total |  |  | 1
| 79347 | 1 | Machine Shop Started | 1
| 79347 Total |  |  | 1
| 75954 | 27 | Machine Shop Started | 1
|  | 28 | Machine Shop Started | 0
|  | 29 | Machine Shop Started | 0
|  | 41 | Machine Shop Started | 0
|  | 42 | Machine Shop Started | 0
| 75954 Total |  |  | 1
| 77938 | 1 | Machine Shop Started | 1
| 77938 Total |  |  | 1
| 78778 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 1
| 78778 Total |  |  | 2
| 78538 | 4 | Machine Shop Started | 1
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
| 78538 Total |  |  | 1
| 78820 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Finished | 1
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
| 78820 Total |  |  | 2
| 79311 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 79311 Total |  |  | 1
| 78729 | 1 | Machine Shop Finished | 1
| 78729 Total |  |  | 1
| 79220 | 1 | Machine Shop Started | 1
| 79220 Total |  |  | 1
| 79133 | 1 | Machine Shop Finished | 1
| 79133 Total |  |  | 1
| 77615 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Started | 1
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Finished | 0
|  | 12 | Machine Shop Finished | 0
|  | 13 | Machine Shop Started | 0
| 77615 Total |  |  | 2
| 78707 | 1 | Machine Shop Started | 1
| 78707 Total |  |  | 1
| 78640 | 1 | Machine Shop Started | 1
|  | 3 | Machine Shop Started | 0
| 78640 Total |  |  | 1
| 78715 | 1 | Machine Shop Finished | 1
| 78715 Total |  |  | 1
| 74695 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Finished | 1
| 74695 Total |  |  | 2
| 79411 | 1 | Machine Shop Started | 1
| 79411 Total |  |  | 1
| 78994 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78994 Total |  |  | 1
| 78515 | 1 | Given to Shipping | 1
| 78515 Total |  |  | 1
| 76468 | 1 | Order UnShipped | 1
|  | 2 | Order UnShipped | 0
|  | 3 | Order UnShipped | 0
|  | 4 | Order UnShipped | 0
|  | 5 | Order UnShipped | 0
|  | 6 | Order UnShipped | 0
| 76468 Total |  |  | 1
| 79017 | 1 | Machine Shop Finished | 1
| 79017 Total |  |  | 1
| 77765 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 22 | Machine Shop Started | 0
| 77765 Total |  |  | 1
| 78930 | 1 | Machine Shop Started | 1
| 78930 Total |  |  | 1
| 78098 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Finished | 1
|  | 7 | Machine Shop Finished | 0
|  | 8 | Machine Shop Finished | 0
|  | 9 | Machine Shop Finished | 0
|  | 10 | Machine Shop Finished | 0
| 78098 Total |  |  | 2
| 78866 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78866 Total |  |  | 1
2/7/2019 Total |  |  |  | 48
2019-02-08 | 70411 |  |  | 1
| 76028 | 32 | Machine Shop Started | 1
|  | 44 | Scheduled/Released | 1
| 76028 Total |  |  | 2
| 77211 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 77211 Total |  |  | 1
| 78986 | 1 | Machine Shop Finished | 1
| 78986 Total |  |  | 1
| 78822 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 78822 Total |  |  | 1
| 76704 | 1 | Machine Shop Started | 1
| 76704 Total |  |  | 1
| 75728 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
|  | 9 | Machine Shop Started | 1
| 75728 Total |  |  | 2
| 78789 | 1 | Machine Shop Finished | 1
| 78789 Total |  |  | 1
| 77630 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
| 77630 Total |  |  | 1
| 76076 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 76076 Total |  |  | 1
| 78889 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 78889 Total |  |  | 1
| 79076 | 1 | Machine Shop Finished | 1
| 79076 Total |  |  | 1
| 78569 | 1 | Machine Shop Finished | 1
| 78569 Total |  |  | 1
| 79186 | 1 | Machine Shop Started | 1
| 79186 Total |  |  | 1
| 76592 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 19 | Machine Shop Started | 0
|  | 22 | Machine Shop Started | 0
| 76592 Total |  |  | 1
| 78401 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Started | 1
| 78401 Total |  |  | 2
| 77607 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Started | 1
|  | 6 | Machine Shop Finished | 0
| 77607 Total |  |  | 2
| 78517 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78517 Total |  |  | 1
| 78964 | 1 | Machine Shop Finished | 1
| 78964 Total |  |  | 1
| 79048 | 1 | Machine Shop Started | 1
| 79048 Total |  |  | 1
| 78047 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
| 78047 Total |  |  | 1
| 79307 | 5 | Machine Shop Started | 1
| 79307 Total |  |  | 1
| 77142 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 77142 Total |  |  | 1
| 78759 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78759 Total |  |  | 1
| 78225 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
|  | 7 | Machine Shop Finished | 0
|  | 8 | Machine Shop Finished | 0
|  | 9 | Machine Shop Started | 1
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
| 78225 Total |  |  | 2
| 78226 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Started | 1
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
| 78226 Total |  |  | 2
| 78171 | 1 | Machine Shop Finished | 1
| 78171 Total |  |  | 1
| 78680 | 1 | Machine Shop Started | 1
| 78680 Total |  |  | 1
| 78506 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
| 78506 Total |  |  | 1
| 74964 | 17 | Machine Shop Started | 1
|  | 18 | Machine Shop Started | 0
|  | 19 | Machine Shop Started | 0
|  | 20 | Machine Shop Started | 0
|  | 21 | Machine Shop Started | 0
|  | 22 | Machine Shop Started | 0
| 74964 Total |  |  | 1
| 78448 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
|  | 16 | Machine Shop Started | 0
|  | 17 | Machine Shop Started | 0
|  | 18 | Machine Shop Started | 0
|  | 19 | Machine Shop Started | 0
|  | 20 | Machine Shop Started | 0
| 78448 Total |  |  | 1
| 78525 | 1 | Machine Shop Started | 1
| 78525 Total |  |  | 1
| 79168 | 1 | Machine Shop Started | 1
| 79168 Total |  |  | 1
| 78624 | 4 | Scheduled/Released | 1
| 78624 Total |  |  | 1
2/8/2019 Total |  |  |  | 40
2019-02-11 | 67150 | 41 | Machine Shop Finished | 1
|  | 42 | Machine Shop Finished | 0
|  | 43 | Machine Shop Finished | 0
|  | 44 | Machine Shop Finished | 0
|  | 45 | Machine Shop Finished | 0
|  | 46 | Machine Shop Finished | 0
|  | 47 | Machine Shop Finished | 0
|  | 48 | Machine Shop Finished | 0
|  | 49 | Machine Shop Finished | 0
|  | 50 | Machine Shop Finished | 0
|  | 51 | Machine Shop Finished | 0
|  | 52 | Machine Shop Finished | 0
|  | 53 | Machine Shop Finished | 0
|  | 55 | Machine Shop Finished | 0
|  | 56 | Machine Shop Finished | 0
|  | 57 | Machine Shop Finished | 0
|  | 58 | Machine Shop Finished | 0
|  | 59 | Machine Shop Finished | 0
|  | 60 | Machine Shop Finished | 0
|  | 61 | Machine Shop Finished | 0
| 67150 Total |  |  | 1
| 75462 | 14 | Machine Shop Started | 0
| 75462 Total |  |  | 0
| 75745 | 5 | Machine Shop Started | 1
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 21 | Machine Shop Started | 0
| 75745 Total |  |  | 1
| 75746 | 5 | Machine Shop Started | 1
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 22 | Machine Shop Started | 0
|  | 24 | Machine Shop Started | 0
|  | 25 | Machine Shop Started | 0
|  | 26 | Machine Shop Started | 0
|  | 29 | Machine Shop Started | 0
|  | 31 | Machine Shop Started | 0
|  | 34 | Machine Shop Started | 0
| 75746 Total |  |  | 1
| 75966 | 8 | Machine Shop Started | 1
| 75966 Total |  |  | 1
| 77926 | 1 | Scheduled/Released | 1
| 77926 Total |  |  | 1
| 78875 | 1 | Scheduled/Released | 1
| 78875 Total |  |  | 1
| 67875 | 1 | Machine Shop Started | 1
| 67875 Total |  |  | 1
| 79098 | 1 | Machine Shop Started | 1
| 79098 Total |  |  | 1
| 79285 | 1 | Machine Shop Started | 1
| 79285 Total |  |  | 1
| 79164 | 1 | Machine Shop Started | 1
| 79164 Total |  |  | 1
| 70875 | 1 | Scheduled/Released | 1
| 70875 Total |  |  | 1
| 79124 | 1 | Machine Shop Started | 1
| 79124 Total |  |  | 1
| 78703 | 1 | Machine Shop Started | 1
| 78703 Total |  |  | 1
| 78699 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
| 78699 Total |  |  | 1
| 77910 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 77910 Total |  |  | 1
| 79370 | 1 | Machine Shop Started | 1
| 79370 Total |  |  | 1
| 78110 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
| 78110 Total |  |  | 1
| 78607 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
| 78607 Total |  |  | 1
| 78221 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
|  | 16 | Machine Shop Started | 0
| 78221 Total |  |  | 1
| 77356 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Started | 1
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
|  | 16 | Machine Shop Started | 0
|  | 17 | Machine Shop Started | 0
|  | 18 | Machine Shop Started | 0
|  | 19 | Machine Shop Started | 0
|  | 20 | Machine Shop Started | 0
|  | 21 | Machine Shop Started | 0
|  | 22 | Machine Shop Started | 0
|  | 23 | Machine Shop Started | 0
|  | 25 | Machine Shop Started | 0
| 77356 Total |  |  | 2
| 75090 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Started | 1
|  | 4 | Machine Shop Finished | 0
| 75090 Total |  |  | 2
| 79110 | 1 | Machine Shop Started | 1
| 79110 Total |  |  | 1
| 78106 | 1 | Scheduled/Released | 1
|  | 2 | Scheduled/Released | 0
|  | 3 | Scheduled/Released | 0
|  | 4 | Scheduled/Released | 0
| 78106 Total |  |  | 1
| 79035 | 1 | Machine Shop Started | 1
| 79035 Total |  |  | 1
| 79116 | 1 | Machine Shop Started | 1
| 79116 Total |  |  | 1
2/11/2019 Total |  |  |  | 27
2019-02-05 | 75697 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
| 75697 Total |  |  | 1
| 79198 | 1 | Given to Shipping | 1
| 79198 Total |  |  | 1
| 78651 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
| 78651 Total |  |  | 1
| 64752 | 8 | Wiring Started | 1
|  | 10 | Wiring Started | 0
|  | 11 | Wiring Started | 0
|  | 12 | Wiring Started | 0
|  | 13 | Wiring Started | 0
|  | 14 | Wiring Started | 0
|  | 15 | Wiring Started | 0
|  | 16 | Wiring Started | 0
|  | 17 | Wiring Started | 0
|  | 18 | Wiring Started | 0
|  | 19 | Wiring Started | 0
|  | 20 | Wiring Started | 0
|  | 22 | Wiring Started | 0
|  | 23 | Machine Shop Finished | 1
|  | 24 | Wiring Started | 0
|  | 30 | Wiring Started | 0
|  | 31 | Wiring Started | 0
|  | 37 | Wiring Started | 0
|  | 40 | Wiring Started | 0
| 64752 Total |  |  | 2
| 77741 | 5 | Machine Shop Finished | 1
|  | 6 | Machine Shop Finished | 0
|  | 8 | Machine Shop Started | 1
|  | 9 | Machine Shop Finished | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Finished | 0
|  | 12 | Machine Shop Finished | 0
|  | 13 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
|  | 17 | Machine Shop Finished | 0
|  | 18 | Machine Shop Finished | 0
|  | 19 | Machine Shop Finished | 0
| 77741 Total |  |  | 2
| 78936 | 1 | Wiring Started | 1
| 78936 Total |  |  | 1
| 79024 | 1 | Order UnShipped | 1
| 79024 Total |  |  | 1
| 78637 | 1 | Packaging Finished | 1
|  | 2 | Packaging Finished | 0
| 78637 Total |  |  | 1
| 78931 | 1 | Packaging Finished | 1
| 78931 Total |  |  | 1
| 79418 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
| 79418 Total |  |  | 1
| 73887 | 1 | Packaging Finished | 1
|  | 3 | Packaging Finished | 0
|  | 4 | Packaging Finished | 0
|  | 5 | Packaging Finished | 0
|  | 6 | Packaging Finished | 0
|  | 7 | Packaging Finished | 0
|  | 8 | Packaging Finished | 0
|  | 9 | Packaging Finished | 0
|  | 10 | Packaging Finished | 0
|  | 11 | Packaging Finished | 0
|  | 12 | Packaging Finished | 0
|  | 13 | Packaging Finished | 0
|  | 15 | Machine Shop Finished | 1
|  | 16 | Packaging Finished | 0
|  | 18 | Packaging Finished | 0
|  | 19 | Packaging Finished | 0
|  | 20 | Packaging Finished | 0
|  | 21 | Packaging Finished | 0
|  | 23 | Packaging Finished | 0
|  | 24 | Packaging Finished | 0
|  | 26 | Packaging Finished | 0
| 73887 Total |  |  | 2
| 77908 | 1 | Given to Shipping | 1
|  | 2 | Given to Shipping | 0
|  | 3 | Given to Shipping | 0
|  | 4 | Given to Shipping | 0
|  | 5 | Given to Shipping | 0
|  | 6 | Given to Shipping | 0
|  | 7 | Given to Shipping | 0
|  | 8 | Packaging Finished | 1
|  | 9 | Given to Shipping | 0
|  | 10 | Given to Shipping | 0
| 77908 Total |  |  | 2
| 75392 | 1 | Machine Shop Finished | 1
| 75392 Total |  |  | 1
| 79043 | 1 | Packaging Finished | 1
| 79043 Total |  |  | 1
| 78744 | 1 | Machine Shop Finished | 1
| 78744 Total |  |  | 1
| 79085 | 1 | Given to Shipping | 1
| 79085 Total |  |  | 1
| 78663 | 1 | Machine Shop Started | 1
| 78663 Total |  |  | 1
| 78806 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
|  | 3 | Machine Shop Finished | 0
| 78806 Total |  |  | 1
| 78521 | 1 | Wiring Started | 1
| 78521 Total |  |  | 1
| 79005 | 1 | Packaging Finished | 1
| 79005 Total |  |  | 1
| 77693 | 1 | Wiring Started | 1
|  | 2 | Wiring Started | 0
|  | 3 | Wiring Started | 0
|  | 4 | Wiring Started | 0
|  | 5 | Wiring Started | 0
|  | 6 | Wiring Started | 0
|  | 7 | Wiring Started | 0
|  | 8 | Wiring Started | 0
|  | 9 | Wiring Started | 0
|  | 10 | Wiring Started | 0
|  | 11 | Wiring Started | 0
| 77693 Total |  |  | 1
| 78971 | 1 | Machine Shop Finished | 1
| 78971 Total |  |  | 1
| 79019 | 1 | Machine Shop Started | 1
| 79019 Total |  |  | 1
2/5/2019 Total |  |  |  | 27
2019-02-12 | 76093 | 2 | Machine Shop Finished | 1
| 76093 Total |  |  | 1
| 77180 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
| 77180 Total |  |  | 1
| 78982 | 1 | Machine Shop Started | 1
| 78982 Total |  |  | 1
| 78590 | 1 | Machine Shop Started | 1
| 78590 Total |  |  | 1
| 77375 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
| 77375 Total |  |  | 1
| 78603 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78603 Total |  |  | 1
| 78535 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
| 78535 Total |  |  | 1
| 76939 | 2 | Machine Shop Started | 1
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
| 76939 Total |  |  | 1
| 79014 | 1 | Machine Shop Started | 1
| 79014 Total |  |  | 1
| 79121 | 1 | Scheduled/Released | 1
| 79121 Total |  |  | 1
| 78727 | 1 | Machine Shop Started | 1
| 78727 Total |  |  | 1
| 78279 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78279 Total |  |  | 1
| 74124 | 1 | Given to Shipping | 1
|  | 2 | Given to Shipping | 0
|  | 3 | Given to Shipping | 0
|  | 4 | Given to Shipping | 0
|  | 5 | Given to Shipping | 0
|  | 6 | Given to Shipping | 0
|  | 7 | Given to Shipping | 0
|  | 8 | Given to Shipping | 0
|  | 9 | Given to Shipping | 0
|  | 10 | Given to Shipping | 0
|  | 11 | Given to Shipping | 0
|  | 12 | Given to Shipping | 0
|  | 13 | Given to Shipping | 0
|  | 14 | Given to Shipping | 0
|  | 15 | Given to Shipping | 0
|  | 16 | Given to Shipping | 0
|  | 17 | Given to Shipping | 0
|  | 18 | Given to Shipping | 0
|  | 19 | Given to Shipping | 0
|  | 20 | Given to Shipping | 0
|  | 21 | Given to Shipping | 0
|  | 22 | Given to Shipping | 0
|  | 23 | Given to Shipping | 0
|  | 24 | Given to Shipping | 0
|  | 25 | Given to Shipping | 0
|  | 26 | Given to Shipping | 0
|  | 27 | Given to Shipping | 0
|  | 28 | Given to Shipping | 0
| 74124 Total |  |  | 1
| 78534 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78534 Total |  |  | 1
| 78926 | 1 | Machine Shop Started | 1
| 78926 Total |  |  | 1
| 77868 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 77868 Total |  |  | 1
| 78664 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
| 78664 Total |  |  | 1
| 79049 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 79049 Total |  |  | 1
| 78220 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
| 78220 Total |  |  | 1
| 78469 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78469 Total |  |  | 1
| 78694 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Started | 1
|  | 3 | Machine Shop Finished | 0
| 78694 Total |  |  | 2
| 78798 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78798 Total |  |  | 1
| 78165 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
| 78165 Total |  |  | 1
| 78423 | 8 | Machine Shop Finished | 1
|  | 9 | Machine Shop Finished | 0
|  | 10 | Machine Shop Finished | 0
|  | 11 | Machine Shop Finished | 0
|  | 12 | Machine Shop Finished | 0
|  | 13 | Machine Shop Finished | 0
|  | 14 | Machine Shop Finished | 0
| 78423 Total |  |  | 1
| 78988 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
| 78988 Total |  |  | 1
| 79431 | 1 | Scheduled/Released | 1
| 79431 Total |  |  | 1
| 74964 | 1 | Scheduled/Released | 1
|  | 2 | Scheduled/Released | 0
|  | 3 | Scheduled/Released | 0
|  | 4 | Scheduled/Released | 0
|  | 5 | Scheduled/Released | 0
|  | 6 | Scheduled/Released | 0
|  | 7 | Scheduled/Released | 0
|  | 8 | Scheduled/Released | 0
|  | 9 | Scheduled/Released | 0
|  | 10 | Scheduled/Released | 0
|  | 11 | Scheduled/Released | 0
|  | 12 | Scheduled/Released | 0
|  | 13 | Scheduled/Released | 0
|  | 14 | Scheduled/Released | 0
|  | 15 | Scheduled/Released | 0
|  | 16 | Scheduled/Released | 0
|  | 23 | Scheduled/Released | 0
| 74964 Total |  |  | 1
| 75212 | 38 | Machine Shop Started | 1
| 75212 Total |  |  | 1
| 78825 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78825 Total |  |  | 1
2/12/2019 Total |  |  |  | 30
2019-02-04 | 75693 | 4 | Machine Shop Finished | 1
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
|  | 7 | Machine Shop Finished | 0
|  | 8 | Machine Shop Started | 1
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
|  | 17 | Machine Shop Started | 0
|  | 18 | Machine Shop Started | 0
|  | 19 | Machine Shop Started | 0
|  | 20 | Machine Shop Started | 0
|  | 21 | Machine Shop Started | 0
|  | 22 | Machine Shop Started | 0
|  | 23 | Machine Shop Started | 0
|  | 24 | Machine Shop Started | 0
|  | 25 | Machine Shop Started | 0
|  | 26 | Machine Shop Started | 0
|  | 27 | Machine Shop Started | 0
|  | 28 | Machine Shop Started | 0
|  | 29 | Machine Shop Started | 0
|  | 30 | Machine Shop Started | 0
|  | 31 | Machine Shop Started | 0
|  | 32 | Machine Shop Started | 0
|  | 33 | Machine Shop Started | 0
|  | 36 | Machine Shop Started | 0
|  | 40 | Machine Shop Started | 0
|  | 41 | Machine Shop Started | 0
|  | 42 | Machine Shop Started | 0
|  | 43 | Machine Shop Started | 0
|  | 44 | Machine Shop Finished | 0
|  | 45 | Machine Shop Started | 0
| 75693 Total |  |  | 2
| 76823 | 1 | Machine Shop Finished | 1
|  | 3 | Machine Shop Finished | 0
|  | 4 | Machine Shop Finished | 0
|  | 5 | Machine Shop Finished | 0
|  | 6 | Machine Shop Finished | 0
|  | 7 | Wiring Started | 1
|  | 8 | Wiring Started | 0
|  | 9 | Wiring Started | 0
|  | 10 | Wiring Started | 0
|  | 11 | Wiring Started | 0
|  | 12 | Wiring Started | 0
|  | 13 | Machine Shop Finished | 1
| 76823 Total |  |  | 3
| 78650 | 1 | Given to Shipping | 1
|  | 2 | Given to Shipping | 0
| 78650 Total |  |  | 1
| 77808 | 1 | Order UnShipped | 1
|  | 2 | Order UnShipped | 0
| 77808 Total |  |  | 1
| 75738 | 1 | Given to Shipping | 1
|  | 2 | Given to Shipping | 0
| 75738 Total |  |  | 1
| 78290 | 1 | Machine Shop Finished | 1
| 78290 Total |  |  | 1
| 79320 | 1 | Packaging Finished | 1
| 79320 Total |  |  | 1
| 76817 | 1 | Given to Shipping | 1
|  | 2 | Given to Shipping | 0
|  | 3 | Given to Shipping | 0
|  | 4 | Given to Shipping | 0
|  | 5 | Given to Shipping | 0
|  | 6 | Given to Shipping | 0
|  | 7 | Given to Shipping | 0
|  | 8 | Given to Shipping | 0
|  | 9 | Given to Shipping | 0
|  | 10 | Given to Shipping | 0
|  | 11 | Given to Shipping | 0
|  | 12 | Given to Shipping | 0
|  | 13 | Given to Shipping | 0
|  | 14 | Given to Shipping | 0
| 76817 Total |  |  | 1
| 79034 | 1 | Machine Shop Finished | 1
| 79034 Total |  |  | 1
| 78442 | 1 | Machine Shop Finished | 1
| 78442 Total |  |  | 1
| 77175 | 17 | Machine Shop Finished | 1
|  | 18 | Machine Shop Finished | 0
|  | 19 | Machine Shop Finished | 0
|  | 20 | Machine Shop Finished | 0
|  | 21 | Machine Shop Started | 1
|  | 22 | Machine Shop Started | 0
|  | 23 | Machine Shop Finished | 0
|  | 24 | Machine Shop Finished | 0
|  | 25 | Machine Shop Finished | 0
|  | 26 | Machine Shop Finished | 0
|  | 27 | Machine Shop Finished | 0
|  | 28 | Machine Shop Finished | 0
|  | 29 | Machine Shop Finished | 0
|  | 30 | Machine Shop Finished | 0
|  | 31 | Machine Shop Started | 0
|  | 32 | Machine Shop Started | 0
|  | 33 | Machine Shop Finished | 0
|  | 34 | Machine Shop Finished | 0
|  | 143 | Machine Shop Finished | 0
|  | 144 | Machine Shop Finished | 0
|  | 145 | Machine Shop Finished | 0
| 77175 Total |  |  | 2
| 78864 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Finished | 0
| 78864 Total |  |  | 1
| 78386 | 1 | Given to Shipping | 1
|  | 2 | Given to Shipping | 0
|  | 3 | Given to Shipping | 0
| 78386 Total |  |  | 1
2/4/2019 Total |  |  |  | 17
2019-02-13 | 75462 | 4 | Machine Shop Started | 1
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
| 75462 Total |  |  | 1
| 75475 | 5 | Machine Shop Started | 1
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 27 | Machine Shop Started | 0
|  | 28 | Machine Shop Started | 0
| 75475 Total |  |  | 1
| 75859 | 91 | Scheduled/Released | 1
| 75859 Total |  |  | 1
| 76203 | 28 | Machine Shop Started | 1
|  | 29 | Machine Shop Started | 0
|  | 30 | Machine Shop Started | 0
|  | 31 | Machine Shop Started | 0
|  | 32 | Machine Shop Started | 0
| 76203 Total |  |  | 1
| 78559 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Finished | 1
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Finished | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Finished | 0
| 78559 Total |  |  | 2
| 79135 | 1 | Machine Shop Started | 1
| 79135 Total |  |  | 1
| 79201 | 1 | Scheduled/Released | 1
| 79201 Total |  |  | 1
| 72101 | 1 | Machine Shop Started | 1
| 72101 Total |  |  | 1
| 78943 | 1 | Machine Shop Started | 1
| 78943 Total |  |  | 1
| 78328 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
|  | 12 | Machine Shop Started | 0
|  | 13 | Machine Shop Started | 0
|  | 14 | Machine Shop Started | 0
|  | 15 | Machine Shop Started | 0
|  | 16 | Machine Shop Started | 0
|  | 17 | Machine Shop Started | 0
|  | 18 | Machine Shop Started | 0
| 78328 Total |  |  | 1
| 79157 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
| 79157 Total |  |  | 1
| 79264 | 1 | Machine Shop Finished | 1
| 79264 Total |  |  | 1
| 79234 | 1 | Machine Shop Started | 1
| 79234 Total |  |  | 1
| 77922 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
|  | 8 | Machine Shop Started | 0
|  | 9 | Machine Shop Started | 0
|  | 10 | Machine Shop Started | 0
|  | 11 | Machine Shop Started | 0
| 77922 Total |  |  | 1
| 78968 | 1 | Machine Shop Finished | 1
| 78968 Total |  |  | 1
| 77432 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
|  | 4 | Machine Shop Started | 0
|  | 5 | Machine Shop Started | 0
|  | 6 | Machine Shop Started | 0
|  | 7 | Machine Shop Started | 0
| 77432 Total |  |  | 1
| 78796 | 1 | Machine Shop Started | 1
|  | 2 | Machine Shop Started | 0
|  | 3 | Machine Shop Started | 0
| 78796 Total |  |  | 1
| 79125 | 1 | Machine Shop Started | 1
| 79125 Total |  |  | 1
| 76021 | 1 | Machine Shop Started | 1
| 76021 Total |  |  | 1
| 78588 | 1 | Scheduled/Released | 1
|  | 2 | Scheduled/Released | 0
| 78588 Total |  |  | 1
2/13/2019 Total |  |  |  | 21
2019-01-31 | 76983 | 1 | Machine Shop Finished | 1
| 76983 Total |  |  | 1
| 77608 | 1 | Wiring Started | 1
| 77608 Total |  |  | 1
| 78272 | 1 | Machine Shop Finished | 1
|  | 2 | Machine Shop Started | 1
| 78272 Total |  |  | 2
| 78686 | 1 | Packaging Finished | 1
|  | 2 | Packaging Finished | 0
| 78686 Total |  |  | 1
| 77939 | 3 | Machine Shop Finished | 1
|  | 4 | Machine Shop Finished | 0
| 77939 Total |  |  | 1
1/31/2019 Total |  |  |  | 6
Grand Total |  |  |  | 277

## Section Completed
Row Labels | Sum of Total Section Completed
70411 | 211
4 | 158
37 | 53
71407 | 16
5 | 13
10 | 3
72049 | 32
3 | 12
4 | 4
15 | 12
16 | 4
75664 | 8
12 | 8
75692 | 8
6 | 3
7 | 1
8 | 2
9 | 2
75738 | 18
1 | 9
2 | 9
75745 | 4
13 | 4
78945 | 3
1 | 3
78580 | 116
1 | 3
2 | 2
3 | 1
4 | 1
5 | 2
6 | 2
7 | 1
8 | 1
9 | 1
10 | 2
11 | 1
12 | 1
13 | 2
14 | 1
15 | 2
16 | 1
17 | 1
18 | 2
19 | 2
20 | 1
22 | 2
23 | 2
24 | 2
25 | 3
26 | 1
30 | 1
32 | 2
33 | 1
34 | 1
35 | 1
39 | 1
42 | 1
61 | 1
62 | 2
63 | 2
64 | 1
65 | 1
66 | 1
68 | 1
72 | 2
74 | 1
77 | 2
79 | 2
80 | 1
81 | 1
82 | 1
83 | 1
84 | 1
85 | 3
86 | 1
87 | 2
93 | 1
96 | 3
97 | 1
98 | 1
101 | 1
103 | 1
105 | 2
106 | 1
119 | 1
124 | 1
134 | 1
41 | 2
94 | 3
95 | 2
102 | 1
44 | 1
99 | 2
100 | 2
67 | 1
88 | 1
43 | 2
76 | 1
91 | 1
89 | 2
92 | 1
90 | 1
69 | 1
75 | 1
108 | 1
70 | 1
78266 | 26
1 | 26
77268 | 11
1 | 11
76336 | 1
13 | 1
75966 | 209
1 | 151
8 | 58
78947 | 4
1 | 4
78633 | 1
1 | 1
78824 | 2
1 | 2
77601 | 1
1 | 1
78682 | 6
1 | 6
76087 | 12
1 | 3
2 | 3
3 | 3
4 | 3
73887 | 132
1 | 7
3 | 34
4 | 1
5 | 2
6 | 1
7 | 30
8 | 1
9 | 2
10 | 4
11 | 4
12 | 8
13 | 4
16 | 12
18 | 2
19 | 4
20 | 1
21 | 7
23 | 2
24 | 3
26 | 3
75668 | 2
4 | 1
6 | 1
77632 | 9
1 | 2
2 | 7
76817 | 67
1 | 1
2 | 3
3 | 4
4 | 1
5 | 2
6 | 2
7 | 25
8 | 7
9 | 9
10 | 2
11 | 4
12 | 4
13 | 2
14 | 1
78464 | 1
1 | 1
78622 | 2
1 | 2
77005 | 32
1 | 16
2 | 16
77361 | 2
11 | 2
78377 | 3
1 | 3
78391 | 43
1 | 43
78406 | 2
4 | 1
7 | 1
77908 | 47
1 | 1
2 | 4
3 | 2
4 | 6
5 | 6
6 | 5
7 | 4
8 | 8
9 | 8
10 | 3
78453 | 10
1 | 2
3 | 3
5 | 2
6 | 3
77346 | 1
1 | 1
79121 | 1
1 | 1
78915 | 7
1 | 7
78484 | 4
1 | 4
79128 | 24
1 | 24
77826 | 9
1 | 4
2 | 5
78697 | 1
1 | 1
78761 | 4
1 | 4
78512 | 8
1 | 8
76468 | 111
1 | 28
2 | 2
3 | 78
4 | 1
5 | 1
6 | 1
79184 | 1
1 | 1
77673 | 2
1 | 2
78548 | 2
1 | 2
78505 | 1
1 | 1
77848 | 4
2 | 1
3 | 2
4 | 1
77177 | 2
1 | 2
(blank) | 0
(blank) | 0
75398 | 116
2 | 115
3 | 1
75164 | 12
1 | 9
2 | 2
3 | 1
78856 | 2
1 | 2
79146 | 1
1 | 1
78335 | 5
1 | 5
78743 | 2
1 | 2
79206 | 6
1 | 6
64752 | 150
10 | 27
11 | 15
12 | 4
13 | 5
15 | 32
16 | 1
17 | 2
18 | 2
19 | 3
20 | 19
22 | 1
23 | 8
24 | 4
30 | 19
31 | 2
37 | 6
77611 | 12
3 | 12
76823 | 149
7 | 24
8 | 15
9 | 2
10 | 3
11 | 90
12 | 15
78690 | 10
1 | 5
2 | 5
79085 | 100
1 | 100
76370 | 3
1 | 3
78768 | 1
1 | 1
78636 | 1
1 | 1
78553 | 1
1 | 1
78905 | 1
1 | 1
78735 | 4
1 | 4
79320 | 4
1 | 4
77808 | 18
1 | 18
78386 | 19
1 | 3
2 | 3
3 | 13
77440 | 12
1 | 12
73829 | 34
1 | 29
2 | 5
79000 | 1
1 | 1
77854 | 2
11 | 2
79001 | 8
1 | 8
79198 | 12
1 | 12
78731 | 12
1 | 12
78927 | 51
1 | 37
3 | 14
78999 | 2
1 | 2
78645 | 2
1 | 1
2 | 1
75212 | 14
30 | 14
77693 | 40
1 | 10
4 | 8
5 | 7
8 | 15
77898 | 2
1 | 2
79106 | 6
1 | 3
2 | 3
79050 | 2
1 | 2
78909 | 2
1 | 2
79005 | 3
1 | 3
79043 | 10
1 | 10
78812 | 10
1 | 1
2 | 3
3 | 1
4 | 5
78637 | 3
1 | 1
2 | 2
79037 | 1
1 | 1
78502 | 1
1 | 1
78515 | 5
1 | 5
72844 | 8
1 | 8
78889 | 3
2 | 2
3 | 1
78861 | 10
1 | 8
2 | 2
70426 | 1
1 | 1
79024 | 1
1 | 1
78902 | 2
1 | 2
Grand Total | 2100